## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Motion Culvert Retaining Wall | itp |  |  |  |  | ITP - Motion Culvert Retaining Wall
section | Setout, Materials and Preparation
checkpoint | 1.1 - Survey Set Out
label | Detail of Activity - GPS Setout of the Retaining wall as per the construction drawings.
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Length of the retaining wall
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Survey Report
label | Record documents - Contractor's site diary and/or photos
label | Responsibility - Contractor
label | Comments - Setout location prior to commencing works.
checkpoint | 1.2 - Materials Approvals
label | Detail of Activity - Submit testing data fir the following materials:
label | – GAP 40
label | – GAP 20
label | – GAP 65
label | – Hardfill
label | – Rip Rap (dump rock)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Once for each material
label | Inspection / Test method - Quarry Testing Data
label | Acceptance Criteria - Engineer's Acceptance
label | Record documents - InEight Records
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
section | Construction and Finishing
checkpoint | 2.1 - Bases, Footings and/or Toes
label | Detail of Activity - Raft Construction (GAP65)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 5m section
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - RAFT SHALL CONSIST OF A 0.9m-DEEP UNDERCUT.
label | ○ A LAYER OF GEOTEXTILE BIDIM A29 OR AN APPROVED EQUIVALENT SHOULD BE LAID ON THE EXPOSED SUBGRADE.
label | ○ LAY AND COMPACT GRANULAR MATERIAL (GAP65).
label | ○ COMPACTED TO 95% OF THE MDD.
checkpoint | 2.2. - Bases, Footings and/or Toes
label | Detail of Activity - Raft Reinforcement
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Whole length
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - THE RAFT SHALL BE REINFORCED WITH GEOGRID (DURAFORCE 40/40 OR APPROVED EQUIVALENT) PLACED AT THE DEPTHS OF 0.3m AND 0.6m AND 0.9 WITHIN THE UNDERCUT.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Bases, Footings and/or Toes
label | Detail of Activity - Reinforcing WSP INSPECTION
label | Action (Hold, Monitor, Witness) - M, H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Length of Wall
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500E MILD STEEL.
label | ○ MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | Record documents - QC Sheets
label | Responsibility - Contractor/Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Bases, Footings and/or Toes
label | Detail of Activity - Formwork
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Length of Wall
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - FORMWORK SUPPLIED BY DOKA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Bases, Footings and/or Toes
label | Detail of Activity - Concrete
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All concrete orders
label | Inspection / Test method - Concrete Dockets
label | Acceptance Criteria - Concrete strength 25MPa at 28 days
label | ○ Mix design to be approved by the Engineer
label | ○ Minimum cover to reinforcing for walls and footings 75mm unless noted otherwise
label | Record documents - Concrete Dockets
label | Responsibility - Contractor
label | Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE.
label | ○ ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2.
label | ○ THE CONTRACTOR SHALL PROVIDE THE CONCRETE MIX DESIGN FOR THE APPROVAL OF THE ENGINEER PRIOR TO THE COMMENCEMENT OF ANY CONCRETE WORKS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Bases, Footings and/or Toes
label | Detail of Activity - Self Compacting concrete
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Void filler between existing culverts and new precast culvert
label | Inspection / Test method - Concrete Dockets
label | Acceptance Criteria - As per Detail A on drawing C01
label | Record documents - Concrete Dockets/ QC Sheets
label | Responsibility - Contractor
checkpoint | 2.7 - Walls
label | Detail of Activity - Reinforcing WSP INSPECTION
label | Action (Hold, Monitor, Witness) - M, H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Length of Wall
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500E MILD STEEL.
label | ○ MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS
label | ○ UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | ○ MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | Record documents - QC Sheets
label | Responsibility - Contractor/Engineer
label | Comments - Scabble or green cut interface in accordance with Type B construction joint to NZS 3109
label | ○ For joints, the surface of the concrete may be prepared by green cutting (using high velocity air/water jets or vigorous wire brush) to remove all laitance and inferior surface concrete after the concrete has hardened sufficiently to prevent loosening of any aggregate which is not removed.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Walls
label | Detail of Activity - Formwork
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 5m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Walls
label | Detail of Activity - Dowels
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 300mm centres
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - R20 DOWEL 450 LONG AT 300 CENTRES
label | ○ CONTROL JOINTS SHALL BE KEY JOINTS SPACED AT MAXIMUM 6.1m INTERVALS OR A SUITABLE LESSER LENGTH IF REQUIRED
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | 2.10 - Walls
label | Detail of Activity - Finish / Joints
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All areas
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Smooth, off shutter finish. Cut joints as appropriate.
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | 2.11 - Walls
label | Detail of Activity - Concrete
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All concrete orders
label | Inspection / Test method - Concrete Dockets
label | Acceptance Criteria - Concrete strength 25MPa at 28 days
label | ○ Mix design to be approved by the Engineer
label | ○ Minimum cover to reinforcing for walls and footings 75mm unless noted otherwise
label | Record documents - Concrete Dockets
label | Responsibility - Contractor
label | Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE.
label | ○ ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.12 - Backfill
label | Detail of Activity - Backfill behind wall - GAP40
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Length of wall
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Backfill behind wall with Hardfill
checkpoint | 2.13 - Drainage
label | Detail of Activity - Installation of subsoil drain
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Length of wall
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets/ Site Records
label | Responsibility - Contractor
label | Comments - 100Ø PERFORATED SUBSOIL DRAIN WITH 40/20 DRAINAGE AGGREGATE WRAPPED IN GEOTEXTILE OF STRENGTH CLASS B AND FILTRATION CLASS 2
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.14 - RIP RAP
label | Detail of Activity - Rip Rap construction at outfall
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Whole length
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - THE RIP RAP SHALL BE CONSTRUCTED MINIMUM 250MM THICK ON GEOTEXTILE - BIDIM 29 OR SIMILAR
checkpoint | 2.15 - Stainless Steel Connector Plates
label | Detail of Activity - Connect new precast culvert to existing culvert
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Per Plate
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - Site Records
label | Responsibility - Contractor
label | Comments - Connect new precast culvert to existing culvert using 400mm x 150mm x 6mm thick stainless steel plates with 4 x M20 Stainless Steel Bolts
section | Close Out
checkpoint | 3.1 - Collate above documentation
label | Detail of Activity - Document review
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Each ITP
label | Inspection / Test method - Review
label | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | Record documents - Review
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - As-built drawings
label | Detail of Activity - Survey
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - At completion of construction
label | Inspection / Test method - Asbuilts to be submitted at the completion of construction, information to be captured
label | Acceptance Criteria - Asbuilts reviewed and submitted
label | Record documents - In Eight record
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - Contractor
note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
signoff | Add Signature
checkpoint | Client Final Inspection - BBO Engineer
note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
textbox | BBO Engineers Rep Name:
signoff | Add Signature