## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
253b3841-5a1d-4d26-9dc3-026a9f629286 | checklist | ITP-004 - Subsurface Drainage | itp | ITP-004 - Subsurface Drainage
96768e7e-ec60-4a0f-b9bf-0379406e4107 | section | Preliminary Works
cba90eed-1a6e-4cbc-996a-a8c841ed5686 | checkpoint | 1.1 Check for correct documentation
f2d97ebb-119c-567c-96d7-db0ee8c7b2c4 | note | FREQUENCY: Prior to commencing any activity
9fd36af9-5cf9-5fa4-ac48-33e620053fe4 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
971a52ff-9621-5ebf-8960-b127461878df | note | – using the correct and complete set of drawings
dcb92054-2452-56d5-bbec-5a5ed565a04d | note | – all drawings are the latest revision
d8621f7d-4adb-5f07-9dd9-d9e9881601b4 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
69335422-c195-53ea-8863-8ced0580bde0 | note | INSPECTION/TEST METHOD: Visual inspection
298d3dbf-b2ef-5fc5-a1a8-bd1a11be1a35 | note | RECORD OF CONFORMITY: This ITP signed off
202ead1d-5d05-507f-9fc1-4073a83abb80 | note | HP*
821fab81-4064-5a2e-bb5e-2b018474178a | note | RESPONSIBILITY: Site Engineer / Site Foreman
d996268d-af42-5d42-a96a-2643f8c0ed05 | textbox | Date Completed:
b034bcff-0eec-4a60-9394-2a907af3ceb3 | checkpoint | 1.2 Implementation of all measures and controls
3f2e22bd-ac92-5445-8688-d4d5882e9538 | note | FREQUENCY: Prior to commencing any activity
66a85fcd-294c-56f0-ac67-35b8c4168f68 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
eda8d7fc-8c1e-542c-a230-9417ec330943 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
272e17da-6bca-59a8-8162-e1c083f51747 | note | INSPECTION/TEST METHOD: Document review
426140f5-de9e-5d94-a112-e2b83df228a4 | note | RECORD OF CONFORMITY: This ITP signed off
e765e1f2-f758-5b97-b212-cfd67077b181 | note | HP*
ba07a038-be74-5fd9-b12c-0f6d28a5471f | note | RESPONSIBILITY: Site Engineer, Site Foreman
02dbd386-7827-5d12-b4bc-a9726f6d22ff | textbox | Date Completed:
af1e8bd7-71d7-486f-af8b-de26c2b07d3c | checkpoint | 1.3 Material Classification
bf52396a-bf19-5fd9-9ffa-bfbd888fada1 | note | FREQUENCY: Each Lot
39c73eb7-42cf-5697-bf9d-ad9d922b060f | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes: (behind bluestone wall) 100mm DIA Class 1000kN/m/m corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
cdd0a5b3-a910-54ae-b4f7-25f1426505d4 | note | ○ Subsurface drainage pipes: (in soft landscaping area) 300mm wide megaflo
296f702f-8565-5147-b07f-a28475314ed1 | note | ○ Granular filter material for bedding and backfill: Trench backfilled and bedded with specified material on drawings (clean washed coarse sand for megaflo, 20mm screenings for behind bluestone wall)
9e4c09ad-2999-569d-9a35-823d3bf82f8a | note | ○ Geotextiles: Shall comply with Cl 702.06.
fe9b99c9-2981-52ee-83a0-02fe560da36b | note | ○ Flushout risers: constructed to the detail of SD 1631
9cdc7b8d-68c4-55f8-83dc-dc4224e4b4ec | note | REFERENCE DOCUMENTS: 702.04, 702.05, 702.06
1228ee77-9a04-5f24-9afc-8abfb85ee9dd | note | INSPECTION/TEST METHOD: Verify
f256adef-92b2-50ec-93ba-3bad7e650bc3 | note | RECORD OF CONFORMITY: This ITP signed off, Delivery dockets, product spec sheets etc.
6c95ad8d-1ea2-54b3-a52b-d50c75e31332 | note | WP
cc84038e-e39e-5d28-ab7f-011f86652b33 | note | RESPONSIBILITY: Site Engineer
055b871b-2d8a-5940-8ba3-3884ab0f4723 | textbox | Date Completed:
fa1ae911-a7d9-4f17-8b9c-61fffa0bfc23 | section | Construction Works
afd37089-32c2-4b63-b70c-4a6ff4d9f2cd | checkpoint | 2.1 Excavation Permit
83a3c8ec-232b-586c-9cb2-49def3162f8f | note | FREQUENCY: Weekly, per operator
c2d3dfbb-d0aa-52f5-818c-6192226a0781 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
450d9568-a2cb-5276-a1d8-e43c108c4064 | note | ○ Plant and equipment shall be appropriate for the task.
ec9d2bf8-7f3a-5f6e-a992-f0e6cf837e68 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
9c78bd07-568a-5f6c-99eb-1ef831558fb6 | note | REFERENCE DOCUMENTS: Excavation permit
d8941c61-6d9d-5439-a0ca-85e72dff4928 | note | INSPECTION/TEST METHOD: Verify
383417d3-3736-527f-a157-c14ddc36b591 | note | RECORD OF CONFORMITY: ITP Signed
4421da55-37c8-57ff-a2a5-fc8925c141ba | note | HP*
d6c56673-5ac4-5690-9796-dfbf4f328259 | note | RESPONSIBILITY: Site Engineer, Site Foreman
4ff9bdb5-a0d1-59f7-8fdb-77fb7f1ce510 | textbox | Date Completed:
9b9d5797-effa-4922-a549-b509f4c6257b | checkpoint | 2.2 Excavation of Trench
2a61144d-0e2b-533e-9aea-c9a71a23e0f1 | note | FREQUENCY: Each Lot
40b8cb9f-a993-5dec-8492-2cb5c0a79a31 | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed.
5f45cf89-0b79-544f-a035-fcfddc3a6179 | note | REFERENCE DOCUMENTS: 702.08
286bde25-ee36-5b70-9fa4-655832cef9f6 | note | INSPECTION/TEST METHOD: Visual Inspection
1258292e-4e92-52c8-b8e8-4597f31f67ee | note | RECORD OF CONFORMITY: This ITP signed off
c9dad189-91d9-5039-9b77-c140492631c0 | note | HP*
1f4b687a-7cca-5c31-9517-6dd8fb2ca8dd | note | RESPONSIBILITY: Site Engineer
34a08e18-e6b3-51e3-a28f-b28c2ce1592b | textbox | Date Completed:
77abe4f1-f7e7-49ed-a541-b0ce2dca77ac | checkpoint | 2.3 Placement of bedding
de27901d-0d37-5d4a-9c12-12dc4dc3325b | note | FREQUENCY: Each Lot
5d67283a-6fa8-541c-bbdb-97351bab97b8 | note | ACCEPTANCE CRITERIA: Bedding of granular filter material, sand or screenings placed across bottom of trench and screeded or graded to level
7e79472f-bb95-542a-931e-b674c0655a1a | note | REFERENCE DOCUMENTS: 702.09 (c )
6ab10106-c42a-505d-8648-3cca315416ba | note | INSPECTION/TEST METHOD: Visual Inspection
70a84da1-b6be-57d7-8da6-5ea7227ced44 | note | RECORD OF CONFORMITY: ITP Signed, Photos
1f1acec0-70f6-554e-9084-36426eaa7130 | note | IP
374d33c5-160c-56aa-98ec-71236a3fca32 | note | RESPONSIBILITY: Site Engineer
52134def-5faa-50d5-a8ea-19c0c2604616 | textbox | Date Completed:
729ccaa8-11fb-4f61-81d1-aa695244b317 | checkpoint | 2.4 Placing pipes and geofabric (if required)
5d0459eb-3d53-518b-a756-595c4fe673e7 | note | FREQUENCY: Each Lot
17f55c23-a591-50ea-8cba-93d3ebadd578 | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
af53b4e4-92af-5e55-86d0-685f04f236a3 | note | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum 150mm lap of geotextile used for wrapping.
ef6e3bc7-b7c0-5cbb-a92d-11a8c8aacb88 | note | REFERENCE DOCUMENTS: 702.09
07782968-0dd0-5402-94ef-bff191104f5f | note | INSPECTION/TEST METHOD: Visual Inspection
60516dee-c0ae-55d4-80df-9c8ad6a1b070 | note | RECORD OF CONFORMITY: ITP Signed, Photos
f6ce6ff4-b08e-5bc1-8660-74387bdcadfb | note | IP
68e2f400-d15b-5db5-8506-533b1287a36b | note | RESPONSIBILITY: Site Engineer
a00519ca-da4b-5ae2-b11c-4d6c3390fcc9 | textbox | Date Completed:
99ec03fb-7074-4712-a3c3-508ce950443c | checkpoint | 2.5 Placement of backfill
a5e1eb90-2cd4-5770-ad79-3e006e05df42 | note | FREQUENCY: Each Lot
466ca703-9c1d-5de2-8e51-0e612ba780c8 | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
aec5cf5f-2863-5e27-8e59-41ebfee9c7c2 | note | REFERENCE DOCUMENTS: 702.09 (g)
d1ae6976-9c4c-5824-ba0b-68b24c34067f | note | INSPECTION/TEST METHOD: Visual inspection
21fd776f-e9bb-5c30-b6b4-f228c073901d | note | RECORD OF CONFORMITY: ITP Signed, Photos
8a948a76-5961-573d-993c-69ff370f7402 | note | IP
8f5dc749-dee9-5b52-b292-7b95ff19a402 | note | RESPONSIBILITY: Site Engineer
27c23095-3dc2-5a2d-9995-de5f4a527875 | textbox | Date Completed:
e8f27fdd-c8ab-4d56-9338-1090eaa7e493 | checkpoint | 2.6 Flushout risers
ba2b82cd-7db2-5617-8e30-c2d083c83e35 | note | FREQUENCY: Each Lot
8019dfc9-286e-5e2f-97a9-6efce31d9fe0 | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
cab57183-d61b-530c-ade8-247989294a26 | note | REFERENCE DOCUMENTS: 702.1
53f1b387-7400-50e6-8c8d-27c7814405af | note | INSPECTION/TEST METHOD: Verify
732c180a-e49f-5995-8c4c-91fcd500c922 | note | RECORD OF CONFORMITY: ITP Signed, Photos
eb91a165-041e-5252-9feb-a9b3fee2ba11 | note | HP*
019a167f-60a4-5c43-97d6-c614469ef4b5 | note | RESPONSIBILITY: Site Engineer
a74da8a3-4893-5c0c-8fe3-a8c6ab432b4a | textbox | Date Completed:
28442f0d-2801-45dd-bc43-bff395b5e8fb | section | Testing & Completion
c8c71327-c4bf-413e-8534-07f489c44401 | checkpoint | Final Inspection
2f5a3170-87a3-599b-8bcf-634362f8ae32 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1ee1da20-195e-543c-81f0-a2a347e6e582 | textbox | Print Name:
38d739ec-1ba6-5799-a741-8655a7a862b0 | textbox | Position:
d8fdde86-e489-5e89-83d8-26cabc9592f2 | textbox | Date:
246215e0-3db9-4f74-92c3-6f65f4e74bdd | checklist | ITP-005 - Tree Pits | itp | ITP-005 - Tree Pits
a3d1f3b8-a341-46b0-bd3e-de46755ba370 | section | Preliminary Works
db98e7ea-4118-4322-bd07-3b2ac18b6c76 | checkpoint | 1.1 Check for correct documentation
9a7bfa0e-f55e-5179-8732-55fddf88c5a0 | note | FREQUENCY:
4bedb7f2-8b0a-5150-9d17-7c65682dbc22 | note | ACCEPTANCE CRITERIA:
75969f09-08ae-5cdd-8486-9d708ae1650e | note | REFERENCE DOCUMENTS: Drawings and drawing registers
431e8e07-7f42-5a74-ab7a-9337db694184 | note | INSPECTION/TEST METHOD: Document review
8255619f-f804-54b9-807f-0a41a4a42a40 | note | RECORD OF CONFORMITY: This ITP signed off
a4331385-d56b-59ee-bf16-886aa693ad31 | note | HP*
336e651a-cfc5-5799-938c-2f0847aa7221 | note | RESPONSIBILITY: Project Engineer
3207551f-0c48-5acc-8fa4-f672e3189047 | textbox | Date Completed:
5803c277-c161-4434-91ec-ebdb2864e0e1 | checkpoint | 1.2 Implementation of all measures and controls
8d968c26-3cce-5c40-b1d5-cf24d2388cc0 | note | FREQUENCY: Prior to commencing any activity
b7df100c-8612-5b35-9d29-555beacc238a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
71474802-be49-554e-9d98-cd44f348747b | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
4bf9adb2-42c4-5418-836e-d27bb495b407 | note | INSPECTION/TEST METHOD: Document review
8db25d7e-f8b8-532a-b059-4885fe027164 | note | RECORD OF CONFORMITY: This ITP signed off
5ecbd14a-1c08-5240-896b-fb06f8ee0bc4 | note | HP*
0efe8ea3-bbef-502c-b067-fc9abd7b6592 | note | RESPONSIBILITY: Site Engineer, Site Foreman
7c547c88-22a3-5887-8141-c8dc3a00c4a7 | textbox | Date Completed:
fde8887c-ca71-46d8-8de8-975176db2f13 | checkpoint | 1.3 Precast Materials acceptance
535a9c46-eb95-5d8f-9878-228ad0ecefd5 | note | FREQUENCY: Each Delivery
b10d9489-bd05-5601-bff5-89d814f830fe | note | ACCEPTANCE CRITERIA: Precast kerb inlet blocks and pit grates and frames shall comply with Design Standard 304.4, and City of Melbourne drawings 1P 50305 and 1P 50320.
c328dc9f-e037-51ec-89f1-b496613a4bb4 | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
f5310983-37e2-5dc7-86a4-f6b82ba5bf1c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 610, City of Melbourne Standard Drawings
2df48d8f-476b-536b-8584-316bf8838a1e | note | INSPECTION/TEST METHOD: Visual Inspection, Verify
bdfcbc1a-96ae-56c7-9173-e48c75b1a98f | note | RECORD OF CONFORMITY: This ITP signed, Manufacturer certificate or accreditation
8f7cef8c-a4e0-5925-a333-a61a3d21c063 | note | IP
27b78785-f0b1-527b-88b4-288b7b12d4f9 | note | RESPONSIBILITY: Site Engineer
16c3a1cb-c585-50ab-8438-ce6978226195 | textbox | Date Completed:
a8f3fec4-227d-4fa1-9f9c-b9488c1cea0d | checkpoint | 1.4 Material Classification
6794a4ce-6908-596b-b1de-2cb7d3fec59a | note | FREQUENCY: Prior to start
a576dd0b-ffa8-5eb4-a9d7-f234596644c5 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
7861317d-7171-501a-ba57-fe1a1fb7381a | note | ○ Drainage Backfill: 5mm screenings
22a85b18-3dfc-51a0-81e0-d5294863b226 | note | ○ Transition Layer: Sand/Coarse Sand
a3c78752-9fcb-5452-aff9-9620bfce906c | note | ○ Filtration Layer: As confirmed by the client (TBC)
f2aa38cb-0ea4-51e5-9267-7252805ad4e7 | note | ○ Drainage pipe: 100mm AGI pipe (no sock)
c77655b7-1713-554d-bd95-a2b4e37105bc | note | ○ Flushout pipe: 100mm PVC solid pipe with screw cap
022a7ce0-b52d-5d7e-ba44-e64152a6c64a | note | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092, Project Drawing CI-00080
ebf29736-b1c7-55c5-bb53-6ef604c70d65 | note | INSPECTION/TEST METHOD: Visual Inspection
a3b21196-f356-517d-85b0-22484444d385 | note | RECORD OF CONFORMITY: This ITP signed off, Delivery dockets, product spec sheets etc.
da6af15e-b830-5cad-8fa2-63cbc28c4c06 | note | WP
63bfd2e8-fe34-55c0-acaf-9f8e24523232 | note | RESPONSIBILITY: Site Engineer
3b105e78-fde5-53ac-b820-43b2a9e5229a | textbox | Date Completed:
8829eef9-505d-4046-a3ec-c6728ebd2713 | section | Construction Works
46a14377-4a2d-4251-835c-fef94c038005 | checkpoint | 2.1 Excavation Permit
372273e8-bef1-5b09-9601-81e463dcbf53 | note | FREQUENCY: Weekly, per operator
16baeddb-280e-5106-b6e4-201d6af6e45e | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
004af7e2-e33b-5422-9a67-fd7c125e023e | note | ○ Plant and equipment shall be appropriate for the task.
317dec31-7cfb-58b9-a67c-ec9c3ce2be8a | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
7b96eb8d-3e12-56eb-8a7a-1ea4be0d49e9 | note | REFERENCE DOCUMENTS: Excavation permit
6919beff-d792-5cd3-970b-35e211bdad88 | note | INSPECTION/TEST METHOD: Verify
1b535283-a408-5955-9cee-b4283a1239c9 | note | RECORD OF CONFORMITY: ITP Signed
6bb05dd4-5c98-51d8-aefc-880bf980063a | note | HP*
72a73181-7078-5396-8f1c-43e985c26454 | note | RESPONSIBILITY: Site Engineer, Site Foreman
a18cc168-7883-5cc0-bae6-bd61fe515b34 | textbox | Date Completed:
f19a2c3a-d9ba-43a9-9ae2-36ae048b68a2 | checkpoint | 2.2 Set out pits
f56d03bd-5985-5f18-9cd4-b0dea65dbe9a | note | FREQUENCY: Prior to start
65914eb3-0cbe-5c43-b9bf-7e5fcc9ce747 | note | ACCEPTANCE CRITERIA: The position of all pits are to be confirmed with the superintendent.
24376009-0a11-526b-a235-b30d40454eb2 | note | ○ The inverts of all outlets are to be checked to ensure there is sufficient flow to the downstream system and that there are no service clashes.
74df81d9-38a9-56a9-80d0-632b8c42ee15 | note | REFERENCE DOCUMENTS: Drawings
c57435a0-dad4-5d25-8323-5a8337dba67e | note | INSPECTION/TEST METHOD: Visual Inspection
4b0249b6-0124-58c4-b705-9cb4aeaa0643 | note | RECORD OF CONFORMITY: ITP Signed
6c2be9d2-84fe-58c8-96c8-283f1a20f842 | note | HP
a498a79d-9a3c-5ef7-a75e-13fa76cc46bf | note | RESPONSIBILITY: Client Site Engineer
8840efc1-a724-5493-8f1c-8d45d50bd81f | textbox | Date Completed:
ae155de9-3a5e-4d28-98bb-a60d8a3a45a4 | signoff | AUTHORITY HOLDPOINT
74c2f090-7c9a-4aa2-b204-a81dfeefe70d | checkpoint | 2.3 Excavation
d48fe5ac-3454-5458-8cbe-db7f02345167 | note | FREQUENCY: Each Pit
42523c16-e4dc-58c9-a3d1-d1ce996326d0 | note | ACCEPTANCE CRITERIA: Excavation is to be to sufficient depth to allow for backfill layers to be placed at the required thicknesses.
70eb21ae-9821-5f7f-b4aa-13e2b099c4f8 | note | REFERENCE DOCUMENTS: Drawings
b40c448c-2be4-52a0-84f2-6eb29dfae4a0 | note | INSPECTION/TEST METHOD: Visual Inspection
5d113685-4ada-579c-a892-781a82033e19 | note | RECORD OF CONFORMITY: ITP Signed, Photos
f37f04ee-6c53-5c8c-87b5-ac3125da6bf4 | note | IP
48f4c163-d7a4-522f-8a16-1ff40042f530 | note | RESPONSIBILITY: Site Engineer
f0e7a54e-497d-5930-8043-2651405f226f | textbox | Date Completed:
4a643003-5680-458e-bb30-351b6068a4cc | checkpoint | 2.4 Placing pipes and geofabric (if required)
c381cd78-22f9-58c4-91ee-e3446bdf6a65 | note | FREQUENCY: Each Pit
3e4993f6-4181-5378-89ef-8ad50fdd40fc | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
e920fcce-f14d-582c-a199-707bcc115ef6 | note | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum 150mm lap of geotextile used for wrapping.
4cbdf134-deef-52fd-8047-8daf27c77311 | note | REFERENCE DOCUMENTS: 702.09
24c144b7-95ed-5e21-81b0-4c0177c90acc | note | INSPECTION/TEST METHOD: Visual Inspection
1aba6f21-a9c2-5ec1-87f7-da1d58c81a7c | note | RECORD OF CONFORMITY: ITP Signed, Photos
445c1139-7ca3-578e-aac0-2e48e6220cf2 | note | IP
99ce3b81-f1ba-50cf-8dcf-9530a3d36f6c | note | RESPONSIBILITY: Site Engineer
fcbcaa8f-c1be-5215-bfd6-1fc20ba92346 | textbox | Date Completed:
dfb6e66a-e628-486b-bbda-c7592f41a76c | checkpoint | 2.5 Placing drainage, transition and filtration layers
a005958a-f517-50ca-8201-00abf84af6cd | note | FREQUENCY: Each Pit
5e41d760-0387-503b-bd72-8fdd73eac155 | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes.
54cce5ec-3fc6-5459-8a84-a32539ce4f36 | note | REFERENCE DOCUMENTS: 702.09 (g)
01699a3d-9058-5213-863e-0927642efce7 | note | INSPECTION/TEST METHOD: Visual inspection
129418a0-7577-521c-b3f8-5214371bbb05 | note | RECORD OF CONFORMITY: ITP Signed, Photos
8ffdf05f-01fa-5986-beaa-fb8b29820b1e | note | IP
9fef6a86-b877-51a2-ae0c-07ca7e727209 | note | RESPONSIBILITY: Site Engineer
55bbdf46-1d77-5abe-b662-1a8fb322df09 | textbox | Date Completed:
10ddad98-f481-4d87-b752-b1566efcbb09 | checkpoint | 2.6 Placing structural soil (if required)
7eb3e579-f55d-55b8-a891-397ff08f8130 | note | FREQUENCY: Each pit
03f403bd-b61b-5fbe-a51b-cd77c66af360 | note | ACCEPTANCE CRITERIA: Structural soil placed and compacted in layers. Volume as per IFCs.
6f15752d-75cb-52ef-8401-0958f23fdc18 | note | REFERENCE DOCUMENTS: Drawings
11de4cdb-6fe1-5231-b69d-8448910c5bcd | note | INSPECTION/TEST METHOD: Visual Inspection Survey Volume
4fd0d493-9879-5aa2-ad50-daa8434d5526 | note | RECORD OF CONFORMITY: ITP Signed
d5993d47-4a68-5a1f-8ef5-403a2487eb5a | note | IP
ccfef117-b876-5d42-a4af-263c16364ef7 | note | RESPONSIBILITY: Site Engineer
ad912dbd-9566-54f3-b41d-421c5fe52484 | textbox | Date Completed:
99d33c7f-0d7c-4aa8-9418-d78facee47e7 | checkpoint | 2.7 Flushout risers
fe479e14-c4ab-5a41-a3cc-d604a0fd99b1 | note | FREQUENCY: Each Lot
cce9f211-25af-575a-82b9-da2b2d8651cc | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
57f7e311-8aa6-5288-b7e3-4d5626032c41 | note | REFERENCE DOCUMENTS: 702.1
dbad4917-26b4-5d6b-b7af-1027ee2c6a66 | note | INSPECTION/TEST METHOD: Verify
81aa359c-c224-5d3e-a289-347ae154821a | note | RECORD OF CONFORMITY: ITP Signed, Photos
648e6877-12cf-579c-8d20-e0bb7882093c | note | HP*
563bb7ea-b584-5d59-b193-c7c85d682ade | note | RESPONSIBILITY: Site Engineer
710608e8-c6d2-578d-84b0-5f472a9c68a0 | textbox | Date Completed:
172182ab-28c5-4082-a7ca-373b17c76f69 | checkpoint | 2.8 Place and set side entry backing block, grate and frame
5e4d3cdc-9595-539d-aefb-1089889b4efe | note | FREQUENCY: Each Pit
3e281f31-c904-5a5e-b301-61e680d6113f | note | ACCEPTANCE CRITERIA: Entry blocks, grates and frames must be set to within ±10mm of the design levels shown on the drawings and In accordance with the relevant COM standard drawings.
b98fcf1a-0445-5258-93dd-d67d87720b89 | note | REFERENCE DOCUMENTS: City of Melbourne drawings 1P 50305 and 1P 50320.
731ba150-7e71-5335-a1df-269b19baa2a5 | note | INSPECTION/TEST METHOD: Visual Inspection
1c408c4f-2421-5ddf-9d83-6360c0b99ecf | note | RECORD OF CONFORMITY: ITP Signed, Photos
1c8257fb-f96f-5d7e-9f4c-2e4b566c7f8b | note | IP
4105b3b4-bf0c-576b-ac91-e8c0f2f705b5 | note | RESPONSIBILITY: Site Enginer
f4a6fe31-3d91-5e69-8b76-969f1797c3fe | textbox | Date Completed:
c45775e8-7b64-4d79-b17d-68a03dc69d9f | checkpoint | 2.9 Place tree guard and grate for bioretention tree pit
18b071a7-c3a1-5ab7-a280-32f071528e40 | note | FREQUENCY: Each Pit
661154fb-a66b-52e9-8db9-a905ca6e9061 | note | ACCEPTANCE CRITERIA: Guards and grates must be set to within ±10mm of the design levels shown on the drawings and In accordance with the relevant COM standard drawings.
bb9e7e03-6e04-5fb1-b80e-b07c56ca7f81 | note | REFERENCE DOCUMENTS: City of Melbourne design standard 706.03
6aa1f5f7-8c2a-5597-8ca6-ec2ad1e8912a | note | INSPECTION/TEST METHOD: Visual Inspection
3e68b594-9f95-5cb0-983f-c2f9f9b296b9 | note | RECORD OF CONFORMITY: ITP Signed, Photos
585902a6-7207-581b-949c-e6ffafebd102 | note | IP
90258878-564d-5d82-85e0-374e6416924d | note | RESPONSIBILITY: Site Enginer
aaea2d80-803c-5081-9f27-4a9abfb2194b | textbox | Date Completed:
9ce6d845-46e7-44b6-b3d7-fe5804fab849 | section | Testing & Completion
a66557d5-99c7-414a-b8c1-bb56128450a2 | checkpoint | Final Inspection
ab7418e4-b1d6-58b0-977b-f6c9a11d6710 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d6200746-3f14-5933-bc81-ba7ce1ba2471 | textbox | Print Name:
d739c3fb-78ad-54d4-89e3-13fdffdb605c | textbox | Position:
95d41f51-2e93-5777-82e3-ef7a43723eac | textbox | Date: