## Enabling Works
ITP - East Tamaki/ Ormiston / Preston Intersection
Site Location |  |  | East Tamaki/ Ormiston / Preston Intersection
Enabling Works - Footpath, Kerb and channel
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable. | Mandatory HOLD POINT - | Onsite records/photos | Site Engineer
Materials
2 | Kerb & Channel | QA FORM | TDM Technical Standards - KC0001 | Everysite | Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 | Inprocess Inspection - Engineer to check the Stringline Set out | FH concrete QA sheet, photos. Concrete Plant Docket | Site Engineer
3 | Extruded standard Kerb & Channel- TYPE 3 | QA FORM | TDM Technical Standards - KC0002 | Everysite | Extruded Kerb & Channel to be laid on site using machine. On compacted GAP40. Concrete 25MPa fibre reinforced @28 Days on 100mm GAP40 | Inprocess Inspection - Engineer to check the Stringline Set out | FH concrete QA sheet, photos. Concrete Plant Docket | Site Engineer
3 | Extruded Cycle Kerb- TYPE 15 | QA FORM | TDM Technical Standards - KC0003 | Everysite | Extruded Kerb to be laid on site using machine or hand. On compacted GAP40. Concrete 25MPa fibre reinforcedfor machine laid or 20 Mpa standard concrete for hand laid @28 Days on 100mm GAP40 | Inprocess Inspection - Engineer to check the Stringline Set out | FH concrete QA sheet, photos. Concrete Plant Docket | Site Engineer
4 | Channel Level | QA FORM | TDM Technical Standards - KC0001 | Everysite | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level | Inprocess Inspection | FH concrete QA sheet, Photos | Site Engineer
CIVIL WORKS
5 | Concrete Footpaths and Pram Crossings | QA FORM | TDM Technical Standards - FP0001 | 10m Intervals | Basecourse - 100mm min. thickness GAP40 Clegg CIV > 15 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish Expansion Joint cut for every 3m interval Pram crossing to have 600mm flare from kerb; Minmum 1.5m deep and wide. | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos | Site Engineer
6 | Shared footpath | QA FORM | Pavement Details- 5 (3236765-CA-3010) | 10m Intervals | Subgrade Improvement materials( If Subgrade CBR <3.5%)- 300mm SIL materials Basecourse - 100mm min. thickness GAP40 Clegg CIV > 15 Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with exposed finish Single layer 665 mesh with 50mm cover (for concrete slabs with service covers) Expansion Joint cut for every 3m interval | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos | Site Engineer
7 | Tactiles |  | TDM Technical Standards - FP0010 | Each PX | Tile set out position to be agreed with ATOC and Engineer. Warning TGSI tiles should have 100mm concrete slab underneath | Inprocess Inspection, Measurement | FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos | Site Engineer
7.1 |  | Visual | NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Everysite | Tactile to be yellow/ green concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. | Inprocess Inspection | Photos | Site Engineer
7.2 |  |  | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Everysite | Edge of warning indicators to set back 300mm from the face of the kerb or lane. | Inprocess Inspection | Photos | Site Engineer
7.3 |  |  | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Everysite | TGSI tiles should be sealed yellow/green pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing | Inprocess Inspection | Materials Dockets | Site Engineer
6
8 | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Yeswanth Vemula | Initial |  |  | Date:
Approving Delegate |  | Sam | Initial |  |  | Date:

## Vehicle Crossing
ITP - East Tamaki/Ormiston / Preston Intersection
Site Location |  |  | East Tamaki/ Ormiston/Preston Intersection
Enabling Works - Vehicle Crossings
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like | Mandatory HOLD POINT - | Survey Receipt | Site Engineer
Materials
2 | Channel Level | QA FORM | TDM Technical Standards - VX0000 | Every site | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level | Inprocess Inspection | FH concrete QA sheet | Site Engineer
3 | Mesh & Steel | QA FORM | TDM Technical Standards - VX0000 | Every site | 661 Mesh and/or D12 Bars to be installed if 4> dwellings or commercial crossing | Mandatory HOLD POINT - | FH concrete QA sheet Photos | Site Engineer
Construction
4a | Vehicle Crossing | QA FORM | TDM Technical Standards - VX103 | Each VX | Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 15 Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 black oxide Exposed Finish | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
4b | Commercial Crossing | QA FORM | TDM Technical Standards - VX0202 | Each VX | Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 15 Surfacing - Concrete 200mm and 20 MPa @ 28 days. 4kg/m3 black oxide Exposed Finish | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
5 | Grass Berms | Visual | ATCOP Section 12 Footpaths and Pedestrian Facilities | 10m Intervals | 100mm thick layer of compacted approved quality topsoil, free of weeds and stones. | Inprocess Inspection | Photos | Site Engineer
Asbuilts
#REF! | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Yeswanth | Initial |  |  | Date:
Approving Delegate |  | sam | Initial |  |  | Date:

## Traffic Islands
ITP - East Tamaki/ Ormiston/preston Intersection
Site Location |  |  | East Tamaki/ Ormiston/preston Intersection
Traffic Islands
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Materials
1 | Standard Mountable Kerb | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Everysite | Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint | Inprocess Inspection - Engineer to check kerb stringline before laying | FH concrete QA sheet, photos. | Site Engineer
2 | Mountable Kerb- TYPE 20 Extruded | QA FORM | TDM Technical Standards - IS0001 & KC0005 | Everysite | Type 20 extruded mountable Kerb to be laid on site using machine and painted with two coats of reflective paint | Inprocess Inspection - Engineer to check kerb stringline before laying | FH concrete QA sheet, photos. | Site Engineer
Construction
3 | Survey Setout | Survey | Setout Kerb Alignment required to construct to design | Prior to commencement. | Survey | As per Construction Drawings | Survey Receipt. | Site Engineer
4 | Concrete Island | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | Kerbs to be haunced with 20MPa Concrete | Inprocess Inspection | Photos | Site Engineer
5 | Standard Mountable Kerb | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | Basecourse to be 150mm min thickness of GAP65 | Inprocess Inspection | Photos | Site Engineer
6 | Type 20 Extruded Mountable Kerb | QA FORM | TDM Technical Standards - IS0001 & KC0005 | Each Site | Basecourse to be 300mm min thickness of GAP65 | Inprocess Inspection | Photos | Site Engineer
7 | Concrete Infil- Extruded Mountable Kerb | QA FORM | TDM Technical Standards - IS0001 | Each Site | 180mm depth of 20MPa broom finish, unreinforced Concrete with 4kg/m3 Red oxide Cross Fall of 2% or max rise in centre of 180mm | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
8 | Concrete Infil- Standard Mountable Kerb | QA FORM | TDM Technical Standards - IS0002 | Each Site | 150mm depth of 20MPa broom finish, unreinforced Concrete with 4kg/m3 Red oxide Cross Fall of 2% or max rise in centre of 150mm | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
Asbuilts
9 | As built information | Drawings |  | Every Site | As built drawings | In Process Inspection | Asbuilt records | Supervisor and Engineer
10 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Yeswanth Vemula | Initial |  |  | Date:
Approving Delegate |  | Sam | Initial |  |  | Date:

## Signage
ITP -East Tamaki/Ormiston/ Preston Intersection
Site Location |  |  | East Tamaki/Ormiston/ Preston Intersection
Signage
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like | Mandatory HOLD POINT - | Survey Receipt | Site Engineer
Materials
2 | Signs/Belisha Disk | QA FORM | TDM Technical Standards | Every site | All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers. | Inprocess Inspection | Dockets/Photos | Site Engineer
3 | Pole, Impact recovery post and Ground Socket | QA FORM | TDM Technical Standards | Every site | Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep | Inprocess Inspection | Dockets/Photos | Site Engineer
Construction
4a | Ground Socket | QA FORM | TDM Technical Standards | Each Socket | The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket. | Inprocess Inspection | Dockets/Photos with tape measurement | Site Engineer
4b | Pole and Impact recovery post | QA FORM | TDM Technical Standards | Each Post or pole | All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent thr pole rotation. The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation | Inprocess Inspection | Dockets/Photos | Site Engineer
5 | Signs/Belisha Disk | QA FORM | TDM Technical Standards | Each Sign | All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately. | Inprocess Inspection | Dockets/Photos | Site Engineer
Asbuilts
6 | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  |  | Initial |  |  | Date:
Approving Delegate |  | Nithin Thomas | Initial |  |  | Date:

## Ducting & Traffic Signals
|  |  |  | ITP |  |  | Approved |  | Signature
|  |  |  | Contract Name: | East Tamaki/Ormiston/ Preston Intersection |  | FH Engineer
|  |  |  | Procedure: | Traffic signal ducting and Pole erection |  | FH Project Engineer
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | Potholing and traffic signal installation |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
Ducting
1 | Permits | H | Obtain Permits | As required | Document Review | Authorisation to work, dig permit and service provider permits | This ITP signed | Site Engineer
2 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
3 | Survey Setout | H | Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor. | Prior to commencement | Survey | Consistency with Drawings and Specifiactions | Survey Records | Site Engineer
|  | H | Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation. | Prior to commencement | Visual Inspection | Consistency with Drawings and Specifiactions | Photos / Engineers approval documentation | Site Engineer
4 | Locate existing services by hand digging/ hydrovac | W | Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation | Prior to Installation | Potholing | All conflicts have been located and survey as built recorded | Digging/Excavating Control Checklist | Site Engineer
5 | Material Compliance | H | Ensure duct pipes and poles are as per drawings and specification | Upon delivery to site | Ensure delivery docket matches materials |  | Delivery Docket | Site Engineer
|  | H | Ensure all concrete used is 20MPa mix | Upon delivery to site | Ensure delivery docket matches materials |  | Delivery Docket | Site Engineer
6 | Trenching | H | Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing) | 10m Intervals | Visual Inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
6.1 |  | H | Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs | 10m Intervals | Measure | Ensure trench alignment and levels match the design drawings | Dipsheet & Photos | Site Engineer
7 | Duct Installation | W | Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct. | Prior to Installation | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
7.1 |  | H | Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
7.2 |  | H | Asbuilt Survey | 20m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Survey Records | Site Engineer
8 | Bedding | H | Lay min. 150mm gap20 or finer for bedding and haunching | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
9 | Warning Tape | H | Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines. | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
10 | Traffic signal pole erection | H | Ensure Design engineer as inspected pole locations prior to proceeding | Per pole | Visual Inspection | Sign off by design engineer | Engineer sign off
10.1 |  | H | Ensure Pot hole is as per design with required depths and widths | Per pole | Measure | Consistency with Drawings and Specifiactions | Dipsheet & Photos
10.2 |  | H | Ensure Poles are plumb and within design tolerances | Per pole | Visual Inspection | Consistency with Drawings and Specifiactions | Photos
11 | As-builts & C&I Diagram | H | As-built as per ATOC requirements | At the completion of the Lot of work | Drawings | As-built as per ATOC requirements | Asbuilt Drawing | Site Engineer
Comments:
Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Project manager |  |  |  |  | Signature: |  |  | Date:
QA checked By Contract Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design/AT Engineer: |  |  |  |  | Signature: |  |  | Date:

## Asphalt Works
[7 empty] | Approved |  | Signature
|  |  |  | Contract Name: | East Tamaki/Ormiston/Preston Intersection |  | FH Engineer
|  |  |  | Procedure: | Asphalt Works |  | FH Quality Manager
Inspection & Test Plan / Checklist
Detailed Location: East Tamaki/Ormiston /Preston Intersection |  |  |  | Corresponding Work Instruction: |  | Documentation Required |  | Compliance with Work Instructions and Specifications
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
Materials
1.1 | Bitumen | M | As per Design | Passing all tests listed in Table 1 of NZTA M/1 | Passing all tests listed in Table 1 of NZTA M1/A (2019) and pavement design | Testing/Visual | IANZ Lab results | Site Engineer
1.2 | Asphalt Mix Design | M | JMF approved | JMF approved | AUSTROADS -PMB AC20 & PMB AC14 | Testing/Visual | IANZ Lab results | Site Engineer
1.3 | Production Tests | M | NZTA M/10 spec | 1 set every 300t | NZTA M/10 | Testing/Visual | IANZ Lab results | Site Engineer
Left Turn Slip lane Wideneing and Wider traffic Island reinstatement Area ( Detail 1) SUBGRADE
2.1 | Cut to Waste (635mm) | W | Dip from stringline or survey as-built | 10m each lane | +0 / -20mm to design level | Inprocess Inspection | Stringline Sheet | Site Engineer
2.2 | Insitu Subgrade Testing | W | Scalar Testing, Shear vane testing and proof rolling if practical | 10m each lane Proof rolling - continuous | CBR greater than 1% No visual movement or cracking in the existing subgrade. | The Scala Penetrometer testing shall be undertaken to a depth 1m below the design subgrade level. If CBR less than 3.5%: | Scalar sheet | Site Engineer
2.3 | Subgrade Improvement Layer | H | CBR test | Every 10m intervals | CBR greater than 15% |  | Scala test sheet | Site Engineer
2.3.1 | Geotextile or Geogrid | W | Visual inspection | Throughout the surface | Visual inspection | Either Geo Textile or Geo grid can be placed below the Subgrade improvement layer | Photos | Site Engineer
Concrete Subbase
3.1 | Concrete Subbase | W | Concrete Dockets | each truck | visual inspection |  | Concrete Dockets | Site Engineer
Sealing - Grade 4 or Tack/Blind if paving on granular surface.
4.1 | Emulsion tack coat | M | Dip emulsion tank | each lot | CAT60 cationic emulsion or approved alternative 0.6 (minimum residual) to 0.9 lt/m2 | Inprocess Testing | Spray sheet | Site Engineer
4.2 | Blinding | M | Aggregate Supply | each lot | Even application of blinding where required in accordance with the design drawings. | Blinding mix or chip | Spray sheet | Site Engineer
4.3 | Chipseal | M | Bitumen Application | each lot | Grade 4 membrane seal (minimum residual bitumen application of 1.0L/m2) | Inprocess Inspection | Spray sheet | Site Engineer
4.4 | AC 14 RW 30 -PG 64 H - 65mm | M | Forecast and thermometer | Daily | Check weather reports No fog, rain or wet surface. Base temp ≥ 5o C | Inprocess Testing | AC check sheet | Site Engineer
4.5 | AC 14 RW 30 -PG 64 H - 65mm | M | Asphalt Trace Sheet as part of QA | During construction | Asphalt Temperature Amount of asphalt laid average calcaulated asphalt thickness etc | Inprocess Inspection | AC check sheet | Site Engineer
4.6 | AC 14 RW 30 -PG 64 H - 65mm | W | Visual | Prior to starting | Ensure previous layer is broomed clean Free of detritius and loose material | Inprocess Testing | AC check sheet | Site Engineer
4.7 | AC 14 RW 30 -PG 64 H - 65mm | W | Grading, binder content, max density, temp | 1/300t | Production tests NZTA M/10 | Inprocess Testing | Lab test | Site Engineer
4.8 | AC 14 RW 30 -PG 64 H - 65mm | M | Visual inspection by the Engineer | Each lot | Surface finish inspection Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate. | Inprocess Testing | Inspection sheet | Site Engineer
4.9 | AC14 PMBRW15- PG 64 V (second layer)-55mm | M | Forecast and thermometer | Daily | Check weather reports No fog, rain or wet surface. Base temp ≥ 5o C | Inprocess Testing | AC check sheet | Site Engineer
4.1 | AC14 PMBRW15- PG 64 V (second layer)-55mm | M | Asphalt Trace Sheet as part of QA | During construction | Asphalt Temperature Amount of asphalt laid average calcaulated asphalt thickness etc | Inprocess Inspection | AC check sheet | Site Engineer
4.11 | AC14 PMBRW15- PG 64 V (second layer)-55mm | W | Visual | Prior to starting | Ensure previous layer is broomed clean Free of detritius and loose material | Inprocess Testing | AC check sheet | Site Engineer
4.12 | AC14 PMBRW15- PG 64 V (second layer)-55mm | W | Grading, binder content, max density, temp | 1/300t | Production tests NZTA M/10 | Inprocess Testing | Lab test | Site Engineer
4.13 | AC14 PMBRW15- PG 64 V (second layer)-55mm | M | Visual inspection by the Engineer | Each lot | Surface finish inspection Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate. | Inprocess Testing | Inspection sheet | Site Engineer
4.14 | AC14 PMBRW15- PG 64 V (Top layer)-55mm | M | Forecast and thermometer | Daily | Check weather reports No fog, rain or wet surface. Base temp ≥ 5o C | Inprocess Testing | AC check sheet | Site Engineer
4.15 | AC14 PMBRW15- PG 64 V (Top layer)-55mm | M | Asphalt Trace Sheet as part of QA | During construction | Asphalt Temperature Amount of asphalt laid average calcaulated asphalt thickness etc | Inprocess Inspection | AC check sheet | Site Engineer
4.16 | AC14 PMBRW15- PG 64 V (Top layer)-55mm | W | Visual | Prior to starting | Ensure previous layer is broomed clean Free of detritius and loose material | Inprocess Testing | AC check sheet | Site Engineer
4.17 | AC14 PMBRW15- PG 64 V (Top layer)-55mm | W | Grading, binder content, max density, temp | 1/300t | Production tests NZTA M/10 | Inprocess Testing | Lab test | Site Engineer
4.18 | AC14 PMBRW15- PG 64 V (Top layer)-55mm | M | Visual inspection by the Engineer | Each lot | Surface finish inspection Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate. | Inprocess Testing | Inspection sheet | Site Engineer
4.19 | AC14RW30 / AC14 PMB RW 15 | M | Dip from stringline or survey as-built | grid pattern | (+10 / -10mm) | Inprocess Testing | Inspection sheet | Site Engineer
4.2 | AC14RW30 / AC14 PMB RW 15 | M | NDM/Cores (Testing plan to be agreed with client) | 1/300m2 or min 8 cores | Density testing Air voids to meet NZTA M/10:2020 +3% / -2% | Paved Area: Air voids, in accordance with NZTA M/10 (2020) Testing undertaken in accordance with NZTA M/10 | Core test report | Site Engineer
4.21 | AC14RW30 / AC14 PMB RW 15 | M | Cores depth (Location plan to be agreed with client) | 1/300m2 or min 8 cores | Thickness - Depth should not be less than design asphalt depth of thickness | Inprocess Testing | Core test report | Site Engineer
Trench Repair pavement and Right Turn Bay ( Detail 2 & Detail 3) SUBGRADE
5.1 | Cut to Waste | W | Dip from stringline or survey as-built | 10m each lane | 740mm (Undercut areas ) and 490mm ( if existing pavement thickness is less than 300mm) and 190mm ( if existing pavment thickness is 300mm +0 / -20mm to design level | Inprocess Inspection | Stringline Sheet | Site Engineer
5.2 | Insitu Subgrade Testing | W | Scalar Testing, Shear vane testing and proof rolling if practical | 10m each lane Proof rolling - continuous | CBR greater than 3.5% below 490mm from the design level No visual movement or cracking in the existing subgrade. | The Scala Penetrometer testing shall be undertaken to a depth 740mm below the design level. If CBR is less than 3.5%: | Scalar sheet | Site Engineer
Subbase ( IF the exixsting base or subbase material is less than 300mm)
6.1 | Subgrade Improvement Layer | H | CBR test | Every 10m intervals | CBR greater than 15% |  | Scala test sheet | Site Engineer
6.2 | Geotextile or Geogrid | W | Visual inspection | Throughout the surface | Visual inspection | Either Geo Textile or Geo grid can be placed below the Subgrade improvement layer | Photos | Site Engineer
Subbase ( IF the exixsting base or subbase material is less than 300mm) Contingency plan
6.3 | Concrete Subbase | W | Concrete Dockets | each truck | visual inspection |  | Concrete Dockets | Site Engineer
6.4 | Geotextile or Geogrid | W | Visual inspection | Throughout the surface | Visual inspection | Either Geo Textile or Geo grid can be placed below the concrete subbase | Photos | Site Engineer
Sealing - Grade 4 or Tack/Blind if paving on granular surface.
7.1 | Emulsion tack coat | M | Dip emulsion tank | each lot | CAT60 cationic emulsion or approved alternative 0.6 (minimum residual) to 0.9 lt/m2 | Inprocess Testing | Spray sheet | Site Engineer
7.2 | Blinding | M | Aggregate Supply | each lot | Even application of blinding where required in accordance with the design drawings. | Blinding mix or chip | Spray sheet | Site Engineer
7.3 | Chipseal | M | Bitumen Application | each lot | Grade 4 membrane seal (minimum residual bitumen application of 1.0L/m2) | Inprocess Inspection | Spray sheet | Site Engineer
7.4 | AC 14 RW 30 -PG 64 H - 70mm | M | Forecast and thermometer | Daily | Check weather reports No fog, rain or wet surface. Base temp ≥ 5o C | Inprocess Testing | AC check sheet | Site Engineer
7.5 | AC 14 RW 30 -PG 64 H - 70mm | M | Asphalt Trace Sheet as part of QA | During construction | Asphalt Temperature Amount of asphalt laid average calcaulated asphalt thickness etc | Inprocess Inspection | AC check sheet | Site Engineer
7.6 | AC 14 RW 30 -PG 64 H - 70mm | W | Visual | Prior to starting | Ensure previous layer is broomed clean Free of detritius and loose material | Inprocess Testing | AC check sheet | Site Engineer
7.7 | AC 14 RW 30 -PG 64 H - 70mm | W | Grading, binder content, max density, temp | 1/300t | Production tests NZTA M/10 | Inprocess Testing | Lab test | Site Engineer
7.8 | AC 14 RW 30 -PG 64 H - 70mm | M | Visual inspection by the Engineer | Each lot | Surface finish inspection Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate. | Inprocess Testing | Inspection sheet | Site Engineer
7.9 | AC 14 RW 30 -PG 64 H (second layer)-65mm | M | Forecast and thermometer | Daily | Check weather reports No fog, rain or wet surface. Base temp ≥ 5o C | Inprocess Testing | AC check sheet | Site Engineer
7.1 | AC 14 RW 30 -PG 64 H (second layer)-65mm | M | Asphalt Trace Sheet as part of QA | During construction | Asphalt Temperature Amount of asphalt laid average calcaulated asphalt thickness etc | Inprocess Inspection | AC check sheet | Site Engineer
7.11 | AC 14 RW 30 -PG 64 H (second layer)-65mm | W | Visual | Prior to starting | Ensure previous layer is broomed clean Free of detritius and loose material | Inprocess Testing | AC check sheet | Site Engineer
7.12 | AC 14 RW 30 -PG 64 H (second layer)-65mm | W | Grading, binder content, max density, temp | 1/300t | Production tests NZTA M/10 | Inprocess Testing | Lab test | Site Engineer
7.13 | AC 14 RW 30 -PG 64 H (second layer)-65mm | M | Visual inspection by the Engineer | Each lot | Surface finish inspection Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate. | Inprocess Testing | Inspection sheet | Site Engineer
7.14 | AC14 PMBRW15- PG 64 V (Top layer)-55mm | M | Forecast and thermometer | Daily | Check weather reports No fog, rain or wet surface. Base temp ≥ 5o C | Inprocess Testing | AC check sheet | Site Engineer
7.15 | AC14 PMBRW15- PG 64 V (Top layer)-55mm | M | Asphalt Trace Sheet as part of QA | During construction | Asphalt Temperature Amount of asphalt laid average calcaulated asphalt thickness etc | Inprocess Inspection | AC check sheet | Site Engineer
7.16 | AC14 PMBRW15- PG 64 V (Top layer)-55mm | W | Visual | Prior to starting | Ensure previous layer is broomed clean Free of detritius and loose material | Inprocess Testing | AC check sheet | Site Engineer
7.17 | AC14 PMBRW15- PG 64 V (Top layer)-55mm | W | Grading, binder content, max density, temp | 1/300t | Production tests NZTA M/10 | Inprocess Testing | Lab test | Site Engineer
7.18 | AC14 PMBRW15- PG 64 V (Top layer)-55mm | M | Visual inspection by the Engineer | Each lot | Surface finish inspection Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate. | Inprocess Testing | Inspection sheet | Site Engineer
7.19 | AC14RW30 / AC14 PMB RW 15 | M | Dip from stringline or survey as-built | grid pattern | (+10 / -10mm) | Inprocess Testing | Inspection sheet | Site Engineer
7.2 | AC14RW30 / AC14 PMB RW 15 | M | NDM/Cores (Testing plan to be agreed with client) | 1/300m2 or min 8 cores | Density testing Air voids to meet NZTA M/10:2020 +3% / -2% | Paved Area: Air voids, in accordance with NZTA M/10 (2020) Testing undertaken in accordance with NZTA M/10 | Core test report | Site Engineer
7.21 | AC14RW30 / AC14 PMB RW 15 | M | Cores depth (Location plan to be agreed with client) | 1/300m2 or min 8 cores | Thickness - Depth should not be less than design asphalt depth of thickness | Inprocess Testing | Core test report | Site Engineer
Comments:
[6 empty] | Signature: |  |  | Date:
QA checked By Quality Manager:
[6 empty] | Signature: |  |  | Date:
Accepted By Engineers Rep: