## Project Checklist Templates
Warnings | Id | Type | Name | Values | Prompting Name | Resource Id
|  | checklist | Attach Drawings |  | Miscellaneous/Attach Drawings | 790e3210-ffbf-4bc0-8540-0a211630b157
|  | checkpoint-no-value | Document Attached
| f58c64ac-1313-4d51-8c43-646af854e2d7 | checklist | Ceilings |  | Ceilings | fb853077-e1ca-4c0e-b0fb-28f156c76ae4
| acc3d382-dc8a-43f2-bf3f-88035796c642 | section | QA - Hanlon Plumbing
| 38ddccc4-2483-4a33-aa2a-805132ac4958 | checkpoint | Work complete and no further access needed
| ee9226f2-3f6d-43f9-a7b6-9dab901bb9fa | checkpoint | Aconex field issues (defects) closed
| 023eb47c-16e4-4511-abdf-7fb734943cb0 | section | QA - HelRimu
| 29cf5b7a-6cb4-4875-aac3-6380e7615ec6 | checkpoint | Work complete and no further access needed
| f379b931-211e-42cf-815e-cfeb0eb2dc95 | checkpoint | Aconex field issues (defects) closed
| ea300015-a566-4797-8502-063541a1b865 | section | QA - Gilcom
| 870f61d0-6697-4d9f-a6f9-00a947f7055d | checkpoint | Work complete and no further access needed
| dc667444-44f8-4eb2-99f1-d843f6b23d4f | checkpoint | Aconex field issues (defects) closed
| d79d20ff-c0f8-4d47-9a06-3206b88183e6 | section | QA - Rauland
| 7bafc6c3-a2dd-47f1-9fe3-773409f1f592 | checkpoint | Work complete and no further access needed
| 39f17d99-87dc-4274-8c01-51b8815a1140 | checkpoint | Aconex field issues (defects) closed
| 59448308-94de-4389-be95-6782275dce71 | section | QA - Premier Fire
| baf10844-67ff-42cb-b59d-6872064780c7 | checkpoint | Work complete and no further access needed
| 5ba77b11-26cd-4376-87f2-db4f1478dec4 | checkpoint | Aconex field issues (defects) closed
| 0b9dd80b-09a0-465d-b821-6fe89c563c47 | section | QA - Data Talk
| 0de083f7-5938-4f7b-be37-f719617f00fe | checkpoint | Work complete and no further access needed
| 424731c2-d567-45af-a2de-368a1b5b8180 | checkpoint | Aconex field issues (defects) closed
| 5e811389-bcb3-4424-a24a-7571ee0f0efb | section | QA - Lamson
| 9e9dcd67-b628-4ca3-bad3-78182bab3581 | checkpoint | Work complete and no further access needed
| c1b788a2-d546-4272-8a3f-bf7bcdd18657 | checkpoint | Aconex field issues (defects) closed
| baf6ef7a-2717-473a-bdb8-1a1fac64a37c | section | QA - VAE
| 0c1ac956-e697-4b73-820b-da4e21c0463e | checkpoint | Work complete and no further access needed
| 023b1c3d-b682-46df-941a-df237b9283ba | checkpoint | Aconex field issues (defects) closed
| 0a96b4a3-462f-4bf2-ae1a-0fa4b31821ed | section | QA - Contego
| c3cb565a-51db-4363-824b-17db04986375 | checkpoint | Fire rating complete and no further access needed
| 0890f526-dc1a-47f9-9e4a-6840c40a12a0 | checkpoint | Aconex field issues (defects) closed
| 4f8440f5-efcb-4503-a8bb-8e0dae7cad2d | section | QA - Alpha
| 78848735-9455-434e-b3be-0a7a142981fd | checkpoint | Work complete
| 5caba4e0-88b8-41ed-9324-192d828909c7 | checkpoint | Aconex field issues (defects) closed
folder-normal has incorrect meta.stepType checkpoint-status folder-normal is not dependant but can't have own status |  | checklist | Checked against drawings |  | Checked against drawings | c231c883-9a4d-43d9-bde3-c119a6ff3250
Data not allowed on folder-normal. | 3742050f-5672-5efe-a872-5cb2e58398c8 | textbox | Drawing No:
Data not allowed on folder-normal. | 62d48bcc-de69-547b-873f-2b0a43049158 | textbox | Revision No:
|  | checklist | Jack to test |  | Jack to test | 7d29be1f-9b64-474a-8c63-886fb72451e6
|  | checkpoint | Checked against drawings
| 020ac9c7-7272-5d89-9ee7-d8f2a824da8a | textbox | Drawing No:
| 2dd8e963-44d3-5184-af51-fe8dc2e25738 | textbox | Revision No:
|  | checklist | QA - Alpha |  | QA - Alpha | e1f90f19-67e1-430b-8dd3-87a77afad40c
|  | checkpoint | Insulation fitted
|  | checkpoint | Plasterboard installed
|  | checkpoint | Stopping complete
|  | checkpoint | Aconex field issues (defects) closed
|  | checklist | QA - Contego |  | QA - Contego | 2774eba0-fb07-48d9-b399-d21290336291
|  | checkpoint | Fire rating of in-wall floor penetrations complete
|  | checkpoint | Aconex field issues (defects) closed
|  | checklist | QA - Contract Coatings |  | QA - Contract Coatings | 377964f2-1ad3-402e-a3f1-898bb3beabce
|  | checkpoint | Sealer Coat
|  | checkpoint | First Coat
|  | checkpoint | Aconex field issues (defects) closed
|  | checklist | QA - Data Talk |  | QA - Data Talk | 1ef7392b-2cdd-4675-84e5-40d3dd8d5fb9
|  | checkpoint | Installation completed
|  | checkpoint | Junction box installed
|  | checkpoint | Acoustic treatment completed
|  | checkpoint | Aconex field issues (defects) closed
|  | checklist | QA - Gilcom |  | QA - Gilcom | 55f0351a-0409-4287-975b-49bd526feaec
|  | checkpoint | Installation completed
|  | checkpoint | Testing completed
|  | checkpoint | Acoustic treatment completed
|  | checkpoint | Aconex field issues (defects) closed
|  | checklist | QA - Hanlon Plumbing |  | QA - Hanlon Plumbing | a4f2cb05-387e-443f-ab73-a2308f14453d
|  | checkpoint | Installation completed
|  | checkpoint | Testing completed
|  | checkpoint | Acoustic treatment completed
|  | checkpoint | Aconex field issues (defects) closed
|  | checklist | QA - HelRimu |  | QA - HelRimu | 7ea4b45b-b4e0-4785-a16c-d1749a585e89
|  | checkpoint | Installation completed
|  | checkpoint | Testing completed
|  | checkpoint | Acoustic treatment completed
|  | checkpoint | Aconex field issues (defects) closed
|  | checklist | QA - Lamson |  | QA - Lamson | bd5ac203-b00e-4d75-ade1-4f27bc1e05ad
|  | checkpoint | Installation completed
|  | checkpoint | Testing completed
|  | checkpoint | Acoustic treatment completed
|  | checkpoint | Aconex field issues (defects) closed
|  | checklist | QA - LCL |  | QA - LCL | 0a428827-d6e2-4c5b-9d83-9d4652304228
|  | checkpoint | Framing completed
| dc771a88-d687-516a-a806-02864bcec994 | tickbox | Nogging
| 2b485389-6779-5158-945c-0af87c79d7b8 | tickbox | Blocking
|  | checkpoint | Framing straight and flush
|  | checkpoint | Fixings complete
|  | checkpoint | Moisture content <20%
|  | checkpoint | Aconex field issues (defects) closed
|  | checkpoint | Services complete and no outstanding work or changes
|  | checkpoint | Checked against drawings
| 3742050f-5672-5efe-a872-5cb2e58398c8 | textbox | Drawing No:
| 62d48bcc-de69-547b-873f-2b0a43049158 | textbox | Revision No:
|  | checklist | QA - LCL - Part 2 |  | QA - LCL - Part 2 | 361b6de7-2df9-425e-87c7-b5361c98d18d
|  | checkpoint | Paint complete
|  | checkpoint | Door frame installed
|  | checkpoint | Door leaf removed
|  | checkpoint | Toe kicks complete
|  | checkpoint | Aconex field issues (defects) closed
|  | checklist | QA - Premier Fire |  | QA - Premier Fire | 3385bb10-4137-4ae7-8aef-cfe102a1c28b
|  | checkpoint | Installation completed
|  | checkpoint | Testing completed
|  | checkpoint | Acoustic treatment completed
|  | checkpoint | Aconex field issues (defects) closed
|  | checklist | QA - Rauland |  | QA - Rauland | 130ae01b-eb4a-4e7a-9a07-b819f3bc2ab2
|  | checkpoint | Installation completed
|  | checkpoint | Testing completed
|  | checkpoint | Acoustic treatment completed
|  | checkpoint | Aconex field issues (defects) closed
|  | checklist | QA - VAE |  | QA - VAE | ad839c79-2875-42d7-884e-c010558d0e32
|  | checkpoint | Installation completed
|  | checkpoint | Testing completed
|  | checkpoint | Acoustic treatment completed
|  | checkpoint | Aconex field issues (defects) closed
| 80cbbbee-686e-4a27-a059-d1bf9847a5bd | checklist | Second Fix |  | Second Fix | 5871b492-b59c-41e6-87bf-8c2182c4eb4a
| c682ae02-1bb6-477f-9278-ae6d86ee4e3d | section | QA - Hills Flooring
| a753145f-4bb7-40fa-9791-426490cc88ac | checkpoint | Work complete
| b7cf496c-c4b1-48fd-99c4-31a7e3639c76 | checkpoint | Aconex field issues (defects) closed
| c8ae6a63-029d-4e75-9526-40f8345275cf | section | QA - Joinery
| b29148cc-6dac-4b0a-a8a6-be5263af5ecf | checkpoint | Work complete
| 8cbf66f2-1840-484e-a20f-90b14061ff3e | checkpoint | Aconex field issues (defects) closed
| 50bdbaab-9445-4245-b286-d3ffd3866576 | section | QA - Hanlon Plumbing
| 91b026f0-09fb-4d04-b300-db6e91258775 | checkpoint | Work complete
| 7a2cf032-e8b4-4509-827e-4bbafc198bcf | checkpoint | Aconex field issues (defects) closed
| 7c391bbb-a579-4ef0-9e48-542cdca5cf58 | section | QA - HelRimu
| 3e3b2281-ef47-4203-ace4-7ea8f152d3be | checkpoint | Work complete
| 319613d6-8bfa-4285-866e-1cb80ba81778 | checkpoint | Aconex field issues (defects) closed
| a05d134c-c900-4fa7-a71a-111e41ebf637 | section | QA - Gilcom
| 6b646b17-cf29-4e46-8c73-6eeb3a3778b9 | checkpoint | Work complete
| 65f2df7b-3add-4f5e-942e-1e2cf71df12b | checkpoint | Aconex field issues (defects) closed
| de613458-faf6-4975-af9e-cccfa12450b4 | section | QA - Rauland
| f4ab9706-0bf1-4bae-9672-ceebc4d1c0ba | checkpoint | Work complete
| b4f5a544-7229-4008-8ce6-11f08510b5fa | checkpoint | Aconex field issues (defects) closed
| 52830fc7-5990-4765-a649-26fa6f963fbc | section | QA - Premier Fire
| 5b27175c-ec80-4d69-a7ad-569bad806669 | checkpoint | Work complete
| f78f483e-f5a5-4630-81a2-45f6c9b93b6d | checkpoint | Aconex field issues (defects) closed
| cddb94f3-f1e3-45d6-87d6-2ad63b9858e6 | section | QA - Data Talk
| 23459953-7cd4-47e2-89c2-d98c1623940d | checkpoint | Work complete
| 8a919267-f0cc-4799-a0df-a311aa6d57ac | checkpoint | Aconex field issues (defects) closed
| 0f5c1faa-424f-4612-bf9a-69b368e3c7e0 | section | QA - Lamson
| c0f78407-cc18-4238-b92f-3e8912ddfd59 | checkpoint | Work complete
| cb73c23b-766b-4e6a-9d69-34cacd39386c | checkpoint | Aconex field issues (defects) closed
| c91d72da-c7a7-4d8d-85af-24ac8bf65fc9 | section | QA - VAE
| ae83804e-649f-4b82-9eda-ef7aa10f10b0 | checkpoint | Work complete
| 2e811894-af06-456d-a981-6fe55fdcd4de | checkpoint | Aconex field issues (defects) closed
| 1bdb3054-a1e0-43dc-acdf-aca2b5120788 | section | QA - LCL
| f87a4fb6-1a1b-4a39-8c93-1e9960f0d1b7 | checkpoint | Work complete
| b5bf4b86-4770-4bda-9922-341113338430 | checkpoint | Aconex field issues (defects) closed