## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-187-CIV-SSB-Rock Beaching-Type 1 | itp |  |  |  |  | ITP-187-CIV-SSB-Rock Beaching-Type 1 Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-187-CIV-SSB-Rock Beaching
label | ITP Description: SSB-Rock Beaching
label | Discipline (e.g. CIV/STR/RAIL): 187-CIV
label | Revision Number: 0
label | Revision Date: 17/04/2024
label | ITP created by: VM
label | ITP approved for use by: VM
label | 1.1 VicRoads Specification and Melbourne Water approval
label | Reference: VicRoads Section 713 April 2017
section | Preliminaries - Materials
checkpoint | 2.1 Beaching Material-Type 1
label | REFERENCE: 713.03 Section 713.03(a) (i) IFC Drawings (MRP-087-C-ACD-DRG-16-BFD-CDR-6001)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All rock beaching materials shall:
label | – Comply with the material requirements for ‘sound’ rock in Section 801 and
label | – The Los Angeles Value (LAV) requirements of Table 801.033. and
label | – The rock shall have a minimum apparent particle density of 2.5 t/m3 and
label | – The rock beaching shall have a minimum wet strength of 100 kN and a wet/dry strength variation not exceeding 45%
label | Rock for Type 1 beaching shall
label | – Consist of field or quarry rock.
label | – Have a mass of between 20 and 70 kg
label | – At least 60% by number shall be over 40 kg.
label | – Rocks shall be of such size that the layer of beaching is not less than 225 mm thick.
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to each use unless previously approved
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Bedding -Geotextile-Type 1
label | REFERENCE: 713.03 Section 713.03(b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The beaching shall not routinely require a granular bedding, however a very robust needle-punched non woven geotextile (mass >250 g/m2) shall be laid over the trimmed surface where rock beaching is to be placed. Geotextiles used shall comply with and be placed in accordance with Section 210.
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to each use unless previously approved
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Beaching Placement Approval
label | REFERENCE: 713.05 Sect (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Prior to commencement of any work where placement of rock beaching is proposed, a detailed job safety assessment shall be undertaken by a suitably qualified and experienced professional and a suitable Safe Work Method Statement developed to cover all necessary elements.
label | ○ The completed job safety assessment and the Safe Work Method Statement shall be submitted to the Superintendent for review.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Site Safety manager
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
section | Pre-construction Activities
checkpoint | 4.1 IFC Drawings
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to starting Works and at regular intervals
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: All
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Confirmation of rock sizing
label | REFERENCE: (MRP-087-C-ACD-DRG-16-BFD-CDR-6001)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Rocks shall be of such size that the layer of beaching is not less than 225 mm thick.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Delivery Dockets and test reports to be attached to this ITP
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Preparation of Underlying Surface
label | REFERENCE: 713.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Areas on which beaching is to be placed shall be compacted and trimmed as required to provide a finished surface level of beaching in accordance with the drawings. Any scours or hollows in the surface shall be filled with compacted Class 4 crushed rock.
label | ○ Trimmed material shall be removed from the site.
label | ○ The geotextile shall be buried to a depth of 300 mm at the edges of beaching and placed under and around the excavation for the toe wall and for any other perimeter walls provided. The geotextile shall be laid evenly with no kinks or folds, and joints shall be formed by overlapping the geotextile by not less than 300 mm and not more than 500 mm.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Toe Rock embedment
label | REFERENCE: 713.07 (MRP-087-C-ACD-DRG-16-BFD-CDR-6001)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Toe wall 600mm wide by 600mm deep shall be constructed. This should be lined with geotextile fabric and the voids between rocks to be filled with smaller stones.Similar walls 600 mm wide by 600 mm deep shall also be constructed across the upstream end of the beaching.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Beaching Placement-Thichness
label | REFERENCE: 713.05 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Layer of beaching is not less than 225mm
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.6 Beaching Placement-embedment
label | REFERENCE: 713.05 Sect (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Beaching materials shall be firmly bedded on the prepared embankment and/or bedding if required and laid in courses commencing from the bottom of any slope.
label | ○ Un-grouted beaching and armour stone when placed shall form a tight ‘interlocking grid’, which shall prevent the removal of individual rocks.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Type 1 Rock Beaching Placement-Surrounding
label | REFERENCE: 713.05 Sect (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Gaps between rocks shall be as narrow as practicable and not exceed 60 mm on average. Voids shall be filled to at least mid height of the rocks with topsoil.
label | ○ The level of the topsoil shall be increased where planting is required within Type 1 rock beaching. The topsoil depth shall be increased to finish flush with the general rock surface and adjacent ground level.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Type 1 Rock Beaching Placement-surface
label | REFERENCE: 713.05 Sect (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The general surface of the finished beaching shall not vary from a 3 metre straight edge laid across the surface of the beaching by more than 100mm for type 1 beaching.
label | ○ Finished surface levels of rock beaching placed in open drains shall be flush with adjacent soil levels to allow mowing and maintenance. Rock beaching shall not protrude more than 50 mm above the surrounding ground levels.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Cleaning
label | REFERENCE: 713.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: On completion of the work, the beaching shall be cleaned to remove all foreign materials and discolouration from the beaching surface.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP