## Sheet1
2.1 | Submit Mix Design - Cement treated crushed rock (CTCR) mix | VicRoads Spec. Cl. 815.05 VicRoads Spec. Cl.306.04 VicRoads Spec. TN 107 VicRoads Spec. CoC 500.02 IFC Drawings | Cement treated crushed rock mixes for use on specified works can be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175. CTCR shall comply with Section 815 CHAR(AMP) 821, TN107 CHAR(AMP) CoC 500.02 Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each mix design, 4 weeks prior to placement of concrete | HP | SE CHAR(AMP) Nominated Authority | Issue to TeamBinder: VicRoads registered cement treated crushed rock mix | 2.1 Submit Mix Design - Cement treated crushed rock (CTCR) mix | REFERENCE: VicRoads Spec. Cl. 815.05 VicRoads Spec. Cl.306.04 VicRoads Spec. TN 107 VicRoads Spec. CoC 500.02 IFC Drawings | ACCEPTANCE CRITERIA: Cement treated crushed rock mixes for use on specified works can be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175. CTCR shall comply with Section 815 CHAR(AMP) 821, TN107 CHAR(AMP) CoC 500.02 Enter: Teambinder Material Approval number [free text box] | METHOD: Document Review | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete | CATEGORY: HP | RESPONSIBILITY: SE CHAR(AMP) Nominated Authority | VERIFYING DOCUMENTS: Issue to TeamBinder: VicRoads registered cement treated crushed rock mix | Date Completed: | 2.1 Submit Mix Design - Cement treated crushed rock (CTCR) mix
2.2 | Hold Point - Alternate Binder (if applicable) | VicRoads Spec. Cl.306.09(a) | If a binder other than those listed in Table 306.091 is proposed for use, laboratory test results must be produced to show that binder satisfies the required working time and strength determined in accordance with the VicRoads Test Method. Enter: Teambinder Material Approval number [free text box] | Document Review | Once per material type, prior to commencement of works | HP | SE CHAR(AMP) Nominated Authority | Issue to TeamBinder: Test Records | 2.2 Hold Point - Alternate Binder (if applicable) | REFERENCE: VicRoads Spec. Cl.306.09(a) | ACCEPTANCE CRITERIA: If a binder other than those listed in Table 306.091 is proposed for use, laboratory test results must be produced to show that binder satisfies the required working time and strength determined in accordance with the VicRoads Test Method. Enter: Teambinder Material Approval number [free text box] | METHOD: Document Review | FREQUENCY: Once per material type, prior to commencement of works | CATEGORY: HP | RESPONSIBILITY: SE CHAR(AMP) Nominated Authority | VERIFYING DOCUMENTS: Issue to TeamBinder: Test Records | Date Completed: | REFERENCE: VicRoads Spec. Cl. 815.05 VicRoads Spec. Cl.306.04 VicRoads Spec. TN 107 VicRoads Spec. CoC 500.02 IFC Drawings
3.1 | Check that current revision drawings are being used | Project Drawings / Drawing Register | Issued For Construction (IFC) and latest available revision used | Document review | Each Lot | HP* | SE / Site Foreman | This ITP | 3.1 Check that current revision drawings are being used | REFERENCE: Project Drawings / Drawing Register | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used | METHOD: Document review | FREQUENCY: Each Lot | CATEGORY: HP* | RESPONSIBILITY: SE / Site Foreman | VERIFYING DOCUMENTS: This ITP | Date Completed: | ACCEPTANCE CRITERIA: Cement treated crushed rock mixes for use on specified works can be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175. CTCR shall comply with Section 815 CHAR(AMP) 821, TN107 CHAR(AMP) CoC 500.02 Enter: Teambinder Material Approval number [free text box]
3.2 | Previous Layer Conformance | IFC Drawings for Previous Layer Type | Confirm previous layer (prior to CTCR layer placemen) conforms to IFC drawing and specification requirements. Check the previous fill level/survey (e.g. fill, foundation . Subgrade, base course etc) to ensure CTCR minimum thickness requirements is achieved Enter: Previous Layer Lot number [Free text box] | Document Review | Each Lot | HP* | SE | This ITP Previous Lot Number | 3.2 Previous Layer Conformance | REFERENCE: IFC Drawings for Previous Layer Type | ACCEPTANCE CRITERIA: Confirm previous layer (prior to CTCR layer placemen) conforms to IFC drawing and specification requirements. Check the previous fill level/survey (e.g. fill, foundation . Subgrade, base course etc) to ensure CTCR minimum thickness requirements is achieved Enter: Previous Layer Lot number [Free text box] | METHOD: Document Review | FREQUENCY: Each Lot | CATEGORY: HP* | RESPONSIBILITY: SE | VERIFYING DOCUMENTS: This ITP Previous Lot Number | Date Completed: | METHOD: Document Review
4.1 | Lot Size | VicRoads Spec. Cl.306.03(b) | The maximum size for a single lot shall be considered a single layer of 4000m² A lot shall consist of a single layer of pavement material placed on the same day | Visual Measure | Each lot | IP | SE | Signed ITP Attach: Lot Map | 4.1 Lot Size | REFERENCE: VicRoads Spec. Cl.306.03(b) | ACCEPTANCE CRITERIA: The maximum size for a single lot shall be considered a single layer of 4000m² A lot shall consist of a single layer of pavement material placed on the same day | METHOD: Visual Measure | FREQUENCY: Each lot | CATEGORY: IP | RESPONSIBILITY: SE | VERIFYING DOCUMENTS: Signed ITP Attach: Lot Map | Date Completed: | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
4.2 | Survey Set-out | IFC Drawings | Survey to set out works in accordance with IFC Drawings ATTACH: Lot Map | Measure Visual | Each lot prior to commencement | IP | Surveyor SE/PE/SPE | This ITP Attach: Lot Map | 4.2 Survey Set-out | REFERENCE: IFC Drawings | ACCEPTANCE CRITERIA: Survey to set out works in accordance with IFC Drawings ATTACH: Lot Map | METHOD: Measure Visual | FREQUENCY: Each lot prior to commencement | CATEGORY: IP | RESPONSIBILITY: Surveyor SE/PE/SPE | VERIFYING DOCUMENTS: This ITP Attach: Lot Map | Date Completed: | CATEGORY: HP
5.1 | Delivery | VicRoads Spec. Cl.306.07 | Review delivery dockets to ensure all information required as per 306.07 (b) is recorded and meets the specificaiton requirements. Attach: Delivery Dockets | Document Review | Each Lot | IP | SE | This ITP Attach: Delivery Dockets Attach: pour records | 5.1 Delivery | REFERENCE: VicRoads Spec. Cl.306.07 | ACCEPTANCE CRITERIA: Review delivery dockets to ensure all information required as per 306.07 (b) is recorded and meets the specificaiton requirements. Attach: Delivery Dockets | METHOD: Document Review | FREQUENCY: Each Lot | CATEGORY: IP | RESPONSIBILITY: SE | VERIFYING DOCUMENTS: This ITP Attach: Delivery Dockets Attach: pour records | Date Completed: | RESPONSIBILITY: SE CHAR(AMP) Nominated Authority
5.2 | Placement - Transverse Joints | VicRoads Spec. Cl.306.08(a)(c) | Material should be spread to minimise number of joints In any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m Transverse joints offset from one layer to next by not less than 2 metres | Visual Measure | Each Lot | IP | SE | This ITP | 5.2 Placement - Transverse Joints | REFERENCE: VicRoads Spec. Cl.306.08(a)(c) | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints In any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m Transverse joints offset from one layer to next by not less than 2 metres | METHOD: Visual Measure | FREQUENCY: Each Lot | CATEGORY: IP | RESPONSIBILITY: SE | VERIFYING DOCUMENTS: This ITP | Date Completed: | VERIFYING DOCUMENTS: Issue to TeamBinder: VicRoads registered cement treated crushed rock mix
5.3 | Placement - Longitudinal Joints | VicRoads Spec. Cl.306.08(a)(d)(e) | Material should be spread to minimise number of joints Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane. | Visual Measure | Each Lot | IP | SE | This ITP | 5.3 Placement - Longitudinal Joints | REFERENCE: VicRoads Spec. Cl.306.08(a)(d)(e) | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane. | METHOD: Visual Measure | FREQUENCY: Each Lot | CATEGORY: IP | RESPONSIBILITY: SE | VERIFYING DOCUMENTS: This ITP | Date Completed: | Date Completed:
5.4 | Placement - Layer Thickness | VicRoads Spec. Cl.306.11 | Compacted layer thickness should be not less than 100mm and not greater than 180mm. | Visual Measure | Each Lot | IP | SE | This ITP | 5.4 Placement - Layer Thickness | REFERENCE: VicRoads Spec. Cl.306.11 | ACCEPTANCE CRITERIA: Compacted layer thickness should be not less than 100mm and not greater than 180mm. | METHOD: Visual Measure | FREQUENCY: Each Lot | CATEGORY: IP | RESPONSIBILITY: SE | VERIFYING DOCUMENTS: This ITP | Date Completed: | 2.2 Hold Point - Alternate Binder (if applicable)
5.5 | Placement - Working Time | VicRoads Spec. Cl.306.07 VicRoads Spec. Cl.306.09 Table 306.091 | Working Shall Not be more than specified for each binder: Rapid Setting (GP) - 2hrs (Oct-Apr) 3hrs (May-Sept) Medium Setting (GB) - 3hrs (Oct-Apr) 5hrs (May-Sept) Slow Setting (Slag) - 8hrs (Oct-Apr) 12hrs (May-Sept) If the ambient temperature within the period from October to April on any day is less than 15°C, the May to September maximum allowable working times may be applied. Attach: Delivery Dockets Attach: Pour record | Measure Document Review | Each Lot | IP | SE | This ITP Delivery Dockets Attach: pour records | 5.5 Placement - Working Time | REFERENCE: VicRoads Spec. Cl.306.07 VicRoads Spec. Cl.306.09 Table 306.091 | ACCEPTANCE CRITERIA: Working Shall Not be more than specified for each binder: Rapid Setting (GP) - 2hrs (Oct-Apr) 3hrs (May-Sept) Medium Setting (GB) - 3hrs (Oct-Apr) 5hrs (May-Sept) Slow Setting (Slag) - 8hrs (Oct-Apr) 12hrs (May-Sept) If the ambient temperature within the period from October to April on any day is less than 15°C, the May to September maximum allowable working times may be applied. Attach: Delivery Dockets Attach: Pour record | METHOD: Measure Document Review | FREQUENCY: Each Lot | CATEGORY: IP | RESPONSIBILITY: SE | VERIFYING DOCUMENTS: This ITP Delivery Dockets Attach: pour records | Date Completed: | REFERENCE: VicRoads Spec. Cl.306.09(a)
5.6 | Water | VicRoads Spec. Cl.306.06 | Except for the purpose of curing, no water shall be added to the cementitious treated material. Water shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances. | Visual | Each Lot | IP | SE | This ITP | 5.6 Water | REFERENCE: VicRoads Spec. Cl.306.06 | ACCEPTANCE CRITERIA: Except for the purpose of curing, no water shall be added to the cementitious treated material. Water shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances. | METHOD: Visual | FREQUENCY: Each Lot | CATEGORY: IP | RESPONSIBILITY: SE | VERIFYING DOCUMENTS: This ITP | Date Completed: | ACCEPTANCE CRITERIA: If a binder other than those listed in Table 306.091 is proposed for use, laboratory test results must be produced to show that binder satisfies the required working time and strength determined in accordance with the VicRoads Test Method. Enter: Teambinder Material Approval number [free text box]
5.7 | Cementious binder content CHAR(AMP) UCS requirements | VicRoads Spec. 815.10 | Contractor shall carry out the UCS Testing to determine the cemenetious binder meet the minimum 7days Attach: test results | Document Review | Each Lot | IP | SE | Test report | 5.7 Cementious binder content CHAR(AMP) UCS requirements | REFERENCE: VicRoads Spec. 815.10 | ACCEPTANCE CRITERIA: Contractor shall carry out the UCS Testing to determine the cemenetious binder meet the minimum 7days Attach: test results | METHOD: Document Review | FREQUENCY: Each Lot | CATEGORY: IP | RESPONSIBILITY: SE | VERIFYING DOCUMENTS: Test report | Date Completed: | METHOD: Document Review
5.8 | Compaction - Modified Compactive Effort | VicRoads Spec. Cl.306.05 VicRoads Spec. Cl.306.09(a)(b) | Moisture content at time of spreading and compactions is within +0.5% and –1.0% of optimum moisture content Scale B: No. of tests per lot shall be 3 Mean density ratio > 96% | Document review | Each Lot | IP | SE | Attach: Test Report | 5.8 Compaction - Modified Compactive Effort | REFERENCE: VicRoads Spec. Cl.306.05 VicRoads Spec. Cl.306.09(a)(b) | ACCEPTANCE CRITERIA: Moisture content at time of spreading and compactions is within +0.5% and –1.0% of optimum moisture content Scale B: No. of tests per lot shall be 3 Mean density ratio > 96% | METHOD: Document review | FREQUENCY: Each Lot | CATEGORY: IP | RESPONSIBILITY: SE | VERIFYING DOCUMENTS: Attach: Test Report | Date Completed: | FREQUENCY: Once per material type, prior to commencement of works
5.9 | Test Rolling | VicRoads Spec. Cl.306.10 Table 306.091 | Test rolling to be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091. | Visual | Each Lot | HP | SE, NA | This ITP | 5.9 Test Rolling | REFERENCE: VicRoads Spec. Cl.306.10 Table 306.091 | ACCEPTANCE CRITERIA: Test rolling to be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091. | METHOD: Visual | FREQUENCY: Each Lot | CATEGORY: HP | RESPONSIBILITY: SE, NA | VERIFYING DOCUMENTS: This ITP | Date Completed: | CATEGORY: HP
6.1 | Curing | Vicroads Spec 306.11 | Pavement Design Modulus of 500 MPa: The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane | Visual | Each Lot | IP | SE/PE | This ITP | 6.1 Curing | REFERENCE: Vicroads Spec 306.11 | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa: The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane | METHOD: Visual | FREQUENCY: Each Lot | CATEGORY: IP | RESPONSIBILITY: SE/PE | VERIFYING DOCUMENTS: This ITP | Date Completed: | RESPONSIBILITY: SE CHAR(AMP) Nominated Authority
6.2 | Protection | Vicroads Spec 306.11 | Pavement Design Modulus of 500 MPa: Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent. | Visual | Each Lot | IP | SE/PE | This ITP | 6.2 Protection | REFERENCE: Vicroads Spec 306.11 | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa: Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent. | METHOD: Visual | FREQUENCY: Each Lot | CATEGORY: IP | RESPONSIBILITY: SE/PE | VERIFYING DOCUMENTS: This ITP | Date Completed: | VERIFYING DOCUMENTS: Issue to TeamBinder: Test Records
6.3 | Surface level | VicRoads Spec. Cl.306.03(c) | No point on the surface of the cementitious subbase layer shall vary by more than 8 mm from a 3 metre straight edge placed in any direction. Water shall not pond on the surface of the cementitious treated subbase | Document review | Each Lot | IP | SE/PE | This ITP | 6.3 Surface level | REFERENCE: VicRoads Spec. Cl.306.03(c) | ACCEPTANCE CRITERIA: No point on the surface of the cementitious subbase layer shall vary by more than 8 mm from a 3 metre straight edge placed in any direction. Water shall not pond on the surface of the cementitious treated subbase | METHOD: Document review | FREQUENCY: Each Lot | CATEGORY: IP | RESPONSIBILITY: SE/PE | VERIFYING DOCUMENTS: This ITP | Date Completed: | Date Completed:
6.4 | Conformity with drawings-Width and alignment | VicRoads Spec. Cl.306.03(b) Table 306.032 | Width and Alignment: The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle. | Document Review | Each Lot | IP | SE/PE | Attach: Survey Report | 6.4 Conformity with drawings-Width and alignment | REFERENCE: VicRoads Spec. Cl.306.03(b) Table 306.032 | ACCEPTANCE CRITERIA: Width and Alignment: The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle. | METHOD: Document Review | FREQUENCY: Each Lot | CATEGORY: IP | RESPONSIBILITY: SE/PE | VERIFYING DOCUMENTS: Attach: Survey Report | Date Completed: | 3.1 Check that current revision drawings are being used
6.5 | Conformity with drawings-Survey Level | VicRoads Spec. Cl.306.03(b) Table 306.032 | Scale B: Measurements per Lot: 40 Subgrade: - Mean value of all level readings to range between +5/-25 - Standard deviation of all level readings to be less than or equal to 15 Subbase: - Mean value of all level readings to range between +6/-12 - Standard deviation of all level readings to be less than or equal to 13 | Document Review | Each Lot Scale B: 40 points per lot | IP | SE/PE | Attach: Survey Report | 6.5 Conformity with drawings-Survey Level | REFERENCE: VicRoads Spec. Cl.306.03(b) Table 306.032 | ACCEPTANCE CRITERIA: Scale B: Measurements per Lot: 40 Subgrade: - Mean value of all level readings to range between +5/-25 - Standard deviation of all level readings to be less than or equal to 15 Subbase: - Mean value of all level readings to range between +6/-12 - Standard deviation of all level readings to be less than or equal to 13 | METHOD: Document Review | FREQUENCY: Each Lot Scale B: 40 points per lot | CATEGORY: IP | RESPONSIBILITY: SE/PE | VERIFYING DOCUMENTS: Attach: Survey Report | Date Completed: | REFERENCE: Project Drawings / Drawing Register
6.6 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Team Binder. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | PE/SPE | This ITP | 6.6 Non-conformance Report (NCR) Closure | REFERENCE: MRPA Quality Management Plan | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Team Binder. | METHOD: Document Review | FREQUENCY: Once, prior to closure of this lot / element / Work area | CATEGORY: HP* | RESPONSIBILITY: PE/SPE | VERIFYING DOCUMENTS: This ITP | Date Completed: | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
METHOD: Document review
FREQUENCY: Each Lot
CATEGORY: HP*
RESPONSIBILITY: SE / Site Foreman
VERIFYING DOCUMENTS: This ITP
Date Completed:
3.2 Previous Layer Conformance
REFERENCE: IFC Drawings for Previous Layer Type
ACCEPTANCE CRITERIA: Confirm previous layer (prior to CTCR layer placemen) conforms to IFC drawing and specification requirements. Check the previous fill level/survey (e.g. fill, foundation . Subgrade, base course etc) to ensure CTCR minimum thickness requirements is achieved Enter: Previous Layer Lot number [Free text box]
METHOD: Document Review
FREQUENCY: Each Lot
CATEGORY: HP*
RESPONSIBILITY: SE
VERIFYING DOCUMENTS: This ITP Previous Lot Number
Date Completed:
4.1 Lot Size
REFERENCE: VicRoads Spec. Cl.306.03(b)
ACCEPTANCE CRITERIA: The maximum size for a single lot shall be considered a single layer of 4000m² A lot shall consist of a single layer of pavement material placed on the same day
METHOD: Visual Measure
FREQUENCY: Each lot
CATEGORY: IP
RESPONSIBILITY: SE
VERIFYING DOCUMENTS: Signed ITP Attach: Lot Map
Date Completed:
4.2 Survey Set-out
REFERENCE: IFC Drawings
ACCEPTANCE CRITERIA: Survey to set out works in accordance with IFC Drawings ATTACH: Lot Map
METHOD: Measure Visual
FREQUENCY: Each lot prior to commencement
CATEGORY: IP
RESPONSIBILITY: Surveyor SE/PE/SPE
VERIFYING DOCUMENTS: This ITP Attach: Lot Map
Date Completed:
5.1 Delivery
REFERENCE: VicRoads Spec. Cl.306.07
ACCEPTANCE CRITERIA: Review delivery dockets to ensure all information required as per 306.07 (b) is recorded and meets the specificaiton requirements. Attach: Delivery Dockets
METHOD: Document Review
FREQUENCY: Each Lot
CATEGORY: IP
RESPONSIBILITY: SE
VERIFYING DOCUMENTS: This ITP Attach: Delivery Dockets Attach: pour records
Date Completed:
5.2 Placement - Transverse Joints
REFERENCE: VicRoads Spec. Cl.306.08(a)(c)
ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints In any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m Transverse joints offset from one layer to next by not less than 2 metres
METHOD: Visual Measure
FREQUENCY: Each Lot
CATEGORY: IP
RESPONSIBILITY: SE
VERIFYING DOCUMENTS: This ITP
Date Completed:
5.3 Placement - Longitudinal Joints
REFERENCE: VicRoads Spec. Cl.306.08(a)(d)(e)
ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
METHOD: Visual Measure
FREQUENCY: Each Lot
CATEGORY: IP
RESPONSIBILITY: SE
VERIFYING DOCUMENTS: This ITP
Date Completed:
5.4 Placement - Layer Thickness
REFERENCE: VicRoads Spec. Cl.306.11
ACCEPTANCE CRITERIA: Compacted layer thickness should be not less than 100mm and not greater than 180mm.
METHOD: Visual Measure
FREQUENCY: Each Lot
CATEGORY: IP
RESPONSIBILITY: SE
VERIFYING DOCUMENTS: This ITP
Date Completed:
5.5 Placement - Working Time
REFERENCE: VicRoads Spec. Cl.306.07 VicRoads Spec. Cl.306.09 Table 306.091
ACCEPTANCE CRITERIA: Working Shall Not be more than specified for each binder: Rapid Setting (GP) - 2hrs (Oct-Apr) 3hrs (May-Sept) Medium Setting (GB) - 3hrs (Oct-Apr) 5hrs (May-Sept) Slow Setting (Slag) - 8hrs (Oct-Apr) 12hrs (May-Sept) If the ambient temperature within the period from October to April on any day is less than 15°C, the May to September maximum allowable working times may be applied. Attach: Delivery Dockets Attach: Pour record
METHOD: Measure Document Review
FREQUENCY: Each Lot
CATEGORY: IP
RESPONSIBILITY: SE
VERIFYING DOCUMENTS: This ITP Delivery Dockets Attach: pour records
Date Completed:
5.6 Water
REFERENCE: VicRoads Spec. Cl.306.06
ACCEPTANCE CRITERIA: Except for the purpose of curing, no water shall be added to the cementitious treated material. Water shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
METHOD: Visual
FREQUENCY: Each Lot
CATEGORY: IP
RESPONSIBILITY: SE
VERIFYING DOCUMENTS: This ITP
Date Completed:
5.7 Cementious binder content CHAR(AMP) UCS requirements
REFERENCE: VicRoads Spec. 815.10
ACCEPTANCE CRITERIA: Contractor shall carry out the UCS Testing to determine the cemenetious binder meet the minimum 7days Attach: test results
METHOD: Document Review
FREQUENCY: Each Lot
CATEGORY: IP
RESPONSIBILITY: SE
VERIFYING DOCUMENTS: Test report
Date Completed:
5.8 Compaction - Modified Compactive Effort
REFERENCE: VicRoads Spec. Cl.306.05 VicRoads Spec. Cl.306.09(a)(b)
ACCEPTANCE CRITERIA: Moisture content at time of spreading and compactions is within +0.5% and –1.0% of optimum moisture content Scale B: No. of tests per lot shall be 3 Mean density ratio > 96%
METHOD: Document review
FREQUENCY: Each Lot
CATEGORY: IP
RESPONSIBILITY: SE
VERIFYING DOCUMENTS: Attach: Test Report
Date Completed:
5.9 Test Rolling
REFERENCE: VicRoads Spec. Cl.306.10 Table 306.091
ACCEPTANCE CRITERIA: Test rolling to be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
METHOD: Visual
FREQUENCY: Each Lot
CATEGORY: HP
RESPONSIBILITY: SE, NA
VERIFYING DOCUMENTS: This ITP
Date Completed:
6.1 Curing
REFERENCE: Vicroads Spec 306.11
ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa: The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane
METHOD: Visual
FREQUENCY: Each Lot
CATEGORY: IP
RESPONSIBILITY: SE/PE
VERIFYING DOCUMENTS: This ITP
Date Completed:
6.2 Protection
REFERENCE: Vicroads Spec 306.11
ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa: Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
METHOD: Visual
FREQUENCY: Each Lot
CATEGORY: IP
RESPONSIBILITY: SE/PE
VERIFYING DOCUMENTS: This ITP
Date Completed:
6.3 Surface level
REFERENCE: VicRoads Spec. Cl.306.03(c)
ACCEPTANCE CRITERIA: No point on the surface of the cementitious subbase layer shall vary by more than 8 mm from a 3 metre straight edge placed in any direction. Water shall not pond on the surface of the cementitious treated subbase
METHOD: Document review
FREQUENCY: Each Lot
CATEGORY: IP
RESPONSIBILITY: SE/PE
VERIFYING DOCUMENTS: This ITP
Date Completed:
6.4 Conformity with drawings-Width and alignment
REFERENCE: VicRoads Spec. Cl.306.03(b) Table 306.032
ACCEPTANCE CRITERIA: Width and Alignment: The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle.
METHOD: Document Review
FREQUENCY: Each Lot
CATEGORY: IP
RESPONSIBILITY: SE/PE
VERIFYING DOCUMENTS: Attach: Survey Report
Date Completed:
6.5 Conformity with drawings-Survey Level
REFERENCE: VicRoads Spec. Cl.306.03(b) Table 306.032
ACCEPTANCE CRITERIA: Scale B: Measurements per Lot: 40 Subgrade: - Mean value of all level readings to range between +5/-25 - Standard deviation of all level readings to be less than or equal to 15 Subbase: - Mean value of all level readings to range between +6/-12 - Standard deviation of all level readings to be less than or equal to 13
METHOD: Document Review
FREQUENCY: Each Lot Scale B: 40 points per lot
CATEGORY: IP
RESPONSIBILITY: SE/PE
VERIFYING DOCUMENTS: Attach: Survey Report
Date Completed:
6.6 Non-conformance Report (NCR) Closure
REFERENCE: MRPA Quality Management Plan
ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Team Binder.
METHOD: Document Review
FREQUENCY: Once, prior to closure of this lot / element / Work area
CATEGORY: HP*
RESPONSIBILITY: PE/SPE
VERIFYING DOCUMENTS: This ITP
Date Completed: