## ITP
|  |  | Inspection and Test Plan - Crack Sealing in Bituminous Surfacing | [7 empty] | Document # ITP-023
[11 empty] | Revision: 1 | Date : 20/2/23
Client: | Melbourne Airport |  | Construction Process: | Crack Sealing in Bituminous Surfacing |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melbourne Airport Runway 16-34 Overlay |  |  |  |  | Name: |  | Name: |  |  | Name:
Contract: | 12554937 |  | Specifications: | Technical Specifications Melbourne Airport Runway 16-34 Overlay Schematic and Detailed Design GHD-DD-SPC-001 (10 June 2022), GHD-DD-SPC-002 (14 June 2022) |  | Catherine Wood |  | Noriko Wood |  |  | Michael Crawford
[6 empty] | Senior Project Manager |  | Quality Manager |  |  | Beca Project Manager
|  |  | Location: | Fulton Hogan Infrastructure Services 500 Princes Hwy, Noble Park VIC 3174 | [6 empty] | BecaCPL-GCOR-001388
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail | [5 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility
|  |  | Frequency |  | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity
1 | Preliminary
1.01 | [5 empty] | GHD-DD-SPC-002 3903(e) WP3903-1
1.02
1.03
1.04
1.05
1.06
1 | Preliminary
1.01 | Demonstration that the sealant and the application method to be used comply with the requirements of the specification. |  | Prior to the commencement of crack sealing. |  | The test section must consist of the sealing of not less than 50 lineal metres of crack. The Contract Administrator will inspect and assess the outcomes of the crack sealing trial prior to the release of the Hold Point. | GHD-DD-SPC-002 5504 HP5504-1 | Inspection | ITP | HP | Quality Manager
1.02 | Material Sources - Conformance Test Certificates/Reports |  | At least 6 weeks prior to shipping and the commencement of construction of crack sealing. |  | The following information must be submitted: a. Source of the material; b. Name and address of the manufacturer; c. Location of manufacture; d. Process(es) used in manufacture; and e. Test certificates for every test property in the set of test properties that are required to demonstrate the compliance of the material with the relevant Specification (AS 2157). The certificate shall indicate full compliance of the bitumen emulsion with the above-specified requirements and shall be issued by a laboratory registered by NATA for the performance of such tests. The test certificates shall be for the manufacturer's current production and samples to which the test certificates pertain shall have been taken not more than 1 month prior to submission. | GHD-DD-SPC-002 5507(b) HP5507-1 | Document submission | ITP | HP | Quality Manager
2 | Materials
2.01 | Rubberised Bituminous Sealant |  | Prior to the commencement of crack sealing. |  | Rubberised Bituminous Sealant must be a proprietary polymer bitumen (PMB) sealant specifically manufactured for the sealing of cracks. It must be a hot applied material and must have a high resistance to bleeding in service during hot weather (minimum Softening Point 90°C) The rubberised bituminous sealant must consist of SAMIfilla HM or similar approved. | GHD-DD-SPC-002 5502(a) | Inspection | ITP | IP | Site Engineer
2.02 | Reflected Joint Bandage |  | Prior to the commencement of crack sealing. |  | The rubber-bitumen compound shall be a flexible weather resistant seal, slump resistant unaffected by permanent immersion in water, or by alkalis or sulphates. The material shall have a minimum storage life of 12 months in original containers stores in cool, dry conditions and have a density of 1.30kg/litre. The sealing compound shall adhere firmly to the concrete in all weather conditions. The sealing compound shall not flow either along or down the joint during hot weather The sealing compound shall be durable and shall not weather beyond the forming of a thin surface skin. | GHD-DD-SPC-002 5502(b) | Inspection | ITP | IP | Site Engineer
2.03 | Herbicide |  | Prior to the commencement of crack sealing. |  | Herbicides shall be a broad spectrum, non-residual, glyphosate based herbicide that has been specifically manufactured for low aquatic toxicity, and complying with any additional environmental requirements in Section 1400 of the Specification. | GHD-DD-SPC-002 5502(c) GHD-DD-SPC-002 1400 | Inspection | ITP | IP | Site Engineer
3 | Preparation
3.01 | Poisoning and removal of grass and weed growth |  | Prior to the commencement of preparation of cracks. |  | Poisoning and removal of grass and weed growth in all cracks and joints shall be carried out prior to commencing any crack and/or joint sealing. | GHD-DD-SPC-002 5503(a) | Inspection | ITP | IP | Site Engineer
3.02 | Preparation of Cracks |  | Prior to the application of the crack sealant. |  | All cracks shall be thoroughly cleaned of all foreign material, including old crack sealant. Cracks shall be blown out with compressed air using a lance, and if hot air is utilised, care shall be exercised to keep the lance moving to avoid burning the surrounding pavement. All wide (greater than 5mm) and/or deep cracks in the all types of pavement shall be choked with dry sand to 15mm below the surface of the pavement. Any sand spilled on the surface of the pavement shall be removed prior to sealing. | GHD-DD-SPC-002 5503(b) | Inspection | ITP | IP | Site Engineer
4 | Sealing
4.01 | Heating of Sealant |  | During crack sealing works |  | Sealant must be heated to a temperature that is within the range recommended by the sealant manufacturer and appropriate for the successful application under the prevailing air and pavement temperatures. The sealant temperature must be maintained so that it always remains within the range recommended by the sealant manufacturer. Localised sealant overheating must be prevented by continuously agitating the sealant while heating and/or by using jacketed heaters with a calibrated temperature measurement device. All hoses and wands must be insulated. Prolonged heating and reheating of sealant must be avoided. | GHD-DD-SPC-002 5505(a) | Inspection | ITP | IP | Site Engineer
4.02 | Applying Sealant |  | During crack sealing works |  | A purpose made applicator or 'shoe' appropriate for the particular sealant and pavement surface must be used to apply the sealant as a bandage and to control its width and thickness over the crack. The cracks must be prepared and the sealant heated and applied so that complete adhesion of sealant to the pavement surface and walls of cracks is achieved. The width of the sealant bandage must be not less than 25mm and not greater than 50mm except where shown otherwise on the Drawings. The target thickness of the sealant bandage must be 3mm (minimum 2mm and maximum 5mm). Any excess sealant must be removed. The cracks or joints must be sealed entirely. | GHD-DD-SPC-002 5505(b) | Inspection | ITP | IP | Site Engineer
4.03 | Protection of Applied Sealant |  | During crack sealing works |  | Applied sealant must be protected from damage by traffic including pick up on tyres of construction vehicles and aircraft until it has cooled to ambient temperature. Dusting with hydrated lime may be required if the weather is very hot (greater than or equal to 32°C) | GHD-DD-SPC-002 5505(c) | Inspection | ITP | IP | Site Engineer
4.04 | Reflected Joint Bandaging |  | During crack sealing works |  | Bandaging shall be applied to reflected joints prior to the overlay as indicated on the drawings or instructed by the Contract Administrator. The joints in any exposed concrete pavements or the reflected cracks in existing asphalt above joints in concrete pavements shall be covered by a joint bandaging as specified in Clause 5502(b), nominally 3mm thick and placed 50mm either side of the joint at a constant width. The bandage shall be applied strictly in accordance with manufacturer's recommendations. | GHD-DD-SPC-002 5505(d) GHD-DD-SPC-002 5502(b) | Inspection | ITP | IP | Site Engineer
4.05 | Cleaning up |  | During crack sealing works. |  | Any sealant spilt on the surface of the pavements must be cleaned off immediately. | GHD-DD-SPC-002 5506 | Inspection | ITP | IP | Site Engineer
5 | Quality Assurance
5.01 | Conformance |  | At the completion of each lot of work |  | A Conformance Report is required to be raised confirming that each lot conforms in all respects with the requirements of the Technical Specification and shall include the results of all tests, inspections, measurements, observations and the like carried out on the lot. Conformance data shall be entered in the record system as soon as possible but not more than 24 hours after compliance testing has been completed. Each lot package for Cracking Sealing in Bituminous Surfacing shall include the following items as a minimum: - Location of work; - Start and finish times; - Crew details; - Equipment details; - Length of crack sealing completed; - Sealant test results applicable and litres of sealant used; and - Non-conformance reports | GHD-DD-SPC-002 5507(c) | Inspection | ITP/ArcGIS | IP | Site Engineer
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Contract Administrator |  |  | IP Inspection point | Formal Inspection to be completed and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP Test Point | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which may be witnessed by the Contract Administrator or Client |  |  | NMS Nominal Mix Size | The nominal size of the asphalt mix
AP | Approval Point | Written or verbal approval given by the Contract Administrator
Document Control
Date | Author | Description of Change |  |  | Revision
2023-02-20 | N. Wood | Final version published. Inspection/Test Method for Item 1.02 updated to 'Document Submission'. |  |  | 1