## Cover Page
Inspection and Test Plan
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL details
Project Name: | State Highway 58 - M2TG | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | DS2681 | [5 empty] | A | Action | Role Key |  | Name | Initial
Customer: | NZTA | [5 empty] | B | Report by Breach | PM | Project Manager | Gordon Lemon
Contract Number: | [6 empty] | C | Check | CM | Construction Manager | Jamie Nisbet
Area/ Sub-System: | W-Section & Wire Rope Barrier Installation |  |  | Lot ID Number: | 15 & 16 |  | D | Dimension Inspection | PE | Project Engineer | Dehan Erasmus
[7 empty] | E | Examine | SE | Site Engineer | Tyrese Dickson
ITP Number: | DS2681-SH58-ITP-M-002 DS2681-SH58-ITP-C-015 DS2681-SH58-ITP-C-016 |  |  | Version: | Rev01 |  | H | Hold Point | SV | Surveyor | Jim Robins
ITP Description: | W-Section & Wire Rope Barrier Installation | [5 empty] | I | Inspection | ST | Superintendent | Nick Talbot
Discipline: | Safety Barrier | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | John Marsters
Specification: | Project Specification M2TG | [5 empty] | O | Operation | ER | Engineer's Representative | Sam Parkinson
[7 empty] | R | Review
Drawings: | 80510096-02B-100-C153 | [5 empty] | S | Subcontractor
[7 empty] | V | Visual Verification
Prepared By: (Name) | Dehan Erasmus |  |  | Date: | 2025-07-22 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
CM Approval |  | Name: | Jamie Nisbet |  |  | Signature: |  |  |  |  | Date: | 2025-07-22
PM Approval |  | Name: | Gordon Lemon |  |  | Signature: |  |  |  |  | Date: | 22/07/2025
Quality Advisor Approval |  | Name: | Lissa Gatehouse |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: why are there 2 numbers. ensure the numbers match the WBS ie DS2681-SH58-ITP-C-015 Barriers (W-Section) DS2681-SH58-ITP-C-016 Barriers (Wire Rope) Reply: Hi Lissa, I have included multiple ITPs in this one to cover all Barrier scope. Listed here correctly now. I can explain to Whineray in the handover

## Material Inspections
Inspection and Test Plan
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity Include frequency, if applicable. | Acceptance Criteria | Specification Reference | Verifying Document | Inspection/ Test |  | Inspection Point/ Signature & Date
[6 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
DS2681-SH58-ITP-M-002
W-Section Roadside Barriers
3.1 | Barrier materials (Standard W-Section) | Barrier materials (Standard W-Section) | To be supplied, fabricated and protected in accordance with the drawings and specification. W-section to comply with MASH TL-3 | PS Cl 22.1.1 NZTA M23 | Docket, Manufacturer's Drawings/install instructions | W | SE
3.2 | Barrier materials (End Terminals W-Section) | Barrier materials (End Terminals W-Section) | To be supplied, fabricated and protected in accordance with the drawings and specification. Leading End Terminals to comply with MASH TL-3 Trailing End Terminals to comply with MASH TL-3 | PS Cl 22.1.4 NZTA M23 | Docket, Manufacturer's Drawings/install instructions | W | SE
3.3 | Ground Beam: Concrete Mix Design | Prior to works | Contractor to provide Concrete Design Mix information to the Engineer. 30MPa Mix | PS Section 24 Per Manufacturer Specifications | Mix Design | H | ER
Thrie Beam Roadside Barriers
3.4 | Barrier materials (Thrie Beam) | Barrier materials (Thrie Beam) | To be supplied, fabricated and protected in accordance with the drawings and specification. | PS Cl 22.1.1 NZTA M23 | Docket, Manufacturer's Drawings/install instructions | W | SE
3.4 | Barrier materials (Thrie Beam Transitions) | Barrier materials (Thrie Beam Transitions) | To be supplied, fabricated and protected in accordance with the drawings and specification. | PS Cl 22.1.3 NZTA M23 | Docket, Manufacturer's Drawings/install instructions | W | SE
Wire Rope Median Barriers
3.5 | Barrier materials (Wire Rope) | Barrier materials (Wire Rope) | To be supplied, fabricated and protected in accordance with the drawings and specification. Wire Rope to comply with MASH TL-4. | PS Cl 22.1.1/22.1.8 NZTA M23 | Docket, Manufacturer's Drawings/install instructions | W | SE
3.6 | Terminal End: Concrete Mix Design | Prior to works | Contractor to provide Concrete Design Mix information to the Engineer. 30MPa Mix | PS Section 24 Per Manufacturer Specifications | Mix Design | H | ER
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: is timber required? Reply: No timber posts required
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I can't see 30MPa in spec table 24.1.11, Reply: This is a prescribed mix from barrier installation manual. Specification does not list this. We still have to follow spec in terms of mix design approval.
Note on D17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 30MPa not in spec table 24.1.11, Reply: As above comment

## W-Section
Inspection and Test Plan
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity Include frequency, if applicable. | Acceptance Criteria | Specification Reference | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | Inspection By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
4 | W-SECTION/THRIE BEAM BARRIER (DS2681-SH58-ITP-C-015)
4.1 | Ground beam installation (Pre-Pour) | Ground beam installation (Pre-Pour) | A concrete pre-pour inspection to be carried out by Engineer to check formwork and reinforced steel (where required), checking dimensions, reo sizes as well as ground preparation. Concrete strength requirement of 30MPa minimum. Specification from NZTA 2014 Technical Memorandum: Road Safety Hardware Series Standard Detail Ground Beam | PS Cl24 | Pre-pour Inspection Sheet Concrete Docket Photos | Prior to every concrete pour | Hold Point | H | ER
4.2 | Ground beam installation (Post-Pour) | Ground beam installation (Post-Pour) | Post pour inspeection to check concrete finishes are up to the required specification. No honeycoming. Any defects to be reported to the Engineer with remediation proposal. | PS Cl24 | Post-pour Inspection Sheet Concrete testing results Photos | After stripping formwork on each concrete pour | Witness Point | W | SE
4.4 | W-beam positioning behind kerb | W-beam postioning behind kerb | Unless detailed in the drawings, where barrier is placed behind a kerb, the face of the barrier is to be no more than 200mm behind the kerb face. Where barrier is placed further than 200mm behind the kerb face this shall be agreed on site with the Engineer prior to installation. | PS Cl22.1.2 | Engineer Inspection / Measurements Photos | Where Used | Witness Point | W | SE
4.5 | Nesting W-beam barrier | Nesting W-beam barrier | Nesting of weak post systems shall be in accordance with manufacturer's instructions. | PS Cl22.1.7 | Photos | Where Used | Witness Point | W | SE
4.6 | Barrier Checklists | Installer Checklist | An approved barrier installation checklist shall be completed by a person with demonstrable recent experence in barrier installation and signed by the Contractor for each barrier installed and provided to the Engineer within four weeks of installation. | PS Cl22.1.6 | Installation Checksheet Photos | Per Barrier String | Witness Point | W | SE
4.7 | Survey | Survey Pick-up | Installed as per the contract drawings | N/A | Survey As-Built | Per Barrier String | Witness Point | W | SV
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 30MPS not listed on table, ensure this is correct Reply: As previous comment. 30MPa is a prescribed strength in the barrier manual.
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: need photos Reply: Added
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: need test results
Note on D12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: how is the installer experience verified Reply: Spec gives no guidance on this. We are using very experienced installer and verification is done by them (Tascon)
Note on F12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: proof of installer experience Reply: photos Reply: added

## Wire Rope
Inspection and Test Plan
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity Include frequency, if applicable. | Acceptance Criteria | Specification Reference | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | Inspection By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
4 | WIRE ROPE BARRIER (DS2681-SH58-ITP-C-016)
4.1 | Terminal End (Pre-Pour) | Terminal End (Pre-Pour) | A concrete pre-pour inspection to be carried out with the Engineer to check dimensions of trench, formwork and reinforcing, anchor points and ground preparation. Concrete strength requirement of 30MPa minimum. | PS Cl24 | Pre-pour Inspection Sheet Concrete Docket, Photos | Prior to every concrete pour | Hold Point | H | ER
4.2 | Terminal End (Post-Pour) | Terminal End (Post-Pour) | Post pour inspeection to check top surface finish and ensure anchor points are in place | PS Cl24 | Post-pour Inspection Sheet Concrete testing results Photos | After stripping formwork on every concrete pour | Witness Point | W | SE
4.3 | Barrier Checklists | Installer Checklist | An approved barrier installation checklist shall be completed and signed by the Contractor for each barrier installed and provided to the Engineer within four weeks of installation. | PS Cl22.1.6 | Installation Checksheet | Per Barrier String | Witness Point | W | SE
4.4 | Survey | Survey Pick-up | Installed as per the contract drawings | N/A | Survey As-Built | Per Barrier String | Witness Point | W | SV
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 30MPS not listed on table, ensure this is correct Reply: As previous comment. 30MPa is a prescribed strength in the barrier manual.
Note on D9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: need test results Reply: Added
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: test results Reply: added