## ITP Cover Page
State Highway 29 - Wastewater Drainage - WWMH-05- WWMH-12 - Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210-SP2 - ITP 016-002 - Rev 3
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | ITP 016-002
Project Number: |  |  | DN1210-SP2 |  |  |  |  | ITP Status: |  |  | IFC - Approved
ITP Description: |  |  | State Highway 29 WW |  |  |  |  | Revision: | 1000 |  | 3
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-WST
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | SH29 Tauriko West Enabling Works Contract No.NZTA8287 Section 22
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
1 | Draft for Approval | 2025-04-03 |  | Cordelia Girdler-Brown & Nick Adams |  | Updated as per WSP comments from NTC 552: 1. CWP Section 1: The chainage on the heading of CWP and section 1 is incorrect. Chainage should be 270 - 530. 2. ITP Section 3.15: Add DS 6.5.12.1 - Contractor should conform to this standard. 3. ITP Section 3.16: Add PS22.6.2. Specification to be added to ITP standard. 4. ITP Section 8.13: Add DS 6.5.12.4b to ITP. Add IDC Standard to ITP - Contractor is to conform to this standard as well. |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) |  | HSE | HSE Manager / Rep
2 | Approved | 30/04/2025 |  | Cordelia Girdler-Brown & Nick Adams |  | Add comms duct installation and drilling to ITP/CWP/JSEA. Added to CWP - MH5, MH22, MH23, MH12, this is to include the crossings where drilling will take place. Added welding and flanges to CWP. |  |  |  | H | Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) |  | PE/SE | QA Manager / Rep
[10 empty] | I | Inspection (Formal inspection activity to be undertaken and recorded) |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
3 | Resubmit to WSP | 15/07/2025 |  | Cordelia Girdler-Brown & Nick Adams |  | Updated as per WSP comments from NTC 0704 CWP 6.5 WSP - CWP does not include remedial actions if frack out Added - All Road Crossings: Plan to drill the bore hole as tight as possible to prevent frack-out and heaving. Will fill voids with grout if this occurs. This is updated in CWP section 6.5. CWP 6.5 WSP - This CWP should include long sections showing the drill methodology including the points specified in the specs. This should also show calculations of how they will get to grade and drill levels (centre of pipe to sleeve inlet) Added - All Road Crossings: Please see drawings provided on the CWP section 6.5. CWP 6.5 WSP - Are any further ground investigations required? Added - WWMH-23 to WWMH-09: Extra investigations were done around the site where WWMH-23 is to be installed. It was decided to dig where the drill will be located and dig again where WWMH23 will be installed. This second cut will be where the road crossing will begin. The drill shot will go under some bushes before the road crossing will be carried out. Added to CWP section 6.5. CWP 6.6 WSP - Vibration monitoring should be in accordance with the specs, please include this in the CWP Added - All Road Crossings: DNZ to organise Hydro-Vac contractor to locate and excavate around services before drilling works commences. Drilling subcontractor to monitor and record local vibration, ground heave and settlement in the vicinity and along the alignment of the installation. This has been added to CWP section 6.6. CWP 6.5 WSP - Contradictory grout mixes proposed. Grout mix should be as per the specs (not a bentonite mix). Added - All Road Crossings: Grout will be 1.5 MPa flowable concrete. It is not bentonite mix, subcontractors sent wrong methodology they are following the project specification. This is added to section 6.5. CWP 6.5 WSP - CWP should include the grouting methodology including: - Grouting pipe diameter - Where and how pipe it is going to be installed - Proof grout is not going to be thermally active and is compatible with the pipe Added - Proof of concrete specs will be provided. Grouting will only be carried out on the ends of the road crossings, as these pipes are going to be installed with protective sleeves. This is in the CWP section 6.5 |  |  |  | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point (Review of text reports/records or other evidence of compliance) |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | NICK ADAMS |  |  | #VALUE! |  | 23/07/2025 | Downer PM |  | NICK ADAMS
Downer QM |  | CORDELIA GIRDLER-BROWN |  |  |  |  | 23/07/2025 | Downer QM |  | CORDELIA GIRDLER-BROWN
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
SH29 Wastewater Drainage Installation - WWMH-05 - WWMH-12
Tauriko Enabling Works
DN1210 - SP2- ITP010-016-002 - REV 3
Item No. | Inspection and Test Point | Detail / Activity | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | ConQA Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
3 | PRE-CONSTRUCTION HOLD POINTS - MATERIALS, PERSONELL & THIRD PARTY APPROVALS
3.1 | Extent of Line Setout | Ensure line and level of Wastewater has been marked out and agreed with Engineer in accordance with Waste water drawings. Identify any clashes before construction. LOT- markup | As Per Drawings & Markup drawing | Design Drawings | ITP Sign Off / Mark-up | Prior to Construction & Every Revision of IFC Drawings/Data. | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.2 | Pipe Laying | Method statement | As Per Specification and IFC Drawings | PS- 22.3 Appendix V | Wastewater Construction Work Pack Sign off | Prior to Construction | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.3 | Pipeline Pressure Testing | Method statement | As Per Specification and IFC Drawings | PS- 22.3 Appendix V | Wastewater Pipeline Pressure Testing Work Pack Sign off | Prior to Construction | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.4 | Material grading: Materials (GAP65/AP65) | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | No Particles >200mm Maximum fines 10% passing 75micron sieve | PS 22.13.1 Appendix XVIII PS 16.5.5 Appendix V | Lab Test Report NZS 4407.3.8.1 | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.5 | Weathering index: Materials (GAP65/AP65) | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB, or CA | Appendix XVIII PS 16.5.5 Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.6 | Crushing Resistance: Materials (GAP65/AP65) | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | Appendix XVIII Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.7 | Maximum Dry Density and Optimum Water Content (AP65/GAP65) | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | Appendix XVIII Appendix V | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.8 | Material grading: Materials (Sand) | Bedding/Side Zone/ Overlay Zone/Embedment Zone | Sand: Sieve Size % Passing 4.75mm 100% passing 2.36mm 90-100% passing 1.18mm 85-100% passing 0.600mm 70-100% passing 0.300mm 50-100% passing 0.150mm 0-40% passing 0.075mm 0-5% passing | AS/NZS 2566.2 Table G3 PS 22.4.5 | Lab Test Report NZS 4407.2015 Test3.8.1 | 0-400m3 2 Test 400-1500m3 3 Test 1500-4000m3 4 Test >4000 1 Test Additional 1000m3 | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG |  |  |  |  | Changed to G3 table PSD for sand
3.9 | Pipes (PVC/PE) | Manufacturer's record and location of extrusion plants. PVC pipes must be Series 1, plain wall construction, rubber ring jointed pipe, unless shown otherwise on the Drawings. All PVC-U (Unplasticised) pipe must conform to the requirements of AS/NZS 1477. Name of the proposed PE resin, the manufacturer, production information on the properties of resin. Full Traceability information and certification of analysis for the resin batch. | Full Traceability information and certification of Material | PS-22.4.1 (d) AS/NZS 1477 | Delivery Dockets | Prior to construction | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.1 | Flanges, Fittings, Bends | Have a pressure rating no less than the designed pressure. Mechanically, chemically and electrically compatible with the class and material of the pipe. Current Water Services Association of Australia (WSAA) appraisal certificate or approved independent proof of fitness-for-purpose. | Engineer approval AS/NZS 4129 | PS-22.4.2 | Delivery Dockets | Prior to construction | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.11 | Pipe and fittings/bends | Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition. | Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition. | Design Drawings | Delivery Dockets / Inspection Checksheet (DG-QA-TP019) | Each Delivery to site | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE
3.12 | Fittings | Confirm class and type as shown on the drawings, and that the fittings are correct and in good condition. | Confirm class and type as shown on the drawings, and that the fittings are correct and in good condition. | PS-22.4.2 | Delivery Dockets / Inspection Checksheet(DG-QA-TP019) | Each Delivery to site | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE
3.13 | Granular Material (Imported Sand, GAP20/AP20, GAP65/AP65) | Confirm Specification and material in good condition. | Confirm Specification and material in good condition. | PS-22.4.1 | Delivery Dockets / Inspection Checksheet(DG-QA-TP019) | Each Delivery to site | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE
3.14 | Bidim/Geogrid | BIDIM A29 Durogrid 30/30 or similar. | Site Engineer Approval | PS-22.4.1 | Delivery Dockets / Inspection Checksheet(DG-QA-TP019) | Each Delivery to site | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE
3.15 | Waste Water Manholes | Confirm the class and type as shown in the drawings, and fittings required for MH is same | Confirm the class and type as shown in the drawings, and fittings required for MH is same | Design Drawings TCC IDC DS 6.5.12.1 | Delivery Dockets / Inspection Checksheet(DG-QA-TP019) | Each Delivery to site | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE |  |  |  | DS 6.5.12.1 - Contractor should conform to this standard | Added DS 6.5.12.1
3.16 | Reinforcing steel (manhole ballast) | Manhole ballast reinforcing steel. | Grade 500E, Confirm the class and type as shown in the drawings. | AS/NZS 4671 PS 22.6.2 | Material Certifications. Delivery Dockets | Each Delivery to site | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE |  |  |  | Specification to be added to ITP standard | Added PS 22.6.2
3.17 | Horizonal Directional Drilling | Detailed methodology of directional drilling | Engineer Approval | PS 21.6.6a | Engineer APPROVAL | Prior to construction | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.18 | Grouting Methodology | Cement grouting the sleeve annulus | Enginner Approval | PS 21.6.6g | Engineer approval | Prior to construction | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | ENG
3.19 | Pipe and fittings. Ducts | Duct Pipes shall be of the 50mm Ducts shall be high impact uPVC Duct colours shall be Salmon Duct colours for the different Utility Structures must be in accordance with the guidelines. | Duct Pipes shall be of the 50mm Ducts shall be high impact uPVC Duct colours shall be Salmon Duct colours for the different Utility Structures must be in accordance with the guidelines. | PS 25.13.6 b) | Delivery Dockets/Material Certification | Each Delivery to site | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | SE
3.2 | Pits Covers | Jointing and pulling pits shall have slip resistant surfaces complying with AS/NSZ 3661-1-1993. the cover set load rating shall be in compliance with AS3996. | Class A-10kN loading - footways and areas only accessible to pedestrian and cyslists. Class B- 80kN loading - footways that may be mounted by vehicle or livestock and light tractor paths. (Light duty) Class C- 150kN loading - grass verges or other areas open to slow moving commercial vehicles such as tractor mowers etc (medium duty) Class D-120kN loading - Carriageway of roads and areas open to commercial vehicles (heavy duty) | PS 25.13.6 c) AS/NZS 3661-1- 1993. | Material Certifications. Delivery Dockets | Each Delivery to site | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | SE
3.21 | Butt-Fusion pre construction weld test | One weld on the most common size of pipes used for the project. One weld on the thickest wall (highest PN) pipe | ISO 13953 for tensile strength and failure mode. WMS Report | PS 22.9.6 (a) ISO 13953 Standard | Visual Inspection | Two test welds per operative(Welder) | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.22 | KWIK Spacers | Confirm Specification and material in good condition. | Installation: Centred and restrained | Manufacturer’s Installation Guide. IFC Drawing 0312 | Photographic Evidence | Every spacer | W Review of text reports/records or other evidence of compliance | SE
4 | CONSTRUCTION - WASTEWATER PIPELINE - Excavation and Laying
4.1 | Foundation Compliance | On Granular or Cohesive Material | Granular Material: Scala 3 blows/100mm (Or) Cohesive Material: Vane Shear Strength min50kpa, ave>60kpa | Appendix V Table 21:11 | Scala/Shear test result | One test per 20m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole. | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE/ENG
4.2 | Undercut approval | Trench Foundation | 300mm Max cut IFC Drawing Sheet 320 (Or) Engineers approval | IFC Drawing WST 0320. AS/NZS 2566.2/2002 | Lab Test Report / Wastewater line record | If Undercut required | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE/ENG
4.3 | Undercut Backfill Compliance (PAP5) | On Granular Material / On each layer as per specification / on the trench foundation. | Visiual Inspection | IFC Drawing WST 0320 | Lab Test Report / Wastewater line record | Every Undercut | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE/ENG
4.4 | Bedding Zone Compaction Testing | On Granular Material / On each layer as per specification (Imported Sand/GAP20/19mm chip) | Bedding Zone: 100mm minimum thickness (compacted) over the bottom of the trench. Minimum Compaction- 85%MDD Paeangaroa Sand: clegg of ave 9 CIV and min of 7 CIV. Wilson Sand No.2: clegg 4 CIV | IFC Drawing 0320-1 AS/NZS 2566.2/2002 | Lab Test Report | As per SW Specification. One test per 20m evenly spaced intervals. | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
4.5 | Laying of Pipes | Lay in straight lines, beginning at the lower end of the line. Lay all pipe with manufacturing codes and class markings facing upwards. | As Per Drawings. Facing upwards | PS22.7.1 C | Visual Inspection / Wastewater line record | Every Line | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
4.6 | Pipe Installation on Curved Alignments | All Industry Guideline PVC, PP AND PE PIPE INSTALLATION ON CURVED ALIGNMENTS (POP202) | AS Per POP 202 | PS 22.7.1 D | Visual Inspection / Wastewater line record | Every Line | M Monitor on Random Basis | SE
5 | CONSTRUCTION ACTIVITY - WASTEWATER PIPELINE (Joint and Connection)
5.1 | Flanges | Manufacturer specifies their own bolt tightening torque and sequence, it should override the project specification. | Flanges to AS/NZS 4087 | PS 22.7.5 | Visual Inspection | First flanged joint | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
5.2 | Bends | PE 100 butt fusion welded segmented bends only where specifically indicated on the Drawings. Fitting must meets the same PN rating as the adjacent PE 100. Fittings must be suitable for producing the joints shown on the Drawings. | PIPA POP 006 and AS/NZS 4129 | PS 22.4.2 | Visual Inspection | As per the IFC drawing | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
6 | CONSTRUCTION ACTIVITY - WASTEWATER PIPELINE INSTALLATION - Directional Drilling
6.1 | Check levels while drilling | Inspection of Pipeline Inverts | Vertical design Setout: Pipes ≤ 1% grade: +/- 10mm variance Pipes > 1% grade: +/- 20mm variance Horizontal design Setout: +/-30mm variance | PS- 21.7.6 Table 21.15 | Survey Data / As-built record | Pipeline invert to be surveyed at chainages as indicated in the drawings. | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
6.2 | Drilling Fluid Mix | Viscosity record | Viscosity record | PS 21.6.6 | Viscosity record | Every shot | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
6.3 | Correct Reamer used | Reamer size to confirm on site | Reamer size to confirm on site | PS 21.6.6 | Visual Inspection/Photo | 1 per drill shot | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
6.4 | Pipe Damage | Damage <10% of wall thickness | Damage <10% of wall thickness | PS 21.6.6 | Visual inspection | Each pipe | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
6.5 | Tracer Wire | Lay a conductive signal strip or tracer wire along the full length of all non-metallic pressure pipelines as shown on the Drawings. Mark fire hydrant positions in accordance with SNZ PAS 4509 | Lay a conductive signal strip or tracer wire along the full length of all non-metallic pressure pipelines as shown on the Drawings. Mark fire hydrant positions in accordance with SNZ PAS 4509 | PS 22.7.3 a | Visual Inspection / Wastewater line record | Every Line | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
6.6 | Drill Report | Drill report to be submitted | Drill report to be submitted | PS 21.6.6 | Report | Every Line | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
6.7 | Settlement monitoring and ground deformation (Baseline measurements) | Topo survey completed before and after drill shot | Topo survey completed before and after drill shot | PS 21.6.6 | Survey data | Every 6m | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
6.8 | Cement Grout - Annulus | The sleeve annulus are to be cement grouted after installation to prevent settlement. | The grouting mix is to be: 1. 1:1 Sand/cement ratio 1 : 1 2. Water/Cement ratio 1 : 0.67 by weight | PS 22.5.8b | Visual inspection | Every Grout | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
7 | CONSTRUCTION - WASTEWATER PIPELINE - Inspection
7.1 | Pipe Inspection | Inspection of Drainage line | Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness | Internal | Wastewater line record | Continious 1 per Line | I Formal inspection activity to be undertaken and recorded. | SE
8 | CONSTRUCTION - WASTEWATER PIPELINE - Backfill
8.1 | Emebment Zone - (Side Haunch Overlay ) | Granular sand backfill compacted in 200mm Layers. NDM/CleggTesting to be completed on maximum 200mm lifts of overlays . NDM BS to be Carried Out | in 200mm layers. More than 85% of MDD. | IFC Drawing 0320-1 | Lab Report / Wastewater line record | One test per 20m evenly spaced intervals. 200mm lift | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
8.2 | Pipe Markers | Lay a conductive signal strip or tracer wire along the full length of all non-metallic pressure pipelines as shown on the Drawings. Mark fire hydrant positions in accordance with SNZ PAS 4509 | AS Per Drawings. | PS 22.7.3 a | Visual Inspection / Wastewater line record | Every Line | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
8.3 | Backfill Compaction Testing | Backfill Compacted in 200mm Layers. NDM Testing to be completed on maximum 200mm lifts of backfill. | GAP65/AP65 or site won material Backfill Compacted in 200mm layers. Testing to be completed on maximum 200mm lifts of backfill. 95% NDM on Shared and Carriageway. OR 25% CIV For site won: Shear Vane min 125kPa | PS- 22.13.5 NDM Standard 25832 NZS 4402 Test 4.1.3 IFC Drawing 0320-1 PS - 16.5.5 | Lab Report / Wastewater line record | As per WW Specification. One test per 20m evenly spaced intervals. | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
9 | CONSTRUCTION - WASTEWATER PIPELINE TESTING
9.1 | Pressure Acceptance Testing (air) | Backfill/cover with embedment before testing End caps in place, provision for filling the pipeline and bleeding air. | Wastewater Rising Main Pipelines – 800kPa Ensure the STP is not more than 25% above the rated pressure of any pipeline component. | PS 22.7.12(d) PS 22.7.13(b) PS 22.7.15 | Test Report Pressure Log in.csv or .xlsx format | All Pipeline All valves | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
9.2 | Constant Pressure Testing (water) | Backfill/cover with embedment before testing, plan for where water will be diverted or sent to | There is no failure of any pipe, fitting or other pipeline component. There is no visible leakage at pipe joints or other fittings. The make-up water volume does not exceed the maximum allowable quantity as calculated. Q ≤ (0.14 x L x D x H). | PS 22.7.15 | Test Report Pressure Log in.csv or .xlsx format | All Pipeline | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
9.3 | Pressure Rebound Test | Backfill/cover with embedment before testing, plan for where water will be diverted or sent to | There is no failure of any pipe, fitting, or other pipeline component, and There is no visible leakage at any joint or fitting. The volume of water bled off (ΔV) is less than the calculated ΔV(max allowable air), and The pressure has not dropped below the rebound peak within 30 minutes, or The test has been extended to 90 minutes and the pressure has not dropped more than 20 kPa below the rebound peak value after 60 minutes. | PS 22.7.16 TCC IDC IT-6 | Test Report Pressure Log in.csv or .xlsx format | All Pipeline | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
10 | CONSTRUCTION - WASTEWATER Manhole installation
10.1 | Foundation Compliance | On Granular or Cohesive Material | Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength min50kpa, ave>60kpa | Appendix V Table 21:11 | Shear vane or Scala test result | 1 Test/Manhole | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE/ENG
10.2 | Undercut approval | On Subgrade | Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material. | PS 21.6.5 Table 21.5 | Lab Test Report | If Undercut required | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
10.3 | Undercut Backfill Compliance AP65 | On Granular Material | Average 95% MDD, min >92% OR Clegg 25% CIV | Appendix XVIII | Lab Test Report | 1 Test per Undercut | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
10.4 | Bedding Compaction Testing AP65 | On Granular Material | Average 95% MDD, min >92% OR Clegg 25% CIV | Appendix XVIII PS- 21.6.11 | Lab Test Report | 1 Test/Manhole | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
10.5 | Survey | Inspection of Structure | Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 30mm. | PS- 21.7.6 | Survey Data | 1 Test/Manhole | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SV
10.6 | Sidefill Compaction Testing | From the bedding layer to the overlay layer of pipe. | AP20/GAP20 Testing to be completed on maximum 200mm lifts of backfill - 85% MDD AP20/19mm chip | PS- Table 21.12 | Lab Test Report | 4 Density test per layer at Quarter Points around the Structure. | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
10.7 | Backfill Compaction Testing | From Overlay layer to the subgrade layer | AP65 Testing to be completed on maximum 200mm lifts of backfill - 92% (Average 95%) of MDD on metal. AP65-Clegg 28%CIV | PS- 16.5.12 | Lab Test Report | 4 Density test per layer at Quarter Points around the Structure. | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE/ENG
10.8 | Man Hole joints inspection | Inspection of joints | Right joint type used, no visual leak or breakage | PS 22.7.10 | Visual inspection | 1 Test/Manhole | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
10.9 | Inspection | Inspection of Structure | Inspection of Structure prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the Structure. | PS- 21.6.11 | Manhole/Catchpit Record | 1 Checksheet per manhole/catchpit | I Formal inspection activity to be undertaken and recorded. | SE
10.1 | Plumb | The maximum permitted installed out of plumb is 25 mm of horizontal deviation in 1 m of vertical rise. | The maximum permitted installed out of plumb is 25 mm of horizontal deviation in 1 m of vertical rise. | PS-22.7.10 | Survey Data | 1 Test/Manhole | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SV
10.11 | Step Rungs | Step rungs evenly spaced at nominal 300mm vertical intervals | Lowest rung more than 450mm above floor highest rung not more than 600mm below the top surface of MH cover | PS-22.7.11 | Visual inspection | 1 Test/Manhole | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
10.12 | Manhole frame and covers | Make up the height between the manhole roof slab or precast lid and the finished surface level using concrete riser rings. Set the manhole frame and cover in concrete so it finishes flush with the finished ground or roadway level. Finish the concrete in a way that allows the final surface to be brought close to the cover frame. | Make up the height between the manhole roof slab or precast lid and the finished surface level using concrete riser rings. Set the manhole frame and cover in concrete so it finishes flush with the finished ground or roadway level. Finish the concrete in a way that allows the final surface to be brought close to the cover frame. | PS-22.7.12 | Visual inspection | 1 Test/Manhole | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
10.13 | Manhole lateral connection | DN150 PVCu connection for future lateral. 800mm above manhole outlet invert DN150PVCu end cap. | DN150 PVCu connection for future lateral. 800mm above manhole outlet invert DN150PVCu end cap. | IFC Drawing 0320-Rev 03 TCC IDC DS6.5.12.4b | Visual inspection | Per connection | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE |  |  |  | Add IDC Standard to ITP - Contractor is to conform to this standard as well | Added DS 6.5.12.4b
10.14 | Concrete Formwork - surveyor to check | Equivalent to check the position of the formwork | +\- 100mm of design | Project Specifications 27.4.5 (b) NZS 3109:1997 | Pre-pour Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE |  |  |  |  | Added this in which isnt in rev 0
10.15 | Concrete Formwork - surveyor to check | Equivalent to check finished height of framework | +\- 10mm of design | Project Specifications 27.4.5 (b) NZS 3109:1998 | Pre-pour Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE |  |  |  |  | Added this in which isnt in rev 0
10.16 | Pre-pour inspection | Pre-pour inspection of manhole before ballast | Stable form work, ready for pour | Design drawing | Visual inspection | Pre each manhole ballasts installation | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SUP/ENG
10.17 | Manhole Ballast WWMH06 to WWMH10 (concrete & reinforcing steel) | Additional manhole ballast. | All Concrete to be 25MPa at 28 days. Minimum cover to steel = 50mm. Reinforcing steel to be grade 500E and to comply with AS/NZS 4671. | IFC Drawing Sheet WST 0321 NZS 3109 5.6.3(B). AS/NZS 4671 PS 22.6.2 PS Table 22.4 specific manhole requirements | Visual inspection | Per manhole | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
11 | CONSTRUCTION ACTIVITY - COMMUNICATION DUCT INSTALLATION
11.1 | Bedding | In wastewater trench ensuring 50mm of beeding over wastewater pipe | Clean Imported Sand or SAP 7 to be placed 50mm minimum thickness (compacted) over the bottom of the trench. | PS 25.13.2 g) | Checklist | Each Cable | M
11.2 | Installation of Ducts | Layed in same trench as wastewater with sand cover. | Must have 50 mm bedding material | PS 25.13.7 b) iii | Checklist | Each Cable | M
11.3 | Draw Wires | A draw wire shall be intalled in all ducts and within all sub-ducts to facilitate the hauling-in of cable after the completion of the ducting. | Pigmented, stranded polypropylene or equivalent rot-proof material draw wire of 5kN breaking load. ≥20 years design life. The ends of draw wires shall be made fast within the pits and be secured to the duct plugs. Blue colour wire | PS 25.13.7 e) ii to iv | Checklist | Each Cable | M
11.4 | Caps | All duct ends shall be capped | Capped ducts | PS 25.13.7 e) v | Checklist | Each Cable | M
11.5 | Warning Tape | Warning tape to be placed above services. | Warning Tape to be placed no more than 300mm above the topmost duct | PS 25.13.7 b) iii & f) | Checklist | Each Cable | M
11.6 | Overlay | 150 mm minimum sand placed on top of duct. No mechanical compaction will caarry out till 300mm drom top of duct. | 100 mm minimum sand placed on top of duct. | PS 25.13.7 b) ii | Checklist | Each Cable | M
12 | CONSTRUCTION ACTIVITY - COMMUNICATION PIT INSTALLATION
12.1 | Pit Installation Location | Locations shall be avoided where running water can flow over the lid or where mud and debris can fall or be washed onto the lid . Confirm on site with engineer, | Pit lid and concrete apron shall be flush with ground level in grass, concrete or asphalt areas. When pit is located on a slope of 10 to 30 degrees, the lid shall be flush with ground on the upper side. When slope is greater than 30 degrees, the lid shall be up to 100mm above the ground level on the upper side. | PS 25.13.8 a) i and ii | Checklist | Each Pit Location | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
12.2 | Pit Installation Bedding | Bedding with 150mm compacted GAP20 hard-fill coverd with 20mm compacted sand. Pits shall be carefully lifted into place and lined up with the ducts to penetrate the chamber. | 150mm compacted GAP20 hard-fill covered with 20mm of compacted sand | PS 25.13.8 d) | Checklist | Each Pit Location | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
12.3 | Pit Installation Sidefill concrete | Plactic pits shall be cast into the ground with 150mm concrete surround | Plactic pits shall be cast into the ground with 150mm concrete surround | PS 25.13.8 d) | Checklist | Each Pit Location | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
12.4 | Pit Installation Backfilling | Backfill and compact the ground around concrete pits. Extra care to be taken to avoid damaging the ducts in 200mm layers of GAP 65. | Min 92% compaction rate and Average of 95%. | PS 25.13.10 a) modified | Checklist | Each Pit Location | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
12.5 | Pit Installation Concrete | Top 300mm of pit shall be concreted around with a with of 150mm with a 20MpA concrete. | 20 mPa | PS 25.13.8 d) iv. | Concrete Dockets | Each Pit Location | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
12.6 | Pit Installation Clean up | Clean out all pit after completion of the work | Pit are free of dirty, mud,water and foreign materials | PS 25.13.8 e) | Checklist | Each Pit Location | M | SE
12.7 | Survey As Built | As Built every ducts joint before backfill | Completed as per drawings | Standard Practise | Survey | On going | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | PE
13 | CONSTRUCTION ACTIVITY - WATERMAIN PIPELINE - Butt-Fusion Welding
13.1 | Butt-Fusion Construction weld test | Test at least two welds from the first 50 welds. One of the welds to be selected by the Engineer for satisfactory result. | Tensile testing and ductility of welds. 95% tensile strength; welds aligned | PS- 22.9.6 (a) (iv) | Test report | Two welds for the first 50 welds | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
13.2 | Butt-Fusion Welding | Use only semi-automatic or automatic welding machines. Maintain a site record for all butt-fusion welds. The lead welder or supervisor must verify on the site record form that all welds have been made in accordance with the WMS and that the information on the record form is correct. | Site Butt Fusion Welding record to be filled out. (Refer to CWP) WMS Report | Appendix XXII PS 22.9.4 C | Visual Inspection / Butt Fusion welding records checklist. WMS Report | Every Welding Point | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
13.3 | Survey | Inspection of Pipeline Inverts | Vertical design Setout: Pipes ≤ 1% grade: +/- 10mm variance Pipes > 1% grade: +/- 20mm variance Horizontal design Setout: +/-30mm variance | PS- 21.7.6 Table 21.15 | Survey Data / As-built record | Pipeline invert to be surveyed at chainages as indicated in the drawings. | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
13.4 | Photograph of Each Weld | Take sharply focused photo while clamped | Unique weld identifier visible | N/A | Weld Records; Photos | Each weld | I Formal inspection activity to be undertaken and recorded. | SUB
14 | POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
14.1 | Survey As-Builts | Quality check on the pipeline and structure based on the tolerances in RITS. | Meets spec as per drawings and capture any NCR or change to design. | Project Specifications | Red pen markup only | Post works completion of a lot | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE