## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-STR-296-ADL-Misc Structural Steel (Supply & Installation)
ITP Description: |  | 296-ADL-Misc Structural Steel (Supply & Installation)
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 0
Revision Date: |  | 2025-07-24
ITP created by: |  | J Ballard
ITP approved for use by: |  | Romualdo Magpantay
Special Notes to ConQA Team : |  | ITP for Akuna Drive only
Misc.Structure Steel (Supply & Installation)
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-07-24
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | MRP-120-C-SME-REP-91-NPT-CSW-0001 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | AS 1252 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | AS4100 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | AS5131 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.5 | Non Dependent | AS4680 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.6 | Non Dependent | AS 610 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Structural Steel Components | IFC Drawings MRPA Quality Management Plan | Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component. Typically this consists of but not limited to: i. Certificate of Compliance ii. Completed ITP iii. Weld Procedure Specifications iv. Weld Procedure Qualifications v. Welder Qualifications vi. Material Certificates and traceability vii. Quality Assurance check sheets viii. Welding Consumable batch certificates ix. Coating certificate(s) x. Non-destructive Testing (NDT) Reports xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot. Enter: Teambinder Material Approval number [free text box] | Document Review | Each component | IP | PE/SE/SPE | This ITP
2.2 | Fasteners | IFC Drawing | Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS 1252 | Document review | Where applicable | HP | PE/SE/SPE | This ITP
3 | Pre-installation Activities
3.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP
3.2 | Materials Inspection | IFC Drawings | General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion. | Visual | Each component | IP | SE/PE/SPE | This ITP
3.3 | Materials Inspection | IFC Drawings | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings. Where bolted faces are sloping at 1:20 or greater, tapered washers must be used. | Visual | Each component | IP | SE/PE/SPE | This ITP
3.4 | Materials Inspection | IFC Drawings | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues. | Visual | Each component | IP | SE/PE/SPE | This ITP
3.5 | Materials Inspection | IFC Drawings | Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects. | Visual | Each component | IP | SE/PE/SPE | This ITP
3.6 | Substrate inspection | IFC Drawings | Substrate is clean and in good condition | Visual | Each component | IP | SE/PE/SPE | This ITP
4 | Installation Activities
4.1 | Connection Point Installation | IFC Drawings | Install HILTI HST4 Stud Anchors with 90mm embedment as per manufactures installation instructions | Visual | Each component | IP | SE/PE/SPE | This ITP
4.2 | Structural Steel Installation - Wall Ties and Brackets | AS4100 Clause 15.2.3 AS5131 Clause 11.5.7 | Place steel component into position,ensuring that it is plumb, level, square. Spacing and location as per plans (horizontal/vertical/height and around openings) Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs. | Measure Visual | Each component | IP | SE/PE/SPE | This ITP
4.3 | Fastener Tightening - Snug Tight Condition | IFC Drawings | Place bolts, washers and nuts as detailed on the IFC Drawings. - Washer as specified(Washers shall cover the hole or slotted hole completely by 0.5 x bolt diamter) - Nut - Bolt protrusion (2 clear tread) | Visual | Where applicable, each bolted connection | IP | SE/PE/SPE | This ITP
5 | Post-installation Activities
5.1 | Inspection of Coating/Surface treatment | IFC Drawings AS4680 | After installation Works are complete, inspect the steel element for damage to the coatings. Where damage exists, it shall be repaired using an approved repair procedure | Visual | Each component | IP | SE/PE/SPE | This ITP
5.1 | As-built /Survey | IFC Drawings | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below: | Document Review | Each elemenmt | IP | Surveyor SE/PE/SPE | This ITP
5.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /