## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-STR-296-ADL-Misc Structural Steel (Supply & Installation) | itp |  |  |  |  | ITP-STR-296-ADL-Misc Structural Steel (Supply & Installation) Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-STR-296-ADL-Misc Structural Steel (Supply & Installation)
label | ITP Description: 296-ADL-Misc Structural Steel (Supply & Installation)
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 24/07/2025
label | ITP created by: J Ballard
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 - Non Dependent
label | Reference - MRP-120-C-SME-REP-91-NPT-CSW-0001
label | 1.2 - Non Dependent
label | Reference - AS 1252
label | 1.3 - Non Dependent
label | Reference - AS4100
label | 1.4 - Non Dependent
label | Reference - AS5131
label | 1.5 - Non Dependent
label | Reference - AS4680
label | 1.6 - Non Dependent
label | Reference - AS 610
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Structural Steel Components
label | Reference - IFC Drawings, MRPA Quality Management Plan
label | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | Typically this consists of but not limited to:
label | i. Certificate of Compliance
label | ii. Completed ITP
label | iii. Weld Procedure Specifications
label | iv. Weld Procedure Qualifications
label | v. Welder Qualifications
label | vi. Material Certificates and traceability
label | vii. Quality Assurance check sheets
label | viii. Welding Consumable batch certificates
label | ix. Coating certificate(s)
label | x. Non-destructive Testing (NDT) Reports
label | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | ○ Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each component
label | Category - IP
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 2.2 - Fasteners
label | Reference - IFC Drawing
label | Acceptance Criteria - Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS 1252
label | Method - Document review
label | Frequency - Where applicable
label | Category - HP
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Pre-installation Activities
checkpoint | 3.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - All
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.2 - Materials Inspection
label | Reference - IFC Drawings
label | Acceptance Criteria - General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
label | Method - Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.3 - Materials Inspection
label | Reference - IFC Drawings
label | Acceptance Criteria - Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | ○ Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
label | Method - Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.4 - Materials Inspection
label | Reference - IFC Drawings
label | Acceptance Criteria - Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | Method - Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.5 - Materials Inspection
label | Reference - IFC Drawings
label | Acceptance Criteria - Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
label | Method - Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.6 - Substrate inspection
label | Reference - IFC Drawings
label | Acceptance Criteria - Substrate is clean and in good condition
label | Method - Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Installation Activities
checkpoint | 4.1 - Connection Point Installation
label | Reference - IFC Drawings
label | Acceptance Criteria - Install HILTI HST4 Stud Anchors with 90mm embedment as per manufactures installation instructions
label | Method - Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Structural Steel Installation - Wall Ties and Brackets
label | Reference - AS4100 Clause 15.2.3, AS5131 Clause 11.5.7
label | Acceptance Criteria - Place steel component into position,ensuring that it is plumb, level, square. Spacing and location as per plans (horizontal/vertical/height and around openings)
label | ○ Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs.
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Fastener Tightening - Snug Tight Condition
label | Reference - IFC Drawings
label | Acceptance Criteria - Place bolts, washers and nuts as detailed on the IFC Drawings.
label | — Washer as specified(Washers shall cover the hole or slotted hole completely by 0.5 x bolt diamter)
label | — Nut
label | — Bolt protrusion (2 clear tread)
label | Method - Visual
label | Frequency - Where applicable, each bolted connection
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Post-installation Activities
checkpoint | 5.1 - Inspection of Coating/Surface treatment
label | Reference - IFC Drawings AS4680
label | Acceptance Criteria - After installation Works are complete, inspect the steel element for damage to the coatings.
label | ○ Where damage exists, it shall be repaired using an approved repair procedure
label | Method - Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.1 - As-built /Survey
label | Reference - IFC Drawings
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | Method - Document Review
label | Frequency - Each elemenmt
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP