## Table 1
Project Name: |  |  |  |  | Otaki to North Levin Project (O2NL) |  |  |  | Prepared by: |  |  |  | Marco Edwards |  |  |  |  | Rev. No. |  | A
ITP No.: |  |  |  |  | O2NL-STH-000-CN-ITP-0008 |  |  |  | Project Engineer: |  |  |  | Nico Aandewiel
Construction Process: |  |  |  |  | North Manakau Temporary Diversion Road |  |  |  | Approved by:
|  | LEGEND | [7 empty] | REFERENCE DOCUMENTS
|  | Verification Activity | [7 empty] | Development:
O2NL- Pavement Design DWGs - Rev2
|  |  | H | Hold Point | Work shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
Ō2NL-STH-000-CN-CEP-0008 - North Manakau Temporary Diversion Road
|  |  | W | Witness Point | An inspection point that may be witnessed by the organisation imposing the Witness Point.
Implementation:
|  |  | I | Inspection | Formal inspection activity to be undertaken and recorded. |  |  |  |  | Ō2NL-STH-000-CN-ITP-0008 - North Manakau Temporary Diversion Road
|  |  | S | Surveillance | An activity that is subject to ongoing monitoring.
|  |  | R | Review | Review of text reports/records or other evidence of compliance.
Responsible Inspectorate (RI) (may be modified to meet site specific requirements)
APPROVAL/REVISION
SA – South Alliance
[10 empty] | Rev |  | Date |  |  | Details |  |  |  | App’d (Alliance) |  |  | App’d (Owner)
PM – Project Manager
CM – Construction Manager
[10 empty] | A |  | 2025-07-25
ENG – Responsible Engineer
SUP – Supervisor
SQN – Subcontractor Quality Nominee
QMR – Quality Management Representative
SMR– Safety Management Representative
EMR– Environment Management Representative
Construction Process: |  |  |  |  | North Manakau Temporary Diversion road | [5 empty] | ITP No.: |  |  | XX |  |  | Rev A
Item | Basic Job Step |  |  |  |  | RI | Acceptance Criteria | Applicable Standard | Inspection Test |  |  |  |  | Verification Activity by |  |  | Verifying Records |  |  |  | Sign-off
[9 empty] | Method |  | Frequency |  |  | SubCon | Alliance | Client
1.0 Preliminaries
1.1 | JSEA Approved Prior to Start |  |  |  |  | ENG | Alliance Approved prior to construction start | Alliance Best Practice | [6 empty] | H |  | Signed JSEA
1.2 | ESC Plan Approved |  |  |  |  | ENG | Alliance Approved prior to construction start | Alliance Best Practice | [6 empty] | H |  | ENV Manager Approval
1.3 | Alliance Excavation Permit |  |  |  |  | SUP | As required for scope of works, in place prior to any excavation | Alliance Best Practice | [6 empty] | H |  | Signe Permit to Work
2.0 – Material Compliance
2.1 | SIL GAP65 Approval |  |  |  |  | ENG | Material complies to TNZ M/3 | TNZ M/3 1986 | N/A |  | Prior to Construction |  |  |  | H |  | Email Approval from QMR
2.2 | Subbase GAP65 Approval |  |  |  |  | ENG | Material complies to TNZ M/3 | TNZ M/3 1986 | N/A |  | Prior to Subbase Construction |  |  |  | H |  | Email Approval from QMR
2.3 | Basecourse AP40 Approval |  |  |  |  | ENG | Material Complies to TNZ M04 | TNZ M04 2024 | N/A |  | Prior to Basecourse Construction |  |  |  | H |  | Email Approval from QMR
2.4 | Subgrade CBR |  |  |  |  | ENG | Soaked CBR: Min. 3 per section (IANZ-accredited laboratory), Unsoaked CBR: Min. 3 per section, Moisture Content: Min. 3 per section | Design notes | N/A |  | Minimum 3 tests per site |  |  |  | R |  | Lab Reports to Design Verifier
2.5 | Culvert Pipe & Rubber Ring Joints |  |  |  |  | ENG | Approved through Alliance Engineering/Quality Team |  |  |  | Prior to Construction |  |  |  | R |  | Email Acceptance from QMR
2.6 | Culvert Bedding Material |  |  |  |  | ENG | Complies to NZTA F/3 Pipe Bedding and Backfilling for Flexible Pipes – Class A | Pipe Bedding and Backfilling for Flexible Pipes | N/A |  | Prior to Construction |  |  |  | R |  | Email Acceptance from QMR
3.0 Construction – Subgrade
| Topsoil Strip |  |  |  |  | SUP | Area stripped of all topsoil and organic material | Alliance Best Practice | Excavation |  | Prior to Subgrade cut |  |  |  | W |  | Site Record Sheet, Photos
| Cut to subgrade level |  |  |  |  | ENG | Cut to design levels – Topographic survey 5m x5m Grid | Alliance Best Practice | Survey |  | Post subgrade cut |  |  |  | I |  | As-built Survey Record
3.1 | Subgrade CBR Verification |  |  |  |  | ENG | Scala Penetrometer (NZS 4402:1986 Sec. 6.5.2) at 50 mm intervals to 1000 mm depth, every 10 m chainage | NZS 4402:1986 Sec. 6.5.2 | Test |  | 10m x 10m grid |  |  |  | I |  | Scala Record Sheet
3.2 | Subgrade Proof Rolling |  |  |  |  | ENG / SUP | Visual inspection & roller observation - No soft spots, deflection, or pumping | TNZ B/02: 2005 | Test |  | Continuous |  |  |  | I |  | Site Records
3.3 | Backfill Undercuts |  |  |  |  | ENG | Unsuitable subgrade material removed, and excavation backfilled in 200mm layers (GAP65) to 95% MDD | Alliance Best Practice | Excavation |  | As required |  |  |  | H |  | Site Records / NDM test sheet
3.4 | Subgrade Approval |  |  |  |  | ENG | Approval to proceed with Subbase | Alliance Best Practice | N/A |  | On completion of Subgrade testing |  |  |  | H |  | Approval to proceed from Design Verifier
4.0 – Subgrade Improvement Layer (SIL)
4.1 | Layer Thickness |  |  |  |  | ENG | SIL Thickness as per SIL Design note, 200mm – 300mm | Design notes | Excavation |  | During Sil Construction |  |  |  | I |  | Site Records
4.2 | Density |  |  |  |  | ENG | Mean percentage of MDD not less than 95% with no single result less than 92% | TNZ B/02 | NZS 4402 – Test 4.1.3 |  | Not less than one test per 150m2 |  |  |  | I |  | Site Records / NDM test sheet
4.3 | SIL Proof Roll |  |  |  |  | ENG | Visual inspection & roller observation - No soft spots, deflection, or pumping | TNZ B/02: 2005 | Test |  | One pass on each lane |  |  |  | I |  | Site Records
5.0 Construction – Subbase
5.1 | Density |  |  |  |  | ENG | Mean percentage of MDD not less than 95% with no single result less than 92% | TNZ B/02 | NZS 4402 – Test 4.1.3 |  | Not less than one test per 150m2 |  |  |  | I |  | Site Records / NDM test sheet
5.2 | Surface Level |  |  |  |  | ENG | +15mm/-15mm from design level. Thickness of subbase shall be within 15mm of design thickness | TNZ F/1 | Survey |  | 5m x5m Grid |  |  |  | I |  | As-built Survey Record
5.3 | Subbase Proof Roll |  |  |  |  | ENG | Visual inspection & roller observation - No soft spots, deflection, or pumping | TNZ B/02: 2005 | TEst |  | One pass on each lane |  |  |  | I |  | Site Records
6.0 Construction - Basecourse
6 | Density |  |  |  |  | ENG | Mean percentage of MDD not less than 98% with no single result less than 95% | TNZ B/02 | NZS 4402 – Test 4.1.3 |  | Not less than one test per 150m2 |  |  |  | I |  | Site Records / NDM test sheet
6.1 | Surface Level |  |  |  |  | ENG | +5mm/-15mm from design level. Thickness of subbase shall be within 15mm of design thickness | TNZ F/1 | Survey |  | 5m x5m Grid |  |  |  | I |  | As-built Survey Record
6.2 | Surface tolerance |  |  |  |  | ENG | Finished surface shall not vary more than +-15mm when tested with a 3m straightedge | TNZ B/02 | Test |  | 20m grid |  |  |  | I |  | Site Records / Photos
6.3 | Basecourse Approval |  |  |  |  | ENG | Approval to proceed with Surfacing | Alliance Best Practice | N/A | [5 empty] | H |  | Approval to Proceed from Design Verifier
7.0 Construction – Culverts
7.1 | Survey Set-Out |  |  |  |  | ENG | Culverts shall be set out and laid where shown in the drawings | Alliance Best Practice | SUrvey |  | Before excavation of drain lines
7.2 | Culvert Trench Excavation |  |  |  |  | SUP | Trench Excavated to subgrade level, If excavation exceeds 1.5m trench battered at 1:1 or benched as required, 600m cover to top of pipe. | JSEA | Excavation |  | During Trench Excavation |  |  |  | H |  | Site Records
7.3 | Subgrade Suitability |  |  |  |  | ENG /SUP | Assumed subgrade CBR 4%, visual inspection on site, organic material removed, geotextile prior to Bedding placement | Alliance Best Practice | Inspection |  | Prior to placing Bedding material |  |  |  | I |  | Site Records
7.4 | Bedding Material |  |  |  |  | SUP | Min 100mm thickness | TNZ F/03 | N/A |  | Check during bedding placement |  |  |  | I |  | Site Records
7.5 | Placing Culvert Pipe |  |  |  |  | ENG | As per design levels and grades | N/A | Survey |  | Post pipe placement |  |  |  | I |  | As-Built Survey Record
7.6 | Pipe Jointing |  |  |  |  | ENG | As per manufacturers specification | N/A | N/A |  | Inspection post jointing |  |  |  | I |  | Site Records
7.7 | Trench Backfill |  |  |  |  | ENG | Approved material compacted in 150mm lifts to 95% MDD | TNZ F/03 | N/A |  | Backfill post pipe placement |  |  |  | I |  | Site Records / NDM Report
4.0 Post-Construction
4.1 | As-Built Records |  |  |  |  | ENG | All As-Builts provided Alliance Quality Team within one month of completion | Alliance Best Practice | [6 empty] | R |  | As-Built Data