## Sheet1
1.1 | JSEA Approved Prior to Start | ENG | Alliance Approved prior to construction start | Alliance Best Practice |  |  | H | Signed JSEA | 1.1 - JSEA Approved Prior to Start | RI - ENG | Acceptance Criteria - Alliance Approved prior to construction start | Applicable Standard - Alliance Best Practice | Inspection Test: Method - | Inspection Test: Frequency - | Verification Activity by: SubCon - | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - Signed JSEA | 1.1 - JSEA Approved Prior to Start
1.2 | ESC Plan Approved | ENG | Alliance Approved prior to construction start | Alliance Best Practice |  |  | H | ENV Manager Approval | 1.2 - ESC Plan Approved | RI - ENG | Acceptance Criteria - Alliance Approved prior to construction start | Applicable Standard - Alliance Best Practice | Inspection Test: Method - | Inspection Test: Frequency - | Verification Activity by: SubCon - | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - ENV Manager Approval | RI - ENG
1.3 | Alliance Excavation Permit | SUP | As required for scope of works, in place prior to any excavation | Alliance Best Practice |  |  | H | Signe Permit to Work | 1.3 - Alliance Excavation Permit | RI - SUP | Acceptance Criteria - As required for scope of works, in place prior to any excavation | Applicable Standard - Alliance Best Practice | Inspection Test: Method - | Inspection Test: Frequency - | Verification Activity by: SubCon - | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - Signe Permit to Work | Acceptance Criteria - Alliance Approved prior to construction start
2.1 | SIL GAP65 Approval | ENG | Material complies to TNZ M/3 | TNZ M/3 1986 | N/A | Prior to Construction | H | Email Approval from QMR | 2.1 - SIL GAP65 Approval | RI - ENG | Acceptance Criteria - Material complies to TNZ M/3 | Applicable Standard - TNZ M/3 1986 | Inspection Test: Method - N/A | Inspection Test: Frequency - Prior to Construction | Verification Activity by: SubCon - | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - Email Approval from QMR | Applicable Standard - Alliance Best Practice
2.2 | Subbase GAP65 Approval | ENG | Material complies to TNZ M/3 | TNZ M/3 1986 | N/A | Prior to Subbase Construction | H | Email Approval from QMR | 2.2 - Subbase GAP65 Approval | RI - ENG | Acceptance Criteria - Material complies to TNZ M/3 | Applicable Standard - TNZ M/3 1986 | Inspection Test: Method - N/A | Inspection Test: Frequency - Prior to Subbase Construction | Verification Activity by: SubCon - | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - Email Approval from QMR | Inspection Test: Method -
2.3 | Basecourse AP40 Approval | ENG | Material Complies to TNZ M04 | TNZ M04 2024 | N/A | Prior to Basecourse Construction | H | Email Approval from QMR | 2.3 - Basecourse AP40 Approval | RI - ENG | Acceptance Criteria - Material Complies to TNZ M04 | Applicable Standard - TNZ M04 2024 | Inspection Test: Method - N/A | Inspection Test: Frequency - Prior to Basecourse Construction | Verification Activity by: SubCon - | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - Email Approval from QMR | Inspection Test: Frequency -
2.4 | Subgrade CBR | ENG | Soaked CBR: Min. 3 per section (IANZ-accredited laboratory), Unsoaked CBR: Min. 3 per section, Moisture Content: Min. 3 per section | Design notes | N/A | Minimum 3 tests per site | R | Lab Reports to Design Verifier | 2.4 - Subgrade CBR | RI - ENG | Acceptance Criteria - Soaked CBR: Min. 3 per section (IANZ-accredited laboratory), Unsoaked CBR: Min. 3 per section, Moisture Content: Min. 3 per section | Applicable Standard - Design notes | Inspection Test: Method - N/A | Inspection Test: Frequency - Minimum 3 tests per site | Verification Activity by: SubCon - | Verification Activity by: Alliance - R | Verification Activity by: Client - | Verifying Records - Lab Reports to Design Verifier | Verification Activity by: SubCon -
2.5 | Culvert Pipe CHAR(AMP) Rubber Ring Joints | ENG | Approved through Alliance Engineering/Quality Team |  |  | Prior to Construction | R | Email Acceptance from QMR | 2.5 - Culvert Pipe CHAR(AMP) Rubber Ring Joints | RI - ENG | Acceptance Criteria - Approved through Alliance Engineering/Quality Team | Applicable Standard - | Inspection Test: Method - | Inspection Test: Frequency - Prior to Construction | Verification Activity by: SubCon - | Verification Activity by: Alliance - R | Verification Activity by: Client - | Verifying Records - Email Acceptance from QMR | Verification Activity by: Alliance - H
2.6 | Culvert Bedding Material | ENG | Complies to NZTA F/3 Pipe Bedding and Backfilling for Flexible Pipes – Class A | Pipe Bedding and Backfilling for Flexible Pipes | N/A | Prior to Construction | R | Email Acceptance from QMR | 2.6 - Culvert Bedding Material | RI - ENG | Acceptance Criteria - Complies to NZTA F/3 Pipe Bedding and Backfilling for Flexible Pipes – Class A | Applicable Standard - Pipe Bedding and Backfilling for Flexible Pipes | Inspection Test: Method - N/A | Inspection Test: Frequency - Prior to Construction | Verification Activity by: SubCon - | Verification Activity by: Alliance - R | Verification Activity by: Client - | Verifying Records - Email Acceptance from QMR | Verification Activity by: Client -
| Topsoil Strip | SUP | Area stripped of all topsoil and organic material | Alliance Best Practice | Excavation | Prior to Subgrade cut | W | Site Record Sheet, Photos | - Topsoil Strip | RI - SUP | Acceptance Criteria - Area stripped of all topsoil and organic material | Applicable Standard - Alliance Best Practice | Inspection Test: Method - Excavation | Inspection Test: Frequency - Prior to Subgrade cut | Verification Activity by: SubCon - | Verification Activity by: Alliance - W | Verification Activity by: Client - | Verifying Records - Site Record Sheet, Photos | Verifying Records - Signed JSEA
| Cut to subgrade level | ENG | Cut to design levels – Topographic survey 5m x5m Grid | Alliance Best Practice | Survey | Post subgrade cut | I | As-built Survey Record | - Cut to subgrade level | RI - ENG | Acceptance Criteria - Cut to design levels – Topographic survey 5m x5m Grid | Applicable Standard - Alliance Best Practice | Inspection Test: Method - Survey | Inspection Test: Frequency - Post subgrade cut | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - As-built Survey Record | 1.2 - ESC Plan Approved
3.1 | Subgrade CBR Verification | ENG | Scala Penetrometer (NZS 4402:1986 Sec. 6.5.2) at 50 mm intervals to 1000 mm depth, every 10 m chainage | NZS 4402:1986 Sec. 6.5.2 | Test | 10m x 10m grid | I | Scala Record Sheet | 3.1 - Subgrade CBR Verification | RI - ENG | Acceptance Criteria - Scala Penetrometer (NZS 4402:1986 Sec. 6.5.2) at 50 mm intervals to 1000 mm depth, every 10 m chainage | Applicable Standard - NZS 4402:1986 Sec. 6.5.2 | Inspection Test: Method - Test | Inspection Test: Frequency - 10m x 10m grid | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - Scala Record Sheet | RI - ENG
3.2 | Subgrade Proof Rolling | ENG / SUP | Visual inspection CHAR(AMP) roller observation - No soft spots, deflection, or pumping | TNZ B/02: 2005 | Test | Continuous | I | Site Records | 3.2 - Subgrade Proof Rolling | RI - ENG / SUP | Acceptance Criteria - Visual inspection CHAR(AMP) roller observation - No soft spots, deflection, or pumping | Applicable Standard - TNZ B/02: 2005 | Inspection Test: Method - Test | Inspection Test: Frequency - Continuous | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - Site Records | Acceptance Criteria - Alliance Approved prior to construction start
3.3 | Backfill Undercuts | ENG | Unsuitable subgrade material removed, and excavation backfilled in 200mm layers (GAP65) to 95% MDD | Alliance Best Practice | Excavation | As required | H | Site Records / NDM test sheet | 3.3 - Backfill Undercuts | RI - ENG | Acceptance Criteria - Unsuitable subgrade material removed, and excavation backfilled in 200mm layers (GAP65) to 95% MDD | Applicable Standard - Alliance Best Practice | Inspection Test: Method - Excavation | Inspection Test: Frequency - As required | Verification Activity by: SubCon - | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - Site Records / NDM test sheet | Applicable Standard - Alliance Best Practice
3.4 | Subgrade Approval | ENG | Approval to proceed with Subbase | Alliance Best Practice | N/A | On completion of Subgrade testing | H | Approval to proceed from Design Verifier | 3.4 - Subgrade Approval | RI - ENG | Acceptance Criteria - Approval to proceed with Subbase | Applicable Standard - Alliance Best Practice | Inspection Test: Method - N/A | Inspection Test: Frequency - On completion of Subgrade testing | Verification Activity by: SubCon - | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - Approval to proceed from Design Verifier | Inspection Test: Method -
4.1 | Layer Thickness | ENG | SIL Thickness as per SIL Design note, 200mm – 300mm | Design notes | Excavation | During Sil Construction | I | Site Records | 4.1 - Layer Thickness | RI - ENG | Acceptance Criteria - SIL Thickness as per SIL Design note, 200mm – 300mm | Applicable Standard - Design notes | Inspection Test: Method - Excavation | Inspection Test: Frequency - During Sil Construction | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - Site Records | Inspection Test: Frequency -
4.2 | Density | ENG | Mean percentage of MDD not less than 95% with no single result less than 92% | TNZ B/02 | NZS 4402 – Test 4.1.3 | Not less than one test per 150m2 | I | Site Records / NDM test sheet | 4.2 - Density | RI - ENG | Acceptance Criteria - Mean percentage of MDD not less than 95% with no single result less than 92% | Applicable Standard - TNZ B/02 | Inspection Test: Method - NZS 4402 – Test 4.1.3 | Inspection Test: Frequency - Not less than one test per 150m2 | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - Site Records / NDM test sheet | Verification Activity by: SubCon -
4.3 | SIL Proof Roll | ENG | Visual inspection CHAR(AMP) roller observation - No soft spots, deflection, or pumping | TNZ B/02: 2005 | Test | One pass on each lane | I | Site Records | 4.3 - SIL Proof Roll | RI - ENG | Acceptance Criteria - Visual inspection CHAR(AMP) roller observation - No soft spots, deflection, or pumping | Applicable Standard - TNZ B/02: 2005 | Inspection Test: Method - Test | Inspection Test: Frequency - One pass on each lane | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - Site Records | Verification Activity by: Alliance - H
5.1 | Density | ENG | Mean percentage of MDD not less than 95% with no single result less than 92% | TNZ B/02 | NZS 4402 – Test 4.1.3 | Not less than one test per 150m2 | I | Site Records / NDM test sheet | 5.1 - Density | RI - ENG | Acceptance Criteria - Mean percentage of MDD not less than 95% with no single result less than 92% | Applicable Standard - TNZ B/02 | Inspection Test: Method - NZS 4402 – Test 4.1.3 | Inspection Test: Frequency - Not less than one test per 150m2 | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - Site Records / NDM test sheet | Verification Activity by: Client -
5.2 | Surface Level | ENG | +15mm/-15mm from design level. Thickness of subbase shall be within 15mm of design thickness | TNZ F/1 | Survey | 5m x5m Grid | I | As-built Survey Record | 5.2 - Surface Level | RI - ENG | Acceptance Criteria - +15mm/-15mm from design level. Thickness of subbase shall be within 15mm of design thickness | Applicable Standard - TNZ F/1 | Inspection Test: Method - Survey | Inspection Test: Frequency - 5m x5m Grid | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - As-built Survey Record | Verifying Records - ENV Manager Approval
5.3 | Subbase Proof Roll | ENG | Visual inspection CHAR(AMP) roller observation - No soft spots, deflection, or pumping | TNZ B/02: 2005 | TEst | One pass on each lane | I | Site Records | 5.3 - Subbase Proof Roll | RI - ENG | Acceptance Criteria - Visual inspection CHAR(AMP) roller observation - No soft spots, deflection, or pumping | Applicable Standard - TNZ B/02: 2005 | Inspection Test: Method - TEst | Inspection Test: Frequency - One pass on each lane | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - Site Records | 1.3 - Alliance Excavation Permit
6 | Density | ENG | Mean percentage of MDD not less than 98% with no single result less than 95% | TNZ B/02 | NZS 4402 – Test 4.1.3 | Not less than one test per 150m2 | I | Site Records / NDM test sheet | 6 - Density | RI - ENG | Acceptance Criteria - Mean percentage of MDD not less than 98% with no single result less than 95% | Applicable Standard - TNZ B/02 | Inspection Test: Method - NZS 4402 – Test 4.1.3 | Inspection Test: Frequency - Not less than one test per 150m2 | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - Site Records / NDM test sheet | RI - SUP
6.1 | Surface Level | ENG | +5mm/-15mm from design level. Thickness of subbase shall be within 15mm of design thickness | TNZ F/1 | Survey | 5m x5m Grid | I | As-built Survey Record | 6.1 - Surface Level | RI - ENG | Acceptance Criteria - +5mm/-15mm from design level. Thickness of subbase shall be within 15mm of design thickness | Applicable Standard - TNZ F/1 | Inspection Test: Method - Survey | Inspection Test: Frequency - 5m x5m Grid | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - As-built Survey Record | Acceptance Criteria - As required for scope of works, in place prior to any excavation
6.2 | Surface tolerance | ENG | Finished surface shall not vary more than +-15mm when tested with a 3m straightedge | TNZ B/02 | Test | 20m grid | I | Site Records / Photos | 6.2 - Surface tolerance | RI - ENG | Acceptance Criteria - Finished surface shall not vary more than +-15mm when tested with a 3m straightedge | Applicable Standard - TNZ B/02 | Inspection Test: Method - Test | Inspection Test: Frequency - 20m grid | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - Site Records / Photos | Applicable Standard - Alliance Best Practice
6.3 | Basecourse Approval | ENG | Approval to proceed with Surfacing | Alliance Best Practice | N/A |  | H | Approval to Proceed from Design Verifier | 6.3 - Basecourse Approval | RI - ENG | Acceptance Criteria - Approval to proceed with Surfacing | Applicable Standard - Alliance Best Practice | Inspection Test: Method - N/A | Inspection Test: Frequency - | Verification Activity by: SubCon - | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - Approval to Proceed from Design Verifier | Inspection Test: Method -
7.1 | Survey Set-Out | ENG | Culverts shall be set out and laid where shown in the drawings | Alliance Best Practice | SUrvey | Before excavation of drain lines |  |  | 7.1 - Survey Set-Out | RI - ENG | Acceptance Criteria - Culverts shall be set out and laid where shown in the drawings | Applicable Standard - Alliance Best Practice | Inspection Test: Method - SUrvey | Inspection Test: Frequency - Before excavation of drain lines | Verification Activity by: SubCon - | Verification Activity by: Alliance - | Verification Activity by: Client - | Verifying Records - | Inspection Test: Frequency -
7.2 | Culvert Trench Excavation | SUP | Trench Excavated to subgrade level, If excavation exceeds 1.5m trench battered at 1:1 or benched as required, 600m cover to top of pipe. | JSEA | Excavation | During Trench Excavation | H | Site Records | 7.2 - Culvert Trench Excavation | RI - SUP | Acceptance Criteria - Trench Excavated to subgrade level, If excavation exceeds 1.5m trench battered at 1:1 or benched as required, 600m cover to top of pipe. | Applicable Standard - JSEA | Inspection Test: Method - Excavation | Inspection Test: Frequency - During Trench Excavation | Verification Activity by: SubCon - | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - Site Records | Verification Activity by: SubCon -
7.3 | Subgrade Suitability | ENG /SUP | Assumed subgrade CBR 4%, visual inspection on site, organic material removed, geotextile prior to Bedding placement | Alliance Best Practice | Inspection | Prior to placing Bedding material | I | Site Records | 7.3 - Subgrade Suitability | RI - ENG /SUP | Acceptance Criteria - Assumed subgrade CBR 4%, visual inspection on site, organic material removed, geotextile prior to Bedding placement | Applicable Standard - Alliance Best Practice | Inspection Test: Method - Inspection | Inspection Test: Frequency - Prior to placing Bedding material | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - Site Records | Verification Activity by: Alliance - H
7.4 | Bedding Material | SUP | Min 100mm thickness | TNZ F/03 | N/A | Check during bedding placement | I | Site Records | 7.4 - Bedding Material | RI - SUP | Acceptance Criteria - Min 100mm thickness | Applicable Standard - TNZ F/03 | Inspection Test: Method - N/A | Inspection Test: Frequency - Check during bedding placement | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - Site Records | Verification Activity by: Client -
7.5 | Placing Culvert Pipe | ENG | As per design levels and grades | N/A | Survey | Post pipe placement | I | As-Built Survey Record | 7.5 - Placing Culvert Pipe | RI - ENG | Acceptance Criteria - As per design levels and grades | Applicable Standard - N/A | Inspection Test: Method - Survey | Inspection Test: Frequency - Post pipe placement | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - As-Built Survey Record | Verifying Records - Signe Permit to Work
7.6 | Pipe Jointing | ENG | As per manufacturers specification | N/A | N/A | Inspection post jointing | I | Site Records | 7.6 - Pipe Jointing | RI - ENG | Acceptance Criteria - As per manufacturers specification | Applicable Standard - N/A | Inspection Test: Method - N/A | Inspection Test: Frequency - Inspection post jointing | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - Site Records | 2.1 - SIL GAP65 Approval
7.7 | Trench Backfill | ENG | Approved material compacted in 150mm lifts to 95% MDD | TNZ F/03 | N/A | Backfill post pipe placement | I | Site Records / NDM Report | 7.7 - Trench Backfill | RI - ENG | Acceptance Criteria - Approved material compacted in 150mm lifts to 95% MDD | Applicable Standard - TNZ F/03 | Inspection Test: Method - N/A | Inspection Test: Frequency - Backfill post pipe placement | Verification Activity by: SubCon - | Verification Activity by: Alliance - I | Verification Activity by: Client - | Verifying Records - Site Records / NDM Report | RI - ENG
4.1 | As-Built Records | ENG | All As-Builts provided Alliance Quality Team within one month of completion | Alliance Best Practice |  |  | R | As-Built Data | 4.1 - As-Built Records | RI - ENG | Acceptance Criteria - All As-Builts provided Alliance Quality Team within one month of completion | Applicable Standard - Alliance Best Practice | Inspection Test: Method - | Inspection Test: Frequency - | Verification Activity by: SubCon - | Verification Activity by: Alliance - R | Verification Activity by: Client - | Verifying Records - As-Built Data | Acceptance Criteria - Material complies to TNZ M/3
Applicable Standard - TNZ M/3 1986
Inspection Test: Method - N/A
Inspection Test: Frequency - Prior to Construction
Verification Activity by: SubCon -
Verification Activity by: Alliance - H
Verification Activity by: Client -
Verifying Records - Email Approval from QMR
2.2 - Subbase GAP65 Approval
RI - ENG
Acceptance Criteria - Material complies to TNZ M/3
Applicable Standard - TNZ M/3 1986
Inspection Test: Method - N/A
Inspection Test: Frequency - Prior to Subbase Construction
Verification Activity by: SubCon -
Verification Activity by: Alliance - H
Verification Activity by: Client -
Verifying Records - Email Approval from QMR
2.3 - Basecourse AP40 Approval
RI - ENG
Acceptance Criteria - Material Complies to TNZ M04
Applicable Standard - TNZ M04 2024
Inspection Test: Method - N/A
Inspection Test: Frequency - Prior to Basecourse Construction
Verification Activity by: SubCon -
Verification Activity by: Alliance - H
Verification Activity by: Client -
Verifying Records - Email Approval from QMR
2.4 - Subgrade CBR
RI - ENG
Acceptance Criteria - Soaked CBR: Min. 3 per section (IANZ-accredited laboratory), Unsoaked CBR: Min. 3 per section, Moisture Content: Min. 3 per section
Applicable Standard - Design notes
Inspection Test: Method - N/A
Inspection Test: Frequency - Minimum 3 tests per site
Verification Activity by: SubCon -
Verification Activity by: Alliance - R
Verification Activity by: Client -
Verifying Records - Lab Reports to Design Verifier
2.5 - Culvert Pipe CHAR(AMP) Rubber Ring Joints
RI - ENG
Acceptance Criteria - Approved through Alliance Engineering/Quality Team
Applicable Standard -
Inspection Test: Method -
Inspection Test: Frequency - Prior to Construction
Verification Activity by: SubCon -
Verification Activity by: Alliance - R
Verification Activity by: Client -
Verifying Records - Email Acceptance from QMR
2.6 - Culvert Bedding Material
RI - ENG
Acceptance Criteria - Complies to NZTA F/3 Pipe Bedding and Backfilling for Flexible Pipes – Class A
Applicable Standard - Pipe Bedding and Backfilling for Flexible Pipes
Inspection Test: Method - N/A
Inspection Test: Frequency - Prior to Construction
Verification Activity by: SubCon -
Verification Activity by: Alliance - R
Verification Activity by: Client -
Verifying Records - Email Acceptance from QMR
- Topsoil Strip
RI - SUP
Acceptance Criteria - Area stripped of all topsoil and organic material
Applicable Standard - Alliance Best Practice
Inspection Test: Method - Excavation
Inspection Test: Frequency - Prior to Subgrade cut
Verification Activity by: SubCon -
Verification Activity by: Alliance - W
Verification Activity by: Client -
Verifying Records - Site Record Sheet, Photos
- Cut to subgrade level
RI - ENG
Acceptance Criteria - Cut to design levels – Topographic survey 5m x5m Grid
Applicable Standard - Alliance Best Practice
Inspection Test: Method - Survey
Inspection Test: Frequency - Post subgrade cut
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - As-built Survey Record
3.1 - Subgrade CBR Verification
RI - ENG
Acceptance Criteria - Scala Penetrometer (NZS 4402:1986 Sec. 6.5.2) at 50 mm intervals to 1000 mm depth, every 10 m chainage
Applicable Standard - NZS 4402:1986 Sec. 6.5.2
Inspection Test: Method - Test
Inspection Test: Frequency - 10m x 10m grid
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - Scala Record Sheet
3.2 - Subgrade Proof Rolling
RI - ENG / SUP
Acceptance Criteria - Visual inspection CHAR(AMP) roller observation - No soft spots, deflection, or pumping
Applicable Standard - TNZ B/02: 2005
Inspection Test: Method - Test
Inspection Test: Frequency - Continuous
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - Site Records
3.3 - Backfill Undercuts
RI - ENG
Acceptance Criteria - Unsuitable subgrade material removed, and excavation backfilled in 200mm layers (GAP65) to 95% MDD
Applicable Standard - Alliance Best Practice
Inspection Test: Method - Excavation
Inspection Test: Frequency - As required
Verification Activity by: SubCon -
Verification Activity by: Alliance - H
Verification Activity by: Client -
Verifying Records - Site Records / NDM test sheet
3.4 - Subgrade Approval
RI - ENG
Acceptance Criteria - Approval to proceed with Subbase
Applicable Standard - Alliance Best Practice
Inspection Test: Method - N/A
Inspection Test: Frequency - On completion of Subgrade testing
Verification Activity by: SubCon -
Verification Activity by: Alliance - H
Verification Activity by: Client -
Verifying Records - Approval to proceed from Design Verifier
4.1 - Layer Thickness
RI - ENG
Acceptance Criteria - SIL Thickness as per SIL Design note, 200mm – 300mm
Applicable Standard - Design notes
Inspection Test: Method - Excavation
Inspection Test: Frequency - During Sil Construction
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - Site Records
4.2 - Density
RI - ENG
Acceptance Criteria - Mean percentage of MDD not less than 95% with no single result less than 92%
Applicable Standard - TNZ B/02
Inspection Test: Method - NZS 4402 – Test 4.1.3
Inspection Test: Frequency - Not less than one test per 150m2
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - Site Records / NDM test sheet
4.3 - SIL Proof Roll
RI - ENG
Acceptance Criteria - Visual inspection CHAR(AMP) roller observation - No soft spots, deflection, or pumping
Applicable Standard - TNZ B/02: 2005
Inspection Test: Method - Test
Inspection Test: Frequency - One pass on each lane
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - Site Records
5.1 - Density
RI - ENG
Acceptance Criteria - Mean percentage of MDD not less than 95% with no single result less than 92%
Applicable Standard - TNZ B/02
Inspection Test: Method - NZS 4402 – Test 4.1.3
Inspection Test: Frequency - Not less than one test per 150m2
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - Site Records / NDM test sheet
5.2 - Surface Level
RI - ENG
Acceptance Criteria - +15mm/-15mm from design level. Thickness of subbase shall be within 15mm of design thickness
Applicable Standard - TNZ F/1
Inspection Test: Method - Survey
Inspection Test: Frequency - 5m x5m Grid
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - As-built Survey Record
5.3 - Subbase Proof Roll
RI - ENG
Acceptance Criteria - Visual inspection CHAR(AMP) roller observation - No soft spots, deflection, or pumping
Applicable Standard - TNZ B/02: 2005
Inspection Test: Method - TEst
Inspection Test: Frequency - One pass on each lane
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - Site Records
6 - Density
RI - ENG
Acceptance Criteria - Mean percentage of MDD not less than 98% with no single result less than 95%
Applicable Standard - TNZ B/02
Inspection Test: Method - NZS 4402 – Test 4.1.3
Inspection Test: Frequency - Not less than one test per 150m2
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - Site Records / NDM test sheet
6.1 - Surface Level
RI - ENG
Acceptance Criteria - +5mm/-15mm from design level. Thickness of subbase shall be within 15mm of design thickness
Applicable Standard - TNZ F/1
Inspection Test: Method - Survey
Inspection Test: Frequency - 5m x5m Grid
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - As-built Survey Record
6.2 - Surface tolerance
RI - ENG
Acceptance Criteria - Finished surface shall not vary more than +-15mm when tested with a 3m straightedge
Applicable Standard - TNZ B/02
Inspection Test: Method - Test
Inspection Test: Frequency - 20m grid
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - Site Records / Photos
6.3 - Basecourse Approval
RI - ENG
Acceptance Criteria - Approval to proceed with Surfacing
Applicable Standard - Alliance Best Practice
Inspection Test: Method - N/A
Inspection Test: Frequency -
Verification Activity by: SubCon -
Verification Activity by: Alliance - H
Verification Activity by: Client -
Verifying Records - Approval to Proceed from Design Verifier
7.1 - Survey Set-Out
RI - ENG
Acceptance Criteria - Culverts shall be set out and laid where shown in the drawings
Applicable Standard - Alliance Best Practice
Inspection Test: Method - SUrvey
Inspection Test: Frequency - Before excavation of drain lines
Verification Activity by: SubCon -
Verification Activity by: Alliance -
Verification Activity by: Client -
Verifying Records -
7.2 - Culvert Trench Excavation
RI - SUP
Acceptance Criteria - Trench Excavated to subgrade level, If excavation exceeds 1.5m trench battered at 1:1 or benched as required, 600m cover to top of pipe.
Applicable Standard - JSEA
Inspection Test: Method - Excavation
Inspection Test: Frequency - During Trench Excavation
Verification Activity by: SubCon -
Verification Activity by: Alliance - H
Verification Activity by: Client -
Verifying Records - Site Records
7.3 - Subgrade Suitability
RI - ENG /SUP
Acceptance Criteria - Assumed subgrade CBR 4%, visual inspection on site, organic material removed, geotextile prior to Bedding placement
Applicable Standard - Alliance Best Practice
Inspection Test: Method - Inspection
Inspection Test: Frequency - Prior to placing Bedding material
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - Site Records
7.4 - Bedding Material
RI - SUP
Acceptance Criteria - Min 100mm thickness
Applicable Standard - TNZ F/03
Inspection Test: Method - N/A
Inspection Test: Frequency - Check during bedding placement
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - Site Records
7.5 - Placing Culvert Pipe
RI - ENG
Acceptance Criteria - As per design levels and grades
Applicable Standard - N/A
Inspection Test: Method - Survey
Inspection Test: Frequency - Post pipe placement
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - As-Built Survey Record
7.6 - Pipe Jointing
RI - ENG
Acceptance Criteria - As per manufacturers specification
Applicable Standard - N/A
Inspection Test: Method - N/A
Inspection Test: Frequency - Inspection post jointing
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - Site Records
7.7 - Trench Backfill
RI - ENG
Acceptance Criteria - Approved material compacted in 150mm lifts to 95% MDD
Applicable Standard - TNZ F/03
Inspection Test: Method - N/A
Inspection Test: Frequency - Backfill post pipe placement
Verification Activity by: SubCon -
Verification Activity by: Alliance - I
Verification Activity by: Client -
Verifying Records - Site Records / NDM Report
4.1 - As-Built Records
RI - ENG
Acceptance Criteria - All As-Builts provided Alliance Quality Team within one month of completion
Applicable Standard - Alliance Best Practice
Inspection Test: Method -
Inspection Test: Frequency -
Verification Activity by: SubCon -
Verification Activity by: Alliance - R
Verification Activity by: Client -
Verifying Records - As-Built Data