## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | O2NL-STH-000-CN-ITP-0008 NMR Temporary Diversion Road | itp
section | 1.0 Preliminaries
checkpoint | 1.1 - JSEA Approved Prior to Start
label | RI - ENG
label | Acceptance Criteria - Alliance Approved prior to construction start
label | Applicable Standard - Alliance Best Practice
label | Verification Activity by: Alliance - H
label | Verifying Records - Signed JSEA
holdpoint | HOLD POINT
checkpoint | 1.2 - ESC Plan Approved
label | RI - ENG
label | Acceptance Criteria - Alliance Approved prior to construction start
label | Applicable Standard - Alliance Best Practice
label | Verification Activity by: Alliance - H
label | Verifying Records - ENV Manager Approval
holdpoint | HOLD POINT
checkpoint | 1.3 - Alliance Excavation Permit
label | RI - SUP
label | Acceptance Criteria - As required for scope of works, in place prior to any excavation
label | Applicable Standard - Alliance Best Practice
label | Verification Activity by: Alliance - H
label | Verifying Records - Signe Permit to Work
holdpoint | HOLD POINT
section | 2.0 Material Compliance
checkpoint | 2.1 - SIL GAP65 Approval
label | RI - ENG
label | Acceptance Criteria - Material complies to TNZ M/3
label | Applicable Standard - TNZ M/3 1986
label | Inspection Test: Method - N/A
label | Inspection Test: Frequency - Prior to Construction
label | Verification Activity by: Alliance - H
label | Verifying Records - Email Approval from QMR
holdpoint | HOLD POINT
checkpoint | 2.2 - Subbase GAP65 Approval
label | RI - ENG
label | Acceptance Criteria - Material complies to TNZ M/3
label | Applicable Standard - TNZ M/3 1986
label | Inspection Test: Method - N/A
label | Inspection Test: Frequency - Prior to Subbase Construction
label | Verification Activity by: Alliance - H
label | Verifying Records - Email Approval from QMR
holdpoint | HOLD POINT
checkpoint | 2.3 - Basecourse AP40 Approval
label | RI - ENG
label | Acceptance Criteria - Material Complies to TNZ M04
label | Applicable Standard - TNZ M04 2024
label | Inspection Test: Method - N/A
label | Inspection Test: Frequency - Prior to Basecourse Construction
label | Verification Activity by: Alliance - H
label | Verifying Records - Email Approval from QMR
holdpoint | HOLD POINT
checkpoint | 2.4 - Subgrade CBR
label | RI - ENG
label | Acceptance Criteria - Soaked CBR: Min. 3 per section (IANZ-accredited laboratory), Unsoaked CBR: Min. 3 per section, Moisture Content: Min. 3 per section
label | Applicable Standard - Design notes
label | Inspection Test: Method - N/A
label | Inspection Test: Frequency - Minimum 3 tests per site
label | Verification Activity by: Alliance - R
label | Verifying Records - Lab Reports to Design Verifier
checkpoint | 2.5 - Culvert Pipe & Rubber Ring Joints
label | RI - ENG
label | Acceptance Criteria - Approved through Alliance Engineering/Quality Team
label | Inspection Test: Frequency - Prior to Construction
label | Verification Activity by: Alliance - R
label | Verifying Records - Email Acceptance from QMR
checkpoint | 2.6 - Culvert Bedding Material
label | RI - ENG
label | Acceptance Criteria - Complies to NZTA F/3 Pipe Bedding and Backfilling for Flexible Pipes – Class A
label | Applicable Standard - Pipe Bedding and Backfilling for Flexible Pipes
label | Inspection Test: Method - N/A
label | Inspection Test: Frequency - Prior to Construction
label | Verification Activity by: Alliance - R
label | Verifying Records - Email Acceptance from QMR
section | 3.0 Construction – Subgrade
checkpoint | Topsoil Strip
label | RI - SUP
label | Acceptance Criteria - Area stripped of all topsoil and organic material
label | Applicable Standard - Alliance Best Practice
label | Inspection Test: Method - Excavation
label | Inspection Test: Frequency - Prior to Subgrade cut
label | Verification Activity by: Alliance - W
label | Verifying Records - Site Record Sheet, Photos
checkpoint | Cut to subgrade level
label | RI - ENG
label | Acceptance Criteria - Cut to design levels – Topographic survey 5m x5m Grid
label | Applicable Standard - Alliance Best Practice
label | Inspection Test: Method - Survey
label | Inspection Test: Frequency - Post subgrade cut
label | Verification Activity by: Alliance - I
label | Verifying Records - As-built Survey Record
checkpoint | 3.1 - Subgrade CBR Verification
label | RI - ENG
label | Acceptance Criteria - Scala Penetrometer (NZS 4402:1986 Sec. 6.5.2) at 50 mm intervals to 1000 mm depth, every 10 m chainage
label | Applicable Standard - NZS 4402:1986 Sec. 6.5.2
label | Inspection Test: Method - Test
label | Inspection Test: Frequency - 10m x 10m grid
label | Verification Activity by: Alliance - I
label | Verifying Records - Scala Record Sheet
checkpoint | 3.2 - Subgrade Proof Rolling
label | RI - ENG / SUP
label | Acceptance Criteria - Visual inspection & roller observation - No soft spots, deflection, or pumping
label | Applicable Standard - TNZ B/02: 2005
label | Inspection Test: Method - Test
label | Inspection Test: Frequency - Continuous
label | Verification Activity by: Alliance - I
label | Verifying Records - Site Records
checkpoint | 3.3 - Backfill Undercuts
label | RI - ENG
label | Acceptance Criteria - Unsuitable subgrade material removed, and excavation backfilled in 200mm layers (GAP65) to 95% MDD
label | Applicable Standard - Alliance Best Practice
label | Inspection Test: Method - Excavation
label | Inspection Test: Frequency - As required
label | Verification Activity by: Alliance - H
label | Verifying Records - Site Records / NDM test sheet
holdpoint | HOLD POINT
checkpoint | 3.4 - Subgrade Approval
label | RI - ENG
label | Acceptance Criteria - Approval to proceed with Subbase
label | Applicable Standard - Alliance Best Practice
label | Inspection Test: Method - N/A
label | Inspection Test: Frequency - On completion of Subgrade testing
label | Verification Activity by: Alliance - H
label | Verifying Records - Approval to proceed from Design Verifier
holdpoint | HOLD POINT
section | 4.0 Subgrade Improvement Layer (SIL)
checkpoint | 4.1 - Layer Thickness
label | RI - ENG
label | Acceptance Criteria - SIL Thickness as per SIL Design note, 200mm – 300mm
label | Applicable Standard - Design notes
label | Inspection Test: Method - Excavation
label | Inspection Test: Frequency - During Sil Construction
label | Verification Activity by: Alliance - I
label | Verifying Records - Site Records
checkpoint | 4.2 - Density
label | RI - ENG
label | Acceptance Criteria - Mean percentage of MDD not less than 95% with no single result less than 92%
label | Applicable Standard - TNZ B/02
label | Inspection Test: Method - NZS 4402 – Test 4.1.3
label | Inspection Test: Frequency - Not less than one test per 150m2
label | Verification Activity by: Alliance - I
label | Verifying Records - Site Records / NDM test sheet
checkpoint | 4.3 - SIL Proof Roll
label | RI - ENG
label | Acceptance Criteria - Visual inspection & roller observation - No soft spots, deflection, or pumping
label | Applicable Standard - TNZ B/02: 2005
label | Inspection Test: Method - Test
label | Inspection Test: Frequency - One pass on each lane
label | Verification Activity by: Alliance - I
label | Verifying Records - Site Records
section | 5.0 Construction – Subbase
checkpoint | 5.1 - Density
label | RI - ENG
label | Acceptance Criteria - Mean percentage of MDD not less than 95% with no single result less than 92%
label | Applicable Standard - TNZ B/02
label | Inspection Test: Method - NZS 4402 – Test 4.1.3
label | Inspection Test: Frequency - Not less than one test per 150m2
label | Verification Activity by: Alliance - I
label | Verifying Records - Site Records / NDM test sheet
checkpoint | 5.2 - Surface Level
label | RI - ENG
label | Acceptance Criteria - +15mm/-15mm from design level. Thickness of subbase shall be within 15mm of design thickness
label | Applicable Standard - TNZ F/1
label | Inspection Test: Method - Survey
label | Inspection Test: Frequency - 5m x5m Grid
label | Verification Activity by: Alliance - I
label | Verifying Records - As-built Survey Record
checkpoint | 5.3 - Subbase Proof Roll
label | RI - ENG
label | Acceptance Criteria - Visual inspection & roller observation - No soft spots, deflection, or pumping
label | Applicable Standard - TNZ B/02: 2005
label | Inspection Test: Method - TEst
label | Inspection Test: Frequency - One pass on each lane
label | Verification Activity by: Alliance - I
label | Verifying Records - Site Records
section | 6.0 Construction - Basecourse
checkpoint | 6.0 - Density
label | RI - ENG
label | Acceptance Criteria - Mean percentage of MDD not less than 98% with no single result less than 95%
label | Applicable Standard - TNZ B/02
label | Inspection Test: Method - NZS 4402 – Test 4.1.3
label | Inspection Test: Frequency - Not less than one test per 150m2
label | Verification Activity by: Alliance - I
label | Verifying Records - Site Records / NDM test sheet
checkpoint | 6.1 - Surface Level
label | RI - ENG
label | Acceptance Criteria - +5mm/-15mm from design level. Thickness of subbase shall be within 15mm of design thickness
label | Applicable Standard - TNZ F/1
label | Inspection Test: Method - Survey
label | Inspection Test: Frequency - 5m x5m Grid
label | Verification Activity by: Alliance - I
label | Verifying Records - As-built Survey Record
checkpoint | 6.2 - Surface tolerance
label | RI - ENG
label | Acceptance Criteria - Finished surface shall not vary more than +-15mm when tested with a 3m straightedge
label | Applicable Standard - TNZ B/02
label | Inspection Test: Method - Test
label | Inspection Test: Frequency - 20m grid
label | Verification Activity by: Alliance - I
label | Verifying Records - Site Records / Photos
checkpoint | 6.3 - Basecourse Approval
label | RI - ENG
label | Acceptance Criteria - Approval to proceed with Surfacing
label | Applicable Standard - Alliance Best Practice
label | Inspection Test: Method - N/A
label | Verification Activity by: Alliance - H
label | Verifying Records - Approval to Proceed from Design Verifier
holdpoint | HOLD POINT
section | 7.0 Construction – Culverts
checkpoint | 7.1 - Survey Set-Out
label | RI - ENG
label | Acceptance Criteria - Culverts shall be set out and laid where shown in the drawings
label | Applicable Standard - Alliance Best Practice
label | Inspection Test: Method - SUrvey
label | Inspection Test: Frequency - Before excavation of drain lines
checkpoint | 7.2 - Culvert Trench Excavation
label | RI - SUP
label | Acceptance Criteria - Trench Excavated to subgrade level, If excavation exceeds 1.5m trench battered at 1:1 or benched as required, 600m cover to top of pipe.
label | Applicable Standard - JSEA
label | Inspection Test: Method - Excavation
label | Inspection Test: Frequency - During Trench Excavation
label | Verification Activity by: Alliance - H
label | Verifying Records - Site Records
holdpoint | HOLD POINT
checkpoint | 7.3 - Subgrade Suitability
label | RI - ENG /SUP
label | Acceptance Criteria - Assumed subgrade CBR 4%, visual inspection on site, organic material removed, geotextile prior to Bedding placement
label | Applicable Standard - Alliance Best Practice
label | Inspection Test: Method - Inspection
label | Inspection Test: Frequency - Prior to placing Bedding material
label | Verification Activity by: Alliance - I
label | Verifying Records - Site Records
checkpoint | 7.4 - Bedding Material
label | RI - SUP
label | Acceptance Criteria - Min 100mm thickness
label | Applicable Standard - TNZ F/03
label | Inspection Test: Method - N/A
label | Inspection Test: Frequency - Check during bedding placement
label | Verification Activity by: Alliance - I
label | Verifying Records - Site Records
checkpoint | 7.5 - Placing Culvert Pipe
label | RI - ENG
label | Acceptance Criteria - As per design levels and grades
label | Applicable Standard - N/A
label | Inspection Test: Method - Survey
label | Inspection Test: Frequency - Post pipe placement
label | Verification Activity by: Alliance - I
label | Verifying Records - As-Built Survey Record
checkpoint | 7.6 - Pipe Jointing
label | RI - ENG
label | Acceptance Criteria - As per manufacturers specification
label | Applicable Standard - N/A
label | Inspection Test: Method - N/A
label | Inspection Test: Frequency - Inspection post jointing
label | Verification Activity by: Alliance - I
label | Verifying Records - Site Records
checkpoint | 7.7 - Trench Backfill
label | RI - ENG
label | Acceptance Criteria - Approved material compacted in 150mm lifts to 95% MDD
label | Applicable Standard - TNZ F/03
label | Inspection Test: Method - N/A
label | Inspection Test: Frequency - Backfill post pipe placement
label | Verification Activity by: Alliance - I
label | Verifying Records - Site Records / NDM Report
section | 4.0 Post-Construction
checkpoint | 4.1 - As-Built Records
label | RI - ENG
label | Acceptance Criteria - All As-Builts provided Alliance Quality Team within one month of completion
label | Applicable Standard - Alliance Best Practice
label | Verification Activity by: Alliance - R
label | Verifying Records - As-Built Data