## Sheet1
01 | Delivery inspection of HDPE ducts and fittings | Each delivery | AS/NZS 4130 / Manufacturer CoC 7.3.3.3 12.3.3, 12,3.4 | Correct SDR, diameter and undamaged | Visual and CoC | Delivery slip / CoC | R. | Sub | R | N/A | Material CoC matches spec; no damage No damaged packing material. | 01 - Delivery inspection of HDPE ducts and fittings | Frequency - Each delivery | Spec/standard - AS/NZS 4130 / Manufacturer CoC 7.3.3.3 12.3.3, 12,3.4 | Acceptance Criteria - Correct SDR, diameter and undamaged | Measuring Devices - Visual and CoC | Reporting Format - Delivery slip / CoC | HCL - R. | SC - Sub | Consult - R | Hold Points Sign off - N/A | Remarks - Material CoC matches spec; no damage No damaged packing material. | 01 - Delivery inspection of HDPE ducts and fittings
02 | Welder qualification check | Before work start | NZ Certifications; standards and industry training | Accept / reject | Document review | Welder Qualification | R | I | R | Hold Point | Welder certification reviewed and approved prior works Hawkins- ITP-000061 | 02 - Welder qualification check | Frequency - Before work start | Spec/standard - NZ Certifications; standards and industry training | Acceptance Criteria - Accept / reject | Measuring Devices - Document review | Reporting Format - Welder Qualification | HCL - R | SC - I | Consult - R | Hold Points Sign off - Hold Point | Remarks - Welder certification reviewed and approved prior works Hawkins- ITP-000061 | Frequency - Each delivery
03 | Trenches and routes inspections | Per section | Drawings Spec 4.23.2 /7.3.4.5/7.3.4.8 | Installed as per project drawings and specifications | Visual | Site coordination | I | I | S |  | Suitable route and bend allowances | 03 - Trenches and routes inspections | Frequency - Per section | Spec/standard - Drawings Spec 4.23.2 /7.3.4.5/7.3.4.8 | Acceptance Criteria - Installed as per project drawings and specifications | Measuring Devices - Visual | Reporting Format - Site coordination | HCL - I | SC - I | Consult - S | Hold Points Sign off - | Remarks - Suitable route and bend allowances | Spec/standard - AS/NZS 4130 / Manufacturer CoC 7.3.3.3 12.3.3, 12,3.4
04 | Duct alignment check | Per section | Project drawings / layout 4.23.2 | Installed as per drawing | Visual | NA | M | I | R |  | No excessive bends or misalignments | 04 - Duct alignment check | Frequency - Per section | Spec/standard - Project drawings / layout 4.23.2 | Acceptance Criteria - Installed as per drawing | Measuring Devices - Visual | Reporting Format - NA | HCL - M | SC - I | Consult - R | Hold Points Sign off - | Remarks - No excessive bends or misalignments | Acceptance Criteria - Correct SDR, diameter and undamaged
05 | Inspection of duct cleanliness and joint | Before welding | ISO 13954 5.10.3 | Ends scraped, dry, and clean | Visual | OMX Quality check sheet | M | I | R |  | Free of debris, scratches, moisture | 05 - Inspection of duct cleanliness and joint | Frequency - Before welding | Spec/standard - ISO 13954 5.10.3 | Acceptance Criteria - Ends scraped, dry, and clean | Measuring Devices - Visual | Reporting Format - OMX Quality check sheet | HCL - M | SC - I | Consult - R | Hold Points Sign off - | Remarks - Free of debris, scratches, moisture | Measuring Devices - Visual and CoC
06 | Fusion setup – pipe end scraping, machine check | Each weld | ISO 13954 / ISO 13955 | Scraping complete, scan barcode | Scraper / EF machine | OMX Quality check sheet | M | M | R |  | Pre-weld approved by supervisor before fusion | 06 - Fusion setup – pipe end scraping, machine check | Frequency - Each weld | Spec/standard - ISO 13954 / ISO 13955 | Acceptance Criteria - Scraping complete, scan barcode | Measuring Devices - Scraper / EF machine | Reporting Format - OMX Quality check sheet | HCL - M | SC - M | Consult - R | Hold Points Sign off - | Remarks - Pre-weld approved by supervisor before fusion | Reporting Format - Delivery slip / CoC
07 | Electrofusion weld execution | Each weld | ISO 13955 12.4.6. 12.5.2 | Parameters met; uniform bead | EF machine logger | Fusion log / OMX Quality check sheet | M | Sub | R |  | Fusion data logged and bead visually compliant Weld number time and date next to weld. | 07 - Electrofusion weld execution | Frequency - Each weld | Spec/standard - ISO 13955 12.4.6. 12.5.2 | Acceptance Criteria - Parameters met; uniform bead | Measuring Devices - EF machine logger | Reporting Format - Fusion log / OMX Quality check sheet | HCL - M | SC - Sub | Consult - R | Hold Points Sign off - | Remarks - Fusion data logged and bead visually compliant Weld number time and date next to weld. | HCL - R.
08 | Post Weld visual inspection and cooling | Each weld | ISO 13955 / 13956 | Bead uniform, cooled per spec | Visual | OMX Quality check sheet | s | R Sub | R |  | Cooling time respected; weld integrity confirmed. | 08 - Post Weld visual inspection and cooling | Frequency - Each weld | Spec/standard - ISO 13955 / 13956 | Acceptance Criteria - Bead uniform, cooled per spec | Measuring Devices - Visual | Reporting Format - OMX Quality check sheet | HCL - s | SC - R Sub | Consult - R | Hold Points Sign off - | Remarks - Cooling time respected; weld integrity confirmed. | SC - Sub
09 | Weld traceability and documentation | Each weld | 7.3.4.9 | Barcode and weld ID logged | Log Sheet | OMX Quality Check sheet | S | Sub | R |  | Log completed and ID matched field location | 09 - Weld traceability and documentation | Frequency - Each weld | Spec/standard - 7.3.4.9 | Acceptance Criteria - Barcode and weld ID logged | Measuring Devices - Log Sheet | Reporting Format - OMX Quality Check sheet | HCL - S | SC - Sub | Consult - R | Hold Points Sign off - | Remarks - Log completed and ID matched field location | Consult - R
10 | Post Weld inspection | Project Scope | DP001-MMD-SPC- EL-Z-Z-001 12.5.2 | CCTV footage of below ground ducting, duct contains no debris or penetrations that could damage cable sheath when pulled | CCTV | Video | S | Sub | R |  | Submission of CCTV footage before handover | 10 - Post Weld inspection | Frequency - Project Scope | Spec/standard - DP001-MMD-SPC- EL-Z-Z-001 12.5.2 | Acceptance Criteria - CCTV footage of below ground ducting, duct contains no debris or penetrations that could damage cable sheath when pulled | Measuring Devices - CCTV | Reporting Format - Video | HCL - S | SC - Sub | Consult - R | Hold Points Sign off - | Remarks - Submission of CCTV footage before handover | Hold Points Sign off - N/A
11 | Electro fusion welder calibration | Project Scope | As per manufactures specification | Electro fusion welder calibration certificate | Calibration certificate | Certificate | S | Sub | R |  | Submission of calibration certificate before handover | 11 - Electro fusion welder calibration | Frequency - Project Scope | Spec/standard - As per manufactures specification | Acceptance Criteria - Electro fusion welder calibration certificate | Measuring Devices - Calibration certificate | Reporting Format - Certificate | HCL - S | SC - Sub | Consult - R | Hold Points Sign off - | Remarks - Submission of calibration certificate before handover | Remarks - Material CoC matches spec; no damage No damaged packing material.
12 | Draw Cord | Each conduit | 12.3.8 | 5 kn | N/A | QC checklist/ photograph | M | Sub | R |  |  | 12 - Draw Cord | Frequency - Each conduit | Spec/standard - 12.3.8 | Acceptance Criteria - 5 kn | Measuring Devices - N/A | Reporting Format - QC checklist/ photograph | HCL - M | SC - Sub | Consult - R | Hold Points Sign off - | Remarks - | 02 - Welder qualification check
13 | Hot Bending of HDPE Ducts | Direction change | DP001-MMD-SPC- EL-Z-Z-001 7.3.4.5 | Minimum bending radius of 2m | Measuring tape | QC checklist | I |  |  |  | Heat apply using controlled hot air: duct support during bending. Cool down in place to retain shape | 13 - Hot Bending of HDPE Ducts | Frequency - Direction change | Spec/standard - DP001-MMD-SPC- EL-Z-Z-001 7.3.4.5 | Acceptance Criteria - Minimum bending radius of 2m | Measuring Devices - Measuring tape | Reporting Format - QC checklist | HCL - I | SC - | Consult - | Hold Points Sign off - | Remarks - Heat apply using controlled hot air: duct support during bending. Cool down in place to retain shape | Frequency - Before work start
14 | Installation of tracer wire | Each installed duct | DP001-MMD-SPC- EL-Z-Z-0017.3.3.11 | Wire securely fixed on top of duct, continuous, accessible at both ends |  | QC checklist Photograph | M | T | R |  | Tracer wire to be installed above duct, secured at 3m intervals. Ends terminated in accessible pits or boxes | 14 - Installation of tracer wire | Frequency - Each installed duct | Spec/standard - DP001-MMD-SPC- EL-Z-Z-0017.3.3.11 | Acceptance Criteria - Wire securely fixed on top of duct, continuous, accessible at both ends | Measuring Devices - | Reporting Format - QC checklist Photograph | HCL - M | SC - T | Consult - R | Hold Points Sign off - | Remarks - Tracer wire to be installed above duct, secured at 3m intervals. Ends terminated in accessible pits or boxes | Spec/standard - NZ Certifications; standards and industry training
15 | Installation of Warning Tape and Polymeric Cover (Mag slab) during Backfilling | Each installed duct | AS/NZ3000. 2018 | Install 300mm above top of duct. | Tape measure, visual check | . QA checklist / photograph | M | W | S |  | Materials supplied by Omexom, installation by civil contractor. Hold point required prior to backfilling. Supplier to verify delivery and provide installation guidance. Coordination required to ensure correct placement and documentation. | 15 - Installation of Warning Tape and Polymeric Cover (Mag slab) during Backfilling | Frequency - Each installed duct | Spec/standard - AS/NZ3000. 2018 | Acceptance Criteria - Install 300mm above top of duct. | Measuring Devices - Tape measure, visual check | Reporting Format - . QA checklist / photograph | HCL - M | SC - W | Consult - S | Hold Points Sign off - | Remarks - Materials supplied by Omexom, installation by civil contractor. Hold point required prior to backfilling. Supplier to verify delivery and provide installation guidance. Coordination required to ensure correct placement and documentation. | Acceptance Criteria - Accept / reject
16 | Pit to Duct Jointing Process | Each duct at each pit | DP001-MMD-SPC- EL-Z-Z-0017.3.3.12 | Manufacturer’s installation guidelines and project specifications | Secure, watertight connection between duct and pit; no gaps or misalignment | Visual check, QA checklist / photograph | S | R | S |  |  | 16 - Pit to Duct Jointing Process | Frequency - Each duct at each pit | Spec/standard - DP001-MMD-SPC- EL-Z-Z-0017.3.3.12 | Acceptance Criteria - Manufacturer’s installation guidelines and project specifications | Measuring Devices - Secure, watertight connection between duct and pit; no gaps or misalignment | Reporting Format - Visual check, QA checklist / photograph | HCL - S | SC - R | Consult - S | Hold Points Sign off - | Remarks - | Measuring Devices - Document review
17 | Coordination with Waterproofing and Concrete Encasing | At each interface with waterproofing or encasement | MMD DP Buildings Elec Spec July 2024 7.3.3.12 | IFC drawings and Sika Details (by others) | N/A | By others | S | R | R |  | By others | 17 - Coordination with Waterproofing and Concrete Encasing | Frequency - At each interface with waterproofing or encasement | Spec/standard - MMD DP Buildings Elec Spec July 2024 7.3.3.12 | Acceptance Criteria - IFC drawings and Sika Details (by others) | Measuring Devices - N/A | Reporting Format - By others | HCL - S | SC - R | Consult - R | Hold Points Sign off - | Remarks - By others | Reporting Format - Welder Qualification
HCL - R
SC - I
Consult - R
Hold Points Sign off - Hold Point
Remarks - Welder certification reviewed and approved prior works Hawkins- ITP-000061
03 - Trenches and routes inspections
Frequency - Per section
Spec/standard - Drawings Spec 4.23.2 /7.3.4.5/7.3.4.8
Acceptance Criteria - Installed as per project drawings and specifications
Measuring Devices - Visual
Reporting Format - Site coordination
HCL - I
SC - I
Consult - S
Hold Points Sign off -
Remarks - Suitable route and bend allowances
04 - Duct alignment check
Frequency - Per section
Spec/standard - Project drawings / layout 4.23.2
Acceptance Criteria - Installed as per drawing
Measuring Devices - Visual
Reporting Format - NA
HCL - M
SC - I
Consult - R
Hold Points Sign off -
Remarks - No excessive bends or misalignments
05 - Inspection of duct cleanliness and joint
Frequency - Before welding
Spec/standard - ISO 13954 5.10.3
Acceptance Criteria - Ends scraped, dry, and clean
Measuring Devices - Visual
Reporting Format - OMX Quality check sheet
HCL - M
SC - I
Consult - R
Hold Points Sign off -
Remarks - Free of debris, scratches, moisture
06 - Fusion setup – pipe end scraping, machine check
Frequency - Each weld
Spec/standard - ISO 13954 / ISO 13955
Acceptance Criteria - Scraping complete, scan barcode
Measuring Devices - Scraper / EF machine
Reporting Format - OMX Quality check sheet
HCL - M
SC - M
Consult - R
Hold Points Sign off -
Remarks - Pre-weld approved by supervisor before fusion
07 - Electrofusion weld execution
Frequency - Each weld
Spec/standard - ISO 13955 12.4.6. 12.5.2
Acceptance Criteria - Parameters met; uniform bead
Measuring Devices - EF machine logger
Reporting Format - Fusion log / OMX Quality check sheet
HCL - M
SC - Sub
Consult - R
Hold Points Sign off -
Remarks - Fusion data logged and bead visually compliant Weld number time and date next to weld.
08 - Post Weld visual inspection and cooling
Frequency - Each weld
Spec/standard - ISO 13955 / 13956
Acceptance Criteria - Bead uniform, cooled per spec
Measuring Devices - Visual
Reporting Format - OMX Quality check sheet
HCL - s
SC - R Sub
Consult - R
Hold Points Sign off -
Remarks - Cooling time respected; weld integrity confirmed.
09 - Weld traceability and documentation
Frequency - Each weld
Spec/standard - 7.3.4.9
Acceptance Criteria - Barcode and weld ID logged
Measuring Devices - Log Sheet
Reporting Format - OMX Quality Check sheet
HCL - S
SC - Sub
Consult - R
Hold Points Sign off -
Remarks - Log completed and ID matched field location
10 - Post Weld inspection
Frequency - Project Scope
Spec/standard - DP001-MMD-SPC- EL-Z-Z-001 12.5.2
Acceptance Criteria - CCTV footage of below ground ducting, duct contains no debris or penetrations that could damage cable sheath when pulled
Measuring Devices - CCTV
Reporting Format - Video
HCL - S
SC - Sub
Consult - R
Hold Points Sign off -
Remarks - Submission of CCTV footage before handover
11 - Electro fusion welder calibration
Frequency - Project Scope
Spec/standard - As per manufactures specification
Acceptance Criteria - Electro fusion welder calibration certificate
Measuring Devices - Calibration certificate
Reporting Format - Certificate
HCL - S
SC - Sub
Consult - R
Hold Points Sign off -
Remarks - Submission of calibration certificate before handover
12 - Draw Cord
Frequency - Each conduit
Spec/standard - 12.3.8
Acceptance Criteria - 5 kn
Measuring Devices - N/A
Reporting Format - QC checklist/ photograph
HCL - M
SC - Sub
Consult - R
Hold Points Sign off -
Remarks -
13 - Hot Bending of HDPE Ducts
Frequency - Direction change
Spec/standard - DP001-MMD-SPC- EL-Z-Z-001 7.3.4.5
Acceptance Criteria - Minimum bending radius of 2m
Measuring Devices - Measuring tape
Reporting Format - QC checklist
HCL - I
SC -
Consult -
Hold Points Sign off -
Remarks - Heat apply using controlled hot air: duct support during bending. Cool down in place to retain shape
14 - Installation of tracer wire
Frequency - Each installed duct
Spec/standard - DP001-MMD-SPC- EL-Z-Z-0017.3.3.11
Acceptance Criteria - Wire securely fixed on top of duct, continuous, accessible at both ends
Measuring Devices -
Reporting Format - QC checklist Photograph
HCL - M
SC - T
Consult - R
Hold Points Sign off -
Remarks - Tracer wire to be installed above duct, secured at 3m intervals. Ends terminated in accessible pits or boxes
15 - Installation of Warning Tape and Polymeric Cover (Mag slab) during Backfilling
Frequency - Each installed duct
Spec/standard - AS/NZ3000. 2018
Acceptance Criteria - Install 300mm above top of duct.
Measuring Devices - Tape measure, visual check
Reporting Format - . QA checklist / photograph
HCL - M
SC - W
Consult - S
Hold Points Sign off -
Remarks - Materials supplied by Omexom, installation by civil contractor. Hold point required prior to backfilling. Supplier to verify delivery and provide installation guidance. Coordination required to ensure correct placement and documentation.
16 - Pit to Duct Jointing Process
Frequency - Each duct at each pit
Spec/standard - DP001-MMD-SPC- EL-Z-Z-0017.3.3.12
Acceptance Criteria - Manufacturer’s installation guidelines and project specifications
Measuring Devices - Secure, watertight connection between duct and pit; no gaps or misalignment
Reporting Format - Visual check, QA checklist / photograph
HCL - S
SC - R
Consult - S
Hold Points Sign off -
Remarks -
17 - Coordination with Waterproofing and Concrete Encasing
Frequency - At each interface with waterproofing or encasement
Spec/standard - MMD DP Buildings Elec Spec July 2024 7.3.3.12
Acceptance Criteria - IFC drawings and Sika Details (by others)
Measuring Devices - N/A
Reporting Format - By others
HCL - S
SC - R
Consult - R
Hold Points Sign off -
Remarks - By others