## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - SWITCHBOARD INSTALLATION – FINAL INSPECTION | itp
section | Details
checkpoint | 1 - Switchboard installation visual inspection
label | ACCEPTANCE CRITERIA - Check for visible internal/external damage
label | ○ Correct installation, level & mounting is satisfactory,
label | ○ Segregation and clearances from other services are satisfactory
label | ○ As per AS/NZS 3000 Standard
label | RESPONSIBILITY - TYRONE
checkpoint | 2 - Doors, cable access, live parts access
label | ACCEPTANCE CRITERIA - locks installed and in working condition
label | ○ Earthing to doors and escutcheons installed (if required)
label | ○ Ensure all insulated barriers, doors and escutcheons are installed and protection is adequate
label | ○ As per switchboard drawings and regulatory requirements
label | RESPONSIBILITY - TYRONE
checkpoint | 3 - MEN point
label | ACCEPTANCE CRITERIA - Installed and clearly identified (if applicable)
label | RESPONSIBILITY - TYRONE
checkpoint | 4 - Cable glands/cabling switchboard entry
label | ACCEPTANCE CRITERIA - switchboard meets required IP rating
label | ○ Sizes and type are correct/acceptable
label | ○ No undue stress on glands/cable or gland lock ring
label | ○ Glands tightened/entry points sealed/completed
label | ○ Pole fillers installed/live parts protected
label | RESPONSIBILITY - TYRONE
checkpoint | 5 - Metering and current transformers (CT)’s
label | ACCEPTANCE CRITERIA - Check meter is configured to the installed CTs ie. ratios are correct.
label | ○ Meter readings and communication to BMS have been checked and verified.
label | ○ VTs and CT links are removed.
label | RESPONSIBILITY - TYRONE
checkpoint | 6 - Identification, labelling & signage
label | ACCEPTANCE CRITERIA - Completed and correct as per regulatory requirements and switchboard drawings
label | RESPONSIBILITY - TYRONE
checkpoint | 7 - Circuit schedule/switchboard legend
label | ACCEPTANCE CRITERIA - Switchboard legend (if applicable) has been printed and installed inside door. No pen or pencil markup on the legend ie. all completed - or changes actioned for reprint and reinstallation.
label | RESPONSIBILITY - TYRONE
checkpoint | 8 - Final Check
label | ACCEPTANCE CRITERIA - Switchboard left clean and tidy
label | ○ Doors are installed and closed
label | RESPONSIBILITY - TYRONE
checkpoint | 9 - Identify any outstanding or rectification works required
label | ACCEPTANCE CRITERIA - Provide details in the comments below
label | RESPONSIBILITY - TYRONE
checkpoint | 10 - COMPLETION POINT: Installation completion
label | ACCEPTANCE CRITERIA - All items above have been completed
label | ○ Any outstanding items, please make comments below for future action by undersigned
label | ○ Completed ITP provided to site manager/ supervisor/commissioning manager
label | RESPONSIBILITY - INSTALLED AND CHECKED BY TYRONE INSTALLER/REPRESENTATIVE:
holdpoint | SIGN:
checkpoint | 11 - ITP/OM Manual documentation
label | ACCEPTANCE CRITERIA - Final check of switchboard has been completed. - Issues/defects have been closed out/ documented for action.
label | ○ All documents have been submitted
label | RESPONSIBILITY - TYRONE COMMISSIONING MANAGER/ SITE SUPERVISOR/ MANAGER:
checkpoint-no-status | COMMENTS:
checkpoint | CHECKED APPROVED BY TYRONE COMMISSIONING MANAGER/ SITE SUPERVISOR/ MANAGER:
signoff | SIGN: