## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP2-010.005 ITP Retaining Wall 4 Magnum Block | itp |  |  |  |  | DN1210-SP2-010.005 ITP Retaining Wall 4 Magnum Block Rev 0
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIALS, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 3.1 - Methodology
label | Detail - The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Approved Methodology
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Ecology Sign Off
label | Detail - Confirmation from Ecology that earthworks and sheet piling can proceed
label | Acceptance / Conformance Criteria - Email
label | Standard / Specification - Internal Hold Point
label | Verifying Document - Email from Ecology NZ
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.3 - Erosion & Sedimentation Controls
label | Detail - Confirm that Erosion and Sedimentation Controls bunds are in place
label | Acceptance / Conformance Criteria - As-built Completed
label | Standard / Specification - Internal Hold Point
label | Verifying Document - ESC As-built
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.4 - Geotextile
label | Detail - The Contractor shall submit the full details of the Class C non-woven geotextile fabric to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.5.7 Appendix V
label | Verifying Document - Material certificate/NTC
label | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Crushing Resistance: Drainage aggregate
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Appendix XVIII PS.17.6.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Partical size distribution: Drainage aggregate
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - DM40/20 OR DM20/7 Grading Envelope
label | Standard / Specification - Appendix XVIII PS.17.6.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test per 100m3
label | ○ Results to Engineer 2wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Weathering Resistance: Drainage aggregate
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CA or better
label | Standard / Specification - Appendix XVIII PS.17.6.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Crushing Resistance: Structural Fill
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Appendix XVIII PS 17.4.3
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Partical size distribution: Structural Fill
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Max Particle Size 53mm
label | ○ Max 10% passing 13.2mm sieve
label | Standard / Specification - Appendix XVIII PS 17.4.3
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test per 100m3
label | ○ Results to Engineer 2wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Weathering Resistance: Structural fill
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CA or better
label | Standard / Specification - Appendix XVIII PS 17.4.3
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 3 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Magnum Stone Block
label | Detail - Magnum Stone blocks are to be supplied by an approved supplier.
label | ○ Concrete Compressive Strength
label | ○ Moisture Absorption
label | ○ Defects, chips and cracks
label | Acceptance / Conformance Criteria - Minimum 28-day
label | ○ Compressive Strength of 30MPa (min.)
label | ○ Less than 6%
label | ○ Every Block
label | Standard / Specification - NZS 3104: 2003, AS/NZS 4456:2003 Method 14
label | Verifying Document - Supplier to provide QA Documents, Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.13 - Subsoil Drainage
label | Detail - Shall be 110mm diameter NZTA F/2 compliant smooth bore perforated pipe with filter sock
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - P.S. 21.5.17
label | Verifying Document - Material certificate/NTC
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – CONSTRUCTION - CUT SUBGRADE TESTING
checkpoint | 4.1 - Cut Subgrade Inspection
label | Detail - Engineer to inspect all foundation surface inspections
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Cut Subgrade Testing - Cohesive Soil, Shear Vane
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU: > 60kPa
label | ○ Single Test Min SU: >50kPa, 2-3m deep
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 0.5m interval, 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3 - Cut Subgrade Testing - Non-Cohesive Soil, Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.4 - Cut Subgrade - Import Structural fill, Release of Hold Point
label | Detail - To release the subgrade hold point and be able to start placing the Magnum Stone Blocks, the Contractor shall provide written certification that all inspected and tested subgrade complies with the requirements in PS 16.6
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.9.3
label | Verifying Document - CONQA Approval
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 – MAGNUM STONE BLOCK
checkpoint | 5.1 - Leveling Pad
label | Detail - The Contractor shall construct a 150 mm thick levelling pad on top of the subgrade using AP40 to accept the Magnum Stone Block wall.
label | ○ Aggregate to be placed on geotextile filter fabric
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - As per Drawing (23273502-WSP-DR-GEO-0414)
label | Verifying Document - Site Photo / Checksheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Magnum Stone Block installation
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2 - Installation of blocks
label | Detail - Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - As per Drawing (23273502-WSP-DR-GEO-0427)
label | Verifying Document - Site Photo / Checksheet
label | Testing Quantity Required (based from schedule qtys) - Each layer
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 5.3 - Drainage Installation
label | Detail - A 110mm Drainage pipe wrapped in filter sock is to be installed along the internal perimeter of the blocks.
label | ○ Core through Magnum Stone blocks at 10m c/c, install PVC subsoil outlet.
label | ○ Internal block void hardfill to be 20/40 drainage aggregate or similar approved by engineer.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.5.8, PS 16.6.10, PS 17.6.3, TNZ F/6
label | Verifying Document - Delivery Dockets/Installation Checksheet
label | Testing Quantity Required (based from schedule qtys) - No less than 24 hours prior to placement of backfill
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 5.4 - Backfill Installation
label | Detail - All backfill is to be installed in 300mm lifts and tested as below
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - As per Drawing (23273502-WSP-DR-GEO-0414)
label | Verifying Document - Site Photo / Checksheet
label | Testing Quantity Required (based from schedule qtys) - Each layer
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 5.5 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Structural Fill
label | — Min CIV 18
label | — Ave CIV 20
label | ○ Non-Structural Fill
label | — Min CIV 10
label | — Max CIV 12
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.6 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | — Min >92% of MDD
label | ○ Non Granular Material
label | — Max Air Voids 8%
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 6 – AS-BUILTS
checkpoint | 6.1 - As-Builts
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Acceptance / Conformance Criteria - As-build record
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Survey Records/redpen markups
label | Testing Quantity Required (based from schedule qtys) - During Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature