## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | Ω (Deprecated) FH-ZU2-QU-ITP0013 - PCC Pavements - Rev 2 (1.6 Checkpoint) | itp | ITP013 - PCC Pavements
5a37da6d-0098-5585-adcb-850f5634087d | section | 1.0 - Preliminary Activities
78f2eb97-4d27-5397-9616-d0974c63c400 | checkpoint | 1.1 - Check for correct documentation
2907e598-3fa6-573d-bd16-0574524c85dd | note | Frequency - Prior to commencing works
b9918449-71ab-57a3-8fb9-16b7aa22b72c | note | Acceptance Criteria - Current revision of drawings, technical specifications and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
e00f65c1-9d2f-5be2-a812-fb0d735c5f0c | note | ○ Current revisions of these documents to be obtained via Aconex or ACC.
fcc655b9-fbb7-56a9-a250-a3e6ddfcdac9 | note | Reference Documents - Current Revisions in Aconex or ACC
7c8e2404-1102-5ee8-a17e-bf5965da5090 | note | Inspection/Test Method - Verify
bbf512ae-8c96-50fe-ab8e-041fb46b2033 | note | Record of conformity - This ITP signed
50155e9b-2035-554f-a3b9-dc1292319b1d | note | HP*
c857cb14-757e-552e-a08f-8d2f33488cba | note | Responsibility - Project / Site Engineer
7985f0ba-6f2a-53e3-86b8-8d2bb4b8fa9e | date | Date Completed:
457fc29c-5478-51c3-a60f-061f5ba4ad0d | checkpoint | 1.2 - Implementation of all measures and controls
f76991b4-2e34-58da-a5a7-07c02f17fe3d | note | Frequency - Prior to commencing works
c651df4c-8e29-5d2d-9375-da49ffe74cdf | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS
48b636c8-8a77-5c74-8d2b-2a67f6f57838 | note | Reference Documents - PSP, EMP, TMP, SWMS, WMS
396ec348-d33a-5b4c-8f22-e1c5c2acb765 | note | Inspection/Test Method - Visual Inspection
7cf37097-e48c-53c0-8bbf-4d645002a09d | note | Record of conformity - This ITP signed
811f2fa4-250a-5ede-9e06-77ba08912d60 | note | HP*
3d378ac4-0b26-56cd-9c2f-4fba1d62a6ed | note | Responsibility - Project / Site Engineer
91cced02-0c77-52ba-9865-19bd3dc69329 | date | Date Completed:
7e28438e-f51f-55d2-9f71-e8c9c5437afc | checkpoint-no-value | 1.3 - Mix Design Report Submission and Approval
4507ccca-25f6-5ce8-996e-f117534195a8 | note | Frequency - Prior to commencing works
5b39bd65-bb88-5915-86f4-2d1b0165bfb7 | note | Acceptance Criteria - Theoretical mix design and preliminary trial mix results submitted in a report to the Contract Administrator for review and acceptance prior to full trial mixing.
98bbfa8e-9bff-5a20-994c-001991a18233 | note | Reference Documents - Beca Spec 002 - 11.5.3
85cbfe58-d6b7-5804-b260-f5c730fa1f47 | note | Inspection/Test Method - Verify
a862afaa-1ec6-58ad-b24c-6eacb2fca986 | note | Record of conformity - Aconex Reference
cb6a07a3-cb1d-5b7a-a016-a5b1ac8a4d5b | note | HP
ab6e881a-aab1-5c9a-9521-b29a5139afc2 | note | Responsibility - Project / Site Engineer, Principal’s Representative
2d313683-5885-50c2-9eb2-66762b61c470 | note | Date Completed: 01/06/2024
3211cacc-9c39-5b9a-9514-0f07b88fe014 | note | Principal's Representative - BecaCPL-GCOR-000846
05fade62-fb69-5838-88b0-d4e2cca8452e | signoff | AUTHORITY HOLDPOINT
1d417a20-1781-524c-8f26-32728ee4d344 | checkpoint-no-value | 1.4 - Job Mix Formula
8b89fdfc-d9d1-527e-8a5a-973029e07bae | note | Frequency - Prior to commencing works
7614f9ac-8801-59ee-a747-c145e86ec76c | note | Acceptance Criteria - The Job Mix Formula must state the mass proportion of all ingredients per cubic metre of concrete. The allowable limits in the Job Mix Formula (when compared to the agreed theoretical concrete mix design) must be in accordance with Table 11-2 of BECA 11.5.4 (see notes section).
57149b72-6f59-5d04-86e7-4525b9b35b55 | note | Reference Documents - Beca Spec 002 - 11.5.4
b51a7841-f170-5d47-8f36-c8cd85564a64 | note | Inspection/Test Method - Verify
503bc281-5ed7-58d1-aa06-fb549f758ad5 | note | Record of conformity - Aconex Reference
93011ee0-68cc-5e96-bafe-17d75aa2198c | note | WP
5375edff-176c-5d66-988f-1c14a5004c0b | note | Responsibility - Project / Site Engineer, Principal’s Representative
71a389be-f505-5ac1-9f06-a680d8c8848e | note | Date Completed: 30/05/2024
e0d8cbf6-790b-5a21-8182-cc284a5187fa | note | Principal's Representative - BecaCPL-GCOR-000839
ea2ed3cc-4240-5302-a62f-08cf18713d1a | checkpoint-no-value | 1.5 - Production and Construction Trials
e5fdbc46-719d-5942-8304-c39bd3e2059a | note | Frequency - Prior to commencing works
19475a37-83f9-5590-bea2-9dc4e0ea4477 | note | Acceptance Criteria - A production and construction trial must be completed as per the requirements in the specification.
1b130452-3c22-5b57-96d2-d425c83968d6 | note | ○ The results, control procedures, construction methods and completed trial pavement will be presented for review and approval by the Contract Administrator.
468ed8d3-72e9-5e5e-9e7c-4cd84000cb62 | note | Reference Documents - Beca Spec 002 - 11.6.1 to 11.6.4
4077b7bd-82bc-5ac9-8abf-482efd9b2c4b | note | Inspection/Test Method - Verify
df708af5-9f11-534c-af7d-32a465b86af9 | note | Record of conformity - Aconex Reference
528f6782-a3f3-5bce-bf62-414e8a0aa3b5 | note | HP
08bcb58d-ea03-5f6c-8d87-068ee9a666c4 | note | Responsibility - Project / Site Engineer, Principal’s Representative
a044b821-045c-516d-806b-4adbf19eae93 | note | Date Completed: 19/08/2024
3f498654-9c27-5215-b0b9-26044de9c986 | note | Principal’s Representative: DCWC Mgt-GCOR-009917
73453e67-147f-57a2-8c4e-a327bf10ac4a | signoff | AUTHORITY HOLDPOINT
e5f4e390-d859-5bb8-8754-88a6610c4a41 | checkpoint | 1.6 - Curing Compound Material Submission
9b855dfe-dcaf-5780-a60c-3107674b9ed2 | note | Frequency - Prior to use of curing compound
83186ab9-3183-5a0d-8af9-d95cee37cc97 | note | Acceptance Criteria - Membrane curing compounds shall be a white pigmented type confirming to AS 3799, Type 2. Wax based compounds shall not be used.
f420a157-3565-5505-8230-a10228b203ee | note | ○ No compound shall be used without written approval by the Contract Administrator.
25cd7b38-ee48-596d-b07d-17fa9f379210 | note | Reference Documents - Beca Spec 002 - 11.4.11.1
60e9e8c5-b8ed-5bd9-a26e-3382693460cc | note | Inspection/Test Method - Verify
c0fd41e0-1e99-5cb1-b48f-4c618b1231d9 | note | Record of conformity - Aconex Reference
725ec045-95ca-572c-9b4e-9c371e3ec53f | note | HP
f35c5635-fb93-5f33-b60d-c63641ec0278 | note | Responsibility - Project / Site Engineer, Principal’s Representative
696d3ed0-b889-5758-aec5-19902ec4d780 | note | Date Completed: 22/05/2024
a818c49e-eaec-5a25-8530-c20a4d5b18bd | note | Principal's Representative - BecaCPL-GCOR-000791
cae769b2-61e3-5ca9-9808-11d45f78e1b4 | signoff | AUTHORITY HOLDPOINT
ba929a80-28cc-56d4-987f-a6898a2999b4 | checkpoint | 1.7 - Impermeable Blanket Material Submission
761302c5-7075-519c-9d7b-694b9d82823c | note | Frequency - Prior to use of impermeable blanket
b5091c95-16c2-5ef1-a417-df9805b7c0ab | note | Acceptance Criteria - If required to be used, impermeable blankets shall comply with the requirements of ASTM C.171.
db67cc05-0893-5f00-99ff-d92e8f8fca9b | note | ○ The blankets shall have sufficient strength and weight to meet the required conditions of service and shall be approved by the Contract Administrator before use.
46bd5aaf-a712-5584-9956-c7ddf7e3671b | note | Reference Documents - Beca Spec 002 - 11.4.11.2
40d7a594-43f0-57e3-8f8e-430fd5f4061f | note | Inspection/Test Method - Verify
6af78c57-3fbc-5181-a1c9-23ad09bdf0ba | note | Record of conformity - Aconex Reference
bb338aed-f7e8-569f-995d-e97baa3ee2b6 | note | HP
4768e536-db22-57da-8f25-3e8dfeda92eb | note | Responsibility - Project / Site Engineer, Principal’s Representative
fdd17bfc-d0c1-55b5-88b6-5f825b05769a | date | Date Completed:
6c2414bf-bba4-528f-9da8-08464c25f39d | signoff | AUTHORITY HOLDPOINT
5885abc0-a77e-5d54-803d-3fd1515e6818 | section | 2.0 - Pre-Placement Activities
16ee8263-a125-5876-ab26-79db8c104fdd | checkpoint | 2.1 - Formwork Installation
65a8de96-f184-5a0b-af0f-2fd24a991fb5 | note | Frequency - Prior to placing concrete
1f1a7b28-fea3-5aa9-b6c2-a714d1d257f5 | note | Acceptance Criteria - Formwork must rest firmly on the base to eliminate gaps and ensure no leakage of concrete will occur during placement.
a5ca7930-6074-5fd1-9a44-03273fc974f8 | note | ○ Formwork must be secured into position and locked together during placing, spreading and finishing of the concrete.
1e88b2e3-5eaf-5da0-8afd-bc24150e6b21 | note | ○ The top of the form must not deviate by more than 3mm from the required level.
2f868783-cb5a-598f-8cfa-65f1caec0add | note | ○ The form face shall be vertical and not vary more than 6mm from the required alignment.
31c77cba-682b-53dc-87ae-5baea14f37a7 | note | Reference Documents - Beca Spec 002 - 11.8.1.1
6ef34b37-ea17-5ff3-ae4b-e99491dfaaaf | note | Inspection/Test Method - Visual inspection
a9ebca94-422a-50d0-83cf-12869d540e0b | note | Record of conformity - This ITP signed
f249917f-23af-5d15-86c4-a29b6426d2d9 | note | WP
5b8afdc5-c63f-53f0-a861-23a7b328949e | note | Responsibility - Project / Site Engineer, Principal’s Representative
7409513b-e0b7-52ca-8954-8936dd8759d3 | date | Date Completed:
fd1f1b65-94f0-536d-a050-a134453028a2 | checkpoint | 2.2 - Pre-pour checklist
ab32c07d-9a9d-53ce-b9b5-123154b34553 | note | Frequency - Prior to placing concrete
18c8a68c-2470-5f7a-a086-63658f6c6540 | note | Acceptance Criteria - Completion of the pre-pour checklist: CL013A – Pre-Pour Checklist which details various checks required for formwork, reinforcement, joints and the pour area.
b28cd113-7abb-5137-9cf8-2b694ff03494 | note | Reference Documents - Beca Spec 002 - 11.8, 11.10, 11.13
be572c26-123b-5025-998f-2abc96f9640b | note | Inspection/Test Method - Visual inspection
d984894d-908e-5b6f-ad12-8ad9faed8fba | note | Record of conformity - CL013A, This ITP signed
d8b6310c-914c-575c-865b-9033ff0b5181 | note | HP*
7a14446c-e20a-5723-ad87-0f7c48d3e202 | note | Responsibility - Project / Site Engineer
ae723b76-57c3-5197-94af-ab6ad7d4b3a6 | date | Date Completed:
ca0fa0ec-49b6-5c2d-9237-de158062e778 | checkpoint | 2.3 - Pre-pour inspection
0d5d906e-fcbc-570f-9189-0a7d6e0ee14a | note | Frequency - Prior to placing concrete
36f2b982-f113-5f64-af91-09c84a5c2070 | note | Acceptance Criteria - The area in which concrete is proposed to be placed shall be inspected and checked immediately prior to commencement of placing.
95f8d6ff-6ebc-58a5-82a5-cc48c697c8d9 | note | Reference Documents - Beca Spec 002 - 11.9.1
ec12b8e5-7bac-50e6-a482-57ff3e913491 | note | Inspection/Test Method - Visual inspection
4a0db4bd-ded3-57d5-a929-3ed0243e8d0e | note | Record of conformity - This ITP signed
851d29f9-48e1-59c4-915c-64990356ff5b | note | WP
74492460-66c9-548e-ae28-8c4b837302a0 | note | Responsibility - Project / Site Engineer, Principal’s Representative
39c274b1-0ec0-570d-bc94-d540fdbfb401 | date | Date Completed:
d9388486-1250-5ff8-b9ad-8d44105f357b | checkpoint | 2.4 - Weather Forecast Checks
d43c1ab9-5201-5007-b19e-cb14e0ad0be0 | note | Frequency - Prior to placing concrete
0a8b717f-0ec7-5292-8236-466654675c31 | note | Acceptance Criteria - Check the weather forecast for unfavourable conditions (rain, wind, hot weather or cold weather) on the day prior and immediately before confirming
ed0bef5e-c778-5d14-9786-2791f8899413 | note | Reference Documents - Beca Spec 002 - 11.9.5.1
c980c01d-b749-5c67-a48b-015656e8fe01 | note | Inspection/Test Method - Verify
5740e4c3-89c1-5bdd-a073-809a08fe31b8 | note | Record of conformity - This ITP signed
a2371590-dbcb-552a-9f00-aa021e745a5c | note | HP*
20538a2e-8184-5d34-a5e7-dbca391524b0 | note | Responsibility - Project / Site Engineer
10ba42c8-0df4-561f-89da-75552b10f2ca | date | Date Completed:
cd1921f5-0447-55dd-a906-346b6c56d7e0 | section | 3.0 - Placing Concrete
4ce1dbde-921b-5f12-92f2-cb172108eb2c | checkpoint | 3.1 - Place, Spread and Compact Concrete
7665b879-a2be-524d-ac3e-ecf0582e021e | note | Frequency - Each concrete pour
723f9130-2ba8-5f32-8090-706d2a025af7 | note | Acceptance Criteria - Concrete placement must be at a rate appropriate to achieve a consistent high quality resulting pavement.
80257cee-5638-514e-a8ff-24d1c99ba788 | note | ○ During placing, the concrete must not drop freely by more than one metre onto the base of the paving lane.
ede5d52d-6d18-5925-a3b4-ed8eb0fbe3a1 | note | ○ Concrete shall be placed uniformly over the width of the slab and in a way to minimise segregation.
fb7bb21a-0517-5585-8cba-f749e3db01cb | note | ○ Concrete to be adequately compacted by internal mechanical vibration.
47ad46e2-d1bd-59d1-992d-bbe52b4d9cbd | note | Reference Documents - Beca Spec 002 - 11.9.1, 11.9.4, 11.11.2.1
638de61b-8375-576b-9262-504c09b1a131 | note | Inspection/Test Method - Visual inspection
39a74bcb-e849-515c-9206-afe7bbf2cd12 | note | Record of conformity - This ITP signed
73d72013-09b1-5d43-9fe7-bab4cde0554c | note | IP
bc0e21bc-775d-5d51-b0cb-529089e2bd84 | note | Responsibility - Project / Site Engineer
4fad147d-594c-5d20-96cf-f52b3f9b9d35 | date | Date Completed:
01340969-6666-50d8-81f7-9de3ba0476a1 | checkpoint | 3.2 - Concrete Deliveries
8246b40e-a538-5ae2-a7e5-ff27722c2f97 | note | Frequency - Each concrete pour
ff9bb630-b1de-5601-afdb-7766627168d9 | note | Acceptance Criteria - Each concrete delivery to site is to be recorded on CL013B – Concrete Pour Record Sheet.
c719bd61-97e4-5c4c-84ed-af3fe5c02149 | note | ○ Concrete shall be placed within 90 minutes from the time of batching and before the concrete has attained its initial set.
fb71dde1-c897-5894-867b-60edb818ef6e | note | ○ The pour location, direction and order to be recorded on CL013C – Load-Batch Traceability.
04107314-7b34-53c4-8165-e6655e2e25de | note | Reference Documents - Beca Spec 002 - 11.9.1
1ad59df4-04e9-5aaa-acc6-fcecf0a20d1e | note | Inspection/Test Method - Verify
3945ca57-c77b-5137-bdc3-c380e553e0df | note | Record of conformity - CL013B CL013C, This ITP signed
b03e5d32-467f-5422-9751-5cd135c27c28 | note | IP
45e148b9-6d9b-5f88-a000-ad7e6419a0c2 | note | Responsibility - Project / Site Engineer
ba507cfd-70e3-534c-bfd9-36d529c0cfe7 | date | Date Completed:
a8846c82-3dab-5b97-8463-d576a7c411cc | checkpoint | 3.3 - Evaporation Rate
620b32c5-666d-5ac5-9d40-c190badf7dab | note | Frequency - Each concrete pour
65d8d07b-bb3e-5b85-89c1-9dcc1f61a1be | note | Acceptance Criteria - Concrete must not be when the evaporation rate from the surface of unprotected concrete is in excess of one (1) kg/m²/hr.
5245a27c-ae3a-572e-82a2-c0a5168e075d | note | ○ When the evaporation rate exceeds 0.6 kg/m²/hr, precautionary measures to prevent plastic shrinkage shall be taken.
1f0914c8-b9e4-5490-8cb3-4394352605b4 | note | ○ Evaporation rate to be recorded on CL013D – Rate of Evaporation.
a658725f-486e-574f-83ff-b8cc2eb40700 | note | Reference Documents - Beca Spec 002 - 11.9.5.2
1f4e2277-f1ef-5141-bc8f-dd05fc26f7a0 | note | Inspection/Test Method - Verify
f76b01c6-bd98-5ff3-9e87-82bc36a34708 | note | Record of conformity - CL013D, This ITP signed
3e4d1077-a8f0-5a0f-9fa6-30268bc119ef | note | IP
acaccec8-ef2c-51a4-a20c-aef89753f903 | note | Responsibility - Project / Site Engineer
cb08b5a5-0abd-51b0-8c20-fdbdb49bb359 | date | Date Completed:
6bde1751-12a1-5704-bd61-b45ba632ac70 | checkpoint | 3.4 - Hot Weather Concreting
744e946e-f126-5621-9e7e-a4972f3ef9ba | note | Frequency - Each concrete pour
a1e7bd7d-1f73-5185-bd3f-77e0967bec30 | note | Acceptance Criteria - Undertake additional precautions when placing concrete in hot weather.
7d9e13d6-291a-5804-8258-3aaced05a93f | note | ○ Ensure the concrete is placed at the coolest temperature practicable – the concrete temperature should not exceed 32°C.
78f48efa-0ae5-5dc1-8f31-3313b3109889 | note | Reference Documents - Beca Spec 002 - 11.9.5.3
d831f3f8-c332-5686-bda4-38c911c66549 | note | Inspection/Test Method - Verify
10d0b85b-3d61-5194-8f9d-e39d2c381564 | note | Record of conformity - CL013B, This ITP signed
4807115e-733f-50c1-b298-52829bceea88 | note | IP
37c77533-2901-5453-b540-56df0c72adc4 | note | Responsibility - Project / Site Engineer
60155a52-54ab-55ff-9c03-8d923452d239 | date | Date Completed:
0a674bc7-9c0b-59d4-b89b-165fe5156d0a | checkpoint | 3.5 - Cold Weather Concreting
b46d4377-743b-5e2c-9a62-72656b686c51 | note | Frequency - Each concrete pour during ‘cold weather concreting’ conditions
7fe02ad8-3085-5f3a-ad2a-0d86841ffc75 | note | Acceptance Criteria - Cold weather concreting applies when placing concrete when the temperature of the air, aggregates or water is below 10°C.
d01a9e14-2976-5bf7-af7e-f001c89aa7a4 | note | ○ Placement of concrete can only proceed if the ground temperature at the concreting site is greater than 5°C and the temperature of the concrete is not below 10°C.
14bec05b-75b6-5cbd-8313-7107a72b00fb | note | ○ Refer to checklist CL013E – Cold Weather Concreting for ground temperature records.
2c83eea4-ede8-58de-8a96-8fdc2ca50a2d | note | Reference Documents - Beca Spec 002 - 11.9.5.4
5400d6da-e277-5552-934d-295719475b4a | note | Inspection/Test Method - Verify
0cf4e0f5-f7b0-591c-a4bc-a74cc1925e3f | note | Record of conformity - CL013B CL013E, This ITP signed
f7ee5f93-57e9-570b-80b5-7e193fd5587f | note | IP
4121e0e9-6a3c-5dea-90e4-8dea93d0437c | note | Responsibility - Project / Site Engineer
16188178-5de4-56d5-bf57-fb2443ec071b | date | Date Completed:
bce17218-2b32-50e2-99bf-8851b7031e92 | checkpoint | 3.6 - Concrete Surface Finishing
b26ed40c-f7fe-5c69-a471-0ad5980c219a | note | Frequency - Each concrete pour
3dd3cb8a-4d02-5a4b-a302-32045875d4e6 | note | Acceptance Criteria - Finishing operations shall compose transverse finishing, longitudinal straight-edge finishing, floating and broom finishing, in that order.
53be0521-6bdd-50fc-b99c-5d2a91eb7f37 | note | ○ Finishing operations must be started immediately after compaction of the concrete and completed as soon as possible but not later than 90 minutes from the time of batching and prior to the concrete attaining its initial set.
2ba31877-3f8d-5551-bf43-08e177e81c36 | note | Reference Documents - Beca Spec 002 - 11.11.2.2
e09b32d0-416e-5346-9c9b-1220537934c9 | note | Inspection/Test Method - Visual Inspection
6e7e4584-a8b0-595f-a24d-de612f1127a2 | note | Record of conformity - This ITP signed
ad934164-50ae-59cb-98b2-675b58179b25 | note | IP
699e0910-0d47-5413-9c83-c52b19be34c6 | note | Responsibility - Project / Site Engineer
6abdad8c-dc11-55fd-8218-36822687b6ab | date | Date Completed:
d4da5116-30ab-56c9-b1eb-849f5003fc96 | section | 4.0 - Sampling and Testing Concrete
43ff8655-1595-5766-8438-ea3569c93eaf | checkpoint | 4.1 - Slump
e7dc755c-ff25-50ee-96af-ff0dab3dcd19 | note | Frequency - 1 test every 2 trucks
9fbac8e6-40ae-5a64-ae00-e85f95490dd9 | note | Acceptance Criteria - 60mm +/- 10mm
1e1c2738-c8ef-566d-b4ef-c0a06b1b95d1 | note | Reference Documents - Beca Spec 002 - 11.24.17, BecaCPL- GCOR- 000846
631b6b02-f4ee-54f6-aab2-f4606e4be2b8 | note | Inspection/Test Method - AS 1012.3.1
6e0d6122-3d83-517b-9fb4-9810dfb73c77 | note | Record of conformity - NATA Test Certificate
3799165a-793c-5f52-9e99-1bc8e66aa85d | note | TP
f33f7e7f-5c6b-5a6f-90b3-368d440763fa | note | Responsibility - Project / Site Engineer, Laboratory Technician
edc8ffe1-57f1-5325-886e-40e630995883 | date | Date Completed:
df8751f1-b783-5ced-bb43-a84f6efb9e3e | checkpoint | 4.2 - Temperature
0c42cd12-866c-585a-869b-e826adc3da04 | note | Frequency - 1 test every 2 trucks
92d7b2a7-237c-52b8-badd-e661cea05acb | note | Acceptance Criteria - Minimum 15°C (except in cold weather concreting where minimum is 10°C)
1ac66703-6f4b-5503-a481-2cd5bf33c432 | note | ○ Maximum 32°C
065863ac-e20e-5236-a611-2c120f585201 | note | Reference Documents - Beca Spec 002 - 11.24.16
867d37cd-753b-5c5e-baa0-37d9c5934684 | note | Inspection/Test Method - AS 1012.3.1
ecc7394e-9e35-58b5-b477-c08cd31a0447 | note | Record of conformity - NATA Test Certificate
be4204fb-85e0-5c77-a84d-bf595ef132ea | note | TP
0b169908-fbcd-530e-a69b-735905db5c2b | note | Responsibility - Project / Site Engineer, Laboratory Technician
dd04c20d-b5c7-5091-8993-9cb5aee071da | date | Date Completed:
2ffe1a6e-8b66-57f5-bbd8-0c2e46eccdea | checkpoint | 4.3 - Flexural Strength (7 day)
506d83af-a213-50cf-bd4c-086b494c9637 | note | Frequency - First 5 lots: 2 Beams per 75m3 or part thereof.
d1c99a14-cafa-596a-96d4-30a78dab4373 | note | ○ After 5 lots: 1 Beam per 75m3 or part thereof.
4a796ae1-7593-5083-acbc-16b5ce896c8d | note | Acceptance Criteria - Results for information only
f079ae4f-0da6-55dd-8f57-d175df0f1741 | note | Reference Documents - Beca Spec 002 - 11.24.10
6f6c0f31-b5d0-51b0-b720-0309c7e52034 | note | Inspection/Test Method - AS 1012.11
909c13bc-855e-5784-919c-3711ccbebb19 | note | Record of conformity - NATA Test Certificate
85fe830c-74ec-52ff-b129-4a3ed94a9760 | note | TP
0c8466ea-46f8-563c-980b-4ccf33c2a639 | note | Responsibility - Project / Site Engineer, Laboratory Technician
7d92ade6-8787-586c-a9f9-909bcaec1671 | date | Date Completed:
f5e85626-3e87-51d9-b123-8dbe71828123 | checkpoint | 4.4 - Flexural Strength (28 day)
68bc7023-086e-52c4-a527-072e730877c5 | note | Frequency - First 5 lots: 2 Beams per 75m3 or part thereof.
25a96de9-b8aa-5d12-9823-ba69d74ca852 | note | ○ After 5 lots: 2 Beams per 75m3 or part thereof.
dc2be2b2-4f0f-552f-8dcf-b7bab6ae9120 | note | Acceptance Criteria - Mean of the pair of beams > 5.0 MPa Individual beams > 4.8 MPa
6f64e51f-d32c-5c63-8e3a-7d51f1de2841 | note | Reference Documents - Beca Spec 002 - 11.24.10
34161891-b4e6-5856-a5cd-40d95a043493 | note | Inspection/Test Method - AS 1012.11
3af3ca24-1695-54ac-ae7f-fbc32c179aab | note | Record of conformity - NATA Test Certificate
0da54949-117b-58bf-b3cd-c3583c3829b3 | note | TP
a3663f3b-081d-58c3-91a7-c63a62d9874a | note | Responsibility - Project / Site Engineer, Laboratory Technician
7eddf880-425d-5c79-88c0-4b9f42dd923a | date | Date Completed:
9e886210-4b93-5748-a95e-ad183ab45c95 | checkpoint | 4.5 - Air Content
beb5fad9-719b-5f31-9ca2-bbe8fea2632b | note | Frequency - 1 test per Lot
cce2068d-7751-5d08-b115-9c85be983a61 | note | Acceptance Criteria - 3% - 5% ±1%
cce38939-39dd-5930-b456-e385fde10ce4 | note | Reference Documents - Beca Spec 002 - 11.24.8, 11.24.9
4f873026-9a91-58f9-bd7f-32975b9c9630 | note | Inspection/Test Method - AS 1012.4.1 or 1012.4.2
96ae24eb-2d77-5f28-89c2-4f1dc3ced80b | note | Record of conformity - NATA Test Certificate
f0e67256-3950-55e7-a7f5-ff9fb9edfb96 | note | TP
c7616360-f69d-5c7a-a9a4-e385f182e23f | note | Responsibility - Project / Site Engineer, Laboratory Technician
eed76a32-8847-5b9f-bcd9-7ac60e6b2939 | date | Date Completed:
9ad6888c-fa3b-5efb-b8a6-dea67ddcb735 | checkpoint | 4.6 - Mass Per Unit Volume
249ca4b9-5f12-5647-bd16-61bb71132964 | note | Frequency - 1 test per Lot
914a1061-d7db-5862-80b3-2dc51c3bbd66 | note | Acceptance Criteria - Results for information only
d61bce60-4427-5438-a778-ac44dd2b9ac6 | note | Reference Documents - Beca Spec 002 - 11.24.9
56516493-bebe-5e10-94d5-968d50da156a | note | Inspection/Test Method - AS 1012.5
89fec65b-8936-51e1-b966-5a9bc9bb695e | note | Record of conformity - NATA Test Certificate
cea769a3-8529-5654-8e6d-9695b25c878c | note | TP
813e7f85-510e-53fa-b17a-6671485216dc | note | Responsibility - Project / Site Engineer, Laboratory Technician
7655c7ad-d1c4-5ddf-a170-5835f574c71f | date | Date Completed:
784088d9-4c0a-591a-bcd5-f66d2ffb7819 | checkpoint | 4.7 - Wet Analysis
343a3167-cf90-59c7-bf56-10568edf0ef9 | note | Frequency - 1 test per Lot
ed0a84e9-18b8-512b-89eb-0fa090f32c09 | note | Acceptance Criteria - Results for information only
a23c85d7-48fb-5dca-accc-8001ad078bf1 | note | Reference Documents - Beca Spec 002 - 11.24.9
b0493a50-ceb7-5173-b70b-785e23524ab0 | note | Inspection/Test Method - AS 1289.3.6.1
715add53-bd8f-5fd2-a2b2-69d474fbef00 | note | Record of conformity - NATA Test Certificate
79d6b9e1-35e3-5868-a636-e5b774e97e92 | note | TP
d74d9e31-040b-53aa-8098-f3eafa8096f7 | note | Responsibility - Project / Site Engineer, Laboratory Technician
c49d4dd6-001e-5b3d-acf4-c27d4f3d7767 | date | Date Completed:
21046b26-0f7a-50ea-a8d4-20fcdb40c85b | checkpoint | 4.8 - Concrete Core Analysis (Density & Compressive Strength)
44ef0abf-113d-5a24-b205-4a368131b77d | note | Frequency - First 10 lots: 6 cores per Lot
8dda6e55-4e3f-5481-a80c-36712dd44c50 | note | ○ After 10 lots: 1 core per 75m3 or part thereof
f698075e-11c4-5bff-b6a4-f3df2e4eb701 | note | Acceptance Criteria - Cores must be not less than 120mm diameter.
f121d421-0622-5526-b970-29ddf62c3769 | note | ○ Calculate the degree of compaction by comparing the density of individual cores with the average density of flexural test beams (exclude beams whose density is less than 97.5% of maximum theoretical density). Refer to notes section for acceptance requirements.
93ff3a2a-1e34-5537-a2c0-92305264f999 | note | ○ On third of the cores taken shall not be tested for density but shall be tested for compressive strength and results submitted for information purposes only.
8998f956-5b2b-5eba-abc6-3cc8f555afbd | note | Reference Documents - Beca Spec 002 - 11.24.12
81946f43-f32b-5770-847b-fca603623b71 | note | Inspection/Test Method - AS 1012.12, AS 1012.9
c579b5f9-7653-5159-950f-b218a132b5a9 | note | Record of conformity - NATA Test Certificate
d065c9e2-e7de-5724-81b2-3ff5c52b422c | note | TP
9d2eceff-0e85-554e-8aa1-6229bdbf671a | note | Responsibility - Project / Site Engineer, Laboratory Technician
59c3b69c-68da-5505-8ce0-3f8a9ece2c03 | date | Date Completed:
782b8ec4-e2e7-589a-bdec-0fe6bc056628 | section | 5.0 - Post-Placement
cf47b8f0-f88a-54c2-b407-91f44e2a654f | checkpoint | 5.1 - Curing
d935de30-5a7e-5f55-8a4c-05bb1a5194a1 | note | Frequency - Each concrete pour
0b1553ac-4ec0-5a8e-8d8f-f4260aefd946 | note | Acceptance Criteria - Concrete shall be cured by protection against loss of moisture and rapid temperature changes for a period of not less than seven (7) days from completion of the finishing operations.
40e0f672-c0b1-5de3-939a-86d62221b715 | note | ○ Curing of the concrete shall comprise an initial mist curing followed as soon as possible with continuous wet curing with hessian matting for the duration of curing period.
a2c4a646-91dd-5a03-97cb-f09b867f8363 | note | Reference Documents - Beca Spec 002 - 11.12.4
8441d7a4-4ca1-5d1d-b5a9-8246823633f8 | note | Inspection/Test Method - Visual Inspection
5ecbc6a7-bdf6-5d88-b7fb-dfe592caf6cd | note | Record of conformity - This ITP signed
da2577af-fbbe-5cc3-836f-f2db59d57582 | note | IP
d887255a-6945-5b74-8988-38edbf9405af | note | Responsibility - Project / Site Engineer
586a76b4-cd49-5ad5-9eb3-335564e3ab27 | date | Date Completed:
aa609089-ea6f-521a-b2a7-7cd41a2d5d49 | checkpoint | 5.2 - Cold Weather Concreting Concrete Protection
b72a3ea0-9cf3-54a7-beec-14b61b7a485d | note | Frequency - Each concrete pour during ‘cold weather concreting’ conditions
bf428b0e-8c96-580d-9b28-a5f2c3a1450c | note | Acceptance Criteria - The surface of the concrete must be maintained at a temperature of at least 10°C, for not less than 72 hours after placing and at a surface temperature above freezing (0°C) for the remainder of the curing period.
f9469610-5e96-5a78-922e-b7dee55d8e29 | note | ○ Concrete surface temperatures post-pour to be recorded on checklist CL013E – Cold Weather Concreting.
a429a458-d908-5b2c-ac3a-8f1ba931df5e | note | Reference Documents - Beca Spec 002 - 11.9.5.4
4f84e7fa-b264-5dfe-bca2-9a95248c0896 | note | Inspection/Test Method - Verify
410a28c0-f2e4-5be6-9d42-669ddbe29548 | note | Record of conformity - CL013E
71518393-0ca3-58de-b30c-7e807bd704e0 | note | IP
148e7960-cfe8-5c7b-a158-389cc3f3c208 | note | Responsibility - Project / Site Engineer
bc31c826-5b56-59c5-9460-f2f09b4366fc | date | Date Completed:
82b7f08a-ab9e-5a58-be5c-738ceda7b9f1 | checkpoint | 5.3 - Inducement Saw Cutting
ba74ad63-a217-5659-8789-4213c2ef4104 | note | Frequency - Each concrete pour
9d64d094-2296-50a1-b47e-7ab9a78b0e8b | note | Acceptance Criteria - An initial 3-5mm wide saw cut to a depth of T/4 to T/3 where ‘T’ is the concrete thickness (generally 150mm) is performed along transverse contraction joints as early as possible post pour.
125b6f42-2b3a-58fe-b46a-92a76549fb7a | note | ○ The concrete must harden sufficiently to permit cutting the concrete without excessive chipping, spalling, or tearing.
1a776220-10f0-5a53-b868-97fef033431d | note | Reference Documents - Beca Spec 002 - 11.13.5.2
30288578-007f-585f-a161-4929011df0c2 | note | Inspection/Test Method - Visual Inspection
377ff993-cbe6-50a7-aa30-10d2d23a7839 | note | Record of conformity - This ITP signed
2b2e9676-0d95-5bfb-9060-7ae0fcc14764 | note | IP
ac9e5c42-5d54-51f0-92a6-47743e8b6671 | note | Responsibility - Project / Site Engineer
ec669d6c-1236-5ce8-b376-bbfb38d60b30 | date | Date Completed:
1415f254-48b2-52a5-8aea-2df0d8845449 | checkpoint | 5.4 - Formwork Removal
4c9f9ded-2540-5aa1-a9b7-1549da9de3ad | note | Frequency - Each concrete pour
c89af9fa-9c3c-5b89-9507-b7f0b4112f66 | note | Acceptance Criteria - Forms must remain in place at least 12 hours after the concrete has been placed (but no longer than 48 hours).
28e65d8a-e481-5fae-b3c1-156e31999afd | note | Reference Documents - Beca Spec 002 - 11.8.1.3
a1b1af8d-5887-5e45-80c8-c711f63c9273 | note | Inspection/Test Method - Verify
f4445baf-2265-5b77-9a96-a3717922e231 | note | Record of conformity - This ITP signed
5d0613f6-7e0b-5386-9b7c-f4e76151a0d6 | note | IP
6d4b2aac-9612-5e27-a9cf-153d627386ae | note | Responsibility - Project / Site Engineer
18f2ef5c-d133-5162-88cf-ce695de1233a | date | Date Completed:
69489b9b-1e23-57b3-b09f-8b123c4734fd | section | 6.0 - Completion
8fa0b7c0-e1be-5bfb-a603-8cd013fc6298 | checkpoint | 6.1 - Surface Smoothness Testing
55e7de99-3c61-538a-a173-cbdebe5c1754 | note | Frequency - Per Lot
0c6efdae-61ee-505e-af82-1add84557269 | note | Acceptance Criteria - The finished surfaces of the concrete pavements shall not deviate from the testing edge of an approved 3.5m straight-edge more than 5mm longitudinally and 5mm transversely. No ponding of water is permitted.
32222931-7dbf-5c57-a8be-fb36823b71be | note | ○ Points exceeding tolerances and any observed areas of ponding water will be recorded on ArcGIS.
8789dc0b-3a2a-58b2-89a8-c6643a4d1cac | note | Reference Documents - Beca Spec 002 - 11.14.3
9d59607b-536c-51a3-b9b8-f275e3994b93 | note | Inspection/Test Method - Visual Inspection
d920b062-aab2-5cc1-8472-ec4909ccab24 | note | Record of conformity - ArcGIS, This ITP Signed
2d893d27-0cfb-5e97-acd3-5a846b45f93c | note | IP
168e7066-b2f9-5912-8c30-42b0df934b3f | note | Responsibility - Project / Site Engineer
4799c1ed-759e-577d-acbc-1c9e9a389eb2 | date | Date Completed:
91cbcdd4-c964-5ba9-81ea-9199af3ff529 | checkpoint | 6.2 - Pavement Surface Levels
f7b31f9b-21d2-5bd8-8aca-6bac5928cc2c | note | Frequency - Per Lot
445217a3-704d-54d0-91f1-f47b50e14278 | note | Acceptance Criteria - The Contractor shall take levels on the finished pavement surface at the corner of each slab.
986af59c-af1b-54e1-b235-cc9960654cdb | note | ○ The finished surface levels taken shall be within ±5mm of the design levels shown on the Drawings.
54cd0821-1456-58c9-9edb-34ea1dfb4396 | note | ○ The levels shall be measured to an accuracy of 2mm.
2479533d-2d5a-5645-94a5-2f3915c91011 | note | Reference Documents - Beca Spec 002 - 11.14.2
7d131307-0cf5-5fb5-a872-6605679b0156 | note | Inspection/Test Method - Verify
30637c20-3975-54ca-b8e5-98e5838a8c78 | note | Record of conformity - Conformance Report
91934272-5c06-53f9-bced-b8f5a45c58a2 | note | SCP
942d3878-1a64-50ba-9f33-700d3f5365a2 | note | Responsibility - Project / Site Engineer, Surveyor
c89333bd-fc10-5caf-a06a-0387ff3ec9a7 | date | Date Completed:
4ea2f5f4-1037-54b8-98fd-5a7f56de6983 | checkpoint | 6.3 - Protection of Slabs
e0a272cc-8031-5c13-94e7-2c52940c54d6 | note | Frequency - Per Lot
ca4200e7-3811-542f-9623-95ab15582db2 | note | Acceptance Criteria - Concrete pavement must not be trafficked until 7 days old or early strength results are obtained. Steel tracked or steel wheeled equipment is not to be used.
d0d67642-8c06-5e46-8e83-6af9a4ec16ed | note | Reference Documents - Beca Spec 002 - 11.17
1981dabb-a7d4-56cc-a815-bb0ec0aac791 | note | Inspection/Test Method - Verify
d9f99ce0-fd9f-523d-b3b0-028767f2b5d5 | note | Record of conformity - This ITP signed
536c33e3-9e33-5297-a415-b849c3716a6b | note | IP
a9977ffb-173a-5f9c-a3fc-11de956a432f | note | Responsibility - Project / Site Engineer
5f06486e-2a73-588f-a366-13292ebceedf | date | Date Completed:
2c5ed52b-149f-5ba6-86ad-1a18b9ce8a73 | checkpoint | 6.4 - Defects to Slabs
3f516d19-5afa-50e8-8656-411903a8c112 | note | Frequency - Per Lot
150631ea-1856-53df-a83c-9a9317be8056 | note | Acceptance Criteria - Check for any nonconforming defects (cracks) in the concrete slabs.
94aceb5c-6f5d-54f3-bdd1-ca5bc232a8a3 | note | Reference Documents - Beca Spec 002 - 11.19
ec7e76c9-dc53-5142-98bd-3df83042df78 | note | Inspection/Test Method - Verify
ff40cd6d-cd44-56b9-a6a1-b07d689665dd | note | Record of conformity - This ITP signed
d109b0da-565c-5772-9e5b-2c8a5ff335e3 | note | IP
36bc9767-f10d-5220-8856-df85756fe6b7 | note | Responsibility - Project / Site Engineer
c9833f31-e161-56f7-9594-e08d707687aa | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
6ec667d0-0f8f-5ddb-9183-5e7d582c3f27 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality/System Procedures and verifies lot compliance with specifications.
d2e6550e-c607-57f6-87e4-4aa671b9d4d2 | textbox | Print Name:
870a6224-29d1-5697-b7e0-a4aee1ba336c | textbox | Position:
3b5d58b4-9d81-5add-bb5f-d6993954ebd6 | date | Work Completed On:
94480ab5-0fac-571f-9c29-dad8053606d3 | date | Date: