## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
650ca38d-40dd-4291-892c-770544ed35fb | checklist | EVAMP001-THS-QA-ITP-0001 - Clear and Grubbing - Rev B | itp | EVAMP001-THS-QA-ITP-0001 - Clear and Grubbing
99768ba4-d48b-4d7a-94e4-e6aa108e40db | section | 1 - Pre-Construction
7b1f87c1-b809-4777-8871-d467d0b9011c | checkpoint | 1 - Drawings supplied most current IFC
89111b25-423c-54c3-abbb-07da20d5360c | note | Responsibility - ENG
c20aaab4-8b74-5f0a-9400-77f0fd6e920d | note | Method - Visual
80e4f95e-ae72-54a1-9be4-9788b9919243 | note | Conformance Criteria - Reviewed drawing register
9bd2c39a-4312-5507-a3e7-a1143c307723 | note | Specification Clause - Reviewed drawing register
7c1b92b9-bd05-51b9-a977-a5cf38401438 | note | Frequency - Prior to works
7646f7f3-21ed-5e35-9aa4-e2e347c1cff9 | note | Verification: THIESS (Initial) - HP
fcce6462-5ff1-51b1-9f41-edd9c79597f7 | note | Verification: Client (Initial) - W
8d289e51-09dd-4a98-a3de-e832cc597d97 | signoff | HOLD POINT
c5a3dcd2-2ac8-4572-b21e-4632bd805cf7 | checkpoint | 2 - Management Plans submitted and approved as per PMP
1a340662-b554-585c-b6a5-891704592c46 | note | Responsibility - ENG
874c2a5f-7d6b-5f18-a0e3-36ba47716efe | note | Method - Visual
26abac50-e2c2-58bc-92a6-0b28e836b022 | note | Conformance Criteria - Approved Package MP’s
0a6252ee-3db2-5486-b391-778ac2bbb6a0 | note | Specification Clause - Approved Package MP’s
6b0a3bdf-9548-5200-b427-0f1e15950d84 | note | Frequency - Prior to works
04a9c812-264c-57e2-8727-a3be5ae54018 | note | Verification: THIESS (Initial) - HP
09312a57-0cfb-5c73-8f85-c95734617a85 | note | Verification: Client (Initial) - W
7df4b227-a7bc-4b95-894b-eab2b8f08308 | signoff | HOLD POINT
35e243cc-aaf4-429f-acdd-c08341905679 | checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
fd0e0c69-cfa1-5ec2-bd10-4cd2872258d5 | note | Responsibility - ENG
2fe9c0f6-ce56-5134-b856-625b5ae91d29 | note | Method - Visual
678f14c5-589a-57a8-a107-bc2e189993a1 | note | Conformance Criteria - Approved ITP revision
43a7cba5-af80-564a-b9e4-c9656b4c9eb2 | note | Specification Clause - Approved ITP revision
32301199-da66-5a36-b919-55deb71aec1c | note | Frequency - Prior to works
800992f3-d3f8-59a2-a989-0899f32ab6e0 | note | Verification: THIESS (Initial) - HP
f05ff70d-ac3f-55c9-a06f-0dd1b428be34 | note | Verification: Client (Initial) - W
33cf753c-5345-4b17-89eb-b4735421aae6 | signoff | HOLD POINT
3d7bf959-e14f-4cf8-85a8-58263e37a22c | checkpoint | 4 - Lot Register/ WBS submitted and approved
13e0807a-1dee-5c37-97a5-d98aadaeb00d | note | Responsibility - ENG
fc961a75-b911-535b-a0ae-a9a7176990bb | note | Method - Visual
9c590ad2-25eb-5e53-9177-251762869175 | note | Conformance Criteria - Approved WBS
28f44be7-447b-59f2-aa45-898e22561a1e | note | Specification Clause - Approved WBS
d62326e4-b14f-59ce-99c9-141f055f962f | note | Frequency - Prior to works
4bb66250-3077-59fb-91b9-b850b576a6c9 | note | Verification: THIESS (Initial) - WP
b919aae5-376c-5947-9b41-f824cbe79371 | note | Verification: Client (Initial) - W
046638ad-3b34-43b4-a38d-f1107cb22e67 | checkpoint | 5 - Erosion and sediment control plan approved
32c84350-1ee7-515e-a7b5-d2e0924e911f | note | Responsibility - ENV/ENG
bd312d9e-2f42-5dcc-8e54-3afa8544b6aa | note | Method - Visual
6c4dd2f6-2b3b-5f5c-909f-8896f2cc089f | note | Conformance Criteria - Approved erosion and sediment control plan
eddbea88-e040-5cfb-ad50-dc76637466d2 | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
adee58bd-8509-57d0-a61c-960183409803 | note | Frequency - Prior to works
c6ec1f9f-bd5e-5d51-98cd-0cc328da704f | note | Verification: THIESS (Initial) - HP
59409af6-bd44-5c6e-aa87-56cd0e2bd525 | note | Verification: Client (Initial) - HP
1186d6fd-e8bb-430e-a217-7f6f96959387 | signoff | HOLD POINT
48298157-57de-48cf-998a-b5ca1758a8e9 | checkpoint | 6 - Check existing services and dial before you dig
80e195af-d4a7-55a7-91b6-2065a79213db | note | Responsibility - ENG
8256ec3e-1ef0-5884-8d75-dff8911649da | note | Method - Visual
dd7cba8d-be74-55ac-8ff0-d4be987d4eef | note | Conformance Criteria - DBYD certificate and EP
a7ae043d-432b-53cb-a6da-586a3cabdfbd | textbox | Specification Clause - Excavation Permit (EP) Doc no.
843816da-efe0-52c7-beb1-d4490acc221d | note | Frequency - Prior to works
e9d465ac-8f69-53bd-babf-9d11cd362e1b | note | Verification: THIESS (Initial) - HP
c858b134-ab80-5a5c-9489-768f83d3df38 | note | Verification: Client (Initial) - W
748eeac4-4328-4e92-94a7-3d09a2266a51 | signoff | HOLD POINT
c4acd5df-dc83-46b0-8c6f-29fa109b5b57 | checkpoint | 7 - Ground Disturbance Procedure (GDP) obtained
4a3aedeb-aa0f-54e4-820f-86c0aa92db8e | note | Responsibility - ENG/ENV
a6fb453d-ed71-58cd-b6b8-3df2e3cabfb3 | note | Method - Visual
c2521a66-52f7-54d4-8e19-fd2b77297b5b | note | Conformance Criteria - GDP permit with work packs
cb980b7a-21c7-5ff6-aafa-1b403c1d885d | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
69e83c88-ed42-5cfc-8402-15bf32996c3c | note | Frequency - Prior to works
4f93652f-2edf-5bb5-895c-34ffe67ff628 | note | Verification: THIESS (Initial) - HP
67a88537-b41d-5a28-8430-9e955ae47522 | note | Verification: Client (Initial) - HP
106e6800-5307-4392-9d84-be558e3602df | signoff | HOLD POINT
11eae57a-9aa1-4e1c-b4ec-f791161f27ca | checkpoint | 8 - Area of works pegged and clearly defined to GDP. Pre- strip area survey pick-up
84e60977-bfdc-5517-ad85-f0586923788a | note | Responsibility - SURV
6cbcd8ed-57c3-56dd-88ce-69f7e3120a4e | note | Method - Visual
fa4f230b-0e1b-5e73-8a87-ede64e1fbe20 | note | Conformance Criteria - Clearing pegs installed at nominal intervals to ensure no over-clearing
687c79b2-6a31-5c1e-9b99-12925f6a716d | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001 to ensure no over-clearing
59b28b6e-93f9-5334-9e70-8cb4e04ef116 | note | Frequency - Prior to works
d517d0fd-b955-55dc-8cb8-e8997d733c0d | note | Verification: THIESS (Initial) - HP
dd20d1be-cd4f-55a0-af99-ae37553e8bb7 | note | Verification: Client (Initial) - HP
6fa2d4d9-a8ca-47f0-b1fc-2526bdeb7071 | signoff | HOLD POINT
f42e2edd-fa1d-4df5-a60b-5fd448b7f8ac | checkpoint | 9 - Area of works been pre-cleared for Fauna/ Flora
4aabc1df-e839-591c-b386-d2813645b180 | note | Responsibility - ENG/ENV
6ccbc6e3-3dd4-567c-99d9-820ea9b0078d | note | Method - Visual
32568ccc-bcfb-53e8-adf2-d32c73a60b1e | note | Conformance Criteria - All areas to be pre-cleared prior to clearing operations.
fc438aef-6070-58b1-926a-ef87a5d9675e | note | Specification Clause - EVAMP001-EVA- EN-PLA-0001
504b47e0-913a-500a-bc6d-7c50a92e40ec | note | Frequency - Prior to works
4ad6444b-7fea-5fa8-ac4d-583a0aef7dfb | note | Verification: THIESS (Initial) - HP
399dbb51-ed64-5cf9-ad5f-7588ea90d442 | note | Verification: Client (Initial) - HP
68bc99ec-6f29-4ad8-9a7d-b62f872c8840 | signoff | HOLD POINT
ff7a217b-0bcd-4de5-9271-a69152d419b7 | section | 2 - Construction
d9230512-0cf7-4a06-bf29-9128c86f4267 | checkpoint | 10 - Clearing of vegetation and removal to nominated stockpile location
9ec30b2c-3ff1-5c99-865d-07970713d91b | note | Responsibility - SV ENV
7fa3fcd8-a832-5d1f-b1bd-6ce225a3c526 | note | Method - Visual
32e2292e-1958-577b-8377-3a816e7ce72e | note | Conformance Criteria - Spotter/ catcher in place during clearing operations
b297214d-7495-5c2b-80fa-3e59aa065521 | note | ○ Habitat vegetation, threatened species and cultural heritage areas demarcated
bdf0570a-f976-53fd-95af-ef5ef309997c | note | Specification Clause - EVAMP001- EVA-EN-PLA- 0001
3ad3a22d-70e1-5f7f-8ea3-d24beb2b7987 | note | — EVAMP001- EVA-7340-PE- PRM-1
b9b9f255-b459-5f31-9784-19ca8b8a37ad | note | — C22 of EVAMP001-QVT- PE-PRM-1
82915ec0-68ee-540d-befe-eed0e6b01e20 | note | Frequency - As required
5a314882-bae0-54d9-bb9f-1ac0b488e099 | note | Verification: THIESS (Initial) - HP
3d7df1b6-8547-57ab-bf06-c070114b5dd4 | note | Verification: Client (Initial) - W
cbd6e942-230b-4f6d-9160-4ed315f5e179 | signoff | HOLD POINT
76bb71da-ab3d-4566-9135-388e7b991e29 | checkpoint | 11 - All Erosion sediment control measures installed prior to construction
a2a6e786-2b3c-5b03-8747-9a0a7cb18be5 | note | Responsibility - ENG/ENV
a361c1d2-e070-5b83-a59f-4bf91144246b | note | Method - Visual
a044c74b-a994-57a1-9a2e-8d677c940176 | note | Conformance Criteria - All control measures for erosion sediment control need to be implemented after clearing has been completed.
1b0b6346-15bd-5577-bde4-719ab72b88e8 | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
c9cae457-809e-501c-8d72-5a1d8a082663 | note | — EVAMP001-EVA- EN-PLA-0001
f4adb0eb-c05c-5660-97df-33b6754d1da9 | note | Frequency - After clearing completed
6a43e62e-a28a-5943-b47f-b6503518ce43 | note | Verification: THIESS (Initial) - HP
526850d4-f9bd-5d88-8b76-4f0bafe64ec9 | note | Verification: Client (Initial) - HP
9c35f85c-f9d5-4a58-afdf-8034e09b8f98 | signoff | HOLD POINT
a0707b61-49da-4bd5-b575-b8dbce7822e6 | checkpoint | 12 - Inspection of foundation prior to next stage of construction
47868d81-6add-506a-8bac-fd579126a668 | note | Responsibility - SV ENG
df2c4744-04bc-5485-9dd4-e35fd801877e | note | Method - Field Test
9ade0960-8b5c-53b3-93d9-1795fe06bdd8 | note | Conformance Criteria - Proof roll where required
78e8e33d-80b1-5ab4-988c-649add1caa4e | note | Specification Clause - EVAMP001-EVA- EN-PLA-0001
8c857f8c-2ac3-5e35-aa49-89f3266a3183 | note | Frequency - As required
d526c092-75d9-50d1-b48f-fec9cc3ae138 | note | Verification: THIESS (Initial) - HP
3fffed97-1031-5786-a3ae-b96d385eaea6 | note | Verification: Client (Initial) - HP
d89cd23b-45b8-434b-abb2-615769c20cd2 | signoff | HOLD POINT
764d3fbe-e73a-4d41-9c7a-6b2be8c72319 | checkpoint | 13 - Surface level check/post-strip area survey pick-up
d22ebb01-29ca-5265-a9c2-def834422058 | note | Responsibility - SV/SURV
4c5c041f-e914-53ed-8443-8123ced4718b | note | Method - Survey/ Field Test
8e4eb6d0-b885-57ac-9174-b41aa51e2dcc | note | Conformance Criteria - DXF file submitted to Company
8501955f-6740-564e-ace8-f9a169bfb96c | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
45b96e5e-b610-5342-9ef5-7dcb61476a47 | note | Frequency - As required
16e7afe2-2547-54bc-87e6-8a5cbf4d77d8 | note | Verification: THIESS (Initial) - HP
046d1947-1d28-54f1-af6b-91620e6d999e | note | Verification: Client (Initial) - W
88b881f2-8230-4629-80ca-373d0691aed6 | signoff | HOLD POINT
b84db826-2024-40ae-b014-85a11d280f9c | section | 3 - Post Construction
c9b3e20d-f6df-4a96-8888-a6f878eb8314 | checkpoint | 14 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
e72654fb-4530-5103-856f-865ea8cc5f7a | note | Responsibility - ENG
ab361d09-0b68-598d-ad35-808da90bb112 | note | Method - Visual
c6cf5d84-03ec-52cd-b7cb-6b6c5851b505 | note | Conformance Criteria - GDP permits closed.
707dcfc9-97c7-5e55-a00a-b4c568739a8a | note | ○ ITP closed. Approved MDR
4eb1ab5b-a384-5a13-853a-0dad02071d0c | note | Specification Clause - EVAMP001- EVA-7340-PE- PRM-0001
8b3ce8f9-5295-5411-802a-6fa30dfa5f24 | note | — EVA PMP
c92dd74d-89c5-5053-83a3-919e70cd25c9 | note | Frequency - As required
4d3f2e49-cbb3-5f78-88f5-ea3be5a55e43 | note | Verification: THIESS (Initial) - HP
66964e09-bc27-5029-aa6d-5ea0606b667d | note | Verification: Client (Initial) - HP
5e7c81bb-55ba-46df-ba4f-ae5cbc10b3d3 | signoff | HOLD POINT
fd4be270-e75a-4b8d-a474-4b812aed51e7 | checkpoint | Final Inspection
7b8b411d-e8c0-58dd-b3b0-2bfee1441f98 | tickbox | Conformance to Specification
009f4040-bb0b-5dfb-a33d-29d1cbf093f7 | tickbox | Requires Re-Work:
672f4c3c-dab1-5028-a2d3-155d3eb0b7b3 | textbox | (Provide Details):
34da4660-2088-555b-9ab1-984208295d5d | tickbox | Non-Conformance
6058c9e5-ea5a-5c6a-9f60-b6e0f8bcebb4 | textbox | NCR No:
8b898533-e533-4c29-8701-4bd49cca6d28 | signoff | Approved by THIESS QA Representative / THIESS Project Manager / Client
35983ad8-869f-4bae-9a7c-59bb0a178bc1 | checklist | EVAMP001-THS-QA-ITP-0002 - Topsoil Stripping - Rev B | itp | EVAMP001-THS-QA-ITP-0002 - Topsoil Stripping
bb2e1762-4d0e-404b-8ed1-f392b37abd6a | section | 1 - Pre-Construction
cf12d4cf-8d20-4aef-9512-b2e24a7eb117 | checkpoint | 1 - Drawings supplied most current IFC
6f47f5b1-f9c9-5055-87cd-5acad000a283 | note | Responsibility - ENG
ebf4682b-03dc-5068-ba29-e438ce222f63 | note | Method - Visual
bca9b4bf-7310-57d0-8f8c-9bf12c4e21ef | note | Conformance Criteria - Reviewed drawing register
418b636e-42da-58e0-b2bf-320aab14a5a5 | note | Specification Clause - Reviewed drawing register
d806c3ba-abcd-5f4c-81b5-94adb14f2fa9 | note | Frequency - Prior to works
cd04b24f-67a4-5223-bb4a-33bf074a6e08 | note | Verification: THIESS (Initial) - HP
9eec282b-a81e-5937-920d-ded0cf3ba88d | note | Verification: Client (Initial) - W
bef32d01-21f1-42f1-92ed-a5688fc3f1d0 | signoff | HOLD POINT
7e16dc27-dcd1-4eb9-94ca-6ccddc853d66 | checkpoint | 2 - Management Plans submitted and approved as per PMP
d275b877-cd08-532f-badc-add96094527d | note | Responsibility - ENG
f37167da-a99a-5ede-a9b5-4e6d2c34cd11 | note | Method - Visual
b0589737-1e0b-5ef6-98c1-444cbfdda3fc | note | Conformance Criteria - Approved Package MP’s
f61aae84-c0ba-559f-b389-a938da63753d | note | Specification Clause - Approved Package MP’s
beb26352-1e51-5366-8014-359122439b09 | note | Frequency - Prior to works
bf81f475-49d0-521c-a45e-e62a150331bd | note | Verification: THIESS (Initial) - HP
93fa279b-9cfd-5daa-a536-4fd7d3d2756d | note | Verification: Client (Initial) - W
bb271914-0701-4350-a305-c54ccadf97e2 | signoff | HOLD POINT
f5a14dfe-e406-4685-b528-6941a30ab661 | checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
c9d54553-b3af-5c86-b9b3-aefa90927027 | note | Responsibility - ENG
a865c642-8cc0-5ee5-9cd0-7e51bb411bf1 | note | Method - Visual
1f79d0f1-86ec-53b2-a131-7c37ce7dcae2 | note | Conformance Criteria - Approved ITP revision
8bf0c372-79f4-5719-8d91-bbb52725cfb7 | note | Specification Clause - Approved ITP revision
909a9806-e890-58d0-bffb-a38655b86901 | note | Frequency - Prior to works
d8fe9910-1e0b-592f-8b99-acdc7fb52696 | note | Verification: THIESS (Initial) - HP
a02f5ed0-d6c8-5320-ade0-90eae7d29fe0 | note | Verification: Client (Initial) - W
504b55b0-562a-4047-a53a-8af3c3d7e82d | signoff | HOLD POINT
dd3634da-4f3a-4aea-ac07-928ac10b9605 | checkpoint | 4 - Lot Register/ WBS submitted and approved
b1eb93f3-b5f9-5ee7-97d5-060b43ab5fb1 | note | Responsibility - ENG
82ebf10f-bdcb-5139-ad29-20173c647620 | note | Method - Visual
1bcbbed1-28e9-5fc2-b755-32b21e4ecc92 | note | Conformance Criteria - Approved WBS
a040b786-fc8c-5d08-a84f-a19b69cd3d01 | note | Specification Clause - Approved WBS
f1f4decc-1d70-53e9-b874-699d9eea793d | note | Frequency - Prior to works
e41369d2-678a-5c4f-940d-a265ade3937d | note | Verification: THIESS (Initial) - WP
2cc65aef-82d3-54a9-ac93-10b858db599b | note | Verification: Client (Initial) - W
d5947c5f-99b7-4939-bf0d-54e7df1859ac | checkpoint | 5 - Check existing services and dial before you dig
88ba553b-bbe0-5693-acb2-1acfe943d56a | note | Responsibility - ENV/ENG
a332abe8-9a5b-504a-9d2b-8b7e763b615a | note | Method - Visual
b4323f6f-0405-5a21-adf9-24234bc8e94e | note | Conformance Criteria - Approved erosion and sediment control plan
e533dbba-a3c3-5348-bb86-9d40ce75b6f9 | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
f7b947ac-9d49-51e7-b900-6f2a05b364f5 | note | Frequency - Prior to works
836a950f-4def-554b-8488-c6ea383589f9 | note | Verification: THIESS (Initial) - HP
5e798303-7cc0-5eef-81aa-9c49d1342b5a | note | Verification: Client (Initial) - HP
6a51f30f-0e8a-4d82-9785-b634c0988b2c | signoff | HOLD POINT
c97f8c59-ce78-4c15-8e2a-04d667126163 | checkpoint | 6 - Ground Disturbance Procedure (GDP) obtained
2c5044e8-4f6f-5e9e-a92e-77c447eef1d8 | note | Responsibility - ENG
6b91c88a-84c4-554c-87bc-5082373615e7 | note | Method - Visual
258b2fbf-af2a-5d2c-abff-f720e5274d5b | note | Conformance Criteria - DBYD certificate and EP
c5de40c7-af62-5d9e-aa29-1857be0d34c3 | note | Specification Clause - Excavation Permit (EP) Doc no.
02604bd1-4601-55a7-9d93-a9bea8fbf448 | note | Frequency - Prior to works
82f370e1-3deb-5efc-a018-6062856cb11e | note | Verification: THIESS (Initial) - HP
56174e55-9147-5943-b81b-ed9a21119fc8 | note | Verification: Client (Initial) - W
ada11cb1-de12-41eb-a21c-5f6ddf3f1d0f | signoff | HOLD POINT
25c3d13c-0422-40c2-92e9-21d2a80ebc3a | checkpoint | 7 - Area of works pegged and clearly defined to GDP. Pre-strip area survey pick-up
eb97e363-e818-53eb-a7f5-514579cc3100 | note | Responsibility - ENG/ENV
91c06af4-96af-5f4e-b63e-f0c6f6b51613 | note | Method - Visual
f254e918-bf94-5358-9e33-f11bb65905e4 | note | Conformance Criteria - Boundary pegs installed at nominal intervals to ensure no over-stripping
557dc8bb-5dac-5302-a576-63c408aa81e1 | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
5eef00b2-78cf-5dde-896a-8073ec628850 | note | Frequency - Prior to works
d0249876-780e-5d21-b3d0-f9fba18d8d68 | note | Verification: THIESS (Initial) - HP
d8ffa544-2007-534d-9efe-1918efa03b82 | note | Verification: Client (Initial) - HP
84d273b0-6521-4f8f-99cd-4d27eb4bff2b | signoff | HOLD POINT
0134881a-cc2b-4495-8a4e-2a219e89cf09 | section | 2 - Construction
15d3a864-cd48-4fab-85fc-1a0b54d65f1b | checkpoint | 8 - Stripped topsoil load and hauled to nominated stockpile location
682c8e66-35ab-5982-bc62-30332bade47c | note | Responsibility - SV
2be64ee8-dc2d-51f1-9c8f-b6d853b7c935 | note | Method - Visual
90cb55bf-6f0d-523b-8c86-838ba045220a | note | Conformance Criteria - Stockpile locations located 40m from watercourses and not exceed 2m in height.
0ffb2b90-2383-50d7-b6e5-81b1823f8486 | note | ○ Native seeding of topsoil stockpiles as agreed with Company.
152c1158-6847-5db7-8ff6-9420d732d0a0 | note | ○ The provisional depth of stripping shall be 150 mm unless shown otherwise on the drawings
b69bcd59-53bd-5606-8487-646f39a58001 | note | Specification Clause - C9 of EVAMP001-QVT-PE-PRM-1
a5ea82f0-eb8f-56e4-a07a-f6157d674465 | note | — EVAMP001-EVA-EN-DCR-0002
68024f57-8529-502f-97fb-e88347bebd79 | note | — EVAMP001-EVA- EN-PLA-0001
350f585c-97b0-5084-ae05-9f8ca7241d49 | note | — 107501-EB- 00000-27280-001 Rev A
70669dd5-9057-5285-9173-aa3d893e9efe | note | Frequency - As required
b2b7f49b-54dc-5f18-b99c-d23dd5bd19d3 | note | Verification: THIESS (Initial) - HP
6c2b69af-1ff1-5668-b4df-36691c8805fa | note | Verification: Client (Initial) - W
841c83d5-857c-4dbe-a647-12e60695f306 | signoff | HOLD POINT
5104befa-de89-4f28-b970-43f37f8f45b4 | checkpoint | 9 - Topsoil location, destination and quantity catalogued.
04f60c26-69e9-5995-88a5-f41fa9fe107d | note | Responsibility - SV
3438c3e1-0d55-5d81-91a0-b12e9571e501 | note | Method - Field Test
fd8d767d-7dec-55b2-93b3-34e7fba9c304 | note | Conformance Criteria - A topsoil inventory will be maintained with information on topsoil volumes and stockpile locations
c78ee30b-8f70-5a49-9ab8-a8931ac9a6db | note | Specification Clause - EVAMP001-EVA-EN-PLA-0001
befffdea-0cf5-50c3-8f41-749e87394115 | note | ○ EVAMP001-THS- CV-REG-0003
743a0459-1a6a-553d-a38d-b30a655a923a | note | Frequency - As required
4792d11d-7842-5e50-9fbf-93420c852649 | note | Verification: THIESS (Initial) - HP
9364e04c-2c12-553c-98f6-b4a62fff431b | note | Verification: Client (Initial) - HP
80742484-eee7-4467-832e-ea20e49dbaf9 | signoff | HOLD POINT
02f71ad7-e8a4-4585-83dc-b013eef0a969 | checkpoint | 10 - Surface level check/post-strip area and volume survey pick-up
894c69e0-4a6c-57cb-ac5d-0eceac6ccbf0 | note | Responsibility - SV/SURV
c5fc7914-d3cf-5586-a1d6-87d309b46708 | note | Method - Survey/Field Test
b0bb0db9-4ec2-55af-b5b3-cc10585793e9 | note | Conformance Criteria - DXF file submitted to Company and inventory updated
c7ca3ae5-4222-5f25-afea-c94599e22349 | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
9db2f9e6-a958-51f6-9269-37ec894d2e4d | note | Frequency - As required
1d14ae1f-2398-5019-9ade-87b064dd8b81 | note | Verification: THIESS (Initial) - HP
b8ee2c11-d47c-56d2-8f65-e957799175f2 | note | Verification: Client (Initial) - W
8650afee-cdd6-45cf-a6e8-83d631f09683 | signoff | HOLD POINT
e06be554-ef9f-4c13-b6a9-8eadbc8aabae | section | 3 - Post Construction
9789f97b-8d3f-4c7d-bea7-0bada95ba9a2 | checkpoint | 11 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
e904e364-cd35-5909-8f55-da5ef86a8515 | note | Responsibility - ENG
3994174c-c988-5ed1-a4b6-0ed00b3d1cba | note | Method - Visual
3bc71412-bff9-5f51-8146-d2561552a3e9 | note | Conformance Criteria - GDP permits closed.
5c3c2402-b346-5c07-8ad0-af2662568473 | note | ○ ITP closed. Approved MDR
cfdee6fd-9a70-5883-9295-857e33bc5f96 | note | Specification Clause - EVAMP001- EVA-7340-PE- PRM-0001
3ceb5748-756a-59e8-bbf4-2aad50430fd3 | note | — EVA PMP
b5ea251e-f767-5c20-8af9-23453232a67f | note | Frequency - As required
b3abc8f0-5100-5a1d-a0ea-d570c9910c4e | note | Verification: THIESS (Initial) - HP
1720935b-24e5-5a70-ac1e-7951f54fad2d | note | Verification: Client (Initial) - HP
f3f6c0de-eb42-4415-8871-7a9e78f6961c | signoff | HOLD POINT
3fe6c12b-1b2e-4c38-b8d0-425f5f150f54 | checkpoint | Final Inspection
756030b9-dc70-5e21-9e75-e579e56ceff2 | tickbox | Conformance to Specification
b8651b46-c877-5252-ae40-b57f4790fb62 | tickbox | Requires Re-Work:
440e874b-3264-5107-8d30-24d0bb436dab | textbox | (Provide Details):
4b97aab6-16d2-5761-8954-f37fddeaadb9 | tickbox | Non-Conformance
cb69cc2f-b3f1-54c7-bfd3-ce0184bb27eb | textbox | NCR No:
99104eec-f7c4-4c6a-be14-9b7bc2d85c2f | signoff | Approved by THIESS QA Representative / THIESS Project Manager / Client
6a11b2a7-3bb5-4f28-93bf-f9317191332e | checklist | EVAMP001-THS-QA-ITP-0003 - Subgrade Preparation - Rev 0 | itp | EVAMP001-THS-QA-ITP-0003 - Subgrade Preparation
5f51824f-f07f-4e9f-9eb1-8a2d83b62efb | section | 1 - Pre-Construction
590ffd40-44d5-4e78-82f2-8d59dfd1e37e | checkpoint | 1 - Drawings supplied most current IFC Retrieved from InEight
d2d3733c-2a44-5bda-afe6-6b8285577657 | note | Responsibility - ENG
21f9d1e0-2706-5f2e-9016-c5745a2796dc | note | Method - Visual
c843b7cf-9327-50cd-bafe-9c20a578ce12 | note | Conformance Criteria - Reviewed drawing register
1f36333d-d67f-5027-8688-aa9fafa3ca5c | note | Specification Clause - Reviewed drawing register
19ecbe90-45eb-58f7-b617-f6bd3a14a401 | note | Frequency - Prior to works
8cc0362e-03cd-5b32-8210-7e17c70ca2b3 | note | Verification: THIESS (Initial) - HP
9a8ea906-da82-54d6-9579-b9d14bfc9eb6 | note | Verification: Client (Initial) - W
094741de-c040-46fe-888c-2afbdb0144d5 | signoff | HOLD POINT
c60240eb-a228-4088-ad42-41d14adb2165 | checkpoint | 2 - Management Plans submitted and approved as per PMP
0a0e9fc3-d274-5fc6-9f57-df74195c497e | note | Responsibility - ENG
e3cc226e-b094-5f75-bb74-6b4e74faeb83 | note | Method - Visual
4d2a8fa9-3ea7-512c-b94b-02d4fa30efd2 | note | Conformance Criteria - Approved Package MP’s
1eac4c94-2620-517f-89f3-a7740741edba | note | Specification Clause - Approved Package MP’s
9f182d1f-963e-51d9-a306-ecdfc73659a6 | note | Frequency - Prior to works
6f54bd9b-2c8f-513b-86dd-7d9d9178288d | note | Verification: THIESS (Initial) - HP
62b2cdc9-add1-51da-b433-a6c965ba8855 | note | Verification: Client (Initial) - W
630ed720-ebbb-4ca2-9030-52ce01538995 | signoff | HOLD POINT
174aea8f-e4c6-4e03-8327-82eb08a4a694 | checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
e7ac2421-5425-5cae-b718-eb00bb14841d | note | Responsibility - ENG
ce9f71a5-862c-5de1-9844-a3723d632f7e | note | Method - Visual
40224ae5-65a5-5078-a48b-f5767c225e9c | note | Conformance Criteria - Approved ITP revision
c521a7d6-961f-5ccf-a157-525c2fb3c83c | note | Specification Clause - Approved ITP revision
1d309c8b-04a1-5df5-850c-8f0b09cc7ba1 | note | Frequency - Prior to works
e8891c51-94b9-5825-82d5-19558d35e4f9 | note | Verification: THIESS (Initial) - HP
5b1aa8bc-49f1-5387-8edb-755bd77ba34a | note | Verification: Client (Initial) - W
dc44237c-dac9-497d-8013-665d7724d8c9 | signoff | HOLD POINT
4f2531ac-f5fc-4fcf-bf76-62ae27d1696f | checkpoint | 4 - Lot Register/ WBS submitted and approved
969e213c-905a-5887-9713-4d93107c396f | note | Responsibility - ENG
82a0ec28-d332-5001-8383-fa24436b4228 | note | Method - Visual
c040dfca-12c5-5bcb-9478-9a79b4f61011 | note | Conformance Criteria - Approved WBS
19252cdd-afd9-5e9f-baf6-4572b6242d69 | note | Specification Clause - Approved WBS
c97fc9b5-e770-53ce-b8fa-0125253812f3 | note | Frequency - Prior to works
1ebadab9-678c-5699-8aca-93c18813babd | note | Verification: THIESS (Initial) - WP
d2d72935-fb7d-5a3d-a2fc-6888d7565da9 | note | Verification: Client (Initial) - W
845b0ced-fb75-4660-88ee-d5ee43d3e95a | checkpoint | 5 - Check existing services and dial before you dig
70ab0ed5-3679-585b-8552-574649778141 | note | Responsibility - ENV/ENG
e9239656-4c63-50d2-bb45-206bdbbde368 | note | Method - Visual
e468b8bc-cdbf-50c8-83f0-3053b66339a7 | note | Conformance Criteria - Approved erosion and sediment control plan
849a38a7-4a5f-5634-b77a-7c4327028029 | note | Specification Clause - EVAMP001-EVA- EN-PLA-0001
a3b7a595-9333-5296-a864-be9222ea8712 | note | Frequency - Prior to works
f8c992b6-9bea-5c19-96d2-ed73c1ee66c6 | note | Verification: THIESS (Initial) - HP
2b310fac-c2bc-5c76-b0d5-0033d4f33221 | note | Verification: Client (Initial) - HP
0b5c0738-e8a0-411b-941d-84b03a35ed5f | signoff | HOLD POINT
1f4e1988-8046-40d6-9475-c0ab54b1e6ec | checkpoint | 6 - Underlying lot & ITP signed off and conforming
da2a04a2-06db-5775-b2a0-01db94013d8a | note | Responsibility - ENG
fc64b149-4132-58bd-a457-1d3681c0952e | note | Method - Visual
9df82a0e-dae8-55e9-a289-2d6763ea0c9f | note | Conformance Criteria - Topsoil stripping ITP signed off
bb022268-fe7e-560c-8e7d-479ca4532f86 | note | Specification Clause - Approved QMP
01c3333e-eeff-5b3c-bbb5-b3702cb1f973 | note | Frequency - Prior to works
d5db27d8-6078-54f8-826c-961fc930fa24 | note | Verification: THIESS (Initial) - HP
349ec6e3-2984-5665-aecf-1c0f0a1d0486 | note | Verification: Client (Initial) - W
4ff7fe79-e456-422e-a883-19ed0261a600 | signoff | HOLD POINT
50a84307-67f5-4988-bc1a-f0ed5a467d87 | section | 2 - Construction
4f3c17e7-cf22-4b9e-970f-1cc3b89487c0 | checkpoint | 7 - Removal and replacement of unsuitable material
6d15325a-43a8-51be-93cb-ca082cec73eb | note | Responsibility - SV
a162525e-e267-5cef-a85f-cdeed12359bf | note | Method - Visual
96eb5412-4f57-5994-a3f8-c7a88999549f | note | Conformance Criteria - Determination of unsuitable material by the Level 1 GITA or Principal is required prior to the removal of any unsuitable material.
152ecdf1-fba3-51d2-9a8b-bf6c67a11266 | note | ○ Unsuitable material shall be disposed as directed by the company or in areas specified in the annexure.
7c9f8867-4c39-5d2b-8559-e5c4322c4de0 | note | Specification Clause - EVAMP001-THS- CV-SPE-0001
89c58d33-88ee-5d94-b980-9406a786f2d9 | note | Frequency - As required
b1efc6b9-1f29-51e1-8df6-c2af3b6546f0 | note | Verification: THIESS (Initial) - HP
a06a1775-cea7-58c1-b432-25716d921461 | note | Verification: Client (Initial) - W
13f0f269-b7a1-4af2-b03b-67752d98f2b0 | signoff | HOLD POINT
c0cb6788-3965-4484-a705-97bbd90019b9 | checkpoint | 8 - Subgrade preparation – 200mm depth
9c171cb3-ec9d-5be5-bad9-6d1ddbdf45ba | note | Responsibility - SV
062dac09-94fd-5b24-a284-910fc8b03471 | note | Method - Visual
b1b6f6a2-95e6-5014-9063-f4b019578e86 | note | Conformance Criteria - Area to be ripped and conditioned to suit a minimum CBR value of 10.
f27465f9-3d39-513a-9527-0fe155d1950d | note | Specification Clause - C10 and C14 107501-EB-00000-27280-001 Rev A
2e44df58-fcaf-5ff9-a059-bb6f489c1fec | note | — EVAMP001-THS- CV-SPE-0001 clause 4.16
b6c48881-2b79-51de-9cb1-47d6ddb716f1 | note | Frequency - As required
ddbfe265-66f3-52cc-b623-8e274195eca7 | note | Verification: THIESS (Initial) - HP
7154ca3b-67dd-56b1-9d8b-78db4af67e66 | note | Verification: Client (Initial) - HP
168f5cc3-8d88-421c-9565-f5c26d87c71f | signoff | HOLD POINT
79069a6f-b2b3-4d3c-969e-1289ae8c6588 | checkpoint | 9 - Proof-roll subgrade surface prior to placement of embankment fill
8b435150-bba7-5e77-856f-924a702d588b | note | Responsibility - SV
af536d8d-5163-5340-9603-f7fbcd906753 | note | Method - Field Test
cf4e4513-6c66-5aa7-bb7b-34200e568e88 | note | Conformance Criteria - All subgrades and foundations shall be proof rolled under a standard 8 tonne axle load to confirm that, in the principal’s opinion, deflections are negligible.
32c2ac09-89b0-5fdd-9edb-28170f85b4ea | note | Specification Clause - EVAMP001-THS- CV-SPE-0001 clause 4.16
0af87cfa-98db-5a22-b888-3d2f7a484b99 | note | Frequency - As required
61a0e4bb-f44c-5eb0-b941-093bd4a953c2 | note | Verification: THIESS (Initial) - HP
b0966c58-5836-5705-b33e-8393613942a3 | note | Verification: Client (Initial) - W
36764525-779a-4fc8-a572-9a7e94d16565 | signoff | HOLD POINT
4d55a7f1-2c81-44b5-9dc5-ed97abd0ba02 | checkpoint | 10 - Surface level check/ and survey pick-up
51bc224c-27e3-5e0c-80f6-a2e6d2054c64 | note | Responsibility - Surv
ef661131-cc5e-5b0f-b4ff-68ab49f56811 | note | Method - Survey/ Field test
68475317-1ce6-5ec7-b034-3ade90d539c5 | note | Conformance Criteria - Surface level as per Table 10 C15
8a1023af-816e-520a-8723-fe591d351ba3 | note | ○ DXF file submitted to Company
97af5012-e1b2-5af8-ac00-5fb60f116721 | note | Specification Clause - EVAMP001-THS- CV-SPE-0001 clause 4.16
5475fdaa-4e74-5684-b88c-8e58ad660819 | note | Frequency - As required
ee04dbd1-67d7-572e-81b7-b590ce56e79e | note | Verification: THIESS (Initial) - HP
acf769ba-8e4c-52b1-98b1-88cc98d065d8 | note | Verification: Client (Initial) - HP
c0ed4d25-9b6b-4184-b44d-68802918898c | signoff | HOLD POINT
73d3b62e-a903-4feb-a426-0c34befe60ce | section | 3 - Post Construction
2f984755-ba40-4cc3-b416-3add8ad7784a | checkpoint | 11 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
be29273c-54cc-5520-9b4b-d7952fdfc881 | note | Responsibility - ENG
8aa7fd2b-ffa7-53f2-871e-f32e90abb977 | note | Method - Visual
48e7cfd9-8a47-5bde-bbbd-fe59f866fd05 | note | Conformance Criteria - GDP permits closed.
38b30851-a13b-557a-a56c-1db39fd8c18b | note | ○ ITP closed. Approved MDR
db1dbfa0-2f1b-50f7-b23f-cb629a1ae23d | note | Specification Clause - EVAMP001- EVA-EN-PLA- 0001
87148216-c0ec-53bb-8f19-6c24a4a841a7 | note | — EVA PMP
0e895a94-a258-54ec-8724-ed3fe3f563e0 | note | Frequency - As required
7c3bfccd-721e-5a2d-b6f0-46e311c73b22 | note | Verification: THIESS (Initial) - HP
c126e273-ed25-5116-b5ad-52ed11fbf4f9 | note | Verification: Client (Initial) - HP
e895a0c2-1edb-4078-895e-0d5a8db7fc2e | signoff | HOLD POINT
8d01fb9a-7180-4365-83a3-24632e66a1e4 | checkpoint | Final Inspection
d2cbae7a-78cd-56c4-a6e2-0083cadab2f2 | tickbox | Conformance to Specification
77c1533c-742e-5254-98e8-5da85d6bb876 | tickbox | Requires Re-Work:
b638b8bd-2caa-5ad8-b27c-94b367f08c29 | textbox | (Provide Details):
88482e79-13ef-5572-827b-c88e216c4903 | tickbox | Non-Conformance
8be7b2ff-7923-5a0e-b1bd-38c61db400de | textbox | NCR No:
fb47f401-cef4-4efb-819c-6ff531e5365c | signoff | Approved by THIESS QA Representative / THIESS Project Manager / Client