## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | EVAMP001-THS-4000-QA-ITP-008 - Embankment Construction | itp |  |  |  |  | EVAMP001-THS-4000-QA-ITP-008 - Embankment Construction - Rev 0
section | 1 - Pre-Construction
checkpoint | 1 - Drawings supplied most current IFC
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Reviewed drawing register
label | Specification Clause - Reviewed drawing register
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 2 - Define Lot dimensions
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Allocate Lot No to ITP and update Lot register
label | Specification Clause - Lot register.
label | — EVAMP001-THS-CV-SPE-0001
label | — EVAMP001-THS-CV-SPE-0002
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 3 - Lot Register/ WBS submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved WBS
label | Specification Clause - Approved WBS
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - WP
label | Verification: Client (Initial) - W
checkpoint | 4 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Topsoil stripping ITP signed off
label | Specification Clause - Approved QMP. Approved ITP
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
section | 2 - Construction
checkpoint | 5 - Ensure Embankment Construction materials have been approved for use and within specification
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Embankments (general fill material)
label | ○ Less than 30% passing 0.075mm sieve
label | ○ Liquid limit 20% to 60%
label | ○ Soaked CBR = or >3% (STD compaction @ OMC), 1 test per 5,000 m3
label | Specification Clause - EVAMP001-THS-CV-SPE-0001
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 6 - Construction Layer Thickness (300mm)
label | Responsibility - SV
label | Method - Visual
label | Conformance Criteria - Depths of such layers shall not exceed the capability of the proposed plant and in any case shall not exceed 300 mm uncompacted.
label | Specification Clause - EVAMP001-THS-CV-SPE-0001 clause 4.17
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
label | Records or Comments - On site verification sheet and survey
holdpoint | HOLD POINT
checkpoint | 7 - Place and compact general fill layer – Subgrade
label | Responsibility - ENG
label | Method - Field Test
label | Conformance Criteria - Material containing a high proportion of large particles may be used in embankments using the Mechanical interlock method of construction.
label | ○ Field density standard minimum Dry density test to be 95%, OMC -1%, +2% with a minimum layer thickness of 150mm and maximum 300mm. Material greater than 600mm may be allowed to be used in the Embankment.
label | Specification Clause - EVAMP001-THS-CV-SPE-0001 clause 4.17
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
label | Records or Comments - On site verification sheet, NATA Test report
holdpoint | HOLD POINT
checkpoint | 8 - Subgrade in cut
label | Responsibility - ENG
label | Method - Survey/ Field test
label | Conformance Criteria - For subgrades under road/rail pavements and buildings/structures, the materials exposed at the subgrade level of cuttings is to have a minimum CBR of 3.
label | Specification Clause - EVAMP001-THS-CV-SPE-0001 clause 4.16
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 9 - Proof rolling
label | Responsibility - ENG/ SV
label | Method - Field test
label | Conformance Criteria - The embankment will be proof rolled with either Proof rolling shall be undertaken using a 10,000 L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes.
label | Specification Clause - EVAMP001-THS-CV-SPE-0001 clause 4.26
label | Frequency - As required, Each lot
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
label | Records or Comments - On site verification sheet
holdpoint | HOLD POINT
checkpoint | 10 - As-built of completed surface
label | Responsibility - ENG/SURV
label | Method - Survey
label | Conformance Criteria - Survey to be completed of the finished surface to confirm to the levels as shown on the drawings with deviations as per Top of earthworks other than the subgrade and pad level ± 50,
label | ○ Road subgrade & building / structure pads +0 -25
label | Specification Clause - EVAMP001-THS-CV-SPE-0001 Appendix A clause 6
label | Frequency - Each finished surface
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
label | Records or Comments - Survey report
holdpoint | HOLD POINT
section | 3 - Post Construction
checkpoint | 11 - Works completed and updated ITP/ Lot Register/ MDR and close out of GDP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - ITP closed. Approved MDR
label | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
label | — EVA PMP
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | Final Inspection
bool | Conformance to Specification
bool | Requires Re-Work:
textbox | (Provide Details):
bool | Non-Conformance
textbox | NCR No:
holdpoint | Approved by THIESS QA Representative / THIESS Project Manager / Client