## Sheet1
3.1 | Material delivery | - each pipe welding location check pipes to be welded - each EF fitting - check bags undamaged and sealed | - Pipes shall be DN180 PE100 PN16 - EF fittings correct size, SDR, PE100 and pressure rating. | - Photo of markings and labels on pipe. - Delivery docket/ packing slip - Scan bar code on fitting | On delivery | Visual | V | CR, IP | 3.1 - Material delivery | Inspection Point: Quality Control Activity - - each pipe welding location check pipes to be welded - each EF fitting - check bags undamaged and sealed | Acceptance Criteria - - Pipes shall be DN180 PE100 PN16 - EF fittings correct size, SDR, PE100 and pressure rating. | Verifying Document - - Photo of markings and labels on pipe. - Delivery docket/ packing slip - Scan bar code on fitting | Frequency - On delivery | Inspection Type (Visual, other) - Visual | Inspection: Key - V | Inspection: By - CR, IP | 3.1 - Material delivery
Inspection Point: Quality Control Activity - - each pipe welding location check pipes to be welded - each EF fitting - check bags undamaged and sealed
Acceptance Criteria - - Pipes shall be DN180 PE100 PN16 - EF fittings correct size, SDR, PE100 and pressure rating.
Verifying Document - - Photo of markings and labels on pipe. - Delivery docket/ packing slip - Scan bar code on fitting
Frequency - On delivery
Inspection Type (Visual, other) - Visual
Inspection: Key - V
Inspection: By - CR, IP