## WBS Expo
WORK BREAKDOWN STRUCTURE | BUILDING | LEVEL | ZONE | ROOM | ITP | *incl ITP01 Soffit Lining
Zone C | [5 empty] | *incl ITP02 Speedpanel
| Building D | Ground Floor | Zone 84 | T04 | *incl ITP03 Plaster Walls | *incl ITP03 Plaster Walls
|  |  |  | COMM LIFT LOBBY GF.D.014 | *incl ITP02 Speedpanel | *incl ITP04 Ceilings (grid/sheeting)
[5 empty] | *incl ITP03 Plaster Walls | *incl ITP05 Shaft Lining
[5 empty] | *incl ITP04 Ceilings (grid/sheeting) | *incl ITP06 Door Frames
|  |  | Zone 85 | T05 | *incl ITP03 Plaster Walls
|  |  |  | Riser GF.D.008 | *incl ITP02 Speedpanel
|  | Level 1 | Zone 84 | T06 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  |  | Riser 1 | *incl ITP02 Speedpanel
|  |  |  | Riser 2 | *incl ITP02 Speedpanel
|  |  |  | Riser 3 | *incl ITP02 Speedpanel
|  |  |  | Riser 4 | *incl ITP02 Speedpanel
|  |  |  | Riser 5 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 6 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 7 | *incl ITP02 Speedpanel
|  |  |  | Riser 8 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 9 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 10 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 11 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Smoke Lobby 01.D.037 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
|  |  |  | Smoke Lobby 01.D.059 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
|  |  |  | WCPU(M) 01.D.001 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  |  | WCPU(F) 01.D.002 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  |  | DDA 01.D.003 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  | Zone 85 | T06 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
|  |  |  | Riser 12 | *incl ITP02 Speedpanel
|  | Level 2 | Zone 84 | T07 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  |  | Riser 1 | *incl ITP02 Speedpanel
|  |  |  | Riser 2 | *incl ITP02 Speedpanel
|  |  |  | Riser 3 | *incl ITP02 Speedpanel
|  |  |  | Riser 4 | *incl ITP02 Speedpanel
|  |  |  | Riser 5 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 7 | *incl ITP02 Speedpanel
|  |  |  | Riser 8 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 9 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 10 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 11 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Smoke Lobby 02.D.042 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
|  |  |  | Smoke Lobby 02.D.040 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
|  |  |  | WCPU(M) 02.D.003 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  |  | WCPU(F) 02.D.001 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  |  | DDA 02.D.002 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  | Zone 85 | T07 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
|  |  |  | Riser 12 | *incl ITP02 Speedpanel
|  | Level 3 | Zone 84 | T08 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  |  | Riser 1 | *incl ITP02 Speedpanel
|  |  |  | Riser 2 | *incl ITP02 Speedpanel
|  |  |  | Riser 3 | *incl ITP02 Speedpanel
|  |  |  | Riser 4 | *incl ITP02 Speedpanel
|  |  |  | Riser 5 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 7 | *incl ITP02 Speedpanel
|  |  |  | Riser 8 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 9 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 10 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 11 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Smoke Lobby 03.D.059 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
|  |  |  | Smoke Lobby 03.D.005 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
|  |  |  | WCPU(M) 03.D.002 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  |  | WCPU(F) 03.D.003 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  |  | DDA 03.D.001 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  |  | T08 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
|  |  | Zone 85 | Riser 12 | *incl ITP02 Speedpanel
|  | Level 4 | Zone 84 | T09 | *incl ITP03 Plaster Walls
*incl ITP06 Door Frames
|  |  |  | Riser 1 | *incl ITP02 Speedpanel
|  |  |  | Riser 2 | *incl ITP02 Speedpanel
|  |  |  | Riser 3 | *incl ITP02 Speedpanel
|  |  |  | Riser 4 | *incl ITP02 Speedpanel
|  |  |  | Riser 7 | *incl ITP02 Speedpanel
|  |  |  | Riser 8 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 9 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 10 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 11 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Smoke Lobby 03.D.059 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
|  |  |  | Smoke Lobby 03.D.005 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
|  |  |  | WCPU(M) 03.D.002 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  |  | WCPU(F) 03.D.003 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  |  | DDA 03.D.001 | *incl ITP03 Plaster Walls
|  |  | ` |  | *incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  | Zone 85 | T09 | *incl ITP03 Plaster Walls
|  |  |  | Riser 12 | *incl ITP02 Speedpanel
|  | Level 5 | Zone 84 | Covered Plant | *incl ITP03 Plaster Walls

## WBS Express
WORK BREAKDOWN STRUCTURE | BUILDING | LEVEL | ZONE | ROOM | ITP
Zone C | Podium | LG | Zone 84 | Lift Lobby (Carpark) LM.D.010 | *incl ITP01 Soffit Lining |  | *incl ITP01 Soffit Lining
[5 empty] | *incl ITP03 Plaster Walls |  | *incl ITP02 Speedpanel
[5 empty] | *incl ITP06 Door Frames |  | *incl ITP03 Plaster Walls
|  |  | Zone 85 | Fan room LG.B.579 | *incl ITP02 Speedpanel |  | *incl ITP04 Ceilings (grid/sheeting)
*incl ITP05 Shaft Lining
|  | LGM | Zone 84 | Lift Lobby (Carpark) LM.D.040 | *incl ITP01 Soffit Lining |  | *incl ITP06 Door Frames
*incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
|  |  |  | T03 | *incl ITP02 Speedpanel
*incl ITP03 Plaster Walls
|  |  |  | T03 (Detail 5) | *incl ITP03 Plaster Walls
|  |  |  | Comm Lift Lobby LM.D.034 | *incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP06 Door Frames
|  |  |  | Comm Lift Lobby LM.D.034 (Detail 7) | *incl ITP03 Plaster Walls
|  |  |  | Comm Lift Lobby LM.D.034 (Detail 2) | *incl ITP03 Plaster Walls
|  |  |  | Hydraulic Riser LM.D.026 | *incl ITP05 Shaft Lining
[5 empty] | *incl ITP06 Door Frames | `
|  |  |  | Riser 1 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 2 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 3 | *incl ITP02 Speedpanel
*incl ITP06 Door Frames
|  |  |  | Riser 4 | *incl ITP02 Speedpanel
|  |  |  | Loading Store LM.D.024 | *incl ITP03 Plaster Walls
|  |  |  | Loading Store LM.D.024 (Detail 1) | *incl ITP03 Plaster Walls
|  |  |  | Loading Store LM.D.024 (Detail 8) | *incl ITP03 Plaster Walls
|  |  | Zone 85 | Bin room LM.D.007 | *incl ITP03 Plaster Walls
|  |  |  | T02 | *incl ITP03 Plaster Walls
|  |  |  | T02 (Detail 6) | *incl ITP03 Plaster Walls
|  |  |  | T01 | *incl ITP03 Plaster Walls
|  |  |  | T01 (Detail 5) | *incl ITP03 Plaster Walls
|  |  |  | Riser 12 | *incl ITP02 Speedpanel