## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Fit Off |  |  |  |  | Yes | Fit Off Checklist | 0995f908-51ea-4d5d-a670-2bf7a9714e67
checkpoint-group |  |  | section | Laundry Fit Off
checkpoint-status |  |  | checkpoint | Laundry Trough
checkpoint-status |  |  | checkpoint | Laundry Trough Mixer
checkpoint-status |  |  | checkpoint | Laundry Trough Mini Stops
checkpoint-status |  |  | checkpoint | Laundry Trough Waste
checkpoint-group |  |  | section | Kitchen Fit Off
checkpoint-status |  |  | checkpoint | Kitchen Mini Stops
checkpoint-status |  |  | checkpoint | Kitchen Sink Waste
checkpoint-status |  |  | checkpoint | Kitchen Sink Mixer
checkpoint-status |  |  | checkpoint | Kitchen Dishwasher
checkpoint-status |  |  | checkpoint | Kitchen Cooktop
checkpoint-group |  |  | section | Bathroom Fit Off
checkpoint-status |  |  | checkpoint | Bathroom Shower Mixer
checkpoint-status |  |  | checkpoint | Bathroom Shower Rail/Rose
checkpoint-status |  |  | checkpoint | Bathroom Basin
checkpoint-status |  |  | checkpoint | Bathroom Basin Mixer
checkpoint-status |  |  | checkpoint | Bathroom Bottle Trap
checkpoint-status |  |  | checkpoint | Bathroom Toilet
checkpoint-status |  |  | checkpoint | Bathroom Urinal
checklist-flat |  |  | checklist | Suspended Sewer Drainage |  |  |  |  | Yes | Suspended Sewer Drainage Checklist | 1d756ec5-bc83-4db2-959a-dc27127148da
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary
checkpoint-status |  |  | checkpoint | Test sewer
checklist-flat |  |  | checklist | Pits/Pumps/Tanks |  |  |  |  | Yes | In-Ground Pits/Pumps/Tanks Checklist | 1d936c12-bbab-4acc-97f0-98b1e16a3830
checkpoint-status |  |  | checkpoint | Sewer pump well
checkpoint-status |  |  | checkpoint | Storwater pump well
checkpoint-status |  |  | checkpoint | Stormwater pits
checkpoint-status |  |  | checkpoint | Grease interceptor trap
checkpoint-status |  |  | checkpoint | Conduits rain to IFC location
checkpoint-status |  |  | checkpoint | Torpedo tanks
checkpoint-status |  |  | checkpoint | Stormwater detention system
checklist-flat |  |  | checklist | Corridor |  |  |  |  | Yes | Corridor Checklist | 233e6f4a-fbb4-41e2-a3e6-50a423da7001
checkpoint-status |  |  | checkpoint | Rainwater
checkpoint-status |  |  | checkpoint | Hot Water
checkpoint-status |  |  | checkpoint | Hot Water Lagged
checkpoint-status |  |  | checkpoint | Cold Water
checkpoint-status |  |  | checkpoint | Test Hot Water
checkpoint-status |  |  | checkpoint | Test Cold Water
checkpoint-status |  |  | checkpoint | Test Rain Water
checkpoint-status |  |  | checkpoint | Fire Caulking (Corridor to Apt)
checkpoint-status |  |  | checkpoint | Cold Water Meter Manifold
checklist-flat |  |  | checklist | Commissioning |  |  |  |  | Yes | Commissioning Checklist | 2aaaa2ee-138d-4546-ad68-2daa5c20e37e
checkpoint-status |  |  | checkpoint | Includes bathroom, bathroom ensuite, kitchen, laundry
checkpoint-status |  |  | checkpoint | Test Hot Water Temperature
checkpoint-status |  |  | checkpoint | Test Waste for leaks
checkpoint-status |  |  | checkpoint | Run Cycle on Dishwasher
checklist-flat |  |  | checklist | DDA Bathroom Fit Off |  |  |  |  | Yes | DDA Bathroom Fit Off Checklist | 6364b91c-9105-4ef4-b4ee-7a5e36372635
checkpoint-status |  |  | checkpoint | Bathroom Shower Mixer
checkpoint-status |  |  | checkpoint | Bathroom Shower Rail/Rose
checkpoint-status |  |  | checkpoint | Bathroom Basin
checkpoint-status |  |  | checkpoint | Bathroom Basin Mixer
checkpoint-status |  |  | checkpoint | Bathroom Bottle Trap
checkpoint-status |  |  | checkpoint | Bathroom Toilet
checkpoint-status |  |  | checkpoint | Bathroom Urinal
checklist-flat |  |  | checklist | Penetrations |  |  |  |  | Yes | Penetrations Checklist | 83725e53-b124-4575-80fd-e03edc5b58e5
checkpoint-status |  |  | checkpoint | All works to be set our as per approved IFC drawings.
checkpoint-status |  |  | checkpoint | Fire collar installation
checkpoint-status |  |  | checkpoint | Cast in drains
checkpoint-status |  |  | checkpoint | Photos of collar end labelling referencing fire matrix if required
checklist-flat |  |  | checklist | Apartment Suspended Drainage |  |  |  |  | Yes | Apartment Suspended Drainage Checklist | ba184bea-400d-46cb-851a-d5a440075a3f
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing. Includes bathroom, bathroom ensuite, kitchen, laundry
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary
checklist-flat |  |  | checklist | Rough In |  |  |  |  | Yes | Rough In Checklist | c51c286d-2dcb-4099-9102-2992c4f0a52c
checkpoint-status |  |  | checkpoint | For apartments includes bathroom, bathroom ensuite, kitchen, laundry
checkpoint-status |  |  | checkpoint | High Level Rough In
checkpoint-status |  |  | checkpoint | Wall Set Out
checkpoint-status |  |  | checkpoint | Wall Rough In
checkpoint-status |  |  | checkpoint | Waste Rollovers
checkpoint-status |  |  | checkpoint | Gas
checkpoint-status |  |  | checkpoint | Test Water
checklist-flat |  |  | checklist | Suspended Copper Works |  |  |  |  | Yes | Suspended Copper Works Checklist | cda0a613-c9a6-46d0-94ea-bf6f941179ef
checkpoint-status |  |  | checkpoint | Pipework installed - domestic hot/cold/rain water
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire rated if necessary
checkpoint-status |  |  | checkpoint | Tested
checklist-flat |  |  | checklist | Suspended Stormwater Drainage |  |  |  |  | Yes | Suspended Stormwater Drainage Checklist | db846d74-294b-4bd2-8d46-af5658ff4cb4
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary
checklist-flat |  |  | checklist | Other Areas Suspended Drainage |  |  |  |  | Yes | Other Areas Suspended Drainage Checklist | e33e393a-2e27-433e-8c8e-a29709ba4379
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing.
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | Smoke seal penetrations
checkpoint-status |  |  | checkpoint | Fire collars installed if necessary
checklist-flat |  |  | checklist | In-Ground Sewer Drainage |  |  |  |  | Yes | In-Ground Sewer Drainage Checklist | eda00818-4bd4-49e8-adbf-d03b7d25c79e
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Pipework checked for correct invert levels & gradients
checkpoint-status |  |  | checkpoint | Book inspection with VBA for in-ground drainage.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint-status |  |  | checkpoint | Test sewer
checklist-flat |  |  | checklist | In-Ground Stormwater Drainage |  |  |  |  | Yes | In-Ground Stormwater Drainage Checklist | f970fbfd-dca4-46c8-843c-cd1be20ddae6
checkpoint-status |  |  | checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint-status |  |  | checkpoint | Pipework installation
checkpoint-status |  |  | checkpoint | Pipework checked for correct invert levels & gradients
checkpoint-status |  |  | checkpoint | Pits checked for correct invert levels & finished floor levels
checkpoint-status |  |  | checkpoint | Ensure correct locations of pits.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.