## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
f5d6cf74-3858-4133-bdd5-7bb57813e537 | checklist | ITC - (1) Drawing Register (For Construction) |  | Drawing Register (For Construction)
aad4b87d-4b7b-46c8-a823-ccc7d9e67e7b | section | Details
2541882c-79d9-418f-bd3b-9db024ea6ba7 | checkpoint-no-value | DRAWING REGISTER
250789a4-9776-5e5f-9b2f-519ed4d4eca7 | date | Date:
db63807a-c4ba-5c96-b76e-77f3a3fe1209 | textbox | DRAWING No.
27c39b8a-a946-545c-8c20-7d123495383e | textbox | DRAWING TITLE
a3bbe8be-e311-5012-a638-270d16970d96 | textbox | REVISION / ISSUE
01421f78-c2d5-4611-b4ff-28f6d7e34437 | checkpoint-no-value | DISTRIBUTION:
50fe52e9-2c59-5557-af8e-d6bc432aed5e | textbox | SITE OFFICE
2b420d1a-6e26-5132-920b-4b1c1c940bbe | textbox | SITE
cac145de-7aba-5283-b665-535ce1d9c27d | textbox | NCR No:
250cc4cb-dda0-456a-8471-e9f9a243c797 | checkpoint | FINAL ACCEPTANCE:
a4401c9d-ac06-58c0-96de-e7ebc3f629e6 | textbox | HEYDAY GROUP (REPRESENTATIVE)
6f94610e-9668-5ebc-b558-767516745105 | textbox | CLIENT (REPRESENTATIVE)
95121fa7-cb8f-5402-b46a-404cfa74072d | textbox | AUTHORITY (IF APPLICABLE)
56bda5b1-60af-4989-9c12-de6a6183393e | signoff | Signoff
f813d2a6-3065-45f0-aa92-6085eaee1bca | checklist | ITC - (2) Temporary Wiring-Temporary DB's |  | Level / Area:
88e15ede-d00d-42b9-a4dd-b98f49ff0da8 | section | Details
12f4cb67-4cce-4336-b94c-05dc018f0722 | checkpoint | EQUIPMENT LOCATED CORRECTLY
6349a484-251b-4323-a955-3c875323cc85 | checkpoint | EQUIPMENT SECURE/BOLTED DOWN
ba41abc7-49c9-4326-94d8-1f40fe3401f3 | checkpoint | WIRING INSTALLED CORRECTLY
b7c3ca9e-aff5-4e4b-bbbd-5d285dec49d3 | checkpoint | WIRING MECHANICALLY PROTECTED
48ab3d59-5030-4027-9809-3fb0778f9de2 | checkpoint | POLE FILLERS INSTALLED
cbc1ce9f-f1dd-4bb2-a320-f8bb42a65d30 | checkpoint | ESCUTCHEON / COVERS CHECKED
c056966f-e438-4d1a-bb9a-8b15ae9fb2f9 | checkpoint | LOCKABLE COVERS AND PADLOCKS
a85f4fe2-0158-41b6-9866-d19be8371c12 | checkpoint | EQUIPMENT TESTED AND TAGGED
4b4b9dca-b831-411c-8743-6012c0dbbf27 | checkpoint | TEMPORARY BOARD NUMBERED
12685319-e003-4ac9-a859-10c0bed277f1 | checkpoint | BOARD LABELLED FOR SOURCE OF SUPPLY
308dce2c-5cc7-401d-a771-b7f65ffa691b | checkpoint | FINAL ACCEPTANCE:
b8876a58-fc97-5412-8616-56bf087c8ab7 | textbox | HEYDAY GROUP (REPRESENTATIVE)
fbcbd81c-7867-579d-aac8-8e9922a32a99 | textbox | CLIENT (REPRESENTATIVE)
51f315c0-2ffa-553f-9a3a-6336e0f09047 | textbox | AUTHORITY (IF APPLICABLE)
7d72b4ae-6d3d-4dbf-b25e-588ac811cb0e | signoff | Signoff
2ccddc3f-79bf-440f-b556-c4fa8a88f0c8 | checklist | ITC - (3) Main and Distribution Panels |  | Board Type or Number or Area:
d13b06d5-0bb4-46eb-a890-fa07d2edff4e | section | Details
6d8b72e4-8de4-4f0b-9a8d-818be71a288e | checkpoint | ACCEPTANCE CRITERIA
776674ea-da15-4be1-9dca-ac286fb2db38 | checkpoint | MFG QA
65239a86-5aa0-4d98-97f9-4a28cd3f7014 | checkpoint | DAMAGE
27389368-a35e-4146-9f98-ffd5185ab488 | checkpoint | LOCATION TO DRAWING
080d76a1-370f-4b4d-97a3-bb126ce77637 | checkpoint | EQUIPMENT TO DRAWING
338d1769-7e14-46ac-8ea8-6d82b82f970e | checkpoint | CONNECTIONS INCOMING & OUTGOING BY HEYDAY.
aee47c2d-a7a5-4ee7-b9cf-69b80db54d72 | checkpoint | NEUTRAL CONNECTIONS CORRESPOND
b38bf6e1-24e1-4a8d-8d9b-abe2da8eff22 | checkpoint | CORRECT EARTHING AND SOLIDLY FIXED
6bf77064-bd1f-4217-86f7-d72dc37b77de | checkpoint | POLE FILLERS INSTALLED
45b9463c-676a-482f-9bbe-b26f7804c2a8 | checkpoint | ALL CABLE ENTRIES WITH ESCUTCHEON PLATES AND SEALS FITTED
21dde43c-8c10-432b-b1b3-8ab688d8b159 | checkpoint | BOARD SEALED AND LOCKED FOR SAFETY INC: FRONT AND REAR PANELS
257d49d9-cc96-49ae-96a3-c88fad88083d | checkpoint | LABELS AND SCHEDULE LIST CORRECT AND INSTALLED
8b87a991-cfed-449d-ad40-d84f18ea73de | checkpoint | FINAL ACCEPTANCE:
970145da-a808-5850-881d-b2389fcee499 | textbox | HEYDAY GROUP (REPRESENTATIVE)
f6e48934-8047-501b-8646-eae05fef8b42 | textbox | CLIENT (REPRESENTATIVE)
8c8b9863-38df-5541-b49c-7cab4edfd17a | textbox | AUTHORITY (IF APPLICABLE)
c85d0212-7388-4961-87e9-8a08c686aa34 | signoff | Signoff
319443d7-bf58-488c-a383-f37bd58a4f69 | checklist | ITC - (3A) MSB and DB's TEST Sheet |  | MSB AND DB's
62e515f8-c8e9-4daa-a331-7ac39e69d8b0 | section | Submain Details as per ITC 4A
6e1c58dc-c646-4aa2-bb01-ec03a827b55f | checkpoint-no-value | Details
64c07371-608c-5cc8-a50e-501ae895fd1f | textbox | Area
6adf9074-36d9-5bec-adb3-46683dc1c5cb | textbox | From
0466b4b5-3754-5e18-b642-e8b7cbe39266 | textbox | Cable No.
e7740768-545a-5f53-942c-49234cf179fd | textbox | MCCB Model
eb1d46bf-33b6-59b8-834c-6f15e678b2e0 | textbox | Cable Type
44debb08-9a78-5221-a5e1-dbfe4978f74d | textbox | Rating (A)
452971e7-49e2-5902-be43-2ebd9f62beb6 | textbox | Drawing No.
914e14b0-97f1-5a30-bb69-72f31e3a7a06 | textbox | To
009f439d-a876-51c8-a6fc-e3bfbfac8d13 | textbox | Cable Size
4bd069ad-3fd2-5cd6-a7ec-63060b3437a4 | textbox | Trip Unit
8d657613-d035-5617-b5e7-d7980c496dc6 | textbox | Length
116d93f2-3a99-5e61-98e7-aa13f830fe74 | textbox | Trip Setting (A)
7680ed0f-601b-5d6a-9387-a88eab8f9f09 | textbox | Cores
9eb77f47-1e65-40ea-a897-0a5b281371f5 | section | 1 - Checklist - Visually Check Cable is -
45a40292-0400-410f-806f-6c544183ecf1 | checkpoint | Approved Factory Acceptance Test completed?
906b55c0-ec6a-48c3-b991-8bdb6e8ebda7 | checkpoint | Switchboard is secure and ready for Consumer Main/Submain Installation
aeefb38f-3ff5-43bc-906e-de07346159c0 | checkpoint | Consumer Main/Submain Installed?
b4828647-905d-40aa-a66c-d57abe401963 | checkpoint | Verify C/B Trip Settings are Correct.
1d824e91-9e7c-4928-838c-731028f38bae | checkpoint | Consumer Main/Submain Test has been completed as per Heyday ITC-4A
22322df5-c3dd-4f56-bd22-43c28f969928 | checkpoint | Are the connections tight, correct tension and marked?
165c1940-16da-4075-9ee5-e6acd7ba4ada | checkpoint | Switchboard is ready to be energised?
6c3f69ff-c0c5-4e60-bb07-ab2eaaca67f3 | section | 2 - Pre Energisation Checks (AS/NZS 3000)
e4158931-4338-42bc-a9f3-4b1052ac0ae0 | checkpoint | Earth Continuity (Value must be less than 0.5 ohms)
f289b477-6169-5016-827a-ac8d9f53a271 | textbox | Earth Size:
06366190-80fb-50fe-9f4d-82e519f9a751 | textbox | FROM:
c17bad6a-2b3f-5a3d-910a-148b0f92675e | textbox | TO:
39691bb6-28e3-563a-855e-785201badece | textbox | Point to Point Reading:
f85622c4-23d3-53f7-b340-3cb96dfb222c | textbox | Ω
2f414361-fcd0-4d2b-acaf-68d8ec79ce8e | section | 3 - BUSBAR Insulation Resistance Test (AS/NZS 3000)
7f7f96af-13b3-4c7d-ae90-db98c0b3bf56 | checkpoint | RED TO WHITE
442003d5-3965-579b-b737-8a7b4a4dd845 | textbox | RED TO WHITE:
eb9320c6-8c31-4f95-926a-b4e2d5d79e62 | checkpoint | RED TO BLACK
77a007c7-d14c-54e4-b8bd-83d9f88a2d9b | textbox | RED TO BLACK:
d93b4fc8-4da1-4ccd-a892-a4b4f02d36bd | checkpoint | RED TO EARTH
439d358c-fd0b-5d45-b6d9-0ae3c1dd51e1 | textbox | RED TO EARTH:
b134e77c-9043-43c0-aa20-e66b43da773e | checkpoint | WHITE TO BLUE
a196c2ea-6860-5a58-b4ba-1c439a7baa0f | textbox | WHITE TO BLUE:
a95df478-e506-48e1-b830-4adac7006e8c | checkpoint | WHITE TO BLACK
c4fb44a5-1b80-58e7-9f48-7efd3869111e | textbox | WHITE TO BLACK:
5fa587cc-0c68-4d55-b016-b6ded1eacfac | checkpoint | WHITE TO EARTH
3556f166-aaed-5ccd-84a0-a968b9a0528c | textbox | WHITE TO EARTH:
1ad3a7b6-949a-450e-b63e-6f705f67553f | checkpoint | BLUE TO RED
e7032837-1020-5063-b3da-3a8c1b217428 | textbox | BLUE TO RED:
f50aef8d-eb3a-4854-870b-e68000fa0d55 | checkpoint | BLUE TO BLACK
38fb592d-c1bf-5ff8-b595-fb66235587c3 | textbox | BLUE TO BLACK:
5ec20a1d-aa34-4a06-9989-6971eb4214c6 | checkpoint | BLUE TO EARTH
39767314-493e-5d40-9849-56397389b30f | textbox | BLUE TO EARTH:
1348946a-0513-4856-9098-20bb12b0778d | section | 4 - Post Energisation Checks (AS/NZS 3000)
2366804a-cd34-4733-ae2e-1dec4d8540df | checkpoint | Phase Rotation
87ace173-f1f0-5c1e-b48d-b9ef15f9b916 | tickbox | Clockwise →
abf202ea-be68-5b91-af37-2f92730d8024 | tickbox | Anti Clockwise ←
09c00a2b-f2ec-4efe-b541-8cd5725c8392 | section | 5 - Voltage Checks (AS/NZS 3000)
88502263-1634-41e3-bc9b-987cb2e2e6db | checkpoint | RED TO WHITE
85662292-1199-5d95-ae73-691283f0b96a | textbox | RED TO WHITE:
2f7277d2-7bd1-448e-94a3-6c8f7cbaf475 | checkpoint | RED TO BLACK
82232b5c-8c09-5dae-beb8-25e97d7c1b2b | textbox | RED TO BLACK:
85272da4-7783-4be3-ba1f-8c3b7747df22 | checkpoint | RED TO EARTH
a187ad33-e9a0-58a4-a5f7-9667b5aa44f5 | textbox | RED TO EARTH:
c4d1eddf-aa12-47bc-88dd-eed455358354 | checkpoint | WHITE TO BLUE
60b22ca6-f7b6-5d23-8676-851001ab765d | textbox | WHITE TO BLUE:
5d08a09e-5a04-41e2-845b-b5b400b9448a | checkpoint | WHITE TO BLACK
e71e3c01-6e17-51c7-a24c-f874398497fa | textbox | WHITE TO BLACK:
52bcbec6-9e37-4049-84c0-968e15d872c9 | checkpoint | WHITE TO EARTH
5cf8227d-8893-57e2-91b5-b69af4a6e4bd | textbox | WHITE TO EARTH:
5743b2be-5821-4f41-9714-78815c732a51 | checkpoint | BLUE TO RED
7dc50fd6-4805-556e-a1ce-377e612e10bf | textbox | BLUE TO RED:
2a3b21ac-9a86-433f-bf2a-742a6209c780 | checkpoint | BLUE TO BLACK
794f8a53-2697-5648-8e0b-fe7d49cb593f | textbox | BLUE TO BLACK:
07575b2c-1d0f-4895-9452-c4079c89ca9e | checkpoint | BLUE TO EARTH
011c7872-1317-5d5c-847c-c27f99d9f910 | textbox | BLUE TO EARTH:
1cd91c38-4a9c-41b8-a7f0-742d1b811ad2 | section | Test Equipment
9240630d-17bf-4b0a-bfff-0f515e8ff72b | checkpoint | Multimeter
80860275-dbff-56e5-86ab-cc0e3df46acb | textbox | Brand/Model
8e31a72f-4119-5056-83c8-24c4f5f61857 | textbox | Serial No.
8b6d3580-f188-5bca-a056-3165281396ce | textbox | Calibration Due
6a4e1255-bb04-538f-b427-2147a88b1bd5 | textbox | Tester
d7acad9c-35f6-56db-8ec0-aa92865d66bb | date | Date:
115cf6be-87ae-4504-a4a3-bfd1bbb3162d | checkpoint | Insulation Resistance Tester
6ebfe217-9f1c-54ca-abee-80b4dae13f44 | textbox | Brand/Model
38a0cd45-4810-5627-b0ca-61f9349cbf06 | textbox | Serial No.
894bfb83-ad38-5c20-a8c2-2778b7756e3c | textbox | Calibration Due
ef86c3b7-0f8e-5519-a8b0-bd26c43d7151 | textbox | Tester
20e16536-eb3b-5c0c-a637-69763e685c21 | date | Date:
726ac892-78c1-470b-89cf-09e8c75c1b8b | checkpoint | Phase Rotation Meter
49101034-65a6-585a-bcea-05b6ddb43683 | textbox | Brand/Model
83ba4cb9-af1b-5571-ae2a-a3604d1a73cf | textbox | Serial No.
f75b19b1-1491-5ab2-8d37-ded460ed11b9 | textbox | Calibration Due
18506efc-fc30-5eed-aa76-f6aea7f4c568 | textbox | Tester
22bfe6cb-cbff-5063-87f2-8d6b6ec99181 | date | Date:
4fc8c6bd-4578-435d-8283-91c9cd27d655 | checklist | ITC - (4) Main and Submain |  | MAINS AND SUBMAINS
beb1c845-04eb-4218-8e1a-b06b922f0875 | section | Details
638ba9c3-3fc6-4903-a6b6-c450ddcb7216 | checkpoint-no-value | Details
ca31c099-6272-5be7-9f59-a259846cdcc3 | textbox | LEVEL
ca14171d-a6f8-5091-9c22-6faf059b542b | textbox | AREA
9bfc2647-9994-5677-943d-8857704d1750 | textbox | FED FROM
0f1dda67-789c-551c-87f5-71e4dd564e58 | textbox | TO DB No
3fff7e7e-e1d9-49d9-b2bc-6213cb0d124e | checkpoint | COMPLIES TO SPEC AND LATEST DRG
a9a8cdfb-cde0-4d85-ba89-3f51a58f9cfd | checkpoint | SIZE CORRECT
e7a0603e-ab1c-4d85-a2a7-46ef2c6c214b | checkpoint | INSTALLED CORRECT
39532773-cafb-49f4-bd9d-1757274049ee | checkpoint | TERMINATED
2caa3a94-3242-452f-88c6-350864193ced | checkpoint | TESTED AS PER ITC 4A
52d84b74-b36d-4497-8d11-de85e5e6e0ec | checkpoint | NOEW SUBMITTED TO COUNCIL
fd510c81-934e-40e6-9379-cfce93d64e93 | checkpoint-no-value | REMARKS/Submain ID
8f8bb2b9-a020-5303-a74c-f36ea7c05962 | textbox | REMARKS/Submain ID:
4bbf6621-9e06-406a-97a8-776a9cf9c235 | checkpoint | FINAL ACCEPTANCE:
fecc5fd7-962c-55cc-9ce3-4788228ace0f | textbox | HEYDAY GROUP (REPRESENTATIVE)
304b5f76-76f2-5a9d-8fd6-f1113295313d | textbox | CLIENT (REPRESENTATIVE)
f3e13d85-87a9-5ce2-bdd0-67a2d6cf001e | textbox | AUTHORITY (IF APPLICABLE)
20326dc3-a95a-4288-8b3a-a61734c82681 | signoff | Signoff
a3d9f25a-0fbe-4f77-a8e2-9046d3755136 | checklist | ITC - (4A) Mains and Submains Test Results |  | MAINS AND SUBMAINS
87421f65-8e15-40a6-babe-2bf605cd6747 | section | Details
4c5715b8-6216-4d49-9b03-e266c211bd58 | checkpoint-no-value | Details
ddaa0d03-42f1-5570-94d0-37e3c69aa5b3 | textbox | Area
18c9ae67-d316-5d9e-ab61-7c863857e46c | textbox | From
c6fa3652-edac-54a3-88a4-56d62b1d2cf4 | textbox | Cable No.
9ff64501-e8c3-5681-8615-2d92f116c272 | textbox | MCCB Model
c01a3e34-774f-5a30-8bf3-1f1fe197e014 | textbox | Cable Type
23b9d0da-d1ef-59c9-ace3-5cb2304c6f86 | textbox | Rating (A)
7d60fed3-d267-5f1f-ad21-d05220685725 | textbox | Drawing No.
b5f8dbab-6090-5800-8fe8-c790e55d621b | textbox | To
6c8db617-86cb-55b2-8d82-30034df6ad5e | textbox | Cable Size
76d8c642-4254-58e6-94bc-d35c74a61492 | textbox | Trip Unit
8498f98a-05b6-56c4-aa44-fcfe16d5e034 | textbox | Length
03fb1759-dc61-5143-9846-6c7a78666674 | textbox | Trip Setting (A)
92b45e4e-e4c5-5aa9-98d8-3efdbe08902c | textbox | Cores
1e5ec618-0120-4b35-bd33-eb6fc40b654f | section | 1 - Visual Inspections (AS/NZS 3000) - Visually Check Cable is -
ae5e03fa-14b3-4d8f-a163-5c21fb712732 | checkpoint | Provided with adequate support, suspension and fixings?
d99941d6-bb46-48cf-9142-1df8eefad47c | checkpoint | Suited for the intended use?
6d6a7bb1-6e40-4354-b55e-684d34573b5e | checkpoint | Protected against mechanical damage, enviromental and other external influnece by enclosure?
19844d9f-be59-4f19-908b-9512c9dc9234 | checkpoint | Is the cable the correct type and size?
63846530-b692-4d3b-b28e-10221d198499 | checkpoint | Is the cable terminated at both ends?
3802d706-be9d-4819-a046-b603ee32d05c | checkpoint | Are the connections tight, correct tension and marked?
2b3a3883-22ef-4003-9665-7f5992489976 | checkpoint | Is the cable free of damaged?
8cfe3f48-4589-41df-a244-16bd09f7dd31 | checkpoint | Is the cable and terminations correctly labeled?
4b821596-ee8f-4809-87e8-d9aadf1d2f41 | section | 2 - Pre Energisation Checks (AS/NZS 3000)
9c0ba7b2-21a0-42c5-9942-efa050162957 | checkpoint | Bolt Tension Check/Bolt Lined and Tension noted?
8816131c-2f15-526d-995b-742bb2ceded9 | textbox | NM
307f91e5-008c-446d-898b-1da73c506a91 | section | 3 - Insulation Resistance Test (AS/NZS 3000)
88ff1eea-3060-45d4-a603-c64e9ac6819d | checkpoint | RED TO WHITE
6bebbcd1-6099-5bf1-8994-44e3937ef30d | textbox | RED TO WHITE:
ba614c7d-7ad1-4e61-b30f-c7bc0fcf1bff | checkpoint | RED TO BLACK
2d92bbed-21ed-5ddd-b28b-a358e4bd540c | textbox | RED TO BLACK:
24b96183-2364-4a5e-abc0-7020c67ed701 | checkpoint | RED TO EARTH
a7cd21ae-21a0-5ffb-a801-99303805190f | textbox | RED TO EARTH:
aa12ea2d-1997-4c66-9dd0-e47f7d275eea | checkpoint | WHITE TO BLUE
075d93bd-1925-5164-9ce4-03d2550cb425 | textbox | WHITE TO BLUE:
4892a8a0-48d5-45e2-b9ab-3d1d201784ef | checkpoint | WHITE TO BLACK
b2901432-21e5-5c1f-8d41-316b0b0bfb26 | textbox | WHITE TO BLACK:
52e00ea1-7c81-44c4-a38c-5e25e20d83f3 | checkpoint | WHITE TO EARTH
ecfdb74a-9092-5be7-9e2a-bab597617ed1 | textbox | WHITE TO EARTH:
3d17df27-6d51-4a58-b97a-1e61cb790652 | checkpoint | BLUE TO RED
e6be3c63-d573-5a59-9d69-1cb49b1dee91 | textbox | BLUE TO RED:
ccc140fa-ad4f-4b99-a84d-70752af156de | checkpoint | BLUE TO BLACK
e9aea0d9-506c-5769-8477-e671519bd96f | textbox | BLUE TO BLACK:
2ec0fa92-c1b3-4528-9eb0-a17e74727ec7 | checkpoint | BLUE TO EARTH
b9e81717-5a00-51ef-a9fc-132d4ae2f148 | textbox | BLUE TO EARTH:
0bd1c380-96e6-47b2-814b-5a84286e5b20 | section | 4 - Polarity Test
87193021-b4eb-4679-9a8b-6e29b620f347 | checkpoint | RED TO RED
37f70551-9ba6-5fd5-8a89-9d3d6213415c | textbox | RED TO RED:
004b8c26-a255-456f-960b-322c474e99b7 | checkpoint | WHITE TO WHITE
52b33f81-096e-51ff-a8e4-e31f537c3ac4 | textbox | WHITE TO WHITE:
84cb91c8-35f2-4450-b9a9-73bc18650567 | checkpoint | BLUE TO BLUE
25ac0ec8-edfa-5629-87ec-30704e023c6e | textbox | BLUE TO BLUE:
e0ee64d0-ec66-4635-88b9-b78febfc52be | checkpoint | BLACK TO BLACK
7049b2e7-f88b-59af-be0e-a3f2ea89d143 | textbox | BLACK TO BLACK:
6d83c13d-14e6-487a-847e-adbf807a1de8 | section | 5 - Fault Loop Impedance (If Applicable)
591d67df-5695-4a5a-b48a-45ba2cfdd41f | checkpoint | Cables have been installed as per design calculations.
85a2478a-90f8-5ae6-b21c-8a7594e000f1 | note | Note, if FAIL seek design clarification to adjust circuit breaker tripping curve characteristics.
321a0baa-8374-4249-94a4-45672bf0763e | section | 6 - Post Engerisation Checks (AS/NZS 3000) - Phase Rotation
9120dcec-b931-41c5-a46d-a776363d3b10 | checkpoint | Phase Rotation
4c32a2cc-9710-517e-bbf1-e606825b7b64 | tickbox | Clockwise →
1553c4cb-1441-5de1-80d7-8cc9c2ebedbb | tickbox | Anti Clockwise ←
eee321dc-81a2-45c9-8a99-a18276f252a3 | section | 7 - Voltage Checks (AS/NZS 3000)
3376bc87-3a07-434c-9f39-2895e8b4dacf | checkpoint | RED TO WHITE
d69b041f-abe7-58a2-8fa4-19d3fabf6e8e | textbox | RED TO WHITE:
6e95f5cd-5f68-44f3-af83-b74d6054ef44 | checkpoint | RED TO BLACK
534b5d9c-fb39-5fde-8ada-fd4de6b5926b | textbox | RED TO BLACK:
1243a481-62dd-44cc-9a27-10f6ace31646 | checkpoint | RED TO EARTH
5ad07a5b-8aec-5549-b328-169cbce36629 | textbox | RED TO EARTH:
436334b1-a2a8-4ada-bfe0-1071d90b2e24 | checkpoint | WHITE TO BLUE
a0ac408c-ef41-55f8-8fbe-a6da976024cb | textbox | WHITE TO BLUE:
91ab01d6-be1f-4940-8e1c-8488187bb2f9 | checkpoint | WHITE TO BLACK
072a8ae7-c2ee-52b4-9eb8-60e3f36fd11c | textbox | WHITE TO BLACK:
d2be82ba-743d-4dc1-976d-25d398f25462 | checkpoint | WHITE TO EARTH
10d265c6-93d1-578b-a70b-0e93e68fb5e8 | textbox | WHITE TO EARTH:
7582e75d-ffe3-4168-80ec-e7409e8e82c5 | checkpoint | BLUE TO RED
55d17b76-1d36-5032-a303-160a9ea3068b | textbox | BLUE TO RED:
af9cbf87-2327-48d2-9381-4b1b4f84b6a6 | checkpoint | BLUE TO BLACK
07d68b72-eae8-573a-81f2-128eb9bbd40e | textbox | BLUE TO BLACK:
204b9b10-9adb-4c83-b656-772ca991dad5 | checkpoint | BLUE TO EARTH
89a2008c-8024-5932-bd6c-6f3cd95779cf | textbox | BLUE TO EARTH:
ec6302cb-4045-472d-92ba-436b09f95906 | section | Test Equipment
823c4ff3-2138-4b36-b36f-de4c60833475 | checkpoint | Multimeter
eceaf28c-f92c-56d5-8179-f85786819a52 | textbox | Brand/Model
1ce00a84-069c-5b4d-ba08-9241ee8adf5a | textbox | Serial No.
77b0b501-bfab-589a-8782-d5046a26685e | textbox | Calibration Due
bb72880d-785e-5e76-94db-dbf0752183f6 | textbox | Tester
ba37a999-3e2e-523d-b5c5-29f6f8ac6776 | date | Date:
54a43f13-dc8e-4d8f-bce3-95775e525109 | checkpoint | Insulation Resistance Tester
002907c6-2183-5867-9f99-6392faf3fae0 | textbox | Brand/Model
cb49d123-694b-542e-9e90-a742e7c8f7d6 | textbox | Serial No.
73edaa95-f3b3-5a2a-a3e3-08b41b157477 | textbox | Calibration Due
b0268046-fc38-5601-bd9e-52b2285407ac | textbox | Tester
76d7e530-f8e4-5a27-a5aa-14e1ccc19b9e | date | Date:
fe5a2c86-c144-4824-982e-1b2aefd94eac | checkpoint | Phase Rotation Meter
8a719d4a-dda2-521c-81e7-06b83d2400cd | textbox | Brand/Model
3aa5c881-7b0a-5109-a829-984773c572e4 | textbox | Serial No.
f9be5cfa-8808-5df0-859e-e4e862b91e9c | textbox | Calibration Due
35d68131-020d-5db1-8d21-b879d63d655b | textbox | Tester
fbb9ce8b-8ce2-57fd-b1ef-1e9176e61e8b | date | Date:
f2ebf1ac-1626-484c-abc8-5bcfe8099685 | checklist | ITC - (5) Cable Tray-Ladder-Trenching |  | Level / Area:
920611f6-3a6f-4240-b900-109da4fda7cd | section | Details
bba4f696-0c04-4b6c-8217-41e60e53d572 | checkpoint | AREA/LOCATION TO DRAWING
a1ec429e-da12-4acf-a6fa-41aa3a2043ff | checkpoint | CORRECT SIZE, TYPE & SPARE CAPACITY
bef8cdbf-0216-4063-bc1f-abe324135a80 | checkpoint | GALVANISED / PAINTED
474bc696-080a-43d6-be18-e10e899c7f81 | checkpoint | CORRECT SPACING
12697dfe-901e-4bcb-b4f5-9962a793bb43 | checkpoint | CORRECT ALIGNMENT
48850c21-dac9-4b65-a4b5-a2c8151f122f | checkpoint | CORRECT BRACKETS AND SAFE FIXING
69d802cf-ab5d-41a9-a817-43682858afbc | checkpoint | CLEAR TO OTHER SERVICES
c771ce99-7f2b-4e16-84ea-261ef4aec66b | checkpoint | FINAL ACCEPTANCE:
4126777a-b4a4-50f2-94a4-81beb0af6a2d | textbox | HEYDAY GROUP (REPRESENTATIVE)
5e17ad88-e91a-56d7-9803-06b67869f7da | textbox | CLIENT (REPRESENTATIVE)
6ffd2f0d-cb4f-539b-a1d2-b5c5ce6809f1 | textbox | AUTHORITY (IF APPLICABLE)
62525a6d-8b61-40a2-9fa9-beff73978b8d | signoff | Signoff
6edae76c-923d-469c-a87b-6a757e2f7e4e | checklist | ITC - (6) Conduit |  | Level / Area:
c8380545-b8df-4e8a-91b5-bb6a3506a157 | section | Details
7cfb0b11-d20e-4085-afe6-71b7e2af14bf | checkpoint | CORRECT LOCATION TO DRAWING
eb28fcf5-bda2-4081-8c34-e5f3a38d678f | checkpoint | CORRECT SIZE AND TYPE
70570835-e05a-4498-8ceb-25c2be910385 | checkpoint | CORRECT SPACING IN SLAB
f9ecdf3a-6480-4545-8ff0-4c367e3d3213 | checkpoint | CORRECT ALIGNMENT
f4b5f9c2-09f9-4e52-9600-bf70c5f7bf8f | checkpoint | CLEAR TO OTHER SERVICES
14e8ba94-6450-4c5f-afad-e3af013ab3fd | checkpoint | CORRECT DEPTH U/GROUND
42061315-6285-4aaa-8a2c-150dd2d11ef7 | checkpoint | CORRECTLY MARKED (TAPE OR OTHER)
1756a309-3a33-4910-9760-4f37d3a48b88 | checkpoint | CORRECT FIXING AND SAFE
bce82d1d-d6b0-458d-9d59-41c9809f8483 | checkpoint | CORRECT BACKFILL AND SURFACES
d78779fe-9e2e-4cd6-b426-95f9352e59be | checkpoint | FINAL ACCEPTANCE:
261e314d-70e1-5757-aa4f-28a28d7b67c8 | textbox | HEYDAY GROUP (REPRESENTATIVE)
525b1980-8e8a-5038-a5cd-094be223278a | textbox | CLIENT (REPRESENTATIVE)
852accf6-8dd6-5bcb-895e-08a6fd83d541 | textbox | AUTHORITY (IF APPLICABLE)
5c5ed48e-2992-4f51-99ba-993e8dc8970f | signoff | Signoff
4f358674-e0ff-4d07-a793-b89762618f7d | checklist | ITC - (7) Light and Power Circuits |  | Level / Area:
bc960f86-88c4-4ad1-9b8f-18710060353f | section | Details
863a7471-f5c3-481d-aa82-4ac71047766d | checkpoint-no-value | Details
e9d451a5-338d-5db2-9ec1-00410af605cc | textbox | D.B. No:
0e1a4a49-a55a-5108-b84d-0889ab00b5e6 | textbox | CCT No:
1d517d3d-d1ba-5c4a-b9a3-72cf5f7cb143 | textbox | C/B No:
0891ee32-74f9-495c-9563-930a0aa519f0 | checkpoint | CONDUIT
8b2a069f-296d-4980-8048-0f45b6332a06 | checkpoint | ROUGH IN
9cb16bf8-c561-4cb0-beba-6307428003ac | checkpoint | FIT OFF
639b97b1-aab8-4db5-9a7b-9c79cc5422b6 | checkpoint | TESTED AS PER ITC 7A AND 7B
edcfb9d4-6dc4-455b-bd0d-eca109117a0d | checkpoint | NOEW SUBMITTED TO COUNCIL
ecdb577a-59f1-4503-a84b-fab138a2334b | checkpoint | FINAL ACCEPTANCE:
8897ff8f-7443-57a7-9004-3c8197087a34 | textbox | HEYDAY GROUP (REPRESENTATIVE)
1f8c7266-088e-59b2-8999-bb25af78682e | textbox | CLIENT (REPRESENTATIVE)
5fc7f560-abb7-512d-a282-72e25e2dac12 | textbox | AUTHORITY (IF APPLICABLE)
e430b7b9-078b-416d-b700-a5c4ed9268eb | signoff | Signoff
c93ff0ee-2cb1-42e5-a2b6-4a4829a4957f | checklist | ITC - (7A) Light and Power Circuits PRE |  | LIGHT/POWER Circuits (PRE)
f3eccfa8-4658-4fee-acef-73d7d419c6ab | section | Lighting/Power Circuits Field PRE ITC
8d88afb6-f597-448e-98a8-7c2d3a78a71e | checkpoint-no-value | Details
ce216f6b-20e9-54d3-a3d4-289fc2e6294e | textbox | Distribution Board
6b1b7a36-8a42-57cd-8e07-2226353201bc | textbox | Fed From
bc81c276-8d87-54d2-b81f-c55d3f309ba1 | textbox | Cable Type
182b1037-4d0f-5248-bb2b-ac340c0569d2 | textbox | Tested By
664ccbb2-7b29-5abd-838b-33ac47a9a4d0 | textbox | Submain Size
7a4a552a-09fd-5506-a21a-101d55755c98 | textbox | Date ITC - 4A
618e8f78-f887-5167-b1cc-3ec253cfda81 | textbox | CB Size
35bda9a0-3e0d-4fba-972e-9ae7cc631c1e | checkpoint | Lighting/Power Circuits Field PRE ITC
860408ee-416b-55aa-bd79-cd0bcdf8780a | textbox | C/B No.
2f637e7f-ccfe-5d59-9490-e477fd55d90f | textbox | C/B Size
897afcf4-93c9-59ef-ab4e-5b942ff1d37b | textbox | Cable Size
bfe59b1e-a962-53a9-951a-542c8a95d71d | textbox | Earth Resistance
13836135-43b0-5732-9367-3a9ca3f3289d | textbox | Insulation Resistance
830eaffb-43a2-5e76-b56f-cb4bb4ab582e | textbox | Polarity
bce9f118-a271-5227-9c93-2cdc8a4c3548 | textbox | Fault Loop
a4fcaf51-7766-53f8-9b12-db524b088fe7 | textbox | Safe to Energise
fd6e8dbd-00b8-5e97-8ae5-5e873dd7ec05 | textbox | Tested By
6a814619-79c3-5c2a-8723-c0809558f0c7 | date | Date:
fcf527dd-28dd-44b4-8c74-9dcfb048f734 | signoff | Sign
9cc615e1-1df8-479c-8387-d27e18292833 | checkpoint | FINAL ACCEPTANCE:
7de26fb4-dda6-532a-aa93-28b5b7566e1d | textbox | HEYDAY GROUP (REPRESENTATIVE)
c2438063-72d5-5afe-94eb-13aeae058c65 | textbox | CLIENT (REPRESENTATIVE)
2f00bd06-ccba-507a-b259-7cdcb52e3e69 | textbox | AUTHORITY (IF APPLICABLE)
82388e1e-2e73-4e2d-99f5-9968941a3c2f | signoff | Signoff
25f01dfa-030a-4fdd-bae8-8b3e416f3b5b | checklist | ITC - (7B) Light and Power Circuits POST |  | LIGHT/POWER Circuits (POST)
7dfb101c-2b3a-414a-9908-077813df4eca | section | Lighting/Power Circuits Field POST ITC
c746e328-2eca-4e2e-8add-07f5b61eeddc | checkpoint-no-value | Details
febafe2d-cf96-5c50-9e85-8c896ed09a10 | textbox | Distribution Board
d4693bcd-a411-5437-9927-f60d79071a0f | textbox | Fed From
7a21e889-4f5c-5f32-848d-f7a65c576b15 | textbox | Cable Type
c0687966-936f-50bf-ad0a-325c157e1a57 | textbox | Tested By
16dd0a26-5bef-52b8-815d-8a74eae1876b | textbox | Submain Size
85c6b340-edc1-55dc-be97-476308328301 | textbox | Date ITC - 7A
abacbd29-daf4-52df-96f0-f5f3dd384157 | textbox | CB Size
b8d3f73e-b72f-4024-a225-ba7ddeeb0eb1 | checkpoint | Lighting/Power Circuits Field POST ITC
1facb683-0c7e-5737-9354-e52abae533f5 | textbox | C/B No.
c9f2a3c1-761d-5f71-889c-be864a5a2275 | textbox | Voltage: RED to WHITE
fe5b269b-ce47-552b-a988-46efbc19c9bf | textbox | Voltage: WHITE to BLUE
8223b541-c445-5495-9c39-01d3e0c1b332 | textbox | Voltage: BLUE to RED
5a2d83ad-9686-579b-b58a-7738e11b62c2 | textbox | Voltage: Active to Neutral
74338dc3-b278-5fa7-8d19-dc5d60644343 | textbox | Voltage: Active to Earth
dade72af-ad37-4e47-8156-4153dbdffbc8 | checkpoint | RCD TEST
aac50e69-0be5-5d8e-ab73-1bafd79e56ac | textbox | TEST TIME
c40ee4b2-4302-5578-9d0a-731fc9c069d5 | tickbox | Circuits Labeled
a58aea42-bad4-44c5-872d-97c6e3807619 | checkpoint | Energised By
55ca72f6-fc04-5f41-ab77-03403cfbb5a9 | textbox | Initial:
25650fd2-9cf0-5efd-b0e8-ed805f048c4e | date | Date:
e9454d69-359b-44a2-88d9-41e0642a629d | signoff | Sign
b5921562-1d25-437e-9d1b-9e268d60ba44 | checkpoint | FINAL ACCEPTANCE:
e20b96fb-a9fb-52e4-ad03-78282ad065d9 | textbox | HEYDAY GROUP (REPRESENTATIVE)
f6d22e5f-0889-5d19-a87a-e3d46e7a8047 | textbox | CLIENT (REPRESENTATIVE)
96f42d92-db11-5325-8f36-a56bf45f37e7 | textbox | AUTHORITY (IF APPLICABLE)
ccb3097a-5547-40fe-b740-02405d8bcfec | signoff | Signoff
7723fd4a-6160-40e5-9477-38082fe97946 | checklist | ITC - (8) Light Fittings |  | ITEM No:
dd317154-1b89-4384-94f9-5d511d8fd28f | section | Details
84337d3c-aecd-4f41-9ee6-47f57b6bcdd2 | checkpoint | CORRECT LOCATION TO DRAWING
7fc8963e-319b-4469-8537-91af59550659 | checkpoint | CORRECT SIZE AND TYPE
d32e13f0-235c-4006-9185-9360719c6d58 | checkpoint | DAMAGE
0fefaf87-6e9b-49f6-86fb-fc4043de50e0 | checkpoint | CORRECT LAMPS
0ff6e0ae-8c26-443b-9d24-1b4fad50e40f | checkpoint | CORRECT DIFFUSERS/ REFLECTORS
d3d24535-07eb-4ed7-bd6a-eca2729d020e | checkpoint | CORRECT OPERATION
94e81169-fcfc-4a49-ad64-221e9a5d216a | checkpoint | CORRECT CIRCUIT / DB DESTINATION
6cae9e14-cd00-42ed-acfa-616ed68a5d1e | checkpoint | CORRECT LABELLING
abfb4b98-6fac-4255-933e-51d03297be0f | checkpoint | FINAL ACCEPTANCE:
0e69ce08-3f8d-529f-9197-6819c309d3a2 | textbox | HEYDAY GROUP (REPRESENTATIVE)
2796a5fb-d963-57e5-9cb8-b070896adece | textbox | CLIENT (REPRESENTATIVE)
471e539f-c59d-55d2-8e4a-0961dfa995fd | textbox | AUTHORITY (IF APPLICABLE)
f8e0c4b3-3271-48e0-87fc-d9288bc4e5ae | signoff | Signoff
b175a565-abaa-46bd-a67f-87b206c90123 | checklist | ITC - (9) Electrical Equipment-Accessories |  | ITEM No:
fc7486b9-fd54-41fd-8f5e-30fadf8c447a | section | Details
bc256e29-ed47-4a93-be71-8bc7d8ef783f | checkpoint | CORRECT TYPE / COLOUR
c2dead83-7230-44b6-b5df-fb8b7527fed7 | checkpoint | CORRECT ALIGNMENT LOCATION
aa6639f0-3026-4bf0-843e-ad03006fb6d5 | checkpoint | CORRECT FIXING AND MADE SAFE
e3ed7d96-d988-471c-b69a-ab97bba869a9 | checkpoint | CORRECT LABELLING
3528320e-cd1b-4b8c-a68a-9b846a238012 | checkpoint | CORRECT TERMINATION
f930fd85-44b0-4e43-94d9-0d1178feba08 | checkpoint | CORRECT EARTHING
3d5ef8ca-384f-4dd6-8fb7-70f0c5652bf4 | checkpoint | CORRECT IP RATING
dfc2b502-8dff-4dcb-bfed-b01ba66d5d16 | checkpoint | CORRECT CLASSIFICATION
13421599-6b08-4a3e-9e6e-b08a4ffe6711 | checkpoint | FINAL CHECK AND NO DAMAGE
dc5b922a-513e-4b2a-9b70-c301e9e9bfe1 | checkpoint | FINAL ACCEPTANCE:
c220556c-0b2d-55bf-8185-1f5872a7438f | textbox | HEYDAY GROUP (REPRESENTATIVE)
5238c6e2-add2-5661-a098-f87ea123997e | textbox | CLIENT (REPRESENTATIVE)
b612534e-8c3d-5f4c-8cd9-9963fc913780 | textbox | AUTHORITY (IF APPLICABLE)
e53a4e22-8c4c-4b9b-a719-198deae929bd | signoff | Signoff
596fd4d9-8739-4427-b45b-968bf4d6cfb3 | checklist | ITC - (10) Cardiac Earthing |  | Cardiac Earthing
f2533806-86bf-494e-898a-cefd257a2488 | section | Details
ba89d854-7d25-4ba7-a5ad-19b097269c6d | checkpoint-no-value | Area Tested
45d9046d-beab-5c7b-807f-87f428d85934 | textbox | DESCRIPTION:
83da3d86-d4f4-5eb1-91ea-d13537369c2d | textbox | CABLE DETAILS: FROM
620adca4-fd18-5e55-bbfc-d20f1c3c46f8 | textbox | CABLE DETAILS: TO
c0b15e51-062e-428c-be4f-390ef1809d47 | checkpoint | CABLE SIZE INSTALLED AS PER AS/NZS 3003:2018 TABLE D1
ff675f7f-f6da-4995-b49c-3426f891e5e6 | checkpoint | ROUGH IN – HIGH / LOW LEVEL
4a8f9048-4e3f-4a40-8268-4b1c19eba495 | checkpoint | FIT OFF
c88b1ef6-92a8-4723-9e64-7ee16715bbee | checkpoint | POINT TO POINT TEST
d15b41ec-ead6-41fb-970f-5d10be2e5578 | checkpoint | DRAWINGS MARKED UP TO REFLECT AS-INSTALLED
53d58afe-7a74-4c26-b7bc-723d8063baf2 | checkpoint | FINAL ACCEPTANCE:
52967c5f-59f2-52f7-876e-e55d110772bb | textbox | HEYDAY GROUP (REPRESENTATIVE)
3e8d9782-0485-573f-a820-34a15bf3b1d7 | textbox | MULTIPLEX (REPRESENTATIVE)
b30f4564-1676-526a-821d-0334a03798e6 | textbox | CLIENT (IF APPLICABLE)
e4d60a7c-1b37-454f-a677-ac24b49f99d4 | signoff | Signoff
1ff82eba-0e1c-472e-ad51-5f1738de4c7c | checklist | ITC - (11) Testing and Commissioning |  | TESTING AND COMMISSIONING
193b1ff4-8ba7-4de0-956b-1422e1344d72 | section | Details
3f38af66-12a6-4220-9cf5-6af3d3cb8deb | checkpoint | EQUIPMENT/ SYSTEM TO BE COMMISSIONED
f7e4b490-3eb5-5bba-9c1d-c3c9c70bebe1 | textbox | GIVE BRIEF DESCRIPTION
0b55aceb-ddaa-50ce-8f81-cbb7d1697d21 | date | DATE OF TESTS
faba75c9-d947-58f5-b326-06e263429e39 | textbox | INSPECTION/WITNESS BY (NAME, COMPANY/DEPARTMENT)
f4809fe5-803f-5ea8-b20e-7819b08682b2 | button | ACCEPTANCE | Yes,No
605a4ce1-7e8c-5def-aa21-a2c834d6e1a1 | textbox | CONFIRMATION NAME
01281034-b652-4058-88c7-fcbdf55348b0 | signoff | SIGNATURE
d3fc98ff-2e2a-46ae-a434-d8573a9d9beb | checkpoint | FINAL ACCEPTANCE:
5ea03330-1d63-5b6e-8dee-062dc1e53cf6 | textbox | HEYDAY GROUP (REPRESENTATIVE)
75fa5730-08a1-5283-9b10-bceda323758e | textbox | CLIENT (REPRESENTATIVE)
402fec24-391d-5128-aab8-87e0be87d2a0 | textbox | AUTHORITY (IF APPLICABLE)
28ccff54-c27c-4562-9f77-d974869ecabe | signoff | Signoff
eaa1f6dc-225d-4629-bcce-ff6a6882da6d | checklist | ITC - (12) As Built Drawings-Maintenance Manuals |  | AS BUILT DRAWINGS/MAINTENANCE MANUALS
f4e5a3dc-b422-4be2-b08a-cf3cf2e263a3 | section | Details
6a2e94e9-b84d-4038-a122-a7f161ac8b9f | checkpoint | AS BUILT DRAWINGS
c85bb9ee-8545-5510-9a0a-3dd4cc091a65 | textbox | AS BUILT DRAWINGS NO:
b17d012f-e812-5d31-8086-7b4b9dee2901 | textbox | DRAWING TITLE
3d174f43-cae1-550b-89b4-05591471fb74 | textbox | FINAL REVISION AND DATE
d0ed5878-dada-560b-978f-300e764571b0 | button | MANUALS (DRAFT) ACCEPTANCE | Yes,No
45b3b6ba-d664-42e6-85ce-6a0d303c2067 | checkpoint | MANUALS AND DRAWINGS SUBMITTED
57f77736-0f30-4ea9-85e3-635c402cef04 | checkpoint | FINAL ACCEPTANCE:
5650c709-bc8d-53df-aba0-ab175b2a4861 | textbox | HEYDAY GROUP (REPRESENTATIVE)
951833b4-78b3-56a2-9d6f-d11dc90fb938 | textbox | CLIENT (REPRESENTATIVE)
7bc46153-7523-52c3-b4a5-93e7670a192f | textbox | AUTHORITY (IF APPLICABLE)
a504bf94-ff1b-4de4-bc35-d59355422521 | signoff | Signoff