## Table 1
Inspection & Test Checklist ITC: 3 MSB AND DISTRIBUTION PANELS | [20 empty] | Heyday5 Pty Ltd ABN 85 158 865 091 Locked Bag 2228 North Ryde NSW 1670 Phone: (02) 9855 6666 Facsimile: (02) 9855 6655
| Client: John Holland Group | [7 empty] | Project Name: Shoalhaven Hospital Redevelopment | [10 empty] | Job No: NEC00138 | [8 empty] | Sheet: Of
| Contract Manager: Brett Lavorato | [7 empty] | Project Manager: Michael McGeehan | [7 empty] | Site Supervisor: Andrew Cairns | [9 empty] | Date:
| Check Authorised By: Michael McGeehan | [7 empty] | Signature: | [6 empty] | Check Delegated To: | [8 empty] | Signature:
| BOARD TYPE OR NUMBER OR AREA | ACCEPTANCE CRITERIA |  | MFG QA |  |  | DAMAGE |  |  | LOCATION TO DRAWING |  | EQUIPMENT TO DRAWING |  | CONNECTIONS INCOMING & OUTGOING BY HEYDAY. |  | NEUTRAL CONNECTIONS CORRESPOND |  |  | CORRECT EARTHING AND SOLIDLY FIXED |  |  | POLE FILLERS INSTALLED |  |  | ALL CABLE ENTRIES WITH ESCUTCHEON PLATES AND SEALS FITTED |  |  |  | BOARD SEALED AND LOCKED FOR SAFETY INC: FRONT AND REAR PANELS |  | LABELS AND SCHEDULE LIST CORRECT AND INSTALLED
|  | CHECK BY | DATE | CHECK BY |  | DATE | CHECK BY | DATE |  | CHECK BY | DATE | CHECK BY | DATE | CHECK BY | DATE | CHECK BY |  | DATE | CHECK BY |  | DATE | CHECK BY |  | DATE | CHECK BY | DATE |  |  | CHECK BY | DATE | CHECK BY | DATE
COMMENTS:
NCR No:
| FINAL ACCEPTANCE |  |  |  | NAME | [5 empty] | SIGNATURE |  |  |  | POSITION | [7 empty] | APPROVED (YES/NO) |  |  |  |  | DATE
HEYDAY GROUP (REPRESENTATIVE):
CLIENT (REPRESENTATIVE):
Authority (If Applicable):
(Client and Authority may elect or not elect to sign the acceptance). ACCEPTANCE CRITERIA: AS PER ITP = (1) AS3000 WIRING RULES. (2) SPECIFICATION. (3) LATEST ISSUE OF DRAWINGS. (5) SUPPLY AUTHORITY APPROVAL. * Proprietary purchased switchboards excluded