## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Level / Area: | [5 empty] | ITC - (5) Cable Tray-Ladder-Trenching
section | Details
checkpoint | AREA/LOCATION TO DRAWING
checkpoint | CORRECT SIZE, TYPE & SPARE CAPACITY
checkpoint | GALVANISED / PAINTED
checkpoint | CORRECT SPACING
checkpoint | CORRECT ALIGNMENT
checkpoint | CORRECT BRACKETS AND SAFE FIXING
checkpoint | CLEAR TO OTHER SERVICES
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | Level / Area: | [5 empty] | ITC - (6) Conduit
section | Details
checkpoint | CORRECT LOCATION TO DRAWING
checkpoint | CORRECT SIZE AND TYPE
checkpoint | CORRECT SPACING IN SLAB
checkpoint | CORRECT ALIGNMENT
checkpoint | CLEAR TO OTHER SERVICES
checkpoint | CORRECT DEPTH U/GROUND
checkpoint | CORRECTLY MARKED (TAPE OR OTHER)
checkpoint | CORRECT FIXING AND SAFE
checkpoint | CORRECT BACKFILL AND SURFACES
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | Level / Area: | [5 empty] | ITC - (7) Light and Power Circuits
section | Details
checkpoint-no-status | Details
textbox | D.B. No:
textbox | CCT No:
textbox | C/B No:
checkpoint | CONDUIT
checkpoint | ROUGH IN
checkpoint | FIT OFF
checkpoint | TESTED AS PER ITC 7A AND 7B
checkpoint | NOEW SUBMITTED TO COUNCIL
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | LIGHT/POWER Circuits (PRE) | [5 empty] | ITC - (7A) Light and Power Circuits PRE
section | Lighting/Power Circuits Field PRE ITC
checkpoint-no-status | Details
textbox | Distribution Board
textbox | Fed From
textbox | Cable Type
textbox | Tested By
textbox | Submain Size
textbox | Date ITC - 4A
textbox | CB Size
checkpoint | Lighting/Power Circuits Field PRE ITC
textbox | C/B No.
textbox | C/B Size
textbox | Cable Size
textbox | Earth Resistance
textbox | Insulation Resistance
textbox | Polarity
textbox | Fault Loop
textbox | Safe to Energise
textbox | Tested By
date | Date:
holdpoint | Sign
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | LIGHT/POWER Circuits (POST) | [5 empty] | ITC - (7B) Light and Power Circuits POST
section | Lighting/Power Circuits Field POST ITC
checkpoint-no-status | Details
textbox | Distribution Board
textbox | Fed From
textbox | Cable Type
textbox | Tested By
textbox | Submain Size
textbox | Date ITC - 7A
textbox | CB Size
checkpoint | Lighting/Power Circuits Field POST ITC
textbox | C/B No.
textbox | Voltage: RED to WHITE
textbox | Voltage: WHITE to BLUE
textbox | Voltage: BLUE to RED
textbox | Voltage: Active to Neutral
textbox | Voltage: Active to Earth
checkpoint | RCD TEST
textbox | TEST TIME
bool | Circuits Labeled
checkpoint | Energised By
textbox | Initial:
date | Date:
holdpoint | Sign
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM No: | [5 empty] | ITC - (8) Light Fittings
section | Details
checkpoint | CORRECT LOCATION TO DRAWING
checkpoint | CORRECT SIZE AND TYPE
checkpoint | DAMAGE
checkpoint | CORRECT LAMPS
checkpoint | CORRECT DIFFUSERS/ REFLECTORS
checkpoint | CORRECT OPERATION
checkpoint | CORRECT CIRCUIT / DB DESTINATION
checkpoint | CORRECT LABELLING
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | ITEM No: | [5 empty] | ITC - (9) Electrical Equipment-Accessories
section | Details
checkpoint | CORRECT TYPE / COLOUR
checkpoint | CORRECT ALIGNMENT LOCATION
checkpoint | CORRECT FIXING AND MADE SAFE
checkpoint | CORRECT LABELLING
checkpoint | CORRECT TERMINATION
checkpoint | CORRECT EARTHING
checkpoint | CORRECT IP RATING
checkpoint | CORRECT CLASSIFICATION
checkpoint | FINAL CHECK AND NO DAMAGE
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | Cardiac Earthing | [5 empty] | ITC - (10) Cardiac Earthing
section | Details
checkpoint-no-status | Area Tested
textbox | DESCRIPTION:
textbox | CABLE DETAILS: FROM
textbox | CABLE DETAILS: TO
checkpoint | CABLE SIZE INSTALLED AS PER AS/NZS 3003:2018 TABLE D1
checkpoint | ROUGH IN – HIGH / LOW LEVEL
checkpoint | FIT OFF
checkpoint | POINT TO POINT TEST
checkpoint | DRAWINGS MARKED UP TO REFLECT AS-INSTALLED
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | MULTIPLEX (REPRESENTATIVE)
textbox | CLIENT (IF APPLICABLE)
holdpoint | Signoff
checklist | TESTING AND COMMISSIONING | [5 empty] | ITC - (11) Testing and Commissioning
section | Details
checkpoint | EQUIPMENT/ SYSTEM TO BE COMMISSIONED
textbox | GIVE BRIEF DESCRIPTION
date | DATE OF TESTS
textbox | INSPECTION/WITNESS BY (NAME, COMPANY/DEPARTMENT)
button | ACCEPTANCE | Yes,No
textbox | CONFIRMATION NAME
holdpoint | SIGNATURE
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff
checklist | AS BUILT DRAWINGS/MAINTENANCE MANUALS | [5 empty] | ITC - (12) As Built Drawings-Maintenance Manuals
section | Details
checkpoint | AS BUILT DRAWINGS
textbox | AS BUILT DRAWINGS NO:
textbox | DRAWING TITLE
textbox | FINAL REVISION AND DATE
button | MANUALS (DRAFT) ACCEPTANCE | Yes,No
checkpoint | MANUALS AND DRAWINGS SUBMITTED
checkpoint | FINAL ACCEPTANCE:
textbox | HEYDAY GROUP (REPRESENTATIVE)
textbox | CLIENT (REPRESENTATIVE)
textbox | AUTHORITY (IF APPLICABLE)
holdpoint | Signoff