## Sheet1
JET PULSE
Pre-Start Jet Pulse Fan
Area clear, access good, enough space for install.
Nogs/Supports in place.
First Fix Jet Pulse Fan
Fan installed straight and level and correct height and orientation.
Correct Fan installed.
Fan serial No. recorded.
Fan seismically braced and vibration isolated.
Plans Marked up showing Jet Fan and CO Sensor Location.
CO sensor installed.
Control Cables Installed.
Power Cables Installed
Second Fix Jet Pulse Fan
Fans accessible for maintenance.
Controllers fitted off.
Power fitted off
Area left clean and tidy, finger prints removed.
Plant and controllers labelled.
Commission Jet Pulse Fan
Commissioning paperwork reviewed and accepted by Project Manager.
Aviator Max Controller Commissioned
Fire Isolate Function Commissioned.
Electrical testing complete.
COC issued.
Electrical As Built updated with DB Board and Breaker Information.