## Master List Templates
Id | Type | Name | Values | Prompting Name
4f727a59-4299-4227-9052-e8b429dd1fd6 | checklist | Fire Dampers |  | Fire Dampers
3e7f85da-877b-4efa-b47b-efce9a349cce | section | Pre-Start Fire Damper
a125b3ab-1bd0-4c4d-8c71-2051fddc6705 | checkpoint | Area clear, access good, enough space for install
6ba5c600-debb-430a-a872-ca1c59e0c7a7 | checkpoint | Duct Route clear, Penetrations complete
79b55644-e611-4038-81bf-3c09f44b52a3 | section | First Fix Fire Damper
7eb77dd2-6432-4ae1-9810-c78af312c5e5 | checkpoint | Correct Fire Damper installed. (Insert Photo)
edb13b58-7d6c-4d0f-a300-f69795250fb9 | checkpoint | Fire Damper installed straight and level with correct orientation.
02e08761-75ee-43d2-9591-b920d72f825a | checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
d697b986-ba81-4a91-8993-ce055e73dfab | checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
cb49af99-b40d-4d66-97f2-46692fef3658 | checkpoint | Access Panels in duct for fire dampers.
28cba624-b158-4d97-8a03-bfa1a24e76d4 | checkpoint | Building Access Panel requirements are marked and given to builders
6a38b280-855c-4c00-8255-23a3f8cf5289 | checkpoint | Plans marked up for As Builts with Access Panel locations
d33ba6eb-28c8-4854-8b42-2940a154e9b8 | section | Second Fix Fire Damper
1d369191-28df-40f0-9afa-3521d492b676 | checkpoint | Fire Damper Label affixed, Asset Number applied.
99fcfadd-4ea2-45ef-b749-c0a4c1d2672b | checkpoint | Fire Dampers Access Panels still accessible for maintenance
5d2eb6ef-1c00-4070-a498-8e46333efb04 | checkpoint | Area left clean and tidy, finger prints removed
ae2acbc5-9afe-4989-8c9f-a1b92fad8b30 | checkpoint | Fire Damper sealed to structure both sides.
f68972b4-6d81-41aa-aa09-4be60adafed1 | section | Commission Fire Damper
35abf88d-b375-479f-8b77-924971281f8a | checkpoint | Drop Tested as applicable
3399aa37-48d7-492c-8a16-93ef940f0411 | checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
7be34150-c368-48a3-ba66-611937573253 | checkpoint | Fire Damper Label filled out, photo uploaded.
40670fb4-21e7-4227-bdb5-faa6329dd3e3 | checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
91a77d34-03fe-4f7c-b402-578d38b427d1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
1b0a4b49-8a0c-4d2e-bb63-6e3edea49d4d | checklist | Completion documents |  | Completion documents
21405333-da65-4a54-8626-69a291b6e202 | checkpoint | O&M
de13e88e-1a75-4822-9613-6acb567e1685 | checkpoint | PS3 Mechanical Service - BCO10328723
f69cd0fe-17c6-4fb5-bdb3-047d88a5092a | checkpoint | Carbon Monitor & Fantech Checksheet
4578a1e9-4c24-4686-a7d3-0082112ae7c5 | checkpoint | HVAC - As built
4bb19ec2-08ce-41ee-b356-a0ea1e2c4dde | checkpoint | PS3 HVAC - BCO10328723
10017f0c-3bb9-4e97-a4ca-67fd6ad31ced | checkpoint | Electrical Safety Certification
d80bf36b-c85c-4c37-9267-95531d1bec66 | checkpoint | PS4 Seismic Support - BCO10328723
a8d7560c-0328-4b02-8bac-e58e149d554c | checklist | Extract Fan |  | Extract Fan
bfc4c44b-fcb7-46fa-9a72-19dc9f0b8659 | section | Pre-Start Ext Fan
1c090a2a-d831-467e-8bd1-db439d363997 | checkpoint | Area clear, access good, enough space for install
308e032f-5c04-44b1-a9b9-083728ea1259 | checkpoint | Duct Route clear, Penetrations complete
971d7327-caec-4b0c-bf0b-173e2701c8b7 | checkpoint | Nogs/Supports in place
948458c9-b74d-4e8d-bc47-e7c2f5d1baed | section | First Fix Ext Fan
898f9753-77b4-46b6-acac-3b4ed0f58eaa | checkpoint | Fan installed straight and level and correct orientation.
a4e85487-8bb1-40fe-bc23-8afc7d0e39f7 | checkpoint | Fan or Cowl sealed to Upstand
75fb9abc-0ceb-4917-932c-1fcbba624f49 | checkpoint | Correct Fan installed
ba06da6c-7bbe-4bbb-90f8-0db8d685476d | checkpoint | Fan serial No. recorded
340e7f48-0a23-41d3-842d-a26adefdd3a9 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
ded0344c-52a5-4523-bf42-bd96482b5ea5 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
307db7bf-6bd6-45ab-8fca-6f9dce083352 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
05c5af82-0f1f-4fcb-83be-8d6f027f2432 | checkpoint | Flexible ducts taped then cable tied
703887bf-5560-4545-8f2c-a1337d73051b | checkpoint | Supply cable installed correctly, protected and secured
f2494147-463c-452f-8b96-fc42291dd509 | checkpoint | Interconnecting cables correctly installed and protected
cee4e101-bd9b-4f5a-9443-564e0f307c1b | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
08c3fcf3-5b52-47f2-9ffc-3906cac2a2a1 | section | Second Fix Ext Fan
07e96289-bae6-456e-b477-b13b96e7b174 | checkpoint | Grilles installed square and level
77f8d6e9-1218-49cc-bce0-6587bdc71266 | checkpoint | Flexible ducts taped then cable tied to grilles/boots
9aa1e7f9-5e08-49d5-97a0-6d265f3a97d5 | checkpoint | Boots sealed to grilles
81c915c9-670e-49f7-b76e-294238a72ec0 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
edbc13e0-ba64-4932-81c4-90a2e26ff5fb | checkpoint | Controllers fitted off
cc7b3e2a-c9d8-4f53-9a61-787ad696c58a | checkpoint | Power fitted off
334eea21-4378-42d9-b0e2-8112672a884b | checkpoint | Area left clean and tidy, fingerprints removed
96fc09d8-7cef-4e90-8473-bc785f805fe4 | checkpoint | Plant and controllers labelled
487a9565-65d1-46da-a7f9-1972e3471d37 | section | Commission Ext Fan
87916ffe-c6ec-4550-89d5-7d33097e305d | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
4e33162e-ac1e-4ec3-a358-893b3a85df26 | checkpoint | Electrical testing complete
fa4be4bb-6727-4771-87a7-1d5977199aac | checkpoint | COC issued
bf397771-74e8-4a66-a032-216b91f10074 | checklist | Jet Pulse Fan |  | Jet Pulse Fan
1651307c-ab20-4c84-b2f7-bebf06e585da | section | Pre-Start SA Fan
d0670663-fe9a-445d-a83c-3777c59e72d1 | checkpoint | Area clear, access good, enough space for install
a2253bb9-08d8-47ad-bf3e-4b8978ffe932 | checkpoint | Duct Route clear, Penetrations complete
35918245-eb9a-4ec7-8f95-5eb140fe84f5 | checkpoint | Nogs/Supports in place
c0b41224-180a-4e65-8f6e-fa55173c9174 | section | First Fix SA Fan
37319aab-6497-4de8-8352-3f71aa416029 | checkpoint | Fan installed straight and level and correct orientation.
cdf09533-441f-41a9-adbc-aaf4c5a88d86 | checkpoint | Correct Fan installed
55a13ba4-852c-47cd-a752-15d807f190b0 | checkpoint | Fan serial No. recorded
ec3acd39-c837-4d52-a042-fb853edfc1f8 | checkpoint | Fan seismically braced and vibration isolated
5e650dd2-7a8e-4d9c-8f87-9abf2caedf73 | checkpoint | Supply cable installed correctly, protected and secured
4d2b54f3-674c-41be-88fb-cbb7878586d6 | checkpoint | Supply cable type, size and manufacturer
a3f5d39c-fed6-42c8-a5b2-ae3d219037e1 | checkpoint | Circuit protection type and rating
fbf106b9-76f9-4d0d-83b1-0bbde9e0c4b0 | checkpoint | Correctly rated isolator installed to standards
c19359a0-9421-48de-bead-b37555cf1b3d | checkpoint | Interconnecting cables correctly installed and protected
3a2fd1c8-8218-4806-9ec1-3940b4ae2242 | checkpoint | Control cables correct rating and type
9356086f-26df-469b-810e-6520378c70f3 | checkpoint | Screened cables drain to earth as per specifications
102fc274-84f5-41d4-82a5-39ef3468de59 | checkpoint | Control cables maintain minimum distance from power cables
77e5f88c-d1b8-4d3f-ba22-991119a1bdb3 | checkpoint | Daisy chain loops complete and correct
5714b6dd-c118-40ba-91e4-eff1c6947bad | checkpoint | Remote controller cable installed
a7ea4423-4627-4bf6-a349-013e78fae846 | checklist | Kitchen Extract Fan |  | Kitchen Extract Fan
f80aa660-a6d1-4c6b-a606-0b49c7811313 | section | Pre-Start Ext Fan
74f12232-33ad-4e4d-987c-a09780b085c1 | checkpoint | Area clear, access good, enough space for install
03a9d0c2-7bca-4561-9b58-b0954a65c4a0 | checkpoint | Duct Route clear, Penetrations complete
be8220b8-fe65-4262-b4b0-a499ae3c5223 | checkpoint | Nogs/Supports in place
5fd663a2-c77d-46aa-81dd-4bdfe8f1919b | section | First Fix Ext Fan
a44c5136-f01d-4476-8b5b-04757fbd3807 | checkpoint | Fan installed straight and level and correct orientation.
53e405e0-fe57-4773-b48a-06d6f542215f | checkpoint | Fan or Cowl sealed to Upstand
35330a94-b91c-4f24-bd1c-ebdbe457296f | checkpoint | Correct Fan installed
50706214-c1c4-4301-bb19-e6510faee410 | checkpoint | Fan serial No. recorded
d40ac509-15df-4054-b635-4d9163d7708a | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
0642e4a6-7661-4831-ae34-bd2638122881 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
4214649d-828f-4d5a-8fb5-551711c43c6b | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
1484200d-bfb2-4d8b-aa61-baa541b0345f | checkpoint | Flexible ducts taped then cable tied
2d3d6ee2-39b1-4214-beb4-cb1a288d42be | checkpoint | Supply cable installed correctly, protected and secured
8cee5050-aaec-4b73-b127-f7246e656c04 | checkpoint | Interconnecting cables correctly installed and protected
03782186-917b-4b4e-92f6-425e8189d0db | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
5768f924-2c0a-443a-a8bb-9088d30cf8b8 | section | Second Fix Ext Fan
4c547e3f-ee04-4f0b-a607-6dfb31f8b6f0 | checkpoint | Grilles installed square and level
b757ea2f-905c-421d-94d3-0edec7481d43 | checkpoint | Flexible ducts taped then cable tied to grilles/boots
f6b8b24a-dfbf-4a13-a972-3ad8c6bc0967 | checkpoint | Boots sealed to grilles
7da2fcad-8618-4f22-9e9e-09cadce29940 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
c33a6059-f0df-4939-8c74-4865c56b147e | checkpoint | Controllers fitted off
c97528f5-50cc-436a-bd3c-6196f4e856ec | checkpoint | Power fitted off
790f0f4c-79b6-46b4-8cee-3b2ac839ead7 | checkpoint | Area left clean and tidy, fingerprints removed
a1d26f7b-644b-4bdc-8e90-55af845f100f | checkpoint | Plant and controllers labelled
27c3790f-3f1b-4395-9341-4d19de4271ca | section | Commission Ext Fan
7c71ea12-e083-4467-a0aa-7e8ee1047102 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
3a170b85-4a13-4332-8830-4498cf0bcda8 | checkpoint | Electrical testing complete
c06bcaf5-53f5-452f-9de9-da865389b024 | checkpoint | COC issued
f4cf5fc9-e78f-4838-afb0-ab8261a078ce | checklist | Pre-Commencement Checks |  | Pre-Commencement Checks
5ac79c7c-2d5a-4eb1-bbc6-aed9d7a5ec66 | checkpoint | Quality Management Plan Completed, Agreed and Attached
887b7e91-a489-4f16-91d2-bd6d861ac12e | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
c4b0df3e-4082-4e1e-bf3d-c9b80e777887 | checkpoint | Relevant Breakdown & Checklist Setup on Conqa & Reviewed by Main Contractor
b0a4fd5d-c743-4e1a-a991-28aebcb20aa4 | checkpoint | Conqa Setup & Project Team Trained & Given Access
f9cc1b91-4e86-4bef-8a0e-14a148d4be86 | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
a62de021-85e7-4a98-8c88-693905035154 | checkpoint | Matrix/Insight Setup (if required)
4c720a29-07e9-4537-b584-9134115b3f23 | checklist | S - S - Air conditioning |  | S - S - Air conditioning
af3fa9b2-4269-4bde-ad66-431eccc9b375 | section | Pre-start checks
a65f6ba0-8a8d-4ef4-88fa-2bfec902e771 | checkpoint | Area/base/wall ready for outdoor unit
54108c13-3216-455f-8d3f-35c672b824df | checkpoint | Pipework route all clear, penetrations complete
c00fab10-a211-4602-a5f9-07cafade177d | checkpoint | Nogs/ply in place for indoor unit
b926f047-ea72-4787-b5f8-27688e3beff4 | checkpoint | Drain 1m from indoor unit location by plumber
f61b1fb5-1030-4201-81b1-b8a276d92c3c | section | First Fix
4c7757d9-cc67-40a8-85e4-8bf446b1e667 | checkpoint | Complete length of pipework is insulated and acceptable
8719c841-308a-4dce-ab21-37d9af93594a | checkpoint | Drain installed and insulated
0bef9eb4-785f-46d4-a488-a0073c4f5e39 | checkpoint | Supply cable installed correctly, protected and secured
8a36b64e-787e-42e3-9d53-2b6ccec23442 | checkpoint | Outdoor wall brackets in place
d05ac3fb-1112-49fe-8f55-a91d9dfdb5f1 | checkpoint | Interconnecting cables correctly installed and protected
7b8cd8af-fae2-4bd3-9d20-19ae334f375b | checkpoint | All seismic restraints in place (if needed)
5ea99b23-77c0-48e7-9292-a73914b4064e | checkpoint | Mechanical First Fix complete and acceptable
882af7f3-ccb2-4991-b8cf-9e7770448a8a | section | Second Fix
15d8c86c-3496-4abb-bdc5-8984cfea4471 | checkpoint | System pressure checked and still holding pressure and acceptable
fd46791a-1f71-4cef-9016-2e89ed02a3b1 | checkpoint | Correct Indoor unit installed, level and tight to wall and acceptable
19981e92-ab5e-4185-9b28-cd6ca0d1414c | checkpoint | Correct Outdoor unit installed and secure
60571827-2854-4fde-a5e3-2ed31223d254 | checkpoint | Indoor unit serial no. recorded
920cb875-ae76-4156-92a0-51ace6daa81c | checkpoint | Outdoor Unit serial no. recorded
37499202-a355-4442-9896-298e7387259c | checkpoint | Indoor unit run, fan speeds, modes etc. are acceptable
1b27453a-422d-440a-a9f9-443591264c8e | checkpoint | Air conditioning Second Fix complete and acceptable
1c640d53-96d0-40f3-917c-38fa0eef293f | section | Commissioning
c0bbb5ad-3fff-40d0-89be-a769a58f4f64 | checkpoint | Installer confirmed commissioned and paperwork submitted
6402b437-5e29-4b33-9de5-6e029f6507c3 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
ff156ea6-8fb5-4234-a529-9ebeae3cc785 | checkpoint | Electrical testing complete
6e5490ec-5038-4523-995e-402800513627 | checkpoint | Commissioning complete and acceptable
947cd8d8-84d2-41d5-afef-07658b2f1957 | checkpoint | Inspections completed and issued to Foreman
98a8b22e-715c-4098-9430-6a7ad52187a6 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
57e1f027-e22f-4757-9651-c2a277078e1e | checklist | S - S - Kitch Extraction |  | S - S - Kitch Extraction
91b02919-4cf0-48ce-bd82-ca40398f58f5 | section | Pre-start checks
b810c440-1d4a-4cd9-bf53-8d45492b7545 | checkpoint | Area clear, access good, enough space for install
5ed33d5a-a9a3-4a1c-a0ad-983f85b98c5e | checkpoint | Duct Route clear, Penetrations completed
690594b6-068b-4646-83c8-07f55661a877 | checkpoint | Nogs/Supports in place
dd809eb0-ab9c-437b-aa39-fb8a6ea0e1fe | section | First Fix
7b3bc762-4cc6-4fb3-aa13-2ba4ab6ce787 | checkpoint | Fan installed straight and level and correct orientation
ec56f0e4-bb4b-4af9-9b7c-14675c960e15 | checkpoint | Correct Fan installed
12f84648-80ef-402b-ae5a-ac596f12c0e5 | checkpoint | Fan seismically braced and vibration isolated
3fc3a96e-8f1e-4ac7-b28e-2defa46b1f20 | checkpoint | Inspections completed and issued to Foreman
612a5a65-9483-4e4f-8ed8-7f321e6b9754 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
6c26533f-2562-4257-93d8-40033ef5ea73 | checklist | S - S - Ventilation - Apartment Ventilation |  | S - S - Ventilation - Apartment Ventilation
b6dd4f5f-5533-48d9-8a0b-5d41721904ad | section | Pre-start checks
f3ee19b7-c26f-4213-8009-1764b3f54aa3 | checkpoint | Penetrations done in floors and walls (if needed)
5d820ddf-e64d-473d-b138-57d00e6fd0d2 | checkpoint | Space for ducting (no trades in the way)
d7cb900e-2c3d-4f7c-9452-154befb26bbd | checkpoint | Pipe through exterior wall installed by RHC to connect to
864dabe9-3cc5-4556-b1d6-0b1d50d6d481 | checkpoint | Drawings and work scope confirmed
623e27d8-675e-4e63-908d-da431620a95d | section | First Fix
837861cb-2cd0-426c-96f6-0ff553fa852e | checkpoint | Ductwork run straight level and well supported
e3736b84-04f8-4e7f-9335-72568d4862e3 | checkpoint | All ductwork joints sealed
b42f151a-fb17-43a7-97b5-9bde356c20b5 | checkpoint | All SAB joints sealed and taped
7772997f-e4a1-42bb-bd40-5aef5a11b5ad | checkpoint | All flexible ducts cable tied and taped to duct
716cb1ac-4886-42db-8d48-62661109551e | checkpoint | Identify locations and correct model of Fire damper to be installed
88c58908-84f7-4c19-adfb-e200f60e7b78 | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
858d1669-221f-4428-821b-1a58965e2080 | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
6a6bea08-f329-41f8-9b79-56744f394c62 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
db1a45c8-191b-4b7c-8f54-8f971703dfc4 | checkpoint | Install using Materials specified in the PS1
e803fc06-c8c5-4905-abed-103b6699c93a | checkpoint | Upload Photos of Install
2eae6d55-f38d-4a15-b229-9949f7ffbdaf | checkpoint | Refer back to Seismic Engineer for PS4 Production.
95ff7dd8-96cc-44eb-98a0-a9e264179884 | checkpoint | Flexible ducts fixed in place to grille location
0c2da016-2f58-4f6b-993b-de49ad1d2487 | checkpoint | Identify Fan Upgrade Requirement
897cbf65-a87c-4d5e-9baa-544d07285b70 | checkpoint | Area Clear for Install of Ducting, Fan, and Control Box
5da74eb1-796d-4604-94ac-091b443144fe | checkpoint | Install Fan, ducting and control box as per spec.
af65dfc4-78ca-4b75-a52f-1bf503303859 | checkpoint | Grille locations/access panels marked on plans
492a071d-bbe2-4941-a1c5-02cc951f6da9 | checkpoint | Mechanical First Fix complete
682e4b12-c5f7-4261-a7cc-f4bbee24d840 | section | Second Fix
7939e776-bcb1-4143-ab15-cfc66407943d | checkpoint | Ceiling fans installed square and level
27a2071e-c74e-48a8-9153-f9a180b537bd | checkpoint | Kitchen range hood installed by RHC to connect to
a85a63db-035c-4345-aadd-8d7dd5b473a5 | checkpoint | Fingerprints removed from grilles/walls/ceilings
6fdacd83-1b56-45cd-b03a-839863b99fb8 | checkpoint | Fan plugged in before install to ceiling
9337ef6b-ef77-40a0-b89b-fddf36a37be4 | checkpoint | External louver supplied by TSL, installed by RHC completed
90f50d67-155c-4d90-88b5-f2e31d67ca47 | checkpoint | Commissioning form completed & given to TSL
c4dcf216-e019-42de-a515-26e32e4dbe25 | checkpoint | Mechanical Second Fix complete
aaed8233-5bc2-437b-8839-301def598c9e | section | Commissioning
75612112-a662-4c03-bb0d-58a6e604ab8d | checkpoint | Correct product used as per requirements
12f10394-a6b3-458a-b7b2-3cdf33b9e4a2 | checkpoint | Correct design followed as per drawings
facc2bee-ec3d-43fe-b785-4ff6e407c184 | checkpoint | Mechanical Plant commissioned
028b6c57-1a82-4610-886d-1eb8955b790a | checkpoint | Inspections completed and issued to Foreman
b04a2dc0-91dc-4d03-966e-279bee7dd6f8 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
57dc1940-cb3d-4461-88c1-b8978d278f66 | checklist | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan |  | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
3ffb6250-34eb-435f-b63a-fc4f0e68b1c5 | section | Pre-start check
ada200ed-b8ee-4e0e-875d-703a15cca0e2 | checkpoint | Area clear, access god, enough space for install
ce539e3b-5d50-4ee2-8fd1-024bd73e4923 | checkpoint | Duct Route clear, Penetrations completed
da63f65a-a477-4ccc-bfa4-728b58af0bad | checkpoint | Nogs/Supports in place
0fee4110-4645-44f0-ade2-adcb75e0994f | section | First Fix
1c4af97b-360b-44e0-8d7e-cf5d8ae9a62e | checkpoint | Access Panel requirements marked up on drawings and submitted to client
033db637-130d-4d91-ab5a-6a21c58f5a6a | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
6f9b1140-2cdc-4e3b-925d-2fe7f22c72ba | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
e814f537-78bc-4d23-a05f-2b2556e4f9fc | checkpoint | Install using Materials specified in the PS1
6ec13a0f-25c1-4614-807d-cce919b8da34 | checkpoint | Upload Photos of Install
82a6f427-c0d1-40f2-b900-02ae3b464a6d | checkpoint | Refer back to Seismic Engineer for PS4 Production.
c3351c81-31d1-4ef6-b6d1-184ac63090b1 | checkpoint | All seismic restraints in place (if needed)
198df8cd-91aa-4b4f-97a1-ef72a78d2e16 | checkpoint | Mechanical First Fix complete
f1e096ef-e9fc-4701-9c4a-0f091233f412 | section | Second Fix
7cad9c04-dbbd-407e-b515-7db73f9e6610 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
39c91235-a811-4a6d-a3d0-4ead1f1efaf2 | checkpoint | Mechanical Second Fix complete
baf90bc7-d521-464a-b3bb-d8611b77d520 | section | Commissioning
6d1f1d8b-f95f-479d-b885-0de3774d961c | checkpoint | Good access to all areas of building
20e8834e-8274-4fc9-a400-09380a54f8a6 | checkpoint | Power live to Mechanical Plant
8f229f25-b6d0-4c35-9dde-0a9cab44d9d6 | checkpoint | Mechanical Plant commissioned
00a9a74c-de08-4f61-a785-b4a49246b861 | checkpoint | Inspections completed and issued to Foreman
cfb64fa1-d359-4ebe-8da7-0b9e70791842 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
c4a7559c-3246-4f3e-ba27-f1f1182557f1 | checklist | S - S - Ventilation - Corridors Ventilation |  | S - S - Ventilation - Corridors Ventilation
6d79b3fb-a6e2-40b4-9f81-33c99467caa5 | section | Pre-start checks
2ff9905e-b48d-4e66-85b1-cf32d8b6493d | checkpoint | Area clear, access god, enough space for install
80a3d3d8-c311-435c-97d2-7de2622baad8 | checkpoint | Duct Route clear, Penetrations completed
7d5e8699-f927-40fa-99f4-91366f40f77d | checkpoint | Nogs/Supports in place
c572c6cd-8558-4b25-b957-be15b7b8f72c | section | First Fix
44a59efb-a6bc-4a13-93ec-e384654005da | checkpoint | Access Panel requirements marked up on drawings and submitted to client
a03b4baa-adc2-4131-a92d-7fca22b173cf | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
5bc427a5-4ab7-4272-947b-5abd7e82ee12 | checkpoint | All flexible ducts cable tied and taped to duct
82556c0b-a841-4dfc-8bb7-fc7f23dc5fed | checkpoint | Identify locations and correct model of Fire damper to be installed
ba0fb8ce-8a53-4669-abf9-54d4908be982 | checkpoint | Install to Manufacturers Specifications
872096b4-f509-465b-a663-c32848da8ed4 | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
ff4f4b53-29ab-4d7c-a0e7-4f4e74d335f4 | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
06b11eb5-bf5b-422f-9f3b-f2be20883c8a | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
34f95825-8ce4-4962-9980-04d6843cba14 | checkpoint | Install using Materials specified in the PS1
e09fbbce-e58d-4c94-8d85-631e8c1a2bf8 | checkpoint | Upload Photos of Install
12033816-2adc-4b83-a349-f15935189949 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
8c3066b5-a68a-4fc6-91f3-bd4e2cbab764 | checkpoint | Mechanical First Fix complete
98d4c8f3-b989-4a7e-871c-efbb4d6e587d | section | Second Fix
0c94b06f-d8cd-4c1f-821a-6b5d533bb343 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
fe9b0fd7-3519-4307-b005-6d22166cc1f6 | checkpoint | Mechanical Second Fix complete
a8107314-dad2-46da-8419-658e9052813e | section | Commissioning
f22f8a51-dbae-483f-8d0f-79717eca75a1 | checkpoint | Mechanical Plant commissioned
72b6b916-7d80-4dc2-a1ad-c5ecd8323016 | checkpoint | Inspections completed and issued to Foreman
f7c8799a-76e2-4c55-820f-aeaeb3cda2b6 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
533259f1-5a54-4df4-84fa-6db1168a2aa2 | checklist | SA FAN |  | SA FAN
00128593-245e-466a-80d6-a6679f0dff45 | section | Pre-Start SA Fan
3a2b1683-fae4-4b20-a432-1d9fd5845690 | checkpoint | Area clear, access good, enough space for install
5355f9ea-d3da-4886-8b20-5f73a5802365 | checkpoint | Duct Route clear, Penetrations complete
7ce70ffc-e1f9-464d-8a72-7dc9b0d4b3a4 | checkpoint | Nogs/Supports in place
87176826-abc4-4939-90c7-3f00940c0538 | section | First Fix SA Fan
4cd434a4-03e0-41de-ba3f-5ca1544afaaa | checkpoint | Fan installed straight and level and correct orientation.
629f9149-669c-4480-ab11-e48d91fa5fe9 | checkpoint | Fan or Cowl sealed to Upstand
82d3ded8-6425-4144-b9ec-65dd930deaed | checkpoint | Correct Fan installed
186cb580-5f83-42d1-9d5c-f148e8243cbd | checkpoint | Fan serial No. recorded
e31c99f3-a63e-418a-ac30-54200bc110fa | checkpoint | Fan seismically braced and vibration isolated
d6227a4c-5201-4834-a175-903676c7fec6 | checkpoint | Heater Bank installed to Manufacturers instructions
9535a3d7-e2cb-4eb1-92a0-9cdb291e8cf7 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
9b5a97a2-b806-4e71-be16-fb9da0826165 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
6ef1d040-04be-41cf-b293-c73da2bc9245 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
f6964fc0-807f-4213-abc4-d917ca347726 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
439ae54a-7de7-4bf7-9559-c2f2cd1da26d | checkpoint | Flexible ducts taped then cable tied
ba772db1-270a-40a6-9570-d787e0a2caaf | checkpoint | Supply cable installed correctly, protected and secured
954f4cb2-c912-4205-af69-32aadf09d925 | checkpoint | Interconnecting cables correctly installed and protected
7842b09c-6059-463b-87f1-831534cfe4df | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
bef6b770-cddc-46a9-9ddb-557c1de6941a | section | Second Fix SA Fan
4bef0442-d37b-4f92-9db5-2398b00f28a7 | checkpoint | Grilles installed square and level
385a8aaa-994c-442b-9b29-f7f01ab1b62a | checkpoint | Flexible ducts taped then cable tied to grilles/boots
fa1f9917-9865-4519-a8e8-9989d0a29975 | checkpoint | Boots sealed to grilles
5087305f-30d3-44bf-90fe-320869038750 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
7806e55b-ba4d-4b0e-8198-acb1e968b6ba | checkpoint | Controllers fitted off. Heater Bank THT set
f84fb844-9423-474f-b9c3-98c4993a6646 | checkpoint | Power fitted off
8fc3d683-f33c-4c88-a7b2-7563861ab2d6 | checkpoint | Area left clean and tidy, fingerprints removed
0803f5c6-3997-4786-beb8-8393df8922c6 | checkpoint | Plant and controllers labelled
96cbdca3-bc5d-4fdf-9261-713459859ddf | section | Commission SA Fan
f23d1782-d17f-497f-823c-0a91900cc362 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
7a69c5a2-0773-4211-b399-556d9c11abc4 | checkpoint | Electrical testing complete
530ae2a8-4a04-491d-9cb2-abcdfcc0567b | checkpoint | COC issued
b025fd65-15d5-4c06-8f0d-b0c3c5287608 | checklist | SPLIT HIGH WALL |  | SPLIT HIGH WALL
093b2e5a-4a94-415b-a438-8cee3ef75367 | section | Pre-Start HW
d65b0904-eab9-4afb-8e59-7b6b8dbb87cf | checkpoint | Area clear, access good, enough space for install
6011abd1-57f4-4afe-9f46-6abfc2544cc2 | checkpoint | Area/base ready for outdoor unit
5ca25a48-6f59-436a-ac1a-d4656776914e | checkpoint | Any required drains for outdoor unit in place
ac748339-f730-4da9-bb8f-46171a9cc8c6 | checkpoint | Pipework route all clear, penetrations complete
041b4fa4-1590-4d23-9108-af4705d5a193 | checkpoint | Nogs in place
b2938345-85e5-4e84-9cdb-655cd028439b | checkpoint | Drain 1m from Indoor unit location by plumber
e8ca27b9-6479-4b47-a31b-9123cecaeb32 | section | First Fix HW
774d711f-09da-4dd3-8a48-d09890689060 | checkpoint | Pipework Insulated complete length
4b498e21-3c13-4ca7-a82a-7916df7cadb1 | checkpoint | Drain installed and insulated
547e7c73-f828-4c7d-ba7a-45d521367a22 | checkpoint | Supply cable installed correctly, protected and secured
9cb83c0f-19e0-426e-9b4c-49ef4d7b7507 | checkpoint | Interconnecting cables correctly installed and protected
7c64e59f-8c03-4791-a540-766e39096f46 | section | Second Fix HW
2341d03b-9e34-442e-9012-e2fd85bfe608 | checkpoint | System pressure checked and still holding 1st fix pressure
6fbd7af6-3e39-44fd-8bec-dc35e694f372 | checkpoint | Indoor unit secure, level and tight to wall
86102b73-e9c2-4251-bf83-141f7d1fcb2f | checkpoint | Correct Indoor unit installed
d03aa8f9-7e26-435e-942a-2cae9ae6416c | checkpoint | Outdoor unit secure and level
63f10872-8a3a-4ff0-be94-11a929d29916 | checkpoint | Correct Outdoor unit installed
c42fd5bd-67c6-41a8-bb00-2de993765393 | checkpoint | Indoor unit serial no. recorded
d545cedb-76db-40b5-853a-7ce00923fd22 | checkpoint | Outdoor Unit serial no. recorded
f9ef278b-2836-457c-9f4c-6624898ad552 | checkpoint | Area left clean and tidy, fingerprints removed
d6a2f93d-69aa-43d8-bd14-0cdb28fdfdcf | section | Commission
4214b773-6eea-4874-8ce9-58666e847230 | checkpoint | Installer confirmed commissioned and paperwork submitted
ac76e613-0fda-41a9-9d0f-1e97a2a9d61d | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
66e08c15-8706-4427-a0e7-22d9a885bc24 | checkpoint | Electrical testing complete
f119bfd5-6cfb-4768-b2b0-320d46387a12 | checklist | SYS - S - S - Ventilation - Apartment Ventilation |  | S - S - Ventilation - Apartment Ventilation
2a9ecd91-9670-48de-ac41-13c023094e91 | section | Pre-start checks
2bf55232-3092-4103-a793-5ac465829bab | checkpoint | Penetrations done in floors and walls (if needed)
a5058456-8e3b-4edc-b562-e436e5275a07 | checkpoint | Space for ducting (no trades in the way)
61a0ddcf-e17b-44a9-b9bd-6bf3aed912bb | checkpoint | Pipe through exterior wall installed by RHC to connect to
64f8b3be-6b07-475a-8f0d-0cc4c40b1c4e | checkpoint | Drawings and work scope confirmed
b9f35315-0959-4844-aa07-79a4c670ea9e | section | First Fix
c47b90ad-56e4-48e8-a7b6-4c65d82eed34 | checkpoint | Ductwork run straight level and well supported
fa585f6c-c57e-4249-a795-c773b034b137 | checkpoint | All ductwork joints sealed
b95a1ab2-6738-45e9-adf2-59b759ce7675 | checkpoint | All SAB joints sealed and taped
5c718a27-74e3-4dcb-8e7d-e56f84ccc88f | checkpoint | All flexible ducts cable tied and taped to duct
107b75ea-16b6-4529-8ec1-aee98c48f8e3 | checkpoint | All seismic restraints in place (if needed)
6d5380f3-2847-4539-933b-e5cf098ac10e | checkpoint | Flexible ducts fixed in place to grille location
22c22a16-fee4-4944-83c1-560b3ba9e1ba | checkpoint | Grille locations/access panels marked on plans
7e4c6003-d350-4511-af02-ca6bf974fefa | checkpoint | Mechanical First Fix complete
74a963eb-aa33-4ef5-9a6f-0ac559b92adf | section | Second Fix
71dd306d-191c-421f-93be-9d1e3f6dfe6a | checkpoint | Ceiling fans installed square and level
83f224c9-45c7-4a9d-a6eb-90cbd8825017 | checkpoint | Kitchen range hood installed by RHC to connect to
6cc1fe96-a4ea-4344-99c9-17f52a7491e9 | checkpoint | Fingerprints removed from grilles/walls/ceilings
117a9c9c-9161-48eb-bdef-802498a33279 | checkpoint | Fan plugged in before install to ceiling
90545d9d-a4fb-4384-a17c-22f0154ba50b | checkpoint | External louver supplied by TSL, installed by RHC completed
c4d33aba-663e-4f52-8316-a679eb6d0c0e | checkpoint | Commissioning form completed & given to TSL
b23d663e-7d85-4575-9991-5c7916e68f44 | checkpoint | Mechanical Second Fix complete
9e588e07-9d8e-48ee-bf80-68b2cad52c54 | section | Commissioning
010f4c6f-9417-4e79-a19a-8f2b9e1883b0 | checkpoint | Correct product used as per requirements
340b0c7b-a613-41be-8681-8d8206f37f30 | checkpoint | Correct design followed as per drawings
4a4190ea-d487-4e2c-bdd6-4347e9a6b1be | checkpoint | Mechanical Plant commissioned
78a85b87-b6dc-4ed7-81e5-06561c99cff7 | checkpoint | Inspections completed and issued to Foreman
12d9224c-81ac-4036-b202-60b512669702 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
c706d50c-9211-4f26-afe8-d5564b00384d | checklist | SYS - S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan |  | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
c649ee96-818e-4649-a492-7a825e2ee093 | section | Pre-start checks
31ad7911-d72a-44c3-91d4-0622e4e23110 | checkpoint | Area clear, access good, enough space for install
0385439f-82e8-4a50-8e88-abad80f2abb8 | checkpoint | Duct Route clear, Penetrations completed
af3ffe3e-2900-4f8d-8271-deac7dbc78e3 | checkpoint | Nogs/Supports in place
03dea435-c39c-454b-8282-fdc1131c856b | section | First Fix
f6b2df1b-590e-4377-a032-89ec5ed587e0 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
e6709270-f12b-4ad6-ac97-edb693e23c77 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations&)
9fc48c80-09c8-4fa3-92bf-b9619cfbd889 | checkpoint | All seismic restraints in place (if needed)
5a1d28c6-6b10-46fa-a180-64a58450156e | checkpoint | Mechanical First Fix complete
7209dbd4-2283-4fd0-add0-54d1494257d1 | section | Second Fix
e800fddb-ba8b-4bd4-b903-3e8b751aad37 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
76bbd1cc-5f6a-44db-99be-9087b2451458 | checkpoint | Mechanical Second Fix complete
fc514a33-aa6a-4e53-bdd0-53fac74bbd3e | section | Commissioning
39c3a161-8ed4-489c-8a8c-0c4cb766f165 | checkpoint | Good access to all areas of building
f4702235-70ce-4e34-8f3c-943550454bba | checkpoint | Power live to Mechanical Plant
717cf23d-4553-4f54-86a2-d1cbfe4e7b83 | checkpoint | Mechanical Plant commissioned
4deb5fb5-4e8f-44b4-849b-02d73c1a3829 | checkpoint | Inspections completed and issued to Foreman
be4686be-ab0d-4ecf-9c53-a50ab700b670 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
a1f360d1-7f5e-4c3b-b43d-a85c3897b85b | checklist | SYS - S - S - Ventilation - Corridors Ventilation |  | S - S - Ventilation - Corridors Ventilation
3b3c4eba-dc16-44bc-9876-cb9699de4328 | section | Pre-start checks
61cf8fec-e62b-4394-8c26-b55ab57586fc | checkpoint | Area clear, access good, enough space for install
8a74f4d0-afb0-4994-8ecd-1e03acfa9638 | checkpoint | Duct route clear, Penetrations complete
0a047580-d8cc-4f50-9921-6fba766ae6d9 | checkpoint | Nogs/Supports in place
fb800e25-a626-40a9-a325-3f03b9c09cc7 | section | First Fix
b95571df-b24c-4e88-9217-010fd2636d2c | checkpoint | Access Panel requirements marked up on drawings and submitted to client
7a546c30-fcf1-460f-8baa-b112861974f1 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations&)
15de8009-9a26-41f1-8149-d0bd1a98ba59 | checkpoint | All seismic restraints in place (if needed)
13d17564-6328-468f-8d20-0754a6de6311 | checkpoint | Mechanical First Fix complete
a3d3bdf8-3f59-467b-9d44-304d7f3e2267 | section | Second Fix
dd586d0c-bffc-430b-a17c-4b9502a1b1e2 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
3aa7fa2e-9bf6-489b-9af3-501a9cbef1be | checkpoint | Mechanical Second Fix complete
8ea5227b-3aa4-4894-b1f1-7dd8f33e70c1 | section | Commissioning
568e05de-8d7b-4b38-97cf-d878f4c7a919 | checkpoint | Mechanical Plant commissioned
aee8f081-be4c-4ec7-8436-27cd03723b42 | checkpoint | Inspections completed and issued to Foreman
dc000573-6bbb-44af-af26-981254288db7 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS