## Master List Templates
Id | Type | Name | Values | Prompting Name
4f727a59-4299-4227-9052-e8b429dd1fd6 | checklist | Fire Dampers |  | Fire Dampers
3e7f85da-877b-4efa-b47b-efce9a349cce | section | Pre-Start Fire Damper
a125b3ab-1bd0-4c4d-8c71-2051fddc6705 | checkpoint | Area clear, access good, enough space for install
6ba5c600-debb-430a-a872-ca1c59e0c7a7 | checkpoint | Duct Route clear, Penetrations complete
79b55644-e611-4038-81bf-3c09f44b52a3 | section | First Fix Fire Damper
7eb77dd2-6432-4ae1-9810-c78af312c5e5 | checkpoint | Correct Fire Damper installed. (Insert Photo)
edb13b58-7d6c-4d0f-a300-f69795250fb9 | checkpoint | Fire Damper installed straight and level with correct orientation.
02e08761-75ee-43d2-9591-b920d72f825a | checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
d697b986-ba81-4a91-8993-ce055e73dfab | checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
cb49af99-b40d-4d66-97f2-46692fef3658 | checkpoint | Access Panels in duct for fire dampers.
28cba624-b158-4d97-8a03-bfa1a24e76d4 | checkpoint | Building Access Panel requirements are marked and given to builders
6a38b280-855c-4c00-8255-23a3f8cf5289 | checkpoint | Plans marked up for As Builts with Access Panel locations
d33ba6eb-28c8-4854-8b42-2940a154e9b8 | section | Second Fix Fire Damper
1d369191-28df-40f0-9afa-3521d492b676 | checkpoint | Fire Damper Label affixed, Asset Number applied.
99fcfadd-4ea2-45ef-b749-c0a4c1d2672b | checkpoint | Fire Dampers Access Panels still accessible for maintenance
5d2eb6ef-1c00-4070-a498-8e46333efb04 | checkpoint | Area left clean and tidy, finger prints removed
ae2acbc5-9afe-4989-8c9f-a1b92fad8b30 | checkpoint | Fire Damper sealed to structure both sides.
f68972b4-6d81-41aa-aa09-4be60adafed1 | section | Commission Fire Damper
35abf88d-b375-479f-8b77-924971281f8a | checkpoint | Drop Tested as applicable
3399aa37-48d7-492c-8a16-93ef940f0411 | checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
7be34150-c368-48a3-ba66-611937573253 | checkpoint | Fire Damper Label filled out, photo uploaded.
40670fb4-21e7-4227-bdb5-faa6329dd3e3 | checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
91a77d34-03fe-4f7c-b402-578d38b427d1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
218aa89f-3b70-4b74-a867-e86c01da2638 | checklist | Car Park SF/EF |  | Car Park SF/EF
9a954560-86bf-49ea-b5bb-38be7bbd97b7 | section | Pre-Start SA Fan
775c505f-a42d-48f7-9599-bcc887990dc5 | checkpoint | Area clear, access good, enough space for install
57ace3ac-57c8-485c-9939-f16dd145893e | checkpoint | Penetrations complete
253db81e-cfd1-482c-beed-a61e878fdd90 | section | First Fix SA Fan
f12425a3-4dc0-45fe-963b-ef9c4f9f8587 | checkpoint | Fan installed straight and level and correct orientation.
83de6b1c-120e-4597-8d9a-9417e7dfd3d1 | checkpoint | Correct Fan installed
61bb60cc-b87d-4071-96be-4d390f682f75 | checklist | Extract Fan |  | Extract Fan
f2c75f06-562c-4797-9e19-2ec15fc4ed4f | section | Pre-start:
6c12645f-6c9e-48fd-a311-d4e56c5596ae | checkpoint | Area clear, access good, enough space for install
5a496a70-884f-405e-bc52-b1613ad3d625 | checkpoint | Duct route clear, Penetrations complete
8308b4f5-069a-4313-9758-54b329e831d4 | checkpoint | Nogs/Supports in place
30786535-41c8-4aa9-905e-1f64d80fc539 | section | First Fix:
fba42c06-e48f-404a-9b18-79d0ff4412b6 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
71ca1efb-21fb-4263-930d-ff47d97257eb | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
68b67bfc-23c8-4220-9244-ba67f6e0486d | checkpoint | Mechanical First Fix complete
5b4ed5f3-fb96-48c6-afa5-60f83fa31be6 | section | Second Fix:
31367b9c-f819-4073-98b1-26c65247d614 | checkpoint | Area clear and access good for Second Fix
d5b53fb9-d94a-46e2-a3d0-b01b84551f53 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
273e5836-1c33-4c7f-ab60-0c4584d7cf26 | checkpoint | Mechanical Second Fix complete
e42a17f5-d371-4497-b644-0e51f2854819 | section | Commission:
5a5eb081-3923-40dc-b1a6-9b41c1102c78 | checkpoint | Mechanical Plant commissioned
2112963a-f6f8-479c-aecd-ace0b1feeb25 | checklist | Jet Pulse Fan |  | Jet Pulse Fan
548b80bb-fe02-4639-a2e7-225e96e805f6 | section | Pre-Start SA Fan
cfe4b7de-d3e7-4fe1-b42f-376cfb153b29 | checkpoint | Area clear, access good, enough space for install
4d55b51c-088a-40e3-a09d-d6cddd7b894c | checkpoint | Duct Route clear, Penetrations complete
bee3ecd9-83a6-422a-a281-a8783a7ff2ed | checkpoint | Nogs/Supports in place
064d6f8a-84ea-465e-84d4-a9aeff45ea32 | section | First Fix SA Fan
f21dab45-fcfd-464d-8474-716019410d64 | checkpoint | Fan installed straight and level and correct orientation.
8d598523-2552-4ca8-a116-942bdad947a6 | checkpoint | Correct Fan installed
b2b98f4d-b513-4198-8589-46ede1a8f63c | checkpoint | Fan seismically braced and vibration isolated
1e142b83-0e52-45c2-b4ed-e3e2f349184a | checklist | Kitch Ext |  | Kitch Ext
05000c17-a887-467d-9bd9-a0aa2a68ece7 | section | Pre-start:
1540cd9a-c512-4894-ae33-2a026c3d494e | checkpoint | Area clear, access good, enough space for install
97fe18cd-76e2-423d-bb2f-dd170210ee9e | checkpoint | Duct route clear, Penetrations complete
88a5fb4f-c081-4531-bbbe-7dd48f795260 | checkpoint | Nogs/Supports in place
643ab297-bbbc-4ebd-b274-ffccd97a99b2 | section | First Fix:
6337c1b0-4ebf-4064-b835-beb7992b3afa | checkpoint | Access Panel requirements marked up on drawings and submitted to client
112da6ee-5733-4c08-bc81-fb04de6eff49 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
d719c985-9b90-49d9-8606-1816ffcaa6d9 | checkpoint | Mechanical First Fix complete
bb4da941-88a0-4069-b8dc-e3f6d0a79275 | section | Second Fix:
65777090-2a54-455c-9f69-f005ede03a52 | checkpoint | Area clear and access good for Second Fix
2308fa10-fa94-439b-b0b4-39cd63fa2a3b | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
d198c22c-65c8-45c6-b4db-cd1a2a0109c1 | checkpoint | Mechanical Second Fix complete
83f895c2-873c-48a2-a54b-0fb678ddd433 | section | Commission:
681f7441-053a-4874-8eda-95a480205ad4 | checkpoint | Good access to all areas of building
84fb0c5f-91ac-4acb-9d9c-5cf893107d19 | checkpoint | Power live to Mechanical Plant
349e261d-01a2-4033-afd8-c79a3b3f669f | checkpoint | Mechanical Plant commissioned
cce8785d-b7da-4ee6-84da-5afee80ebbb4 | checklist | S - S - Ventilation - Apartment Ventilation |  | S - S - Ventilation - Apartment Ventilation
f4b54f1c-593d-47ce-be5c-0b182e5c6b16 | section | Pre-start checks
cb66b666-3aa3-4968-b991-42076dacfa06 | checkpoint | Penetrations done in floors and walls (if needed)
38dbabec-ebc0-4ace-9396-fb763266e027 | checkpoint | Space for ducting (no trades in the way)
19c06d96-ee0a-4600-88b0-5daa240637f6 | checkpoint | Pipe through exterior wall installed by RHC to connect to
bf4d267c-0815-4e9f-b785-cc08953dab94 | checkpoint | Drawings and work scope confirmed
2177a791-8ea6-42da-b58e-d5a015af7a3e | section | First Fix
010f7736-ef15-4959-936c-8b893839ec1a | checkpoint | Ductwork run straight level and well supported
929d4143-ade0-471f-96b8-fe6fdb2a21b7 | checkpoint | All ductwork joints sealed
94c22a71-192e-4a2d-9a3b-6a7b90c6a48f | checkpoint | All SAB joints sealed and taped
09c1e0d6-095e-4c7b-93e5-d37b2cd75b5c | checkpoint | All flexible ducts cable tied and taped to duct
87ba0378-42f1-4826-89e0-91b483680cdc | checkpoint | Identify locations and correct model of Fire damper to be installed
f6a051ed-6cfb-405c-9595-41f202122012 | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
4bc747db-781a-47c3-9716-03c93910e26c | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
e4708a09-aa11-4382-981d-bfc74d7d3132 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
04417424-323a-4ca7-8135-7f108de6e7d5 | checkpoint | Install using Materials specified in the PS1
6dd5f514-5d52-48fd-bc6e-dfa24c1562b2 | checkpoint | Upload Photos of Install
18da4004-f90c-4610-995d-4136cd6f92c8 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
0c72215d-48e1-48d7-920d-5c0a613c9c64 | checkpoint | Flexible ducts fixed in place to grille location
1d0f3076-c4dc-4fef-a79a-50f75a0cc0f8 | checkpoint | Identify Fan Upgrade Requirement
674571ae-5884-4aba-a64b-d9769c348e9c | checkpoint | Area Clear for Install of Ducting, Fan, and Control Box
05ab53a0-5b6b-4693-86b7-0a38db5096ca | checkpoint | Install Fan, ducting and control box as per spec.
7167b783-d131-4a34-9b51-6fd23fa35d89 | checkpoint | Grille locations/access panels marked on plans
3befd412-d99f-4658-aa94-540e9997e4a7 | checkpoint | Mechanical First Fix complete
51852fff-d1f1-42fb-9667-6190782bedd7 | section | Second Fix
5987ebac-e6b1-4281-88c9-04ffa7a9f11c | checkpoint | Ceiling fans installed square and level
e7cb0161-7975-4c7b-b965-7f1fb08a7c3a | checkpoint | Kitchen range hood installed by RHC to connect to
bebca415-2bc4-4de8-b8d3-0c48e32333a4 | checkpoint | Fingerprints removed from grilles/walls/ceilings
e2ae9a17-6c23-4945-b170-fe10fb241fb0 | checkpoint | Fan plugged in before install to ceiling
d29c3426-9fb8-48bd-acd2-f9a8cc8e3f38 | checkpoint | External louver supplied by TSL, installed by RHC completed
bd127964-dce2-4aa4-88b2-38ad8d9cd8b2 | checkpoint | Commissioning form completed & given to TSL
0b38929a-82ab-4a8e-a364-79f2aa699a44 | checkpoint | Mechanical Second Fix complete
f4bac7e0-0f5c-46e6-9f60-27ce51797529 | section | Commissioning
4d492992-f83c-40e3-b67c-3c2d283f2c5e | checkpoint | Correct product used as per requirements
26ffb3d9-e517-4368-8d3c-623f4254480b | checkpoint | Correct design followed as per drawings
cd5e23e9-9021-4ff1-a282-746722af8a7a | checkpoint | Mechanical Plant commissioned
18d2a4e0-fc14-4b85-b496-21e0b189f5cd | checkpoint | Inspections completed and issued to Foreman
ec2830d1-23ed-471b-ab45-1187dc92b905 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
2f29a44f-dbc1-4aa3-a131-b248dfe0a91f | checklist | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan |  | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
cad90e85-a189-43ca-8da1-064385d618ff | section | Pre-start check
93eb2fec-848a-4159-a93b-76a115c074ce | checkpoint | Area clear, access god, enough space for install
3106a02f-455e-4246-852c-58b06f3f29c1 | checkpoint | Duct Route clear, Penetrations completed
00feb5e6-7b08-4ebc-9d61-c061abdcebfc | checkpoint | Nogs/Supports in place
efaf94e8-72ed-433e-8f8d-53713dfa4708 | section | First Fix
7b8307bb-53ad-4384-a8ec-2cb45aeb6c55 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
3a49ad05-249e-4f9f-b9d5-3b520c216beb | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
3ba45112-adfa-4840-84f1-5f7c54cc5648 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
dc17f261-2428-419f-8181-dcfc851f3440 | checkpoint | Install using Materials specified in the PS1
31de0810-2b3c-4a34-abf0-a1e9a2619bd4 | checkpoint | Upload Photos of Install
f1206baf-f26e-4280-938f-3633ae2a4696 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
a9d3787c-562a-49d2-9194-833f0516451a | checkpoint | All seismic restraints in place (if needed)
73e0848c-db49-4527-ac22-cf5d51277e0a | checkpoint | Mechanical First Fix complete
cbbb28ff-19b9-4fed-bc4c-71effa7a3b0e | section | Second Fix
af7e2cc0-e196-434d-945d-8bfa8013ef26 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
7331fe41-8d20-47ae-ad48-2b342b50f62a | checkpoint | Mechanical Second Fix complete
890c2bec-e186-4d24-8cb2-74cac498b7bf | section | Commissioning
f74c70a0-12c9-40c6-a67d-240fa0aa06f0 | checkpoint | Good access to all areas of building
d11c6a55-4794-4bd9-98c3-0e8168a3c091 | checkpoint | Power live to Mechanical Plant
d465f15c-9ccd-42f2-b3d0-7f601ad00202 | checkpoint | Mechanical Plant commissioned
6ca349e4-9f9f-4376-b258-c9eca2aeda91 | checkpoint | Inspections completed and issued to Foreman
ee479132-3fac-471d-b237-c326039f07b5 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
b6f74439-7513-435f-b36f-ad045c2e9c6e | checklist | S - S - Ventilation - Corridors Ventilation |  | S - S - Ventilation - Corridors Ventilation
7176b7a9-dd17-43ce-8d4d-47734e21e194 | section | Pre-start checks
64eccbcb-7792-471d-9abb-516b2e7b2bae | checkpoint | Area clear, access god, enough space for install
0092cc74-c7bb-4b7c-85f8-9fa109fc55a0 | checkpoint | Duct Route clear, Penetrations completed
ea9e0968-a3ba-4080-affb-31f45b002ce5 | checkpoint | Nogs/Supports in place
87335cbd-f051-4f26-88ab-db20ba621b27 | section | First Fix
20191879-65bc-46b3-af9a-aa0cdb67d70c | checkpoint | Access Panel requirements marked up on drawings and submitted to client
f9d74126-f2d1-4de2-b1f8-68bed8a86477 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
598995cb-3d28-4698-bd2a-67f97b5f4519 | checkpoint | All flexible ducts cable tied and taped to duct
77d2c459-7081-44f8-9d85-1e735387b4af | checkpoint | Identify locations and correct model of Fire damper to be installed
7b1ad558-9ce7-4675-a015-0702e708fb51 | checkpoint | Install to Manufacturers Specifications
5510e69c-b087-4d38-9602-dc9756b7dada | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
ad4e3b6b-531e-4f12-a695-1ed42266ad38 | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
d4df9422-a325-4d42-b44f-0e8016620eb4 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
7bd798a1-c90e-4120-8daf-5c7f6f36c816 | checkpoint | Install using Materials specified in the PS1
d897dfca-d83e-4846-b1ac-dc3d0cd38adf | checkpoint | Upload Photos of Install
abfbdae2-ae11-4204-b017-df18564037d1 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
bc234e5e-9be5-4df2-82b8-a275377eea06 | checkpoint | Mechanical First Fix complete
d5c3c88b-40ad-4e1b-b789-d4d76ee7d488 | section | Second Fix
ec48e22b-df12-429f-974c-75b7b895ea4e | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
2adea058-f400-477b-85fa-02eea3b6983e | checkpoint | Mechanical Second Fix complete
70d5d8a9-0db9-4332-befa-283b5316b618 | section | Commissioning
484ad7af-2553-4e83-9a48-8be73347b84f | checkpoint | Mechanical Plant commissioned
16a8557b-5fec-4566-9324-cc1c1291daed | checkpoint | Inspections completed and issued to Foreman
2d7bcc10-8876-4d83-95ff-443499496447 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
fd093923-9b5d-4b8f-bbc8-36ef52a8be74 | checklist | SA Fan |  | SA Fan
964d4770-4ebc-4aee-8626-8da88d119ada | section | Pre-start:
5e3428c5-9ae3-42f3-b31e-fc7c5de65085 | checkpoint | Area clear, access good, enough space for install
5784fe20-0877-4bd7-9230-ba9e266ee111 | checkpoint | Duct route clear, Penetrations complete
bad6468d-2e8a-4317-b492-326d90ca17ba | checkpoint | Nogs/Supports in place
d01f452c-ca55-493d-8252-798e8120c012 | section | First Fix:
79e18c6b-ec35-4624-ae12-821a18bad160 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
52b48107-181a-44ca-a842-1abfc5ea3724 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
568fc97c-7cc7-45f7-aa79-07104d2d92df | checkpoint | Mechanical First Fix complete
27987896-4fac-4cb8-8c28-a33581e872e8 | section | Second Fix:
eec818dd-dadf-47c9-93f5-76276feee49d | checkpoint | Area clear and access good for Second Fix
db0852b4-1eed-4039-ab0b-5745a31bd8df | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
7755c391-6752-4940-b65b-4872081a0f76 | checkpoint | Mechanical Second Fix complete
7bcca89c-081d-4c56-aed9-e78bb97070a4 | section | Commission:
5e1f0549-32a2-417a-9749-f9c9536d9db2 | checkpoint | Mechanical Plant commissioned
c18cf36a-0aee-42c6-8705-e1d004c848f0 | checklist | Split HW |  | Split HW
5debd7ee-971f-40e5-9189-aab11f91b25c | section | Pre-start:
cb4a5d90-bc0c-4bd0-81d6-ed1b858ce555 | checkpoint | Area clear, access good, enough space for install
68cccdfc-c9b1-432e-b47c-3e9f968621f2 | checkpoint | Area/base/wall ready for outdoor unit
8ea09501-e2c0-4ba5-ad2f-ba7f40a49ada | checkpoint | Pipework route all clear, penetrations complete
a42400cf-5734-4bcb-a3cf-5323ca59e83e | checkpoint | Nogs in place
27f6d17b-dbd4-4634-a024-ccf4f3740fb8 | checkpoint | Drain 1m from Indoor unit location by plumber
4370163e-dad7-4225-ba68-513b4fd94a1c | section | First Fix:
d0712bab-d3e8-4566-9e60-391078438dcf | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
2cfce65f-96ca-4374-8ff7-0b1c1f878712 | checkpoint | Mechanical First Fix complete
59a0cbfd-770e-479e-8bad-29d635feb999 | section | Second Fix:
5beed319-02cf-4e9a-ad80-6d2090b15d5b | checkpoint | Area clear and access good for Second Fix
39547091-c984-4a13-b6fe-e79a7d61e145 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
c337d952-7c15-4fac-9d42-e3259252d624 | checkpoint | Mechanical Second Fix complete
ee41c398-e5c8-407d-9a55-a30bf9746849 | section | Commission:
f89fbf66-7fa1-4624-b16b-84d129adb61f | checkpoint | Mechanical Plant commissioned