## Master List Templates
Id | Type | Name | Values | Prompting Name
4f727a59-4299-4227-9052-e8b429dd1fd6 | checklist | Fire Dampers |  | Fire Dampers
3e7f85da-877b-4efa-b47b-efce9a349cce | section | Pre-Start Fire Damper
a125b3ab-1bd0-4c4d-8c71-2051fddc6705 | checkpoint | Area clear, access good, enough space for install
6ba5c600-debb-430a-a872-ca1c59e0c7a7 | checkpoint | Duct Route clear, Penetrations complete
79b55644-e611-4038-81bf-3c09f44b52a3 | section | First Fix Fire Damper
7eb77dd2-6432-4ae1-9810-c78af312c5e5 | checkpoint | Correct Fire Damper installed. (Insert Photo)
edb13b58-7d6c-4d0f-a300-f69795250fb9 | checkpoint | Fire Damper installed straight and level with correct orientation.
02e08761-75ee-43d2-9591-b920d72f825a | checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
d697b986-ba81-4a91-8993-ce055e73dfab | checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
cb49af99-b40d-4d66-97f2-46692fef3658 | checkpoint | Access Panels in duct for fire dampers.
28cba624-b158-4d97-8a03-bfa1a24e76d4 | checkpoint | Building Access Panel requirements are marked and given to builders
6a38b280-855c-4c00-8255-23a3f8cf5289 | checkpoint | Plans marked up for As Builts with Access Panel locations
d33ba6eb-28c8-4854-8b42-2940a154e9b8 | section | Second Fix Fire Damper
1d369191-28df-40f0-9afa-3521d492b676 | checkpoint | Fire Damper Label affixed, Asset Number applied.
99fcfadd-4ea2-45ef-b749-c0a4c1d2672b | checkpoint | Fire Dampers Access Panels still accessible for maintenance
5d2eb6ef-1c00-4070-a498-8e46333efb04 | checkpoint | Area left clean and tidy, finger prints removed
ae2acbc5-9afe-4989-8c9f-a1b92fad8b30 | checkpoint | Fire Damper sealed to structure both sides.
f68972b4-6d81-41aa-aa09-4be60adafed1 | section | Commission Fire Damper
35abf88d-b375-479f-8b77-924971281f8a | checkpoint | Drop Tested as applicable
3399aa37-48d7-492c-8a16-93ef940f0411 | checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
7be34150-c368-48a3-ba66-611937573253 | checkpoint | Fire Damper Label filled out, photo uploaded.
40670fb4-21e7-4227-bdb5-faa6329dd3e3 | checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
91a77d34-03fe-4f7c-b402-578d38b427d1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
8babaeb4-33a5-4bfd-b8d0-f4830d6378e7 | checklist | AHU |  | AHU
c373ea85-5a0e-4517-aa77-f22f15bae3b5 | section | Pre-Start AHU
42ee57b4-51cb-427c-b7ed-9f382b3d71db | checkpoint | Area clear, access good, enough space for install
91c52dfd-476a-4a60-9af6-d980fac2886a | checkpoint | Duct Route clear, Penetrations complete
2c524224-0715-4507-9a3d-7549aca619a6 | checkpoint | Nogs/Supports in place
c83e73ef-e806-40c1-ac05-40d792c7dbd8 | section | First Fix AHU
3cc46b58-e93e-4baf-b8bc-4669693cb463 | checkpoint | Unit installed straight and level and correct orientation.
cb6cd12b-2013-4c76-bc58-ea36a8bb6011 | checkpoint | Unit bolted in place, seismically restrained and vibration isolated
16a828fe-d183-4045-a598-04ff91a0f53e | checkpoint | Correct Unit installed
0286cca0-816a-401e-966e-84d425d4757b | checkpoint | Unit serial No. recorded
45f63755-f5f0-4eb6-b3f5-e499e5163f24 | checkpoint | Good access to Service access panel
7b8306ed-3ca9-40a8-a26d-439b0d6f57b5 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
094174be-0768-4a72-bfd2-213655c0ecd8 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
3837055e-31a5-4795-8e49-b71c3969395f | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
0ce97155-6a64-4013-b30d-18c5584a6a12 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
3b846eec-54d1-4923-9bfb-a1d2f6b9d2c8 | checkpoint | Flexible ducts taped then cable tied
8fb5277e-4e85-4296-81ac-c8c5ac033af0 | checkpoint | Supply cable installed correctly, protected and secured
29e74625-43ea-4023-b434-5da23a7fcb47 | checkpoint | Interconnecting cables correctly installed and protected
1ee52ad1-21b8-40f3-aefd-11e8580fb415 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
c66a5041-bf4f-4b91-b66e-cd4021f07797 | section | Second Fix AHU
e4ba7d7d-ee92-467f-a708-af7326b24624 | checkpoint | Grilles installed square and level
2c2049d5-47cf-4290-bc58-52311dce1ad5 | checkpoint | Flexible ducts taped then cable tied to grilles/boots
006724ab-18df-4b37-b911-15740a044d94 | checkpoint | Boots sealed to grilles
2e61e7ec-3244-4aa0-ace6-44d0ee450a5d | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
b27c6013-ce8d-4459-aad5-866e8dfaa19c | checkpoint | Controllers fitted off. Heater Bank THT set
a421d5b8-d988-4d4d-9fb7-5711c66cba4a | checkpoint | Power fitted off
5797f840-85a1-4f75-a9d2-15dbb93b0ca3 | checkpoint | Area left clean and tidy, finger prints removed
53e3877d-b770-4ada-9c17-ca12f8c6bec5 | checkpoint | Plant and controllers labelled
8be971d3-d1b5-42eb-9e87-a48355da950f | section | Commission AHU
918b447c-acbd-4044-a179-b69626a2adc6 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
dbf1116c-933d-46b3-9118-d0fb936e625d | checkpoint | Electrical testing complete
50264566-1d2a-4075-a00f-d7552383d9c4 | checkpoint | COC issued
6c336ad4-c411-487c-9134-d424dcebaf12 | checklist | B01 - Extract Fan |  | Extract Fan
07f05881-125e-4399-a776-3574a91be375 | section | Pre-Start Ext Fan
581d0d68-c97a-4d15-9e00-5cff795734f4 | checkpoint | Area clear, access good, enough space for install
64982a6a-49f7-4384-a601-d340c5f6d1d0 | checkpoint | Duct Route clear, Penetrations complete
3c22723b-efdf-4077-ae92-a5f49754e6e8 | checkpoint | Nogs/Supports in place
93ad83d1-7823-40b7-be22-443c60443044 | section | First Fix Ext Fan
8e0821b2-cc6e-490d-8f8b-db0e932f9873 | checkpoint | Fan installed straight and level and correct orientation.
0ed1f822-7eb6-4aba-bb37-13d235147996 | checkpoint | Fan or Cowl sealed to Upstand
97e9e55d-be55-41d1-a7bf-d94a35012255 | checkpoint | Correct Fan installed
f0875ff4-4229-4521-9283-c2c95368c8b8 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
760e6690-8ce8-445a-b715-5e92fbf8d855 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
b18a0ada-d2eb-4403-a0f8-243fdfac84d9 | checkpoint | Flexible ducts taped then cable tied
63eca2ef-e87e-42a9-9c53-f8a661c10281 | checkpoint | Supply cable installed correctly, protected and secured
3808d47a-36b0-408e-adc5-b05be8a693ac | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
2cd73366-848a-470b-a462-d0d2f6161466 | section | Second Fix Ext Fan
d8abbe67-40f1-4699-8c7a-70a43db9ea27 | checkpoint | Grilles installed square and level
9a0b0882-7c6e-4a0c-a904-323c0754ae94 | checkpoint | Flexible ducts taped then cable tied to grilles/boots
484af16e-64ef-4c05-bbaa-b9888bb6774a | checkpoint | Boots sealed to grilles
bf1aa6bc-b4de-4f5d-b809-06c0e985361d | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
3a1c4b0d-d75d-480e-af99-66a437397127 | checkpoint | Power fitted off
9e742be1-f95e-4598-9afd-606cd726c72e | checkpoint | Area left clean and tidy, finger prints removed
f666e448-36f5-4a21-94cd-cd2098c8c4bc | checkpoint | Plant labelled
945889c4-5fe7-46d9-9171-66f9954d30f0 | section | Commission Ext Fan
65a5f289-9bb5-43e2-86f5-128d0bd69b33 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
5611a9ea-3253-4889-b22b-3347988d48df | checkpoint | Electrical testing complete
86ecd7a8-66b3-4d0c-a652-db42aa1820e0 | checkpoint | COC issued
ee14d6b4-ff1c-4d1e-a807-d37ab15ef875 | checklist | B01 - SA Fan |  | SA Fan
21f6f8b3-f0f6-498a-8884-0564abcbd051 | section | Pre-Start SA Fan
f7a6e338-594e-440f-ab42-408e25f04234 | checkpoint | Area clear, access good, enough space for install
7ea8dc7e-5477-4e93-b613-e1be134614c2 | checkpoint | Duct Route clear, Penetrations complete
8d54d2aa-0672-4226-bccf-cce0cdcb1134 | checkpoint | Nogs/Supports in place
74fbf29d-e921-4fca-b1f5-275b4d090bb4 | section | First Fix SA Fan
c5eadffd-6855-41c8-9444-641dd00e584f | checkpoint | Fan installed straight and level and correct orientation.
0372bf82-1019-418d-91ad-d0aea37937b0 | checkpoint | Fan or Cowl sealed to Upstand
e56f5b36-3079-4af5-8743-c6c6bddc380e | checkpoint | Correct Fan installed
c05d392d-a5bb-4dbc-8d19-89f3293edc79 | checkpoint | Fan serial No. recorded
b55f3092-bf28-4b99-a1c3-52541ea35d8c | checkpoint | Fan seismically braced and vibration isolated
a38b894b-d2b6-4882-b496-904152eac94c | checkpoint | Heater Bank installed to Manufacturers instructions
90e6d741-914f-47d1-858e-b774ac8661a7 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
c4e79dee-e5b5-453e-981a-34b37e56fad0 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
ada3ac97-1544-49ce-9533-67d8ca54b6ec | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
491a2535-89c5-4ee7-b569-ee7767a6cdd1 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
6acf5c73-4382-42c4-937f-55576b0cb6d7 | checkpoint | Flexible ducts taped then cable tied
e180e568-bda1-4d38-bf49-5547f894b8e6 | checkpoint | Supply cable installed correctly, protected and secured
4a11da45-80c5-4675-88e4-0d24132315e8 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
81026935-cded-4789-88f2-ca63fd84b54e | section | Second Fix SA Fan
5100124c-6283-41c3-9261-828bd8df38c2 | checkpoint | Grilles installed square and level
1f2fe212-f7a8-4bba-86d1-0662ba952fca | checkpoint | Flexible ducts taped then cable tied to grilles/boots
a8f42145-1b3e-45d1-bed8-308f17a44b81 | checkpoint | Boots sealed to grilles
6c73c977-d6bc-45e1-b413-43d24033bc08 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
9d029092-4706-4ae1-9fb6-50219ce10674 | checkpoint | Controllers fitted off. Heater Bank THT set
f0a17431-7238-489b-8f09-2616a7b99315 | checkpoint | Power fitted off
3585b151-53b9-4327-b1ff-e0ac045c5e2b | checkpoint | Area left clean and tidy, finger prints removed
9926994a-14e8-461c-aa37-468b29517b42 | checkpoint | Plant and controllers labelled
7b13e305-bf7a-4a46-a289-c461a7e71949 | section | Commission SA Fan
901fad86-3468-457e-8a7c-b289f69a417a | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
a3ebbc69-93ec-4eb3-9d44-1f4c3b5d84e1 | checkpoint | Electrical testing complete
f31f6243-57d9-4473-9bee-0470b6bd880d | checkpoint | COC issued
10846f47-1932-4fa5-aa26-79e270c7b401 | checklist | Completion documents |  | Completion documents
be47ea6f-096c-42e7-877c-69eab7da2db0 | checkpoint | O&M
96afe1a6-bda8-4d51-82a7-c7c5e68dd901 | checkpoint | PS3 Mechanical Service - BCO10328723
9f89bb39-0132-4eac-86f8-4df209004e69 | checkpoint | Carbon Monitor & Fantech Checksheet
887d610f-2429-495a-a30c-b3db13a022e5 | checkpoint | HVAC - As built
5cdb375e-3461-4660-9bfe-b7e94748ade5 | checkpoint | PS3 HVAC - BCO10328723
c05f9fc1-0cc5-4e81-9c9a-cb43ef6042aa | checkpoint | Electrical Safety Certification
7e3cfb2b-7684-498a-822c-6de568d3a7ab | checkpoint | PS4 Seismic Support - BCO10328723
d636fa5d-dc9f-4601-b5ac-ba8530ea9fc5 | checklist | Extract Fan |  | Extract Fan
265ec06d-ae8b-4618-a89d-8cac152fed47 | section | Pre-Start Ext Fan
f37e52a5-e75b-4392-b06e-97ba9857b23d | checkpoint | Area clear, access good, enough space for install
f09da787-5861-4735-b6c6-22bd3b220059 | checkpoint | Duct Route clear, Penetrations complete
f5b941fa-f94d-4072-8d89-b504b75b457b | checkpoint | Nogs/Supports in place
afcb5c10-eeac-4264-a6de-dca651e54c13 | section | First Fix Ext Fan
d866d5ad-62ca-47f5-82ea-1e75422993d1 | checkpoint | Fan installed straight and level and correct orientation.
23c2a066-7148-4984-9634-b4629150ded3 | checkpoint | Fan or Cowl sealed to Upstand
c1693ca9-a0ed-4013-8a06-ecb44064c81f | checkpoint | Correct Fan installed
f4cb3844-afad-4a1f-8df5-7cbcf269da85 | checkpoint | Fan serial No. recorded
1986f37e-29e4-4a09-b334-f9bba2971e4a | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
3c67c747-9d4b-44eb-a3ee-7659eec68bbd | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
b80fa446-cf4c-4987-89b8-39f02fd40459 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
033ac7e1-ae12-41a6-b748-895cd5ba25cb | checkpoint | Flexible ducts taped then cable tied
5250f953-0541-47fa-b71f-43b37fca8f0f | checkpoint | Supply cable installed correctly, protected and secured
0d0b0252-4826-4b94-ae8c-37133cc6b32d | checkpoint | Interconnecting cables correctly installed and protected
42b23fa9-16fa-48f7-b205-96e24ccb79d8 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
a866035f-df81-4896-9528-9fe43633ef2c | section | Second Fix Ext Fan
cbc17682-8c09-4ea7-b4b9-44a8492ccdbe | checkpoint | Grilles installed square and level
5e585314-3535-44f4-af31-b2ebe70e6cbe | checkpoint | Flexible ducts taped then cable tied to grilles/boots
ba999298-f2ff-4eb6-a065-a6315dba5636 | checkpoint | Boots sealed to grilles
7a597fd4-98af-4198-bd72-860437eaf096 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
9c63ed63-00fa-49d4-ab01-6a8c27da50e6 | checkpoint | Controllers fitted off
dd91e5d3-f23d-4aa9-83b4-6618ab6c5773 | checkpoint | Power fitted off
c12389bb-4e20-4252-9d91-91d45c863698 | checkpoint | Area left clean and tidy, fingerprints removed
74c54ab6-481e-4b03-bff1-69b8552204d4 | checkpoint | Plant and controllers labelled
367d2224-8a2f-4c3d-8b6b-590e408d376f | section | Commission Ext Fan
4ddbe99e-e198-4b94-bc1f-cf447f162025 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
3bbb3535-8554-4b64-ada3-bdc5f41932ba | checkpoint | Electrical testing complete
16615620-1495-4f1b-8e84-eaa5b0868400 | checkpoint | COC issued
0cae6a19-5838-431b-835f-2e583ffb8493 | checklist | HRV |  | HRV
be8aafb8-df16-4fbb-bb4b-95a83ac5e040 | section | Pre-Start HRV
f86dadcb-ed12-4195-9536-4f0902458dfb | checkpoint | Area clear, access good, enough space for install
42e76340-d033-4c7f-b0fb-9862df0bb368 | checkpoint | Duct Route clear, Penetrations complete
4e7b585d-ad02-43e0-92b6-81dd48b92e12 | checkpoint | Nogs/Supports in place
73a56b87-7986-4cd8-afd3-75436bc01c87 | section | First Fix HRV
014494f0-dd41-4dab-b529-5f1253259d3c | checkpoint | Unit installed straight and level and correct orientation.
9560137d-87a8-441d-8dfa-a5bbc5aaf51d | checkpoint | Unit bolted in place, seismically restrained and vibration isolated
996cc463-c835-45d9-972e-e0209cb4d849 | checkpoint | Correct Unit installed
4e6697e6-3301-457c-a0f8-e337384a8fce | checkpoint | Unit serial No. recorded
3bcc4f31-b8c2-4d96-85eb-aa082f64d2a6 | checkpoint | Good access to Service access panel
9888b696-a98d-4ffc-bb9a-3f24ef43aeec | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
2887c157-4bec-40d0-a910-37b0f677fd8b | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
764885a6-cabf-40bb-a329-5f461665d1b6 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
e3241cdc-83f2-4d30-9c64-90a2059b7c98 | checkpoint | Balancing Dampers locked open and accessible
7bf2f3cc-077e-46f5-9f6e-0bbaead085b5 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
8596abda-5a24-4745-b47c-0a1e4d0b5f7b | checkpoint | Flexible ducts taped then cable tied
2ef3d434-f537-4b92-963a-3602aeb3d737 | checkpoint | Supply cable installed correctly, protected and secured
7ac85e8d-504a-4b00-a961-8318efdcbc8e | checkpoint | Interconnecting cables correctly installed and protected
1f4631ac-8280-49cb-a1e4-e001f2ba2a92 | checkpoint | Remote controller cable installed
cb90979f-8c3b-4f55-8614-bbb3032b9ed7 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
b3307f57-f397-4e28-a989-e7ebf2183e2d | section | Second Fix HRV
32d3c09f-26f5-4b16-a6a0-9f7b668c5222 | checkpoint | Grilles installed square and level
f07792cf-d1a1-46e5-b235-bd1b8143c6af | checkpoint | Flexible ducts taped then cable tied to grilles/boots
912b0829-b80d-4bfe-92af-f733b394f830 | checkpoint | Boots sealed to grilles
120add55-385b-4065-b321-a54983ae6fab | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
2fe93394-6215-4176-a73f-7095a24ffcf6 | checkpoint | Controllers fitted off. Heater Bank THT set
ad0eca60-6f04-4668-82ee-5aee25c5a95d | checkpoint | Power fitted off
e084a0ef-4ef9-419e-863d-bcbd50f1f7db | checkpoint | Area left clean and tidy, finger prints removed
fe81660f-605c-4838-ac0c-1090832d1a92 | checkpoint | Plant and controllers labelled
0e2e2927-e0be-409d-8a3e-9627e48e21cb | section | Commission HRV
b4a91dc3-da8f-4d12-aa17-8d698b56b5b6 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
b5ed2f61-acb0-40f4-a90a-9fd53787be73 | checkpoint | Electrical testing complete
8d193208-85ee-4188-a5dc-d2c46399a327 | checkpoint | COC issued
dc6ceccf-f93d-4b6a-8bbc-3d20fbc5aaa1 | checklist | Jet Pulse Fan |  | Jet Pulse Fan
5ed5cc1d-89f7-46fb-aaa5-fe1ffbdd4613 | section | Pre-Start SA Fan
f5cbb335-dfe1-44c4-873b-136767fe96da | checkpoint | Area clear, access good, enough space for install
42263a70-f446-4a95-947d-c4af248bd9f4 | checkpoint | Duct Route clear, Penetrations complete
5ee8bb96-e9f2-43c5-ab18-e43f57d2d95e | checkpoint | Nogs/Supports in place
da136fbb-8a3f-4697-b4d1-c1b35c2c7b94 | section | First Fix SA Fan
57284dfa-31cc-471e-96e3-72826cc1e6e5 | checkpoint | Fan installed straight and level and correct orientation.
9455eb90-c52d-48ae-8bbe-b2165cc6925b | checkpoint | Correct Fan installed
44de78bb-de45-4bf2-bcc7-8814e828659f | checkpoint | Fan serial No. recorded
fbfb2a6c-fe52-4c7b-af01-c5c9af2f8409 | checkpoint | Fan seismically braced and vibration isolated
91804b91-d614-4fc3-aaa6-1729d221bb60 | checkpoint | Supply cable installed correctly, protected and secured
8e400563-8da4-4d03-9687-c7d2e60d9b3f | checkpoint | Interconnecting cables correctly installed and protected
366d01f0-4246-4662-ab38-e811a7bd11fb | checkpoint | CO sensor installed
12fbc86d-47a2-415e-86ff-923f7fb2968f | checklist | Kitch Ext |  | Kitch Ext
f33104fc-7ba7-4871-b65f-05c7c4767b72 | section | Pre-Start Ext Fan
fa00a3b9-7e36-46bf-95bb-2e384d0d8e35 | checkpoint | Area clear, access good, enough space for install
e2c176a3-906e-4270-bbb1-4fc8d75c8e4a | checkpoint | Duct Route clear, Penetrations complete
a24e0f4d-51b5-4eb0-8225-344f48287ed6 | checkpoint | Nogs/Supports in place
c6586b71-5d65-4357-be6c-7662167aeff6 | section | First Fix Ext Fan
4de6324c-faae-49b8-aee8-c97994594232 | checkpoint | Fan installed straight and level and correct orientation.
4349d719-364d-4a52-84cb-5daef34d5d5f | checkpoint | Fan or Cowl sealed to Upstand
514edde1-8e3f-46a6-a9d2-70ac1596230d | checkpoint | Correct Fan installed
472d64cb-e2b8-4707-988a-788cac0b292c | checkpoint | Fan serial No. recorded
92c77a5d-a413-4e36-aaf5-c1b50cac7ced | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
f6fd26ea-2371-419c-a7ea-760dbceadb30 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
8a8d9d5c-0380-4da3-8906-b16961389c86 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
ff8a1e6a-a610-4deb-b7bf-ea46afc6c61f | checkpoint | Flexible ducts taped then cable tied
0b12fdc8-76a7-4897-8429-a7007a73500b | checkpoint | Supply cable installed correctly, protected and secured
19073390-e016-49d4-91be-e600d8e2e7c4 | checkpoint | Interconnecting cables correctly installed and protected
8ec6033b-5a02-4f32-9087-91cd93972c3d | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
e638ed24-9d28-4dc9-8d26-6f45c4a022c2 | section | Second Fix Ext Fan
b2fdaea4-7289-442a-82aa-082fabc1d478 | checkpoint | Grilles installed square and level
a5ec845e-724b-4d6f-937a-5bb228ad9f74 | checkpoint | Flexible ducts taped then cable tied to grilles/boots
3bcccbe0-09d3-4a33-a6a8-5c47c4470cd3 | checkpoint | Boots sealed to grilles
40c12c9f-fccc-4ad7-96dc-b26b30cb8299 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
28461bd6-c4c1-4377-99e4-1d8d181d188c | checkpoint | Controllers fitted off
52a8775b-b4fa-4468-8141-00fd94003d8d | checkpoint | Power fitted off
565ae8af-da6f-4e8b-a4d9-3d3c1ff635f5 | checkpoint | Area left clean and tidy, fingerprints removed
45604dcb-1b5d-4530-a57d-32e5b0d3a980 | checkpoint | Plant and controllers labelled
cab13d0f-7d91-4f8a-8ede-2c9e2e53f5e5 | section | Commission Ext Fan
18a49a57-e68d-4728-8ebb-f9a5ac38d342 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
de0c1756-1410-4256-ba54-51cc1feec740 | checkpoint | Electrical testing complete
b943ee2c-9399-4b0d-a348-53e025728686 | checkpoint | COC issued
d54e753c-0e78-44b9-b80a-dc1b08a7b864 | checklist | Pre-commencement checks |  | Pre-commencement checks
175c273d-b45e-48ca-bdb8-33b049e64ccb | checkpoint | Quality Management Plan Completed, Agreed and Attached
17a73d14-171e-4725-b2de-c4c17dc222e4 | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
a6d58314-abda-43a5-9d08-15270c3a62c5 | checkpoint | Relevant Breakdown & Checklist Setup on Conqa & Reviewed by Main Contractor
03cf4f88-2bab-4bbd-9e53-17863a9c3fd9 | checkpoint | Conqa Setup & Project Team Trained & Given Access
fef95f0f-ccec-43f4-a6f5-372d80be82ad | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
ff12aed5-8407-46c7-a0d0-cf0772e59919 | checkpoint | Matrix/Insight Setup (if required)
76cc6f7e-8ca8-44c0-9cc8-948383f7f4e7 | checklist | S - S - Air conditioning |  | S - S - Air conditioning
97f5720e-a224-451a-a831-6c45e36421c7 | section | Pre-start checks
c7cd7d98-99cf-461c-be6c-534a8361721f | checkpoint | Area/base/wall ready for outdoor unit
81c0e643-3691-4821-9bb1-c1604d02f747 | checkpoint | Pipework route all clear, penetrations complete
3a103617-5692-439d-9371-0edbeda4dd21 | checkpoint | Nogs/ply in place for indoor unit
17b4cb51-ad5d-49d6-bdd9-e01bb98db512 | checkpoint | Drain 1m from indoor unit location by plumber
819b105a-9f41-4632-bb26-d0dedd31b2a9 | section | First Fix
46a1fe4a-408d-4328-b33e-8e15b901bf66 | checkpoint | Complete length of pipework is insulated and acceptable
2a72f523-b029-4e2e-acc4-85d7b7f7c92f | checkpoint | Drain installed and insulated
809a3636-98c6-45ab-9e56-43a3ebf85023 | checkpoint | Supply cable installed correctly, protected and secured
fa0ad517-c399-4826-9bfb-5a12ab1596d7 | checkpoint | Outdoor wall brackets in place
9948d4dc-f4e7-4d1a-aefd-4c494eeef2c4 | checkpoint | Interconnecting cables correctly installed and protected
ec26141a-9d21-4d53-b9f1-b68b0ff45a68 | checkpoint | Mechanical First Fix complete and acceptable
6a492da8-a6bd-46ae-a989-fe9f14ae10e4 | section | Second Fix
00b3ea1c-75f6-4b4e-8b0c-d954821d3fc3 | checkpoint | System pressure checked and still holding pressure and acceptable
161d86f3-a902-423e-9f9b-ecfdeb24789b | checkpoint | Correct Indoor unit installed, level and tight to wall and acceptable
396df7af-cc4e-4f54-a313-19f50ce5373c | checkpoint | Correct Outdoor unit installed and secure
203436c1-e810-46ab-90c1-1fa4b299b793 | checkpoint | Indoor unit serial no. recorded
0f40f462-8564-4a5e-9fd7-c0b57ca21f66 | checkpoint | Outdoor Unit serial no. recorded
d89f1883-e331-4e6a-9893-6961ad0065ce | checkpoint | Indoor unit run, fan speeds, modes etc. are acceptable
64a8a228-129c-4200-b96e-86d7b0736017 | checkpoint | Air conditioning Second Fix complete and acceptable
b15d411d-2e16-497e-a722-b027fb7c4b67 | section | Commissioning
d9647edb-fba0-463e-8879-736cc3d86d95 | checkpoint | Installer confirmed commissioned and paperwork submitted
2b3a2bbb-1c99-40d1-93ae-35cafe40534f | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
54541818-aedb-4f74-9608-9ce3aa3330ed | checkpoint | Electrical testing complete
ac0f77c0-a45b-4d54-a7b2-3eaf2dc2a984 | checkpoint | Commissioning complete and acceptable
68b11f78-6ee0-4077-bb9b-cc4e0b8d87b0 | checkpoint | Inspections completed and issued to Foreman
ad3f44e3-6eaa-4c7e-b5d5-0ccfc134116b | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
5d8eda58-a25a-473b-9393-ec5098f2c248 | checklist | S - S - Kitch Extraction |  | S - S - Kitch Extraction
43816810-5242-4350-9c3b-507ee0e2290d | section | Pre-start checks
27a6e7ed-da9e-4286-bd9b-8259edb4e307 | checkpoint | Area clear, access good, enough space for install
90977165-bd22-4b2b-8549-832854a5ee40 | checkpoint | Duct Route clear, Penetrations completed
2d736514-99cb-4b88-8c02-8f03f509e370 | checkpoint | Nogs/Supports in place
ad036655-8a7d-4d94-8e79-16fc81607aa3 | section | First Fix
e7f3ca6b-b8a1-4946-bea5-93911649142c | checkpoint | Fan installed straight and level and correct orientation
d5aa5273-7140-42b7-acca-3492d6c05f8a | checkpoint | Correct Fan installed
5dd58870-f82d-49d4-846b-6a9fd44b2b92 | checkpoint | Fan seismically braced and vibration isolated
34191821-3424-4cf4-bd15-98697c068dfd | checkpoint | Inspections completed and issued to Foreman
2820366c-eb7b-43e5-a839-a0f8ef98a0ce | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
51232e05-f948-4c3d-8ed5-35a44aaef413 | checklist | S - S - Ventilation - Apartment Ventilation |  | S - S - Ventilation - Apartment Ventilation
6e218199-8541-485b-9b47-af9e8bd12511 | section | Pre-start checks
0f49514b-5b69-46d5-bdca-5b43c315be52 | checkpoint | Penetrations done in floors and walls (if needed)
858761c4-2d0f-4861-807a-204fd2c1a553 | checkpoint | Space for ducting (no trades in the way)
3adb1daf-e3f9-4b01-9ebd-f962e15dcc79 | checkpoint | Pipe through exterior wall installed by RHC to connect to
223b1e69-a9ba-49cc-ae73-47faac668ce7 | checkpoint | Drawings and work scope confirmed
8315eb30-8845-4f33-8a73-a508bc151633 | section | First Fix
9f1f2320-bb8d-4ba0-a452-c94b47e5aae2 | checkpoint | Ductwork run straight level and well supported
6ce5dee8-bf1d-446a-b635-9ed2a6cb2fd7 | checkpoint | All ductwork joints sealed
d3a3e1b8-5a33-4ae2-8caa-93543aba7471 | checkpoint | All SAB joints sealed and taped
e2881fc8-84fb-4194-980b-01022ca66393 | checkpoint | All flexible ducts cable tied and taped to duct
c147cd6c-4767-45aa-be2b-0ba19fac9fdb | checkpoint | Identify locations and correct model of Fire damper to be installed
25039198-db70-479d-8143-b9e157bf4010 | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
30440231-39cc-4ce1-bcd2-a2359cad1abd | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
ecc30cef-37c5-41ac-bac7-66cc692d6b83 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
9748df83-37ab-4a07-abc4-2fae98cdea4c | checkpoint | Install using Materials specified in the PS1
9e9d0851-9ec0-4e6e-a06b-647af285fb10 | checkpoint | Upload Photos of Install
8b9aeb05-f8bf-413a-bd60-0652702590f7 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
fd291f3d-9f54-417b-bf05-9db864ce3800 | checkpoint | Flexible ducts fixed in place to grille location
82acfde8-8775-49d6-b8cb-4ac44376420b | checkpoint | Identify Fan Upgrade Requirement
92f6a548-9b91-4e3d-bc9b-2da782a55f46 | checkpoint | Area Clear for Install of Ducting, Fan, and Control Box
355449df-fad9-4c18-8f14-74cfaf7cac4c | checkpoint | Install Fan, ducting and control box as per spec.
3b70e6a1-6c20-4d14-84c2-63c82246b805 | checkpoint | Grille locations/access panels marked on plans
6a2c8960-901d-483f-a404-9997a398a38a | checkpoint | Mechanical First Fix complete
424f6704-7d70-4900-9d8d-0355f79864cc | section | Second Fix
3bff92d2-82c5-494c-aa06-ba2ecf437d4d | checkpoint | Ceiling fans installed square and level
ecc0ab19-3c32-4589-8661-f94b23d7255e | checkpoint | Kitchen range hood installed by RHC to connect to
40e1c850-8604-484c-a3a2-8e2e2701d083 | checkpoint | Fingerprints removed from grilles/walls/ceilings
15846ee6-5edd-490f-a08d-1a658a421c54 | checkpoint | Fan plugged in before install to ceiling
b955675c-da01-447f-aa79-0b5855325a78 | checkpoint | External louver supplied by TSL, installed by RHC completed
4e1aa294-33ed-4fc7-8c1b-06afb439ddbf | checkpoint | Commissioning form completed & given to TSL
43d49333-7caf-41ae-9ebb-202971a8c2ea | checkpoint | Mechanical Second Fix complete
5cd57e3d-77d3-4c2e-960e-3783b5a4d5d2 | section | Commissioning
b9a0072d-91c3-478b-b994-7319ce7ebaab | checkpoint | Correct product used as per requirements
5e84172f-c0d4-4017-bc92-afd0b5e7f76c | checkpoint | Correct design followed as per drawings
ceabaafa-b0c0-4543-bba4-64f91939dbe1 | checkpoint | Mechanical Plant commissioned
ed9b60cd-d6a6-434f-bd00-479c5954a889 | checkpoint | Inspections completed and issued to Foreman
b760f73a-3913-4093-abbe-3b23337de686 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
44f7e0e3-eee5-4ef4-95fc-c043db057f22 | checklist | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan |  | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
71c7d3e7-4b2b-4acd-b0fb-5f4508fd31b8 | section | Pre-start check
e511d41a-9cbf-4f8d-b06d-32255a238402 | checkpoint | Area clear, access god, enough space for install
8df1fbab-e6f0-41e6-949f-0622718e78db | checkpoint | Duct Route clear, Penetrations completed
6d2eac70-a267-432f-beb3-11878c9dc530 | checkpoint | Nogs/Supports in place
7a8ec831-5d7d-4199-9781-9c6a96e294f7 | section | First Fix
f211edd3-b9e5-4382-8550-6955c5124874 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
f7de54c0-205b-4185-85a5-b1cabc343dd6 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
66336f14-a52b-4c09-910a-6a495ff11d00 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
57ff194e-02fe-422f-8fb9-50c47829e42d | checkpoint | Install using Materials specified in the PS1
c915700f-7822-4577-9484-30b274e18da0 | checkpoint | Upload Photos of Install
75c2e27d-ef98-4e58-8734-d3ee32f2855e | checkpoint | Refer back to Seismic Engineer for PS4 Production.
897a190b-2992-4f3f-b544-0b45c66fc583 | checkpoint | All seismic restraints in place (if needed)
2ec08ac0-0c07-430b-94f3-3b2ab7415350 | checkpoint | Mechanical First Fix complete
900e8e57-3320-44d8-90ea-615422b8110c | section | Second Fix
71687e0f-0591-4052-a5d2-0393d2d0a8af | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
47995e18-5e3e-4dc3-8e97-ba2017d393db | checkpoint | Mechanical Second Fix complete
71be1cd6-afe8-4cee-bd32-1e41ed04b21b | section | Commissioning
e321636c-dc33-4a29-b651-e2c3b163da01 | checkpoint | Good access to all areas of building
a58d2f6f-ff7a-4925-80c0-f0d13d97d7d7 | checkpoint | Power live to Mechanical Plant
8683d9d4-121b-4fd8-8bb3-1005d982c179 | checkpoint | Mechanical Plant commissioned
fc864924-79c9-4428-bdca-71c537649f64 | checkpoint | Inspections completed and issued to Foreman
40eafb68-ac02-42dd-ae17-0ccc08f094a9 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
e79b0d39-28ff-48e7-80f4-a31cad4090a0 | checklist | S - S - Ventilation - Corridors Ventilation |  | S - S - Ventilation - Corridors Ventilation
25fc908e-196c-4896-99ae-738d840d7a53 | section | Pre-start checks
098d8ee7-a279-44ad-9d56-4dd5583a6301 | checkpoint | Area clear, access god, enough space for install
71488b79-b908-488c-a47d-877e29b61fba | checkpoint | Duct Route clear, Penetrations completed
a0cfa35a-8285-4f9a-aa47-9b584dbeb85b | checkpoint | Nogs/Supports in place
50ce3f52-a287-4435-a759-e2f6cabbbcb4 | section | First Fix
9097b2d8-5e37-4bb8-875c-0165d114cba4 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
2d71e435-cce0-459b-bd1d-c7300b1275fe | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
dbaeebfe-1d34-4c6c-9c22-d8f858d91cdf | checkpoint | All flexible ducts cable tied and taped to duct
7a46100c-780d-4f03-803a-32f00b26331d | checkpoint | Identify locations and correct model of Fire damper to be installed
4a62ca89-bc6e-4e7e-b159-50d122235f08 | checkpoint | Install to Manufacturers Specifications
3bdbd423-dac6-4f5a-8c85-55b9eba546f9 | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
d27f8968-3d9b-4717-8039-624116227a41 | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
90e65f70-1411-447b-af6d-55835cab0c52 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
b4672f36-8d11-485b-9bd7-868c7022e877 | checkpoint | Install using Materials specified in the PS1
c4dee9ab-e976-4572-b223-abac1a147e07 | checkpoint | Upload Photos of Install
1728def1-3b4f-45b0-bd80-9f857112456f | checkpoint | Refer back to Seismic Engineer for PS4 Production.
74080b31-96d1-4e3e-8c57-ccac837bf079 | checkpoint | Mechanical First Fix complete
1c7b5289-e89d-4e08-899c-0700da296eae | section | Second Fix
881d152c-28aa-4037-94a3-192c129e408a | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
e11bbabe-9739-49dc-a05e-ab37ebe125f5 | checkpoint | Mechanical Second Fix complete
0ff7bbfb-0f14-47ad-9843-6a5a54f39a6b | section | Commissioning
b2fef284-f90d-4032-851c-49176589dd79 | checkpoint | Mechanical Plant commissioned
530685e7-aca0-43f5-9fd9-4247f505966c | checkpoint | Inspections completed and issued to Foreman
96feedb6-1c20-4b93-9c8b-6e2533c41be9 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
19ef01d2-5e07-41a3-acdd-79215dedd440 | checklist | SA FAN |  | SA FAN
cfad8343-f8c5-4eac-b92a-5dcb630b3d81 | section | Pre-Start SA Fan
c9da187b-8768-41b4-a064-9a5afdaeb61b | checkpoint | Area clear, access good, enough space for install
14759a29-c4eb-4049-aded-cd869fb0cae3 | checkpoint | Duct Route clear, Penetrations complete
ea99b6bf-f83c-48e0-bd18-5369033198dd | checkpoint | Nogs/Supports in place
08c8a946-f056-4246-84a2-d73c66a6f8a3 | section | First Fix SA Fan
ccde4110-bb35-433c-8332-7487ba857e98 | checkpoint | Fan installed straight and level and correct orientation.
3b7fa667-4330-4c29-a3e1-b231c9384cbc | checkpoint | Fan or Cowl sealed to Upstand
d720de10-4ad4-4a0a-81fe-498574178409 | checkpoint | Correct Fan installed
2d15a3a6-3e81-4ffb-9781-025cfa3b9dce | checkpoint | Fan serial No. recorded
1f3b75e5-2625-4a4a-817b-d9b67e5859df | checkpoint | Fan seismically braced and vibration isolated
5fce4c98-c2d9-4b94-a27c-14ea33fae317 | checkpoint | Heater Bank installed to Manufacturers instructions
cb4c7cc9-fd7f-4bd7-b85f-bfea2c78c693 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
5bb3e0f6-f0e7-457c-9343-ffd1cfe23e08 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
feb47491-e454-4e15-85f7-4a022a1e9f98 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
2caf5bde-dd8c-4d00-badf-a9731748d597 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
a4579235-2ad8-4a4b-b842-6a5acd6f8036 | checkpoint | Flexible ducts taped then cable tied
dc94b0d0-3172-47b8-914e-bbca3113dd0f | checkpoint | Supply cable installed correctly, protected and secured
a0743053-3bc6-40ec-bf6a-51d98e926170 | checkpoint | Interconnecting cables correctly installed and protected
7c1e1e62-ad62-423a-8a3f-878314d07ffa | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
380bf9ee-6069-475d-815c-9fff8cffb20d | section | Second Fix SA Fan
d8501bac-6149-4c62-a9c8-4c4a1e49fd32 | checkpoint | Grilles installed square and level
227d9e5f-1f27-4118-89ce-59ecdc9cf964 | checkpoint | Flexible ducts taped then cable tied to grilles/boots
5418e44e-525a-45f8-aa6b-aeb639a266f5 | checkpoint | Boots sealed to grilles
b11d2d1a-609a-40be-9ae0-8d6a74dcab76 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
dc069d3f-bacf-4255-ba7f-62e0769447ef | checkpoint | Controllers fitted off. Heater Bank THT set
74931b5a-6410-4d80-8bb2-38b1e2badd68 | checkpoint | Power fitted off
7a9abe83-d8ad-491a-9f79-27cab172fef3 | checkpoint | Area left clean and tidy, fingerprints removed
7bad3642-64d5-4e4d-9885-502907d7ba8d | checkpoint | Plant and controllers labelled
62cebbfc-23bd-4544-90f1-ea12bcf6d3ba | section | Commission SA Fan
3968ff3b-5f15-4191-8441-c3b3bff01001 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
dd10b8d0-9774-446b-b5c0-5fd95f27be8a | checkpoint | Electrical testing complete
8a71ab93-a54f-497b-9db8-b697389f8f52 | checkpoint | COC issued
c2144b71-00fc-40b7-a488-80455f34abdf | checklist | Split HW |  | Split HW
ba7e7ce1-fbc8-4a2e-8db5-dfbbccefa8e3 | section | Pre-Start HW
2d9da7b0-354a-43cd-91e2-46e402c73c72 | checkpoint | Area clear, access good, enough space for install
5da09642-c451-4cf6-9847-13ecb4158659 | checkpoint | Area/base ready for outdoor unit
66b653b0-5e4d-406f-8dea-8c1a06cab3f5 | checkpoint | Any required drains for outdoor unit in place
5e692fe5-ac38-4221-8b17-16dcd2deab94 | checkpoint | Pipework route all clear, penetrations complete
d922e4e0-e8f2-4fbe-bc5d-f63507b1436b | checkpoint | Nogs in place
8e3598f3-17b0-4092-b2a7-f9d23c6a48aa | checkpoint | Drain 1m from Indoor unit location by plumber
1768f3ec-82b7-48f2-9bfa-a6634a5d3bfb | section | First Fix HW
77640eb0-df59-43f6-a5f3-290fee20c383 | checkpoint | Pipework Insulated complete length
7935ff3e-2478-4a66-90e9-cb38e5ce4242 | checkpoint | Drain installed and insulated
eb982ab3-42b9-4c4a-a5e7-9769b6177cf8 | checkpoint | Supply cable installed correctly, protected and secured
c688d5f6-63fb-4477-8bd2-c9beaa50a90e | checkpoint | Interconnecting cables correctly installed and protected
ebc5a48e-a4d7-4cb6-9cd3-1a69c9791152 | section | Second Fix HW
ad7d9763-69e9-4701-90b3-5e1e1560b360 | checkpoint | System pressure checked and still holding 1st fix pressure
8b29fa31-0872-4f2c-bd9a-b7ffbc158859 | checkpoint | Indoor unit secure, level and tight to wall
ff8805a5-2d16-4613-aee1-9450abe81604 | checkpoint | Correct Indoor unit installed
9fcd79d2-4baa-43a1-83d5-0255131f2906 | checkpoint | Outdoor unit secure and level
6fb7608c-c231-4505-b919-2174c9ff737c | checkpoint | Correct Outdoor unit installed
a0391a5c-8ba5-4736-bb3f-35608acdb65b | checkpoint | Indoor unit serial no. recorded
536e43a5-6364-4a47-abee-8a920a7bdf3f | checkpoint | Outdoor Unit serial no. recorded
21b37bbf-982e-4e99-80ce-256612f30318 | checkpoint | Area left clean and tidy, fingerprints removed
7dd83865-950c-4414-9411-d209aa4cdf4e | section | Commission
b3525aae-a8b1-4a64-8285-f63bb5817f4f | checkpoint | Installer confirmed commissioned and paperwork submitted
8739864f-f8c0-48b0-aeb3-c39bd5b67c22 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
a17dd38f-dde7-46a5-91a9-947416103d6c | checkpoint | Electrical testing complete
e025a74a-015a-4733-ac5e-8e8405d4aac9 | checklist | VRV Cassette |  | VRV Cassette
0a954b9c-2614-404d-9cd3-82b891158be6 | section | Pre-Start VRV Cass
a61cd125-ea37-44fb-bc27-713d07ec56a8 | checkpoint | Area clear, access good, enough space for install
e357816d-b0a3-4631-b534-f4b2397ba3dd | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
608350d6-ca3d-41b2-af83-91e197d6fb5c | section | First Fix VRV Cass
7e367efd-6966-4761-98dc-a0e2b3692426 | checkpoint | Pipework connected to BS Box and Indoor unit
e4e39118-ef6b-459a-88ab-eb538c13878f | checkpoint | Pipework Insulated complete length
dbf572e6-f193-4e92-9146-ae6c5a48eee3 | checkpoint | Pipework supported incl any seismic restraints
f5c83e77-83d2-4344-9cdb-25c173d815c8 | checkpoint | Indoor unit level, secure, vibration isolated and seismically retsrained
2de5fb9c-9c36-4256-9721-a0b9bb5173ee | checkpoint | Correct Indoor unit installed
d1872696-6e64-4ba5-bbc8-c41e92110310 | checkpoint | Indoor unit serial no. recorded
6ca745f2-f8a4-44ca-9b3e-ae9272ced998 | checkpoint | Drain 1m from Indoor unit location by plumber
105977f7-5b9b-408d-ad12-68e9ab10de53 | checkpoint | Drain installed and insulated
63014bff-37aa-4b7e-9031-60effb55e859 | checkpoint | Supply cable installed correctly, protected and secured
ff520b86-ea76-46aa-98e5-61333a115ea9 | checkpoint | Interconnecting cables correctly installed and protected
24c21790-886c-40b6-b074-85144fa4ad09 | checkpoint | Remote controller cable installed
8d110c5f-eca9-4565-a952-19bce41c8688 | checkpoint | Access Panel requirements are marked and given to builders
f1971171-f3af-4fd9-a9ce-b67bc74b6601 | checkpoint | Plans marked up for As Builts
c4680a9e-2c2b-4073-ae11-70d03b798b0c | section | Second Fix VRV Cass
cca84d36-5ee5-488a-877f-c5604fe48157 | checkpoint | Face plate installed flush and square
b6efe794-00a6-45d6-b088-a68623a08a6c | checkpoint | Controller installed
d97dc569-f542-48d3-aaed-cd4b838592e0 | checkpoint | Area left clean and tidy, finger prints removed
69683a39-0ac0-4fd7-a73a-ce08a19c75cc | checkpoint | Plant and controller labelled
77d999f2-f5f9-4ed4-a1dc-36ca19c6be67 | checklist | VRV High Wall |  | VRV High Wall
0ccf59d2-f15c-437a-a824-bee6bcbc8510 | section | Pre-Start HW
cd9e46fc-047c-4bec-9769-2b1ac4d43dfa | checkpoint | Area clear, access good, enough space for install
05b7a2e1-7b1e-4472-8fbf-2f35c5f64a09 | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
f555549b-21b9-4c8e-8dae-434212c85bb2 | section | First Fix HW
5e4e760d-776b-49e1-867a-9e300fbcd10d | checkpoint | Pipework connected to BS Box and Indoor unit
5dae8698-2f9d-4a16-845b-dd412c133287 | checkpoint | Pipework Insulated complete length
190b5204-2319-468b-9791-ce037a83e15d | checkpoint | Insulation Joins Glued and taped
22c9dba3-54a4-4077-92e3-02112195c879 | checkpoint | Pipework supported incl any seismic restraints
f2076cf2-f166-431c-a073-b828ba593b51 | checkpoint | Drain 1m from Indoor unit location by plumber
d257033b-862a-48f1-a30f-06bb4a78fb1d | checkpoint | Drain installed and insulated
3f6512a5-e9bd-4593-a31e-a03e7d841c91 | checkpoint | Supply cable installed correctly, protected and secured
16ef197b-d41c-4252-89e1-6c05f64fbb53 | checkpoint | Interconnecting cables correctly installed and protected
6b2bcbcc-bf6f-4417-9568-80a851ab2982 | checkpoint | Remote controller cable installed
39c3dc94-aba5-4985-b0ee-4806d271c179 | section | Second Fix HW
80dec31b-da2f-413c-8909-db03ce288bf5 | checkpoint | Indoor unit secure, level and tight to wall
8f1a903d-f28a-4193-9722-4adf0b8cf5f7 | checkpoint | Correct Indoor unit installed
731c8bc6-9356-4bdd-8872-af83ee65be4e | checkpoint | Indoor unit serial no. recorded
094dbcd1-4319-46a4-af4b-36d73eeb71b8 | checkpoint | Installer confirmed drain tested
8915eb71-e46e-4b76-8d1a-ade8e95b9b93 | checkpoint | Controller installed
54a73129-2a88-4122-86e4-edf56e007bd3 | checkpoint | Area left clean and tidy, finger prints removed
781a6c05-0917-48ed-9e01-3505d11fb6af | checkpoint | Plant and controller labelled
8fc1cb31-18b4-48b8-b6cd-21e2bb6e008d | checkpoint | Access for future maintenance all clear. Filter can be easily removed
fc728a5b-e383-4425-8fcc-ddbc8c0ca3a9 | checklist | VRV Outdoor Unit |  | VRV Outdoor Unit
1115b592-b930-4dd0-8f4e-72d701af1fa1 | section | PRE-START VRV OU
beda0538-f2f5-4734-9a01-6b25f7f9246c | checkpoint | Area/base ready for outdoor unit
7604d0da-8d62-4223-96eb-1ef2af18ecdb | checkpoint | Any required drains in place
07322967-c44a-4e52-94e2-583a5de0b3c4 | checkpoint | Outdoor unit area accessible
73e14f64-e420-470e-951d-02f486a313d6 | checkpoint | Pipework route from OU to BS box all clear, penetrations complete
8f8b8155-bd1f-409d-9dff-047cc4d8f7f6 | checkpoint | Area clear for BS Box installation
cf225294-a777-4de1-b9ea-1ad7edba04be | section | FIRST FIX VRV OU
dfccb59b-1024-4fc1-991e-f601d3feae4a | checkpoint | Outdoor unit brackets/feet/strut in place
fdc83dcd-2646-4bf9-a37c-6e895c12050c | checkpoint | Unit level, secure, bolted down, seismically restrained
6e2fea7f-8e12-4d4c-a626-f041cb393e21 | checkpoint | Correct VRV unit installed. (INSERT PHOTO)
888179ab-ab1b-48ad-9c80-5cd1a8432f3c | checkpoint | Pipework connected from OU unit to BS box
79f260d9-ef21-48df-9d5d-c402ac199dd1 | checkpoint | Pipework Insulated, glued and taped
5348d99f-4cdb-40d0-a25e-66e08697ce76 | checkpoint | Pipework supported incl any seismic restraints
b81e3da7-c3ec-487f-9cc4-879adf4e205f | checkpoint | Pipework supported up off the ground
886d1a6b-93f4-46cc-bae4-5ffdaff54a04 | checkpoint | Refnets installed as per Manufacturers Instructions
f8eba974-dba3-4eeb-8d76-dd423544bd71 | checkpoint | BS Box level, secure and seismically retsrained
d4ad1a9b-d73d-42cb-9587-9ac7e517a34c | checkpoint | Correct BS unit installed. (INSERT PHOTO)
c6fb85d1-e8d3-4886-82d0-450e7c464695 | checkpoint | Drain installed and insulated
ad925225-b936-41ba-bc06-3c49bfb1dd81 | checkpoint | Pipe lengths are recorded accuratley. INSERT PIPE LENGTH (IN NOTES):
405c2320-0593-4436-80cc-f41614ef9be4 | checkpoint | Pipe sizes from OU to BS box match manufacturers schematic
72613895-b018-4725-bfb2-6e285bcce52a | checkpoint | Access Panel requirements are marked and given to builders
5e7f4bb5-ab83-4f50-8b67-5e73c2c08e4f | checkpoint | Plans marked up for As Builts
52477478-0081-4a11-a107-f24b0345d2a8 | checkpoint | All Waste and Surplus Materials removed from worksite.
6ab075d5-5739-4cc4-96cb-9f0283ed6523 | section | COMMISSION VRV OU
c78bb2f2-1969-47b8-a7ff-79569feecd83 | checkpoint | Access to OU unit is good
966412fa-8a52-400e-a65f-51ea1ced9497 | checkpoint | Access to BS Box is good
9e2bdb8c-c349-4fa7-a353-aaa06bfa13c6 | checkpoint | Access to Indoor units is good
53e3e766-6dbb-4eb9-a863-c74312bedc9b | checkpoint | Pre-commissioning paperwork completed and sent to TSL PM
2a914401-8412-4ae6-af19-5c4c42a13e13 | checkpoint | Power on to compressor for 24 hours (impt: only once evac completed)
99c76ecf-33d4-4276-aa63-f811a7e872ff | checkpoint | Commissioned by Supplier
77ddf0d6-1947-42e7-bd47-ba1843540727 | checkpoint | All plant labelled incl OU/BS/Indoors/Controllers/Pipework
ab6aca38-c8f7-4cde-9755-d9efc95fd720 | checklist | Z - VRV Outdoor Unit |  | VRV Outdoor Unit
8a9604d0-4972-4620-b84a-647eaf199e95 | section | Pre-Start VRV OU
d96ca2a7-33d2-4385-91fd-e72705b605ff | checkpoint | Area/base ready for outdoor unit
8847d149-ddea-438b-bd45-f76a149d5c69 | checkpoint | Outdoor unit area accessible
d3e59174-c721-4582-b267-e25ae0e2f703 | checkpoint | Pipework route from OU to BS box all clear, penetrations complete
a6befc4d-753f-45e2-84e1-347be427d89f | checkpoint | Area clear for BS Box installation
d541d1ab-9427-4f01-b1df-8372d559740a | section | First Fix VRV OU
20d83c12-de41-4803-a03a-d408a810e00c | checkpoint | Outdoor unit brackets/feet/strut in place
d33f34c8-9957-4311-b586-934dc1c363c5 | checkpoint | Unit level, secure, bolted down, seismically restrained
5af3ab46-7e8f-45e4-afdd-d55a4ad503b0 | checkpoint | Correct outdoor unit installed
17e60370-df96-4336-8a4d-940ceac6a7f6 | checkpoint | Clearance under unit for cleaning
c86ffce8-9a56-4fe2-8e94-2312770dc854 | checkpoint | Pipework connected from OU unit to BS box
f6a36582-85e6-421a-9499-696f4dc34d4e | checkpoint | Pipework Insulated
d086bf76-6a3a-459a-838a-2eeeeb479214 | checkpoint | Insulation joins glued and taped
ecc7e920-2ab5-462f-aaf7-eb94f1a04a6b | checkpoint | Pipework supported incl any seismic restraints
9a9c7110-d868-42b0-afe2-3e4c0bfd4f61 | checkpoint | BS Box level, secure and seismically retsrained
958d0a39-dcc3-4a3c-9384-e59171fb8640 | checkpoint | Correct BS Box installed
8b53512c-a85b-40dd-91de-fa11ec1bd347 | checkpoint | BS Box serial no. recorded
7a7ab605-4dba-4883-8671-32f32db343b3 | checkpoint | Drain 1m from BS Box location by plumber
2a6010a9-b569-41aa-b9d0-e78c3d90da57 | checkpoint | Drain installed and insulated
e35606f3-ac97-4479-b3b3-7509d1a5725c | checkpoint | Supply cable installed correctly, protected and secured
01a78c01-a03b-4d3b-9c32-3b9aacd8e0e5 | checkpoint | Interconnecting cables correctly installed and protected
7e634808-f355-4fdf-b669-8005ac3d1389 | checkpoint | Remote controller cable installed
52a71103-f60b-4eb8-9692-4f990570022b | checkpoint | Access Panel requirements are marked and given to builders
90c5872b-e870-422b-a090-7274eba37101 | checkpoint | Plans marked up for As Builts
f829f623-d201-4415-858d-b37b3ec026e5 | section | Commission VRV OU
aa4e9e31-65ad-4355-9463-6b3f9cc956f1 | checkpoint | Access to OU unit is good
5e4e2ac8-18e4-45af-8e64-6cb8ab41dc29 | checkpoint | Access to BS Box is good
311168a2-efe4-4565-8805-4c6ad0cb7a3d | checkpoint | Access to Indoor units is good
1b103113-1912-4a5a-b5ae-4c9f854e791e | checkpoint | Commissioned by Daikin
829ce05a-cca9-45dd-8c76-f6da99555daa | checkpoint | OU model and serial number(write in comments and take photo)
8c4840e2-6be1-43ea-9049-6ed47a6dd6c2 | checkpoint | All plant labelled incl OU/BS/Indoors/Controllers/Pipework