## Master List Templates
Id | Type | Name | Values | Prompting Name
4f727a59-4299-4227-9052-e8b429dd1fd6 | checklist | Fire Dampers |  | Fire Dampers
3e7f85da-877b-4efa-b47b-efce9a349cce | section | Pre-Start Fire Damper
a125b3ab-1bd0-4c4d-8c71-2051fddc6705 | checkpoint | Area clear, access good, enough space for install
6ba5c600-debb-430a-a872-ca1c59e0c7a7 | checkpoint | Duct Route clear, Penetrations complete
79b55644-e611-4038-81bf-3c09f44b52a3 | section | First Fix Fire Damper
7eb77dd2-6432-4ae1-9810-c78af312c5e5 | checkpoint | Correct Fire Damper installed. (Insert Photo)
edb13b58-7d6c-4d0f-a300-f69795250fb9 | checkpoint | Fire Damper installed straight and level with correct orientation.
02e08761-75ee-43d2-9591-b920d72f825a | checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
d697b986-ba81-4a91-8993-ce055e73dfab | checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
cb49af99-b40d-4d66-97f2-46692fef3658 | checkpoint | Access Panels in duct for fire dampers.
28cba624-b158-4d97-8a03-bfa1a24e76d4 | checkpoint | Building Access Panel requirements are marked and given to builders
6a38b280-855c-4c00-8255-23a3f8cf5289 | checkpoint | Plans marked up for As Builts with Access Panel locations
d33ba6eb-28c8-4854-8b42-2940a154e9b8 | section | Second Fix Fire Damper
1d369191-28df-40f0-9afa-3521d492b676 | checkpoint | Fire Damper Label affixed, Asset Number applied.
99fcfadd-4ea2-45ef-b749-c0a4c1d2672b | checkpoint | Fire Dampers Access Panels still accessible for maintenance
5d2eb6ef-1c00-4070-a498-8e46333efb04 | checkpoint | Area left clean and tidy, finger prints removed
ae2acbc5-9afe-4989-8c9f-a1b92fad8b30 | checkpoint | Fire Damper sealed to structure both sides.
f68972b4-6d81-41aa-aa09-4be60adafed1 | section | Commission Fire Damper
35abf88d-b375-479f-8b77-924971281f8a | checkpoint | Drop Tested as applicable
3399aa37-48d7-492c-8a16-93ef940f0411 | checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
7be34150-c368-48a3-ba66-611937573253 | checkpoint | Fire Damper Label filled out, photo uploaded.
40670fb4-21e7-4227-bdb5-faa6329dd3e3 | checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
91a77d34-03fe-4f7c-b402-578d38b427d1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
58b1ea97-b983-5fa0-a594-0cbe9c82b184 | checklist | Extract Fan QA |  | Extractor Fan
e4db0c9e-5f80-5dc2-8d9e-3bfd335a3cb6 | section | Pre-start:
73781626-9a7f-547c-bb9e-792ce2d92db9 | checkpoint | Area clear, access good, enough space for install
5d1e6871-d176-5502-a838-e737a9d940fc | checkpoint | Duct route clear, Penetrations complete
f4d4b28c-ccd8-52c3-84fd-4cf59532d0d0 | checkpoint | Nogs/Supports in place
0e34b7c3-d763-5cbe-9ad7-7d9c7a9b7a26 | section | First Fix:
67d603cb-5e59-59bc-9ae4-4e12753175cd | checkpoint | Access Panel requirements marked up on drawings and submitted to client
8d2f8a1e-43b5-5b21-b7bc-30833556c3ed | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
8c9775bd-01a6-5596-aa0f-b58ae0943be2 | checkpoint | Mechanical First Fix complete
d08b3de0-cdb8-5336-b73d-44027e802613 | section | Second Fix:
15b7a5dd-5828-5e7d-8f8c-240c0bd4b5a8 | checkpoint | Area clear and access good for Second Fix
9a35dd68-9f9f-54da-944e-7afabc5685c7 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
ee75c421-5dfc-5d9a-9a06-09076e5e52f4 | checkpoint | Mechanical Second Fix complete
52f6f8d4-ee57-5bae-8f5f-2f5c943c4605 | section | Commission:
5d3b6254-844a-5db5-8083-3c581fc02142 | checkpoint | Good access to all areas of building
d5d1e6c6-5b3b-5b74-b788-f0cef7434f53 | checkpoint | Power live to Mechanical Plant
640f984e-3a9b-5fa0-95da-e1343917ef4f | checkpoint | Mechanical Plant commissioned
58591919-fe90-4b3e-884c-a60fa969631f | checklist | Jet Pulse Fan |  | Jet Pulse Fan
c723b74c-4c51-48dd-b2b6-6478670289f2 | section | Pre-Start SA Fan
b6408cd9-8d58-4fdc-9a3e-55124410076d | checkpoint | Area clear, access good, enough space for install
e6b54da9-bdaa-44f0-a43d-ff290a28dcac | checkpoint | Duct Route clear, Penetrations complete
c96d116f-d6d4-4474-8336-99d6b35fe16b | checkpoint | Nogs/Supports in place
94750626-d9d4-4dae-a222-8f235642c54b | section | First Fix SA Fan
dbc0ea22-2a83-48ad-88b9-c2aafe906d58 | checkpoint | Fan installed straight and level and correct orientation.
c3b6704d-6f42-4cd8-81f6-63c24a834555 | checkpoint | Correct Fan installed
fcf467d0-8da1-46b7-b453-12487c62c465 | checkpoint | Fan serial No. recorded
679b4203-ffd7-47ac-9461-ba441e109257 | checkpoint | Fan seismically braced and vibration isolated
b853623e-778e-4f41-8164-4545f1608743 | checkpoint | Supply cable installed correctly, protected and secured
22af564e-f5e8-4f44-8de9-a4597f1c2622 | checkpoint | Supply cable type, size and manufacturer
416189ce-0dc7-4cf0-b9ae-fc05ecb64a4c | checkpoint | Circuit protection type and rating
81358baf-05a4-4de5-87b4-9bc452c7a266 | checkpoint | Correctly rated isolator installed to standards
b4548009-972e-4cfa-8fe5-b368574a522a | checkpoint | Interconnecting cables correctly installed and protected
5b6782ae-cdcf-4294-a57a-13c598fcdd76 | checkpoint | Control cables correct rating and type
25836709-8f81-4a94-9da2-c716fe1141d4 | checkpoint | Screened cables drain to earth as per specifications
ca0f1717-658e-4aa6-9d57-4e07cc4f8ea2 | checkpoint | Control cables maintain minimum distance from power cables
dbae85dd-962a-44f9-95dc-834ff36677bb | checkpoint | Daisy chain loops complete and correct
4bb22eb7-bd96-4e24-95aa-9c15f6c45812 | checkpoint | Remote controller cable installed
e1abbeaf-4815-4fe8-82b4-ac035b492a1e | checklist | S - S - Air conditioning |  | S - S - Air conditioning
e004e699-755c-463d-8260-8d4a8690b64f | section | Pre-start checks
19fc1f63-b422-4418-9d2f-f27641e1fdf1 | checkpoint | Area/base/wall ready for outdoor unit
6c351b0a-9f25-441c-9fb3-f1be99c4d870 | checkpoint | Pipework route all clear, penetrations complete
70bf9840-c374-4912-808c-c02130538297 | checkpoint | Nogs/ply in place for indoor unit
aa14e78c-8be3-4d20-8e84-4ce6c38ea3cc | checkpoint | Drain 1m from indoor unit location by plumber
39a64c16-6fe0-4903-bd62-755b81e91bf7 | section | First Fix
65faeaa3-95bb-4c74-b260-bfcd0b4a6ca3 | checkpoint | Complete length of pipework is insulated and acceptable
7447793a-d0cf-444d-ab4a-aae0b7c0b0a8 | checkpoint | Drain installed and insulated
43aa99e5-ced4-47f0-82e3-411878ffac16 | checkpoint | Supply cable installed correctly, protected and secured
cab8cad9-29db-4bc9-9340-f0463b92c26a | checkpoint | Outdoor wall brackets in place
b531f66c-c417-4dd9-a609-3233eb353678 | checkpoint | Interconnecting cables correctly installed and protected
d82957cb-b573-4131-9b60-bdce9d4075d6 | checkpoint | Mechanical First Fix complete and acceptable
d01b0b23-0d99-486a-8c3b-94e64e147578 | section | Second Fix
56aa7a96-0653-44aa-af56-f184d526a0b1 | checkpoint | System pressure checked and still holding pressure and acceptable
11533163-4147-4835-a371-2974e518ebc4 | checkpoint | Correct Indoor unit installed, level and tight to wall and acceptable
f89ee500-9676-40b2-a021-862403c9d6ee | checkpoint | Correct Outdoor unit installed and secure
f16b0789-affb-43aa-a96a-2390924d35cc | checkpoint | Indoor unit serial no. recorded
6d9ef9c3-0cd7-441c-acdd-4315f5e49048 | checkpoint | Outdoor Unit serial no. recorded
f22d6539-dad5-45db-b9e4-501e7c857d8c | checkpoint | Indoor unit run, fan speeds, modes etc. are acceptable
b360e77a-4713-41fd-9af6-55f6c8ba5b00 | checkpoint | Air conditioning Second Fix complete and acceptable
12e04be5-25de-44eb-9f8e-4c1143309a93 | section | Commissioning
d3c6dabe-7cfe-4434-b068-961b3d35332d | checkpoint | Installer confirmed commissioned and paperwork submitted
efce5508-751c-44c9-950e-ed75c02609f2 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
ff2eb2ea-e9b5-4793-bf77-af78c08e70c6 | checkpoint | Electrical testing complete
04239570-16fe-4c1c-bf2f-8111bb38b71b | checkpoint | Commissioning complete and acceptable
e591034c-fa1c-4781-bcdc-a967f34bed90 | checkpoint | Inspections completed and issued to Foreman
8a443737-d454-423a-8074-b168159fa72f | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
4bdb0032-c7e5-48ed-8fb9-fc7c40d82c7a | checklist | S - S - Ventilation - Apartment Ventilation |  | S - S - Ventilation - Apartment Ventilation
c9a7b82f-4711-4ffb-b03d-f209d36df6d9 | section | Pre-start checks
eaaa0dc9-0399-4f14-a0fe-11a4a689f1ba | checkpoint | Penetrations done in floors and walls (if needed)
2d6d1995-fd16-432d-8a71-8344cb0945de | checkpoint | Space for ducting (no trades in the way)
a2a90e47-d1e0-4047-b63d-9ccbec6efcf7 | checkpoint | Pipe through exterior wall installed by RHC to connect to
767e048c-5d99-45f7-8eb7-854d1a64c269 | checkpoint | Drawings and work scope confirmed
cedc8f5e-d1c9-4084-a021-037d8416d4a9 | section | First Fix
8de5d90d-93d1-46b9-a5ad-601aeae1793b | checkpoint | Ductwork run straight level and well supported
2420264f-d800-4492-90e7-c0099bcd3a5f | checkpoint | All ductwork joints sealed
b3e8838a-f751-4afe-8afa-651f250bb66c | checkpoint | All SAB joints sealed and taped
3beacbdc-27fa-4abd-9c14-e798bc46507a | checkpoint | All flexible ducts cable tied and taped to duct
d89f76d7-80d8-4f1f-9be4-ad64382df054 | checkpoint | Identify locations and correct model of Fire damper to be installed
799bcf67-7dc5-412a-8e34-92ba35b3ef0f | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
2784e3b6-ae77-4922-89a4-80fe796da105 | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
fb728531-3637-4921-b47c-aad5a8ca10cd | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
0a228e74-528e-43c6-ba9b-518bf56625aa | checkpoint | Install using Materials specified in the PS1
f0fb5e20-2a99-469f-a6c5-b01364083a73 | checkpoint | Upload Photos of Install
38a27910-1132-4259-904a-e4b3f79013e1 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
29e5392a-d838-4ebd-9220-9c91d575601e | checkpoint | Flexible ducts fixed in place to grille location
681acad2-db8c-4097-9889-125916170741 | checkpoint | Identify Fan Upgrade Requirement
e69bc0bf-a52d-4b14-9759-aca7f3720db1 | checkpoint | Area Clear for Install of Ducting, Fan, and Control Box
6ac41462-37d7-411e-b83f-819157fb7beb | checkpoint | Install Fan, ducting and control box as per spec.
363c0fdb-2531-45e2-905d-7e591fdd25d2 | checkpoint | Grille locations/access panels marked on plans
f81e507a-309a-43ae-805f-f7ed73913567 | checkpoint | Mechanical First Fix complete
55d0cc69-26d8-44a8-b882-04dde57d6ba9 | section | Second Fix
26a77b24-434e-457d-8639-3716dece15a9 | checkpoint | Ceiling fans installed square and level
19fe2890-3e23-470b-b32c-1af856799282 | checkpoint | Kitchen range hood installed by RHC to connect to
51265a48-dfff-4497-9145-7308f207dba3 | checkpoint | Fingerprints removed from grilles/walls/ceilings
3616a06d-2fa6-4b5b-9eeb-6bfb8e2f7707 | checkpoint | Fan plugged in before install to ceiling
4088aa19-ee98-4c6c-84ff-bff7194566a6 | checkpoint | External louver supplied by TSL, installed by RHC completed
8ebef741-42ad-46c5-a8d5-41eb69a0e825 | checkpoint | Commissioning form completed & given to TSL
fb4ccf71-ac3e-416f-a2af-78419f2dd6fc | checkpoint | Mechanical Second Fix complete
19ff61ac-0d03-4526-93ce-4667c83051fd | section | Commissioning
d0afb6ce-23e6-4ac7-b1d8-af216d0dd66b | checkpoint | Correct product used as per requirements
adac864a-6c27-444f-b739-3044e285ba21 | checkpoint | Correct design followed as per drawings
5fb7d9ce-2e9a-4b90-94a7-af981c66183e | checkpoint | Mechanical Plant commissioned
45294caf-6c5c-49bb-a2f2-a9c083d810b7 | checkpoint | Inspections completed and issued to Foreman
9dc8e085-5197-42b2-9d2e-c0033ae6e61e | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
96c60819-4972-48d4-8fae-977c45cf851c | checklist | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan |  | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
8817c5a6-3ffe-49ec-8188-fe243f529065 | section | Pre-start check
a97ccdec-2376-47dc-9c81-a7961e68999e | checkpoint | Area clear, access god, enough space for install
15bd6e9b-55f9-4b97-802e-99282eb1d9b6 | checkpoint | Duct Route clear, Penetrations completed
c43dd692-9ee4-4d5b-9a16-9f1e8bdfaee7 | checkpoint | Nogs/Supports in place
137a42f2-2594-418b-89a6-c20a9a380f2c | section | First Fix
120e90e8-0e00-45ad-8c71-512ecc8779a0 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
afb1e231-17b5-4295-beb8-568d456005a6 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
cd9255b7-0e6e-4192-bde1-b173a6fa22e0 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
b2d8f1ae-d106-44e3-9f1b-85bf25db7cf9 | checkpoint | Install using Materials specified in the PS1
3b8b1317-c490-4772-8dc3-2b50da899a6f | checkpoint | Upload Photos of Install
3b4c81c7-80d2-4fe0-b0e9-9e4505a367e4 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
0bcf5e96-9ed3-4b8d-af31-b7d67e4d2735 | checkpoint | All seismic restraints in place (if needed)
8a790768-12ee-41d7-ab0c-90c0f98c01a8 | checkpoint | Mechanical First Fix complete
32f46156-4e90-4880-88d2-ad404e182ec4 | section | Second Fix
e47f2811-6435-452b-834f-b2cd29821dbc | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
bd190f92-ee09-4ddf-84c3-4f2df8127e44 | checkpoint | Mechanical Second Fix complete
94e8f8af-1d0c-4fa2-b45f-9182be9945a4 | section | Commissioning
9b6b01bd-811c-4a4c-87e7-c5ccf2fb8728 | checkpoint | Good access to all areas of building
b2f46a47-9853-4afa-abd4-bc0c80a98593 | checkpoint | Power live to Mechanical Plant
30e70b34-6228-49d9-b49f-c0ce73264feb | checkpoint | Mechanical Plant commissioned
573999fa-7abf-4f20-b608-f8bdc3ac5276 | checkpoint | Inspections completed and issued to Foreman
ea6ba91e-7479-43b1-a4f7-7059e06a3876 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
b4681af4-431f-496e-a2d2-d555c9b5c452 | checklist | S - S - Ventilation - Corridors Ventilation |  | S - S - Ventilation - Corridors Ventilation
ceaf539b-4e01-4572-bdd0-c884949b2e2e | section | Pre-start checks
b83d10ed-1f3a-4162-bdf5-53a4d6dd1fc1 | checkpoint | Area clear, access god, enough space for install
7e0b1872-515c-4def-854e-43109bf358bf | checkpoint | Duct Route clear, Penetrations completed
6f695b98-2126-4d90-8916-a889d7abc211 | checkpoint | Nogs/Supports in place
16094733-d3d1-4187-bbbf-a1e2a44429b3 | section | First Fix
16ab3d36-a0ca-4516-9ea8-76d466bc43f5 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
f797e802-8db8-484d-95cc-22444798d635 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
5de1858b-ba89-4fb8-a23f-624e879eeff0 | checkpoint | All flexible ducts cable tied and taped to duct
e417903b-426c-434e-9a22-43f3615dd6b6 | checkpoint | Identify locations and correct model of Fire damper to be installed
eb27b4d5-6c6b-4f30-a557-c4bcad10d3c8 | checkpoint | Install to Manufacturers Specifications
3d548424-1de6-4480-95a2-f32ccb6f84b4 | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
67b66ced-a2fb-46a8-9bd9-34603892d9d7 | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
a476ca81-5c4a-4cd2-ba06-b1989e2c3dd9 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
02a29659-983e-4499-9826-ad9722f0edb1 | checkpoint | Install using Materials specified in the PS1
b4cadb08-139e-4bfc-a4f0-e557761bf6bf | checkpoint | Upload Photos of Install
3cf40236-3f0c-4ced-ae84-af2a21967e49 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
e4ade1c2-34ed-47ec-a83b-79a5c9ca02d5 | checkpoint | Mechanical First Fix complete
6d1890b9-e4ae-444c-bede-779ff2c2e668 | section | Second Fix
aeb356b9-7417-4efc-b7fd-6e09c82ee46d | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
499550f7-1250-4b19-b1a8-4461a38dd90e | checkpoint | Mechanical Second Fix complete
63cc7a60-800e-4c33-82c3-8e0e53619277 | section | Commissioning
691323de-c9ca-439b-9dd9-a7ed8dd1c22d | checkpoint | Mechanical Plant commissioned
85f28a73-c39f-4af5-9fa8-83847e559ba6 | checkpoint | Inspections completed and issued to Foreman
b099adab-4c2b-48dc-8d0b-d6e32afa810e | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
776fe5ae-bafa-5977-a9c5-ce0782623f90 | checklist | SA Fan QA |  | SA Fan
75716990-002f-5325-9fa7-7131739709a7 | section | Pre-start:
57f016ac-2846-5186-8a5f-01b829c079e7 | checkpoint | Area clear, access good, enough space for install
c7c49816-74fd-5e85-96f9-08034b9f2bad | checkpoint | Duct route clear, Penetrations complete
427da08a-20b3-561f-aa28-99fba21e2074 | checkpoint | Nogs/Supports in place
ef08c9b8-d19d-5bb6-808a-c0ef4fe63c98 | section | First Fix:
31963167-b233-5bb1-b525-1c2e7712d4d0 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
f5ef700e-d98f-5003-830e-39a6a9e11e12 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
a06ce468-f8d0-569c-8438-a08e804cfb24 | checkpoint | Mechanical First Fix complete
b3130177-8602-500d-b7fe-1b5306360287 | section | Second Fix:
c325b9c7-4a41-541c-ad1a-cdc64649001c | checkpoint | Area clear and access good for Second Fix
3f5c3f52-9051-594d-a9ee-d4570ede9367 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
9411c7ae-a0e0-5f8f-bea7-2f75cade9757 | checkpoint | Mechanical Second Fix complete
8bb8fa69-7443-5ec2-9d07-d0d1addd3153 | section | Commission:
75630062-5d42-5d85-ae65-cca5f69822b9 | checkpoint | Good access to all areas of building
63f5a1d8-3ed4-58dd-907f-1d85d8960f73 | checkpoint | Power live to Mechanical Plant
f2139290-2fbb-57da-909b-be7ebc044dd1 | checkpoint | Mechanical Plant commissioned
5b99fe6c-f4e3-54e0-9ff3-2f4591ad7390 | checklist | Split HW QA |  | Split HW
f6175e19-2bcd-5d3d-a593-35650e080ccb | section | Pre-start:
d4fdd6b8-5476-5b4a-bec5-5daecbc1e72b | checkpoint | Area clear, access good, enough space for install
87589dee-79fa-52cd-9111-9d0de97cabb5 | checkpoint | Area/base/wall ready for outdoor unit
208b2e21-6612-53ed-9203-b519aea6e3cb | checkpoint | Any required drains for outdoor unit in place
223ddca0-4467-5d11-84e1-d1a11c0b4f0f | checkpoint | Pipework route all clear, penetrations complete
625325ff-0bf4-5daa-a996-98c73fdc9a8a | checkpoint | Nogs in place
ba9acc0d-4668-5bc3-a67a-657d51ab2f8e | checkpoint | Drain 1m from Indoor unit location by plumber
091926ed-0d75-58d0-a2e7-10b794f1140c | section | First Fix:
f7e8e68b-f640-5996-8161-96759ea62bdf | checkpoint | Access Panel requirements marked up on drawings and submitted to client
77fcf60a-662d-541b-808c-7743b9a0520b | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
09f83453-18a8-5b8b-b5e8-e8d3f77a8732 | checkpoint | Mechanical First Fix complete
34198943-3a21-5542-a43e-18b163b0dedc | section | Second Fix:
c24845e0-756c-5a7a-90cf-3988e300c30c | checkpoint | Area clear and access good for Second Fix
368fa737-1bfa-51ec-94d3-8285aae869e2 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
04493dc5-0fef-5ac5-b178-894cec2139c2 | checkpoint | Mechanical Second Fix complete
38c52499-f94c-5e14-a3e4-150ea5b3cb9e | section | Commission:
63863c78-2f1f-5b84-aad0-c1352f4c8abe | checkpoint | Good access to all areas of building
29351cb3-faf0-537d-b550-17267ba63d33 | checkpoint | Power live to Mechanical Plant
30d30b71-a511-5ceb-8702-dd8b929334b5 | checkpoint | Mechanical Plant commissioned
12ce432c-e0c6-4a5f-8805-a3983867b063 | checklist | SYS - S - S - Ventilation - Apartment Ventilation |  | S - S - Ventilation - Apartment Ventilation
1b8b792a-7d44-448b-8ba2-7507a91a4b8e | section | Pre-start checks
4f06da1f-4287-4740-81ec-e009f04ff9b8 | checkpoint | Penetrations done in floors and walls (if needed)
183b17dd-8ab8-4411-83c5-ac9ef3e16e72 | checkpoint | Space for ducting (no trades in the way)
62103c10-14a4-450a-814a-58f99e4f864a | checkpoint | Pipe through exterior wall installed by RHC to connect to
5b81ac48-6af6-464c-b15b-14d7975ac3ea | checkpoint | Drawings and work scope confirmed
8a7b75ed-c69f-4dd9-8340-d898f42350e4 | section | First Fix
d1ff8b83-57ac-4115-b74d-ea9d9cd60d0c | checkpoint | Ductwork run straight level and well supported
de0db4ac-a974-4552-aa59-f59a15de3ef2 | checkpoint | All ductwork joints sealed
51c5078f-b127-4664-93cd-753c59d7e60b | checkpoint | All SAB joints sealed and taped
1116421b-6d62-4199-b5ad-95f370e3c186 | checkpoint | All flexible ducts cable tied and taped to duct
177350ac-0398-497d-8e10-45c9802ec0c1 | checkpoint | Identify locations and correct model of Fire damper to be installed
efd90228-b41b-485c-b683-de799be20c36 | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
fbbf1e70-6a1e-4776-ab5b-2ccfee71275c | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
e221c40b-8161-417b-bae5-5fc0e9de5414 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
b64224e2-0f30-423f-9c83-7c71a871b319 | checkpoint | Install using Materials specified in the PS1
be0073c6-b1da-4d20-ab81-e11ed7c15a57 | checkpoint | Upload Photos of Install
e5a1828b-b5a0-47aa-9865-e8f7f4ff57ab | checkpoint | Refer back to Seismic Engineer for PS4 Production.
3638c294-a947-4cc9-8395-66220c2b7d5b | checkpoint | Flexible ducts fixed in place to grille location
82a641c2-0cf2-4885-b1ec-d8a86d4c6b92 | checkpoint | Identify Fan Upgrade Requirement
dba5aec9-3eba-4fed-b917-f476739c0057 | checkpoint | Area Clear for Install of Ducting, Fan, and Control Box
fdaaa27b-d82d-4318-9063-e8d2bae33d8c | checkpoint | Install Fan, ducting and control box as per spec.
eb679aa1-cfb1-4707-94d2-28d401cb644e | checkpoint | Grille locations/access panels marked on plans
2b2de2c5-1b78-40ec-8922-4bf4486e39ea | checkpoint | Mechanical First Fix complete
0f9441f6-0ccc-4cf6-802e-cb346c6f8b74 | section | Second Fix
aa39a2f0-cc27-43bd-8209-fa17e8e3117b | checkpoint | Ceiling fans installed square and level
8af60ffc-58ee-4bcc-819f-06b97dc444c3 | checkpoint | Kitchen range hood installed by RHC to connect to
5b7b67b5-c5d9-4fd7-841f-4aa83f1dd185 | checkpoint | Fingerprints removed from grilles/walls/ceilings
4569ef24-512d-48c9-b39b-70894affd444 | checkpoint | Fan plugged in before install to ceiling
6a888f93-fed6-4d8c-ba6a-2e9f88a01b44 | checkpoint | External louver supplied by TSL, installed by RHC completed
363bb7e4-d4a3-4854-a848-996ddd9b8afc | checkpoint | Commissioning form completed & given to TSL
ed5f3ffd-6648-4eca-8638-6f6ced98f0fc | checkpoint | Mechanical Second Fix complete
5b6a193b-81a7-4a70-9716-a978dab95915 | section | Commissioning
d97f0825-7d41-4c08-841c-b88f49632d6e | checkpoint | Correct product used as per requirements
a0c34fed-8c34-4bc4-91e8-5e6115da78e4 | checkpoint | Correct design followed as per drawings
88c25499-be22-4822-a2ab-5cf9c8e7cadd | checkpoint | Mechanical Plant commissioned
6c8f4a23-6bfc-400a-acfe-5e7e94cf5896 | checkpoint | Inspections completed and issued to Foreman
d690f6d0-48c8-4e23-bcb5-108b71004c44 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
fc23b32f-bd1c-44e3-8940-ad6bfd8623d3 | checklist | SYS - S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan |  | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
3136f6f3-a11d-4ff0-bc47-8b5677510464 | section | Pre-start checks
ddf14b22-7724-47ca-bd75-4d8ac11ebf78 | checkpoint | Area clear, access good, enough space for install
6e4b33b8-fe44-4e1f-bd35-5794fa89a556 | checkpoint | Duct Route clear, Penetrations completed
f223374a-379e-44d3-9aa1-e1af2cbfb365 | checkpoint | Nogs/Supports in place
9e8d5420-2b6a-4011-8406-c46c3e8efc32 | section | First Fix
b53ec490-9464-4c4a-a7fe-cd4dd72735c5 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
1a773a7b-2ecf-4b4d-9236-c307037cf71f | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
1aca9453-b5f3-4224-ad0b-4c4bc0d4ffb9 | checkpoint | Mechanical First Fix complete
77061827-99a0-4318-8a4e-13ac603f67ed | section | Second Fix
6119c11a-83ef-4271-b9af-159cadd211e3 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
2eb9fc2d-4767-4169-9774-3660047fe61c | checkpoint | Mechanical Second Fix complete
61db78a7-d926-4ae6-b44c-6b5912c1b69a | section | Commissioning
0b8a5d40-3692-46bb-88ed-c02151113a73 | checkpoint | Good access to all areas of building
81a57835-2a67-4c71-969b-56973923613d | checkpoint | Power live to Mechanical Plant
7fe706d4-f9c4-4f33-9225-f4b5df529fc9 | checkpoint | Mechanical Plant commissioned
b3251372-7b74-4b07-8da0-7ff135c6ead8 | checkpoint | Inspections completed and issued to Foreman
e102c04b-a5e9-4688-8122-a1fe9c9b274a | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
fc79f4e9-4fca-4022-920f-cc137b299909 | checklist | SYS - S - S - Ventilation - Corridors Ventilation |  | S - S - Ventilation - Corridors Ventilation
644d8b52-c9c0-4757-b078-94dc8a9f59a9 | section | Pre-start checks
c0c05cac-f258-421a-b75e-a6addfc0c733 | checkpoint | Area clear, access god, enough space for install
325f6dd8-e847-4558-a22b-a902d8d7b7f3 | checkpoint | Duct Route clear, Penetrations completed
ddedc965-009e-4e9a-8799-d993ee646675 | checkpoint | Nogs/Supports in place
a36f418d-5d97-446b-b788-915acae07766 | section | First Fix
bf844125-192d-4f55-a35a-3bfc0005f125 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
869eb314-97a1-4fd0-96a7-55e60000acda | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
3d03040a-dabe-4d9b-963f-eeeb3046a879 | checkpoint | All flexible ducts cable tied and taped to duct
a6391d52-9671-440d-8ea1-1a6b5f37c68a | checkpoint | Identify locations and correct model of Fire damper to be installed
ee916a86-07bb-4510-a9ca-f7d6bf284546 | checkpoint | Install to Manufacturers Specifications
c3ea770c-52b1-47e8-8b1e-dd570342daa8 | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
b362dbe4-c8f4-4ae6-806e-83dfed7144ca | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
eb84770d-6ad2-4d6b-babf-82d878eb8fcf | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
a838cbe1-0fa9-4034-8a35-f65c2407c22c | checkpoint | Install using Materials specified in the PS1
627853b8-0438-48e2-8b35-364a62bcf9f5 | checkpoint | Upload Photos of Install
b385a571-a667-4bdf-a31b-b6529deb26c2 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
b1b35aac-18df-48cc-b654-839669baef06 | checkpoint | Mechanical First Fix complete
ae0f5b98-28f6-4745-a57d-772d5b42e136 | section | Second Fix
39f79f07-9117-42e4-898c-92926d78f2c0 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
6a3dcfab-c8c7-4a36-972e-3e4cd76c74c0 | checkpoint | Mechanical Second Fix complete
4b5fff84-e75e-4874-b80c-fec5a6713aae | section | Commissioning
5ecfd690-2f0a-4264-ad4a-dcf148305e06 | checkpoint | Mechanical Plant commissioned
5eda3d98-a28e-4629-9166-9f70dc82e53f | checkpoint | Inspections completed and issued to Foreman
bf59fe08-3885-41d8-81b5-8ebafa4f3b4e | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS