## Master List Templates
Id | Type | Name | Values | Prompting Name
4f727a59-4299-4227-9052-e8b429dd1fd6 | checklist | Fire Dampers |  | Fire Dampers
3e7f85da-877b-4efa-b47b-efce9a349cce | section | Pre-Start Fire Damper
a125b3ab-1bd0-4c4d-8c71-2051fddc6705 | checkpoint | Area clear, access good, enough space for install
6ba5c600-debb-430a-a872-ca1c59e0c7a7 | checkpoint | Duct Route clear, Penetrations complete
79b55644-e611-4038-81bf-3c09f44b52a3 | section | First Fix Fire Damper
7eb77dd2-6432-4ae1-9810-c78af312c5e5 | checkpoint | Correct Fire Damper installed. (Insert Photo)
edb13b58-7d6c-4d0f-a300-f69795250fb9 | checkpoint | Fire Damper installed straight and level with correct orientation.
02e08761-75ee-43d2-9591-b920d72f825a | checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
d697b986-ba81-4a91-8993-ce055e73dfab | checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
cb49af99-b40d-4d66-97f2-46692fef3658 | checkpoint | Access Panels in duct for fire dampers.
28cba624-b158-4d97-8a03-bfa1a24e76d4 | checkpoint | Building Access Panel requirements are marked and given to builders
6a38b280-855c-4c00-8255-23a3f8cf5289 | checkpoint | Plans marked up for As Builts with Access Panel locations
d33ba6eb-28c8-4854-8b42-2940a154e9b8 | section | Second Fix Fire Damper
1d369191-28df-40f0-9afa-3521d492b676 | checkpoint | Fire Damper Label affixed, Asset Number applied.
99fcfadd-4ea2-45ef-b749-c0a4c1d2672b | checkpoint | Fire Dampers Access Panels still accessible for maintenance
5d2eb6ef-1c00-4070-a498-8e46333efb04 | checkpoint | Area left clean and tidy, finger prints removed
ae2acbc5-9afe-4989-8c9f-a1b92fad8b30 | checkpoint | Fire Damper sealed to structure both sides.
f68972b4-6d81-41aa-aa09-4be60adafed1 | section | Commission Fire Damper
35abf88d-b375-479f-8b77-924971281f8a | checkpoint | Drop Tested as applicable
3399aa37-48d7-492c-8a16-93ef940f0411 | checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
7be34150-c368-48a3-ba66-611937573253 | checkpoint | Fire Damper Label filled out, photo uploaded.
40670fb4-21e7-4227-bdb5-faa6329dd3e3 | checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
91a77d34-03fe-4f7c-b402-578d38b427d1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
75169c75-d9cc-4775-924e-36cc756aed85 | checklist | AHU |  | AHU
1b3e9c9b-4432-4e81-9c13-234d2550d15a | section | Pre-start:
41aafcc1-5615-4488-879a-94e2a89b598e | checkpoint | Area clear, access good, enough space for install
3e2e3fa7-04a5-4419-a256-8acb8e681430 | checkpoint | Duct route clear, Penetrations complete
7e3f0196-6789-4a44-bc54-9ca916076621 | checkpoint | Nogs/Supports in place
0623beb5-2b5c-4d6e-9d9b-9577ef17209b | section | First Fix:
23c3091a-174c-403b-9fb2-8546aee135fd | checkpoint | Access Panel requirements marked up on drawings and submitted to client
6d0d9d34-a900-42ba-ae6b-8c5297f2c07d | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
87249542-5c3d-423a-8a91-c0bbf7d09a00 | checkpoint | Mechanical First Fix complete
b9d4d20d-93c7-4fcf-86c4-cf8b4f290eee | section | Second Fix:
e212c6e1-b22b-496f-922e-c799c06da8a1 | checkpoint | Area clear and access good for Second Fix
c9d91a22-a716-4348-8a51-cb5561e3d0af | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
ad1fca3d-d654-42b8-97f1-4fb825e35ab7 | checkpoint | Mechanical Second Fix complete
2ee238f1-c49f-45a6-b61f-272f7ba6d20a | section | Commission:
c1f7b03b-6c7f-4a5c-a1f6-45151165dfa8 | checkpoint | Good access to all areas of building
c2ba895a-158e-4104-b44e-68d604650f01 | checkpoint | Power live to Mechanical Plant
c71f6c21-8567-4a80-bb92-48eb9fa083a8 | checkpoint | Mechanical Plant commissioned
5428607a-d96a-4748-88d9-e2b0306d4279 | checklist | Car Park SF/EF |  | Car Park SF/EF
a0e20fca-5ec5-4fc5-b0d3-aabefd84a8c5 | section | Pre-Start SA Fan
ffb211ba-abde-4e81-95c7-1233337e46a1 | checkpoint | Area clear, access good, enough space for install
a3a85950-2d3c-4078-9154-f8c9cff65f50 | checkpoint | Penetrations complete
c75a4771-c4fa-4bde-889d-cf1c17bebbce | section | First Fix SA Fan
9d73ce30-0a2d-4813-a9a4-cc5ee958fd5b | checkpoint | Fan installed straight and level and correct orientation.
ac47ca67-8bdc-49bc-b65f-c4476abcc455 | checkpoint | Correct Fan installed
8faf74b7-5208-4496-bf4c-3c93ec79b4ba | checklist | Coolroom |  | Coolroom
02a9b6dc-6480-4cfe-b43b-426b17f41692 | section | Pre-start:
26fd7fb5-565c-437f-b9ad-9e751010acb7 | checkpoint | Area clear, access good, enough space for install
8c7319ef-125a-4e17-8575-2b91741887d0 | checkpoint | Area/base/wall ready for outdoor unit
7718d102-b28d-4daf-bfb0-226ed2a1de6e | checkpoint | Any required drains for outdoor unit in place
24b7b3a2-9b0b-4147-9207-f599aecd2a94 | checkpoint | Area/Base/Walls ready for Coolroom Panels. Floor requirements met.
aadb8c59-57b4-4f6f-8c23-9c36fb69ed9a | checkpoint | Check set down for any rough surfaces (Smooth set down required).
ba9b82d5-6d77-4229-8fb1-ba56311684cd | checkpoint | Pipework route all clear, penetrations complete
6db43ac2-b9c1-41e6-bfae-454d2c47cf13 | checkpoint | Nogs in place
b706975c-ba59-4b78-91d7-fdeeeb826b43 | checkpoint | Drain in place by plumber
b70f428b-b5ea-4a9c-b711-1538d0579eb8 | checkpoint | Measure set down and mark out door cut out
c4ac3401-872d-4564-9b13-c306a5fbdf27 | checkpoint | Check if set down is dry and area is water tight
6bd52628-3da2-4190-8d86-fa47a2d73d3c | section | First Fix:
5d942f9b-7293-456c-bbf6-f36f78717d86 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
3b61df33-ee92-42a9-a224-d1c9a1a5c663 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
3efeb514-de0f-4e4f-a78a-4b39fa97b695 | checkpoint | Mechanical First Fix complete
ae9d58b9-973d-4182-a52b-72b97487b6e5 | section | Second Fix:
3133b3c4-0fc9-48c8-a11c-4637aa81c00c | checkpoint | Area clear and access good for Second Fix
353a1dd8-7b43-4edb-9bf9-ac644accb7a2 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
3abfbed8-5eea-47fb-aaf7-2d29fbcf62c7 | checkpoint | Mechanical Second Fix complete
096886d7-6dc9-46f2-a1a9-e3049d4f56da | section | Commission:
42c88671-7aa4-42d8-af8f-a60b7cd367cd | checkpoint | Good access to all areas of building
b3ec6c7e-ef68-41c3-bb7f-22b94f75a5a2 | checkpoint | Power live to Mechanical Plant
484fface-5ca2-46b6-b6a7-3202642048b2 | checkpoint | Mechanical Plant commissioned
a9673207-c98b-45af-b455-d73d0c793cb2 | checklist | CST - S - Completion Documents |  | CST - S - Completion Documents
e1df456c-6a98-451e-8ff6-9b13a4338fa2 | checkpoint | All relevant Compliance Documentation completed and attached above
63826e29-d281-579e-ba7a-b348ad99a991 | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
975c6935-98cb-590a-872a-22ed164e902c | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
e6b2c015-e866-4b00-99bc-9f33b8019c9e | signoff | Request Signoff
be18782d-136f-440a-aef2-19018d730d75 | checkpoint | Inspections completed and issued to Foreman
00af2a18-14fd-41e2-bcbe-e6331ad154d8 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
af521e47-0347-472f-8e4d-147beea25396 | checklist | Extract Fan |  | Extract Fan
75eb8133-4f11-47e7-97d9-d5b2ed5a5fb7 | section | Pre-start:
96c37fba-1c50-4ddd-a7b3-d8750e4498b1 | checkpoint | Area clear, access good, enough space for install
f482ed07-0552-4999-92be-916d45261c38 | checkpoint | Duct route clear, Penetrations complete
43f6e564-7984-47a9-8d3c-ff237062445e | checkpoint | Nogs/Supports in place
fedb4cf3-03d9-4bb4-859d-fd0d39b00b3d | section | First Fix:
5d4460f3-a6d1-4a83-8558-6896644c9a6b | checkpoint | Access Panel requirements marked up on drawings and submitted to client
67b8e271-93e9-440d-aefa-7242b40bbcb3 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
54385dbc-ae26-47af-a49b-a0295a9c15ab | checkpoint | Mechanical First Fix complete
ff1dacc6-8032-40ea-803b-c7b5e1882eca | section | Second Fix:
8d30e011-16f9-4d22-a3c7-eff0854ff4c0 | checkpoint | Area clear and access good for Second Fix
8acc6c88-a62f-473d-aa10-01742e937926 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
8ff77f37-7df5-4255-ab07-62484ee1c80f | checkpoint | Mechanical Second Fix complete
688efd7c-f3b8-4e2d-a326-91f32eb97db1 | section | Commission:
2780f31a-09d1-4cdc-a5bd-b389a53674db | checkpoint | Mechanical Plant commissioned
bcafe476-0724-438f-a64f-283296bb9f77 | checklist | HRV QA |  | HRV QA
34b5f5f5-da44-48dd-8618-1d39d29e5874 | section | Pre-start:
ab86fcb3-ec84-440c-ab35-063d0d50c469 | checkpoint | Area clear, access good, enough space for install
893b15a8-b5a4-45fe-b290-370a766b57ff | checkpoint | Duct route clear, Penetrations complete
2659339c-f852-4c4a-bf79-e5cff8b94376 | checkpoint | Nogs/Supports in place
102b2555-9219-46a3-8f1f-41c9f08c5d28 | section | First Fix:
df715d3e-a909-4f97-bc87-aa1deb6c874d | checkpoint | Access Panel requirements marked up on drawings and submitted to client
7b3b0de6-dfdb-44e7-9b28-7474909e496a | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
f98073a1-1dd7-4762-b6b8-e537691c5613 | checkpoint | Mechanical First Fix complete
8489451c-4bda-4975-b84c-5dfaee4fe47c | section | Second Fix:
50c8e6fa-7602-4eaf-a52d-bd72aad52e87 | checkpoint | Area clear and access good for Second Fix
9ca8b067-2d2a-4539-9017-bbf04f52e6f0 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
03248a8a-b71a-46ef-9a37-0ea69165486b | checkpoint | Mechanical Second Fix complete
18496132-013c-46e6-9467-72c98ac71e5d | section | Commission:
672ead26-fe6e-4822-a420-72583c156f04 | checkpoint | Good access to all areas of building
ea5566d3-e3ae-4beb-936f-153c1ae51660 | checkpoint | Power live to Mechanical Plant
3579c4a0-e962-4e31-965b-320c787db890 | checkpoint | Mechanical Plant commissioned
ea711d37-9424-4214-bad5-76313303b5be | checklist | Jet Pulse Fan |  | Jet Pulse Fan
13ef82dd-798e-4b69-a534-557469c62633 | section | Pre-Start SA Fan
654ca13a-88ae-4e1a-afd8-5b55b9006d54 | checkpoint | Area clear, access good, enough space for install
a27fdf3e-9fd9-4b70-8d9a-61ebec2ce5c6 | checkpoint | Duct Route clear, Penetrations complete
962e909c-a85b-4b23-89dd-08ad136d2be9 | checkpoint | Nogs/Supports in place
ce67b652-a5df-40d0-aa6b-44265051db54 | section | First Fix SA Fan
70a69cb6-eaa2-4884-bca0-a447aad5d45f | checkpoint | Fan installed straight and level and correct orientation.
c8a1eeb1-2ee0-4ccc-98ba-be0bb3b61eea | checkpoint | Correct Fan installed
c14a7536-ecf0-4058-8aac-b514fab5a1b1 | checkpoint | Fan seismically braced and vibration isolated
22200eb9-a2c3-433a-93d6-fafb0260a5d5 | checklist | Kitch Ext |  | Kitch Ext
2db9b20a-fdf6-46df-868b-d92128707da1 | section | Pre-start:
1cbc54ce-62fc-4a14-98d9-ebcf2da571d7 | checkpoint | Area clear, access good, enough space for install
fa43d522-ad5c-4d2b-88d8-bdf5338b49d0 | checkpoint | Duct route clear, Penetrations complete
62def74d-3d08-4b51-a906-2ac18d72a876 | checkpoint | Nogs/Supports in place
6d2fe0cf-29bd-4f85-bf70-777530ca238c | section | First Fix:
5ae0c8a9-b12b-4ff5-81b8-c79cf088db18 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
c945f168-94fa-48c6-836e-9ffe2344cee6 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
e80126af-5f9f-45ef-98e6-4c7efa6f0aa6 | checkpoint | Mechanical First Fix complete
3263804d-1fad-4138-b8ac-d13544220b04 | section | Second Fix:
5c2b206d-8408-48e9-81f0-eb7dd1a176f1 | checkpoint | Area clear and access good for Second Fix
d08c95ff-3466-4278-8daa-87802a5157e5 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
e4b24919-b9ea-45df-831b-23308c3cee8f | checkpoint | Mechanical Second Fix complete
b6b03671-5ffa-4dae-84d6-7080079d6bbb | section | Commission:
1f4acbc7-d515-4953-af9f-623ac6a80616 | checkpoint | Good access to all areas of building
00fef09d-c30f-4d5e-b6a7-5891e4441579 | checkpoint | Power live to Mechanical Plant
5cd51d34-c9ca-42c8-93a8-9edb9d638f5a | checkpoint | Mechanical Plant commissioned
0bf1e89c-0c2c-4805-9feb-5ce333e2fe2c | checklist | PRE - S - First Fix - Air Conditioning |  | PRE - S - First Fix - Air Conditioning
b80b8b8c-00e3-4567-9581-4bdc4cfced98 | checkpoint | Complete length of pipework is insulated and acceptable
ecc4b35c-3754-4f55-b51a-35f11e025a4f | checkpoint | Drain installed and insulated
703f3add-a2c0-492e-ba82-eb2bdce2a228 | checkpoint | Supply cable installed correctly, protected and secured
6edc5a89-f470-4707-a83b-fc491d60778d | checkpoint | Outdoor wall brackets in place
aea5a391-6a64-4e3d-8b11-201f599c8909 | checkpoint | Interconnecting cables correctly installed and protected
dd58e550-dc53-4581-af8e-6f156adbe628 | checkpoint | Mechanical First Fix complete and acceptable and area clean and tidy for next trade
f67b7922-5df5-43e5-ae1b-ac8a671e7706 | checklist | PRE - S - First Fix - Ventilation |  | PRE - S - First Fix - Ventilation
ee2079ed-1584-4e26-9401-d653001d0145 | checkpoint | Ductwork run straight level and well supported
4b3e7dfe-558f-4a54-b285-5cc5c9947e66 | checkpoint | All ductwork joints sealed and acceptable
881173d2-3285-4b4c-b0b1-ab0aa12811d1 | checkpoint | All SAB joints sealed and taped and acceptable
0d645ded-6cdf-49af-855a-e78f5856ae8d | checkpoint | All flexible ducts cable tied and taped to duct and acceptable
e7915e73-0570-4620-9275-35773a373bf1 | checkpoint | All seismic restraints in place (if needed) and acceptable
0d44829b-b042-4ad7-a1a1-069f0ab5fb16 | checkpoint | Flexible ducts fixed in place to grille location and acceptable
8c16030f-4797-4b1e-819a-76acc3495b9e | checkpoint | Grille locations/access panels marked on plans and acceptable
e710736e-d3b1-4cab-80d5-28a88ea1c5d2 | checkpoint | Mechanical First Fix complete and acceptable and area clean and tidy for next trade
cd087dcc-13f7-412d-82bc-02c8e62ce6b9 | checklist | Pre-commencement checks |  | Pre-commencement checks
b9ba1e75-0615-4cc4-ae62-fb0c92edf6fc | checkpoint | Quality Management Plan Completed, Agreed & Attached
58fa83dd-00ec-4019-b4be-037373fb5406 | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
3646550b-9e48-49d5-82a7-59409f6c8622 | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
bd2b938e-d5ec-41d5-a4a0-4eff75d9b558 | checkpoint | Conqa Setup & Project Team Trained & Given Access
8942f9e2-3af3-4499-885d-0c9a01375fa9 | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
e7af5502-cca0-471b-ad47-91343c12f785 | checkpoint | Matrix/insights Setup (if required)
4b0a1dce-b058-43ce-b355-477bafd96728 | checklist | S - S - Air conditioning |  | S - S - Air conditioning
210d75c7-ac18-4615-91e2-ce7099c9a168 | section | Pre-start checks
753ea959-c398-44f9-9896-3dd5b9c6ef4d | checkpoint | Area/base/wall ready for outdoor unit
8e78b38d-afad-4c66-9c42-7748a9a41425 | checkpoint | Pipework route all clear, penetrations complete
ef6ee0ef-d842-4803-bf28-b5754ee9d418 | checkpoint | Nogs/ply in place for indoor unit
e3a02d92-07db-4c71-a029-472bac7a23b0 | checkpoint | Drain 1m from indoor unit location by plumber
df00bbb8-f8b2-4406-988c-a761ace68282 | section | First Fix
618149a8-2aa5-40ae-8d2f-f12eafcc384f | checkpoint | Complete length of pipework is insulated and acceptable
7113651a-6e7d-4996-8b01-8d73df1dd292 | checkpoint | Drain installed and insulated
12f0de73-e6f8-4807-8f01-9231d3d057a7 | checkpoint | Supply cable installed correctly, protected and secured
7097fa7d-0fe0-4dad-bda9-bbccc108bdf7 | checkpoint | Outdoor wall brackets in place
e42a9c51-a2d0-4709-af78-2b43e85a039f | checkpoint | Interconnecting cables correctly installed and protected
4e668a1e-94b7-4c42-898b-67e49ab3c766 | checkpoint | Mechanical First Fix complete and acceptable
582345ad-61bc-41a4-b9f9-aaf706c03f8c | section | Second Fix
b5db202a-f8f7-403e-baa4-bc53d80a5bdf | checkpoint | System pressure checked and still holding pressure and acceptable
fe0b3bf7-f85b-47ec-888c-eb0de9b30f47 | checkpoint | Correct Indoor unit installed, level and tight to wall and acceptable
2f6cd534-5e99-4bb0-9da2-065e94b3787a | checkpoint | Correct Outdoor unit installed and secure
a0928d6f-c7f9-4498-b54a-b7f801cadfbc | checkpoint | Indoor unit serial no. recorded
6b4617b7-75e0-462b-9a68-689af5dd7922 | checkpoint | Outdoor Unit serial no. recorded
8a9dec18-f861-477d-957e-69ac8a053569 | checkpoint | Indoor unit run, fan speeds, modes etc. are acceptable
16aece5f-1c39-4f15-971d-1cf6340e58c6 | checkpoint | Air conditioning Second Fix complete and acceptable
8abf0467-a202-4aba-b741-d59171de48d1 | section | Commissioning
a106c7fe-85eb-40d0-9b25-dd29bd7375d2 | checkpoint | Installer confirmed commissioned and paperwork submitted
5deccddd-61ba-4b53-9500-d0df09048501 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
320f880e-ebab-4554-bbf9-08aadca5c887 | checkpoint | Electrical testing complete
1bea1b04-921b-469f-8802-f22e75fb2151 | checkpoint | Commissioning complete and acceptable
6c0b5dfe-6f91-4f96-8e99-53e1b26f908c | checkpoint | Inspections completed and issued to Foreman
a4853d36-b291-4625-8db1-f7a4693dd3b6 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
c8bf5303-e5be-476d-83b1-83ff4c99756a | checklist | S - S - Kitch Extraction |  | S - S - Kitch Extraction
208e93b5-e46d-42ee-b4c5-db02bb935dc0 | section | Pre-start checks
d3016674-3005-49d4-a774-c6328dea21a5 | checkpoint | Area clear, access good, enough space for install
0f7d225b-48e4-4b3f-b682-b41e7b1f4438 | checkpoint | Duct Route clear, Penetrations completed
50477036-9055-4467-8d73-d4d8e907c37d | checkpoint | Nogs/Supports in place
15773736-ef47-4df4-8781-1c63b2744a02 | section | First Fix
1e3d4511-c03b-4d82-9b35-5a9e6f02011d | checkpoint | Fan installed straight and level and correct orientation
51a24782-307a-4801-8639-232134621038 | checkpoint | Correct Fan installed
fdc1892a-2140-4c1b-8c91-56cc167782f0 | checkpoint | Fan seismically braced and vibration isolated
f92aa0ab-b760-4ef0-b20b-ad5ec1d9542b | checkpoint | Inspections completed and issued to Foreman
608cbcfb-4ccf-44fa-b5f3-f4310934082c | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
43e02c1c-09e5-4516-a958-73f66518a982 | checklist | S - S - Ventilation - Apartment Ventilation |  | S - S - Ventilation - Apartment Ventilation
a392ed55-c87c-4b1b-88ed-7bfd0ecc2f09 | section | Pre-start checks
83f69601-72ed-49d6-b216-4d1364eaf4bf | checkpoint | Penetrations done in floors and walls (if needed)
422da4b2-d189-4654-b30f-41b6076a1cb6 | checkpoint | Space for ducting (no trades in the way)
7af0c282-e58a-400c-8e0a-c240687889c8 | checkpoint | Pipe through exterior wall installed by RHC to connect to
54625aaf-6401-4baf-b25a-92533365a036 | checkpoint | Drawings and work scope confirmed
95f816a1-8e8c-432b-b806-991d3a05bf6b | section | First Fix
1b6d2854-6324-4d6e-9c25-78d6b507eb65 | checkpoint | Ductwork run straight level and well supported
5b220393-53a6-4784-8992-978789cca4d9 | checkpoint | All ductwork joints sealed
01689334-6cb0-4a0a-885f-e29403dd97f0 | checkpoint | All SAB joints sealed and taped
976cb389-650a-4543-81ee-29218c2e17a9 | checkpoint | All flexible ducts cable tied and taped to duct
5a1893bd-a213-4dfc-8066-ed6ba533b7fc | checkpoint | Identify locations and correct model of Fire damper to be installed
29da6788-013a-48c6-b7be-4eb7b34b715f | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
dc5b8ead-6441-4285-8e7a-da0927462ff3 | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required postition
745ff41d-f8f6-41ca-916d-0121accec90e | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
fb7451f4-6b30-4fc6-8535-f892d7d98271 | checkpoint | Install using Materials specified in the PS1
8c256ca9-7ebc-48bf-b85f-8f6d32f1a4f8 | checkpoint | Upload Photos of Install
80430b23-3f6f-448b-87e3-f183a1ad2242 | checkpoint | All seismic restraints in place (if needed)
3f996e1b-6a87-4c6f-9e6f-ddc373898f97 | checkpoint | Flexible ducts fixed in place to grille location
20260f55-0183-4632-8af6-ac540216ced9 | checkpoint | Identify Fan Upgrade Requirement
5044235c-021a-49f7-b738-858a2d0d1e91 | checkpoint | Area Clear for Install of Ducting, Fan, and Control Box
a160274b-4b5d-417e-a56f-e7868e94a127 | checkpoint | Install Fan, ducting and control box as per spec.
835d2b47-71ee-4104-ae99-7371f92de055 | checkpoint | Grille locations/access panels marked on plans
ca4294cd-5e6d-45f0-a8b4-bf78acd1689e | checkpoint | Mechanical First Fix complete
c6adc303-db60-4aa5-b407-585580e48a0f | section | Second Fix
89f73a8a-8a50-4eb6-bb9a-0a6864fa85b0 | checkpoint | Ceiling fans installed square and level
f484265d-2b87-4448-bc4d-057699db3d8b | checkpoint | Kitchen range hood installed by RHC to connect to
f592a1cc-ae41-4bfa-929a-1496f742f25f | checkpoint | Fingerprints removed from grilles/walls/ceilings
9c61f6c0-f1f3-4c3c-9902-65b75f09725b | checkpoint | Fan plugged in before install to ceiling
423fbc61-27b4-43ae-b252-91f565f9ccff | checkpoint | External louver supplied by TSL, installed by RHC completed
34689023-a3d5-49bb-af4d-95afb0746879 | checkpoint | Commissioning form completed & given to TSL
3f70de9f-e9d9-41ba-92e7-8d580f4ac480 | checkpoint | Mechanical Second Fix complete
2b43b003-c9c9-4021-92cb-bd31b7f093b6 | section | Commissioning
cb1a6216-8324-4f4a-8696-6c968dd6bd04 | checkpoint | Correct product used as per requirements
311648dc-75c1-4801-b3ed-acd4bfd14043 | checkpoint | Correct design followed as per drawings
b69d613e-f04a-4e66-91df-290a2b0770c1 | checkpoint | Mechanical Plant commissioned
97355cb7-b10b-426e-879f-c41d3ae690ec | checkpoint | Inspections completed and issued to Foreman
842d6102-4ce3-4bed-b1e2-5f2ae3c1b18a | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
e426209f-c7d6-4eb4-81b7-673289462a49 | checklist | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan |  | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
aa3074a7-de94-4de5-b44e-de87dca43479 | section | Pre-start checks
a4560563-13ab-4dbf-b469-26740e97b9ca | checkpoint | Area clear, access good, enough space for install
34ba7038-2f8e-4eaf-be86-5a18e70fdc76 | checkpoint | Duct Route clear, Penetrations completed
44dba169-026d-47b8-b7a7-5c7d9f754b2c | checkpoint | Nogs/Supports in place
d06314bb-1e84-480c-8602-3b901c7c5cc5 | section | First Fix
d98185be-4acc-45c5-847c-dceda3c42c21 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
40d6e0ee-0733-4e10-9cc0-d0c8984bcc64 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations&)
fd518be5-04c9-4946-a4d9-fb01f0d1d348 | checkpoint | Mechanical First Fix complete
e5d4d242-5b67-4b69-b2de-f31adf0a5032 | section | Second Fix
eac87eb7-1521-4563-9323-12ce3005f6c3 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
6c2ce394-cdb3-4d7b-83f6-03f970d2981c | checkpoint | Mechanical Second Fix complete
bb47ca46-e332-424e-b018-c3616d2db612 | section | Commissioning
e6a14452-1895-44de-b449-e49910c620df | checkpoint | Good access to all areas of building
e3c1262c-5ae5-4b10-b907-e9ecad3ad949 | checkpoint | Power live to Mechanical Plant
a0cf9548-2098-41ad-bfaf-64e775ccb0f1 | checkpoint | Mechanical Plant commissioned
19d36296-5fa6-4dd4-980d-de229ca5a5d5 | checkpoint | Inspections completed and issued to Foreman
076230ce-3fb1-4d54-9af7-7e7965c9c673 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
cf35ad8d-2cca-4e45-a6b3-c23f19a31fef | checklist | S - S - Ventilation - Corridors Ventilation |  | S - S - Ventilation - Corridors Ventilation
753c49af-4816-4b92-b6ee-ca313f6f20f7 | section | Pre-start checks
1668d522-be63-470b-bb7c-cb59b284f7f6 | checkpoint | Area clear, access good, enough space for install
fd185ee2-992f-4199-95f7-48f0d8bef4a7 | checkpoint | Duct route clear, Penetrations complete
5f088bb3-53b0-41ba-a6ae-f1bd5aa8c27d | checkpoint | Nogs/Supports in place
49ac3196-92bf-45a6-9f6c-e19f038ee4aa | section | First Fix
4faf0487-edab-441a-a190-5aea18d5e441 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
8bd6aee5-5c9c-4d12-8a1b-28021920c3e2 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations&)
8ff6f1a2-90de-4161-aff4-097b8ef5528d | checkpoint | All flexible ducts cable tied and taped to duct
c15caffa-5fb4-4c1d-9a7e-578ab27e4a41 | checkpoint | Identify locations and correct model of Fire damper to be installed
1585494a-695a-4dd6-8aa0-3447c1c77c24 | checkpoint | Install to Manufacturers Specifications
90aa0ccf-1d81-4faa-b696-3c7fc43dc5ae | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
a8defa78-1bd7-4414-a504-6e86e3bb2413 | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required postition
832d8973-4c74-45a3-818b-454e5acb29d3 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
331245bf-0df4-4382-b0db-37c1997e5db8 | checkpoint | Install using Materials specified in the PS1
6a39bec8-8fed-41b2-aaf9-59e1761ef4c1 | checkpoint | Upload Photos of Install
1776a069-ea1e-4b74-b988-3f82ad874424 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
3027b3e8-9696-4815-a528-d5d78c94697e | checkpoint | Mechanical First Fix complete
6d780a8f-1895-40b6-b6e5-aa1079376148 | section | Second Fix
a10bf0a8-6d36-4124-8aa6-f0d1519d8803 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
28f92cb6-f4e9-4aa2-8b19-30905e413efc | checkpoint | Mechanical Second Fix complete
6b28ad85-dea4-4851-868e-13b6a0c56711 | section | Commissioning
240cc353-8ca5-4699-8d45-0dff68eaa367 | checkpoint | Mechanical Plant commissioned
16f8e454-ed5e-4e10-865c-929eeea5c943 | checkpoint | Inspections completed and issued to Foreman
27a68cbb-10ee-4f97-9ed8-30f004314544 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
ef697c85-d7ca-4adb-b376-67d34cb34d55 | checklist | SA Fan |  | SA Fan
3016b3f1-fd26-452b-b156-2b08a63401a4 | section | Pre-start:
87f0fcc0-e467-4227-8b29-b8f29fa3157a | checkpoint | Area clear, access good, enough space for install
96aa72fa-8d4e-45a5-b7f6-6ca44e12be38 | checkpoint | Duct route clear, Penetrations complete
76da37c2-bd55-48b9-a2ec-909caf84367c | checkpoint | Nogs/Supports in place
13ad43db-f07c-4450-b5f1-18695c6ee574 | section | First Fix:
9c562a75-8b65-42af-aa20-f9d1caf1b6d0 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
12141cde-e4fe-4414-8392-9ce1baed7b62 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
450b7cd8-06ce-4119-b677-250a3a0fb55a | checkpoint | Mechanical First Fix complete
20549bce-f110-4af7-b9fe-b928bd5a611f | section | Second Fix:
99528c7b-5644-411a-afdc-a57eae733654 | checkpoint | Area clear and access good for Second Fix
317cce1a-476b-4e63-96f9-5e558bd0127b | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
ed1af5cf-5375-470f-b4f4-541e799eea1f | checkpoint | Mechanical Second Fix complete
d06f1af5-da6a-45c9-b3f2-39adb8d21335 | section | Commission:
88d5bc0e-c59b-4258-983a-e949d2d61309 | checkpoint | Mechanical Plant commissioned
79f96284-8818-45a7-b1be-e49d014bfae6 | checklist | Split HW |  | Split HW
17926349-01cc-4540-9ff0-69e6a748644d | section | Pre-start:
62f66d30-c4cc-4e32-b5e5-3ce56bd46548 | checkpoint | Area clear, access good, enough space for install
13d89616-1ec0-4b1e-9266-75ea470ae131 | checkpoint | Area/base/wall ready for outdoor unit
5d12cfd1-5a94-4077-bafd-f6a0cba02e38 | checkpoint | Pipework route all clear, penetrations complete
79a2a823-7872-4526-bfa8-ab5acc244d20 | checkpoint | Nogs in place
585c101a-892b-4fd9-91c1-775ff95d4d66 | checkpoint | Drain 1m from Indoor unit location by plumber
539902a4-e89b-45a9-898a-4fae957229c0 | section | First Fix:
0b8b12f1-d21f-457f-a720-eaff8e6b73d3 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
883d85d4-c7ac-4c81-af4a-9ab30306874b | checkpoint | Mechanical First Fix complete
4aed454c-4ccd-48c3-9845-71c03e75ba02 | section | Second Fix:
fb6ad031-a7d8-42ea-b488-c8227fffa24f | checkpoint | Area clear and access good for Second Fix
9f320225-6d82-4bd9-a2e5-0ee3113fe259 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
0cb6fc73-3188-4100-bbed-72c1243cdcd7 | checkpoint | Mechanical Second Fix complete
30b63218-be0e-4be2-8f27-8fcd7b201864 | section | Commission:
4acd4b26-5987-46c9-b8d9-bed9848c4127 | checkpoint | Mechanical Plant commissioned
aab361e0-b9d0-49d8-93cc-fc6fb7337b89 | checklist | Ventilation |  | Ventilation
4e5d2d19-4ad7-4634-98a8-3d21becbd234 | section | Preinstall checks
b09bc95d-c2f6-425d-8759-1d2acabbc05b | checkpoint | Area accessible, clean and tidy
2cb9e568-156e-4f59-a5e4-d2bb628a7a02 | checkpoint | Penetrations done in floors and walls (if needed)
624266ac-bdee-4733-bf4f-dcc10bec3b3a | checkpoint | Space for ducting (no trades in the way)
b9b9fb0d-4534-47c7-a2df-64783939a450 | checkpoint | Pipe through exterior wall installed by RHC to connect to
96130a53-dc6c-4e01-877a-596673005b42 | checkpoint | Drawings and work scope confirmed
bf1b9f86-983c-4e35-927d-1bb823a65c4d | section | First Fix - Apartment Ventilation
0815da4a-934a-42d6-97c0-706164aaf2af | checkpoint | Ductwork run straight level and well supported
3353c35e-e0b4-49d7-afac-95fb9b8ba77a | checkpoint | All ductwork joints sealed
9cedb65b-1679-484c-b66d-895b826a5ae7 | checkpoint | All SAB joints sealed and taped
789070a9-8a97-428e-8c26-906b09af4a12 | checkpoint | All flexible ducts cable tied and taped to duct
d85e7179-bd26-494e-94a5-3a99bbd43169 | checkpoint | All seismic restraints in place (if needed)
bd42f1a3-1600-428a-9af3-61b7d0c66b9e | checkpoint | Flexible ducts fixed in place to grille location
1670c60d-28ed-451d-9560-46b5e96c86b8 | checkpoint | Grille locations/access panels marked on plans
d2dfa05a-a76e-42f2-9d16-9ed1df087605 | checkpoint | Mechanical First Fix complete
ad2cf5c5-e185-473b-8879-3de9a6e10b81 | section | Second Fix - Apartment Ventilation
9caf8999-b716-4664-a5aa-0446e96ffb70 | checkpoint | Ceiling fans installed square and level
73e5db31-984c-4518-8fda-c0bf4c4bbe18 | checkpoint | Kitchen range hood installed by RHC to connect to
232a9104-cb8c-49a4-ac19-4791c8f00394 | checkpoint | Fingerprints removed from grilles/walls/ceilings
339d0597-f1ad-40e8-97f0-cfdf5748ec19 | checkpoint | Fan plugged in before install to ceiling
eca03057-95a3-4f85-93bf-018567d35acf | checkpoint | External louver supplied by TSL, installed by RHC completed
1f0f1fc3-7726-4901-b1b3-7773028b0b51 | checkpoint | Commissioning form completed & given to TSL
16bd6e14-ba2c-4f6b-b6ae-3ffdab92338c | checkpoint | Mechanical Second Fix complete
90d8b28d-691b-405f-84fa-db03d0cca5fe | section | Post check & Commission
04329606-e02c-4ba0-84bc-f31f67a831c8 | checkpoint | Correct product used as per requirements
5fd13cd0-1295-4a78-8cff-ef5763a0c097 | checkpoint | Correct design followed as per drawings
e32b243d-972c-4110-9876-965a54679068 | checkpoint | Mechanical Plant commissioned
1e950f36-74bb-4676-9129-66c3e19a8a38 | signoff | Request sign off/remedial from RHC
13af1f3a-997d-435a-b924-ed896339d203 | checklist | VRV Bulkhead |  | VRV Bulkhead
538502c2-d518-4264-bd4e-0ade30c85fd4 | section | Pre-start:
2f3ab74f-db11-4d44-952d-64b09d5fa43d | checkpoint | Area clear, access good, enough space for install
bb2fe9d4-cc01-48c4-bd45-b0f11cf2746d | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
c22b6be0-e90a-4756-9fc0-cf81aeaaaf33 | checkpoint | Ply fixed to ceiling
e71fe86d-50c6-46e8-9442-3ecd593e9e08 | checkpoint | Bulkhead frame built
5c858e2d-e707-49c4-9f85-485f948000a0 | checkpoint | Grille openings framed out
140ecf0a-9aa3-4c5a-848a-413713498351 | checkpoint | Drain 1m from Indoor unit location by plumber
47f1db2e-677b-4fa6-870d-92811e307b76 | section | First Fix:
2a7a7657-7a7e-4e25-84bf-5c6db01b6931 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
e16a879f-62d1-42ff-9c6d-229108743790 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
9820a0aa-6d80-4469-a0b3-bdacebe83c5e | checkpoint | Mechanical First Fix complete
35359960-1089-4de8-a8b8-39e268faa168 | section | Second Fix:
ab703919-a0af-41bf-9a6a-fff5a87a6b1f | checkpoint | Area clear and access good for Second Fix
cfff1eac-5406-4023-93b9-23474541a54d | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
6105dbed-3332-4b06-aeed-35994750ab27 | checkpoint | Mechanical Second Fix complete
e533d10a-e37b-4979-87d8-3bf8870f8478 | checklist | VRV Cass |  | VRV Cass
c247870d-2eb9-490f-bf16-1143d6e6202d | section | Pre-start:
24f2fb4c-9e96-4c7f-aa5a-372e626fe3b5 | checkpoint | Area clear, access good, enough space for install
52e44925-603a-46e2-abbd-ef8b2f79d848 | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
cf443687-19dd-49ba-81b0-2687e6854a8b | section | First Fix:
686e094f-a7ef-4669-a068-07c6a84793f9 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
c1c57378-9500-4712-91bc-97b1e39f6c4c | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
b9bdcc83-3a65-4a7c-ba4b-d82c5078eb77 | checkpoint | Mechanical First Fix complete
0e196969-5c0e-42be-9516-2e70b0182580 | section | Second Fix:
0643f844-5ecf-4d5b-ad69-62e499bce52c | checkpoint | Area clear and access good for Second Fix
c2a65c14-e259-4721-b31a-a39930c554e2 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
9620d72c-45dd-4beb-a9e7-310974821911 | checkpoint | Mechanical Second Fix complete
f2532f17-de54-44d6-bc3e-f110bd5b51c3 | checklist | VRV HW |  | VRV HW
968cc2fb-82e7-4b19-a811-1722814f5459 | section | Pre-start:
c388687f-9ff8-492c-ac66-eadb18b09f28 | checkpoint | Area clear, access good, enough space for install
db124dc7-fc9c-428c-bcad-9ff8fa3894b3 | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
62d19ca9-9ecd-4e7a-96bc-0086fb3d7d6a | section | First Fix:
3473b7c2-d4ed-45bd-b1ab-729e84e1032e | checkpoint | Access Panel requirements marked up on drawings and submitted to client
5a2369c4-f354-46ed-9f74-d7765eafc2c2 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
87ccb11a-62bf-4a38-a9ed-7d9240702873 | checkpoint | Mechanical First Fix complete
013806b9-ffa9-4176-ab23-d9f9f61a13ba | section | Second Fix:
5e106cee-3c51-41d7-b766-0fe45dcd655a | checkpoint | Area clear and access good for Second Fix
49a945f5-8ca3-48f7-9e00-a6154316f671 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
cdf8c3c8-dd90-4e00-b23d-d1b2a6052fae | checkpoint | Mechanical Second Fix complete
a9c67181-aa8d-4c67-a400-1592db4d4b65 | checklist | VRV OU |  | VRV OU
ba0a00eb-08bd-475f-a7cf-28a0edd70f0a | section | Pre-start:
59d4d28b-1b71-48dd-b06e-9100768705bf | checkpoint | Area/base ready for outdoor unit
c340ab0e-45c5-4db7-8768-1eb5ef5c5c57 | checkpoint | Any required drains in place
bae92d50-ed3a-4259-86cb-d35634466898 | checkpoint | Outdoor unit area accessible
72d61da7-a03a-4ef3-8f4c-75b2633e99c4 | checkpoint | Pipework route from OU to BS box all clear, penetrations complete
6a34ac5d-4591-423a-9273-cc41ad35afd5 | checkpoint | Area clear for BS Box installation
b8550531-5fed-4d73-a47c-7289cf269bed | section | First Fix:
554bcfb8-6bf9-4814-b413-a0e6f7b50186 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
d63c5ab1-8b71-4388-a609-e8ad9294f022 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
0b35fff6-1802-4687-9bf1-598b38f2bc97 | checkpoint | Mechanical First Fix complete
90795f30-5b7d-4ef5-9ba9-2c8af34ef6fa | section | Commission:
da34ce7c-b15c-4715-8ba0-7a5b4e39950a | checkpoint | Good access to all areas of building
2a03e22d-b3e6-4000-91ae-33f8f9070d8b | checkpoint | Power live to Mechanical Plant
0566efc3-5f45-4804-8ae7-46b0557f2f8d | checkpoint | Mechanical Plant commissioned