## Master List Templates
Id | Type | Name | Values | Prompting Name
4f727a59-4299-4227-9052-e8b429dd1fd6 | checklist | Fire Dampers |  | Fire Dampers
3e7f85da-877b-4efa-b47b-efce9a349cce | section | Pre-Start Fire Damper
a125b3ab-1bd0-4c4d-8c71-2051fddc6705 | checkpoint | Area clear, access good, enough space for install
6ba5c600-debb-430a-a872-ca1c59e0c7a7 | checkpoint | Duct Route clear, Penetrations complete
79b55644-e611-4038-81bf-3c09f44b52a3 | section | First Fix Fire Damper
7eb77dd2-6432-4ae1-9810-c78af312c5e5 | checkpoint | Correct Fire Damper installed. (Insert Photo)
edb13b58-7d6c-4d0f-a300-f69795250fb9 | checkpoint | Fire Damper installed straight and level with correct orientation.
02e08761-75ee-43d2-9591-b920d72f825a | checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
d697b986-ba81-4a91-8993-ce055e73dfab | checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
cb49af99-b40d-4d66-97f2-46692fef3658 | checkpoint | Access Panels in duct for fire dampers.
28cba624-b158-4d97-8a03-bfa1a24e76d4 | checkpoint | Building Access Panel requirements are marked and given to builders
6a38b280-855c-4c00-8255-23a3f8cf5289 | checkpoint | Plans marked up for As Builts with Access Panel locations
d33ba6eb-28c8-4854-8b42-2940a154e9b8 | section | Second Fix Fire Damper
1d369191-28df-40f0-9afa-3521d492b676 | checkpoint | Fire Damper Label affixed, Asset Number applied.
99fcfadd-4ea2-45ef-b749-c0a4c1d2672b | checkpoint | Fire Dampers Access Panels still accessible for maintenance
5d2eb6ef-1c00-4070-a498-8e46333efb04 | checkpoint | Area left clean and tidy, finger prints removed
ae2acbc5-9afe-4989-8c9f-a1b92fad8b30 | checkpoint | Fire Damper sealed to structure both sides.
f68972b4-6d81-41aa-aa09-4be60adafed1 | section | Commission Fire Damper
35abf88d-b375-479f-8b77-924971281f8a | checkpoint | Drop Tested as applicable
3399aa37-48d7-492c-8a16-93ef940f0411 | checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
7be34150-c368-48a3-ba66-611937573253 | checkpoint | Fire Damper Label filled out, photo uploaded.
40670fb4-21e7-4227-bdb5-faa6329dd3e3 | checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
91a77d34-03fe-4f7c-b402-578d38b427d1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
83a2c736-5bcf-41d4-b04d-597cc6a59ec2 | checklist | Extract Fan |  | Extract Fan
a8c4774b-09ae-4354-8896-d8a0814c8e16 | section | Pre-Start Ext Fan
88888991-8cc5-42c3-aa93-0f6d3ccb170b | checkpoint | Area clear, access good, enough space for install
c541dd93-bc92-48d8-84b6-7053a1958edd | checkpoint | Duct Route clear, Penetrations complete
3c3b3bc1-0872-47b7-a4f7-667c202afcfe | checkpoint | Nogs/Supports in place
9815a347-68a4-40bf-8084-063442986bb3 | section | First Fix Ext Fan
7cd55a88-b47f-47aa-bc2e-8d2c49a7550a | checkpoint | Fan installed straight and level and correct orientation.
6ea5f55a-c8af-4aff-a063-543fa3c26859 | checkpoint | Fan or Cowl sealed to Upstand
f0cb4026-c3ff-4ce0-a329-11f840292592 | checkpoint | Correct Fan installed
a6f56793-9ace-43f2-ab50-81d28e849237 | checkpoint | Fan serial No. recorded
c6808fc7-120a-4cb7-bdf2-10ce4d11d5e0 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
506f7b6c-6825-4579-930c-132c9955c048 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
fbe10839-b7a4-4138-b647-0d5aa850d303 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
d98e49d5-8819-4d17-a719-4674d59a9f53 | checkpoint | Flexible ducts taped then cable tied
ef26f978-3717-4329-b2cf-d904220fe20b | checkpoint | Supply cable installed correctly, protected and secured
10146088-7cf4-49ba-8b21-53616b409095 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
402644b0-175c-40c1-9e54-4931518fd33b | section | Second Fix Ext Fan
878660d2-4824-4998-b3e4-8c8339fefa1a | checkpoint | Grilles installed square and level
5634465b-1258-45a3-80f9-1c5567b905c1 | checkpoint | Flexible ducts taped then cable tied to grilles/boots
926a9796-623c-432c-b430-d388db425fec | checkpoint | Boots sealed to grilles
9c969699-3aca-49d8-a2a5-b9db366666ef | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
c120d14b-edd2-447f-b4f3-7d28a4e3543a | checkpoint | Controllers fitted off
4244d066-e9dc-42be-82d9-54c421ca270e | checkpoint | Power fitted off
ce466093-868a-41f6-8af6-d9702fd7f667 | checkpoint | Area left clean and tidy, fingerprints removed
6e6cefd3-5574-4b31-9607-a865bd753f74 | checkpoint | Plant and controllers labelled
278a88b3-939a-4e80-91c2-2ff74c96d741 | section | Commission Ext Fan
c7ba05a2-a1c4-492c-826a-f1891aa70a84 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
7d1c8b05-716e-4160-878a-5cc06969dd27 | checkpoint | Electrical testing complete
ec12c8e0-785e-4911-98e3-c93ea0c62e45 | checkpoint | COC issued
58a6e9d4-c73c-4982-841a-d16d27e4f0d7 | checklist | SA Fan |  | SA Fan
a04544a2-e409-492a-97f2-4bf54f3d1a4f | section | Pre-Start SA Fan
bb4773c9-e80a-456c-b9de-2703d501793a | checkpoint | Area clear, access good, enough space for install
78c556ba-f4f6-4cdb-9596-d50cd604a303 | checkpoint | Duct Route clear, Penetrations complete
b149de93-387f-4d98-b5ae-0670d3ca1924 | checkpoint | Nogs/Supports in place
f2bf3cde-b1bc-4416-bf14-ec8ca62f871b | section | First Fix SA Fan
707aa56e-b014-4518-92f3-b41b10a82abe | checkpoint | Fan installed straight and level and correct orientation.
2950f314-ba75-4e4f-b6bf-8493a9ffc687 | checkpoint | Fan or Cowl sealed to Upstand
c17e3bed-fca0-4ea9-953f-01d9b155f211 | checkpoint | Correct Fan installed
dbcf8ebe-e65b-4c0a-bd67-1d853376702c | checkpoint | Fan serial No. recorded
28b06dd6-ca35-4ec0-8d2f-a356f68959ef | checkpoint | Fan seismically braced and vibration isolated
4732187f-7a27-419d-88ed-764438cfe631 | checkpoint | Heater Bank installed to Manufacturers instructions
7faa3000-a97b-43db-bd45-e9260359f666 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
315f2f4e-551c-4c17-84ab-a9c751dc55f1 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
8373444b-bafe-4ac7-97b6-f3b3103ed67a | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
227f5ba0-0658-4d08-8608-1488f1ed9755 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
333cbe4f-bc94-43c2-aa97-6f64d5cd9412 | checkpoint | Flexible ducts taped then cable tied
9e264f56-b4ab-49e2-a4e7-f3a89df93863 | checkpoint | Supply cable installed correctly, protected and secured
056cb6b8-8ff9-407a-89ae-5b52eb4e2d99 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
db94c4bd-7eae-4a3e-93c6-4622fb1bddf5 | section | Second Fix SA Fan
ef970161-192f-4715-b08f-a1dff144275a | checkpoint | Grilles installed square and level
212c1c97-c66c-48bd-a161-ce0d65ade961 | checkpoint | Flexible ducts taped then cable tied to grilles/boots
81c61323-38ba-4d6b-9b58-463bd8bc54f7 | checkpoint | Boots sealed to grilles
652c11b2-7364-4f39-a93d-3861bdb78fd9 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
0d792ebd-7871-4ed4-b201-802aa507964a | checkpoint | Controllers fitted off. Heater Bank THT set
072f77fd-e917-404b-b5c9-fe51fdccefd9 | checkpoint | Power fitted off
fe63487a-df5e-4fe1-844f-d978f2370ebe | checkpoint | Area left clean and tidy, fingerprints removed
1ae259de-720d-410c-bcd5-8a02ec5cf0f3 | checkpoint | Plant and controllers labelled
0b776f3b-8a27-41dd-bc0f-29771116fe14 | section | Commission SA Fan
3e4bfb57-a227-4ef6-b111-637652a37d66 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
0becadbf-c5cf-46d4-8985-4a5e9ab1d1ce | checkpoint | Electrical testing complete
91f136c6-9945-4aad-9c24-d5c89c504563 | checkpoint | COC issued
cba6a0c0-4233-42be-b0e6-0de7afaed323 | checklist | Split High Wall |  | Split High Wall
e9a73a4f-1ddb-4602-9df4-a687d901c19a | section | Pre-Start HW
9c5c8807-5f8f-45b1-b005-8d6679a51736 | checkpoint | Area clear, access good, enough space for install
1c68d6d9-a01d-420d-b296-e2b0c14e0a70 | checkpoint | Area/base ready for outdoor unit
a6acc92a-42ca-42c2-8fb7-9086908b731a | checkpoint | Any required drains for outdoor unit in place
ca0ffb83-2c75-4119-b9c6-ad6e9a23bd5e | checkpoint | Pipework route all clear, penetrations complete
61dc469f-1cfb-4741-9f2a-f5fe7cc3cdb1 | checkpoint | Nogs in place
b8c198a0-64b9-4cdd-a0de-6d63b43279b8 | checkpoint | Drain 1m from Indoor unit location by plumber
49b39358-cab9-400d-8274-0c6108eeedf9 | section | First Fix HW
2c620a3a-f6c0-4735-a84c-3704e96928f8 | checkpoint | Pipework Insulated complete length
9b7e2a5d-e94b-4f7f-903d-abcfdb79af4c | checkpoint | Drain installed
bb382459-ac7b-4de7-a089-ff1c10171f98 | checkpoint | Supply cable installed correctly, protected and secured
856e2a9e-305e-4bc9-922e-3a374242672f | checkpoint | Interconnecting cables correctly installed and protected
a5569b60-ae35-46ac-a029-b3ba42f5adaa | section | Second Fix HW
e17fd665-67ac-426c-bb09-5099ddcf0f79 | checkpoint | System pressure checked and still holding 1st fix pressure
b94e9cbf-7ee4-4f40-a81e-b843605cd144 | checkpoint | Indoor unit secure, level and tight to wall
76789dc1-4542-4779-a3e5-c92ca3eacbc8 | checkpoint | Correct Indoor unit installed
e93fd940-eeee-4b8d-b677-db7175f61cd1 | checkpoint | Outdoor unit secure and level
a33d7292-a192-4b25-8fbd-416e98983800 | checkpoint | Correct Outdoor unit installed
98a211fe-e82d-43a8-8ca9-d55d048c812e | checkpoint | Indoor unit serial no. recorded
9a8d479e-5b99-4861-b72a-1232c43f36a6 | checkpoint | Outdoor Unit serial no. recorded
c6b94585-aed5-4947-ab20-c4332a99235a | checkpoint | Area left clean and tidy, fingerprints removed
5a5be395-3835-471c-b63c-d9c2f9ec91e5 | section | Commission HW
9aac8883-1a8c-461c-926f-6c31dfbde4f7 | checkpoint | Installer confirmed commissioned and paperwork submitted
b9cf1950-ba7f-43da-aa1c-b446a6c4c177 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
9f07b2cb-e03a-4af5-bc5a-30fa33db656d | checkpoint | Electrical testing complete