## Master List Templates
Id | Type | Name | Values | Prompting Name
4f727a59-4299-4227-9052-e8b429dd1fd6 | checklist | Fire Dampers |  | Fire Dampers
3e7f85da-877b-4efa-b47b-efce9a349cce | section | Pre-Start Fire Damper
a125b3ab-1bd0-4c4d-8c71-2051fddc6705 | checkpoint | Area clear, access good, enough space for install
6ba5c600-debb-430a-a872-ca1c59e0c7a7 | checkpoint | Duct Route clear, Penetrations complete
79b55644-e611-4038-81bf-3c09f44b52a3 | section | First Fix Fire Damper
7eb77dd2-6432-4ae1-9810-c78af312c5e5 | checkpoint | Correct Fire Damper installed. (Insert Photo)
edb13b58-7d6c-4d0f-a300-f69795250fb9 | checkpoint | Fire Damper installed straight and level with correct orientation.
02e08761-75ee-43d2-9591-b920d72f825a | checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
d697b986-ba81-4a91-8993-ce055e73dfab | checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
cb49af99-b40d-4d66-97f2-46692fef3658 | checkpoint | Access Panels in duct for fire dampers.
28cba624-b158-4d97-8a03-bfa1a24e76d4 | checkpoint | Building Access Panel requirements are marked and given to builders
6a38b280-855c-4c00-8255-23a3f8cf5289 | checkpoint | Plans marked up for As Builts with Access Panel locations
d33ba6eb-28c8-4854-8b42-2940a154e9b8 | section | Second Fix Fire Damper
1d369191-28df-40f0-9afa-3521d492b676 | checkpoint | Fire Damper Label affixed, Asset Number applied.
99fcfadd-4ea2-45ef-b749-c0a4c1d2672b | checkpoint | Fire Dampers Access Panels still accessible for maintenance
5d2eb6ef-1c00-4070-a498-8e46333efb04 | checkpoint | Area left clean and tidy, finger prints removed
ae2acbc5-9afe-4989-8c9f-a1b92fad8b30 | checkpoint | Fire Damper sealed to structure both sides.
f68972b4-6d81-41aa-aa09-4be60adafed1 | section | Commission Fire Damper
35abf88d-b375-479f-8b77-924971281f8a | checkpoint | Drop Tested as applicable
3399aa37-48d7-492c-8a16-93ef940f0411 | checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
7be34150-c368-48a3-ba66-611937573253 | checkpoint | Fire Damper Label filled out, photo uploaded.
40670fb4-21e7-4227-bdb5-faa6329dd3e3 | checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
91a77d34-03fe-4f7c-b402-578d38b427d1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
fb8b3496-2b7b-4e98-87b4-9078543d640c | checklist | EXTRACT FAN |  | EXTRACT FAN
9111a8fb-8246-4c9e-821f-44f102c703e6 | section | Pre-Start Ext Fan
62bb7ed1-d9c6-4372-97d0-6bd3b360b8b9 | checkpoint | Area clear, access good, enough space for install
1d83fa15-894c-4d98-a7b9-3f067afdbeef | checkpoint | Duct Route clear, Penetrations complete
f29976eb-c82a-47f4-9601-b5bb3d4a1f17 | checkpoint | Nogs/Supports in place
eccc6999-307e-4170-8383-5680b5f21201 | section | First Fix Ext Fan
b4c04002-0b5b-4a46-993c-c668b55b3b33 | checkpoint | Fan installed straight and level and correct orientation.
f004a8f5-a234-4cd1-8f7e-73691b1f3960 | checkpoint | Fan or Cowl sealed to Upstand
06662af5-b94e-4e68-a830-44b35e2bbc2d | checkpoint | Correct Fan installed
ff0401e7-9659-4f24-b743-c34c51a028e1 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
9eef92d5-364f-4dab-b8b8-c30df46bddb2 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
0d697a4c-639c-4b43-952c-d7357e54d909 | checkpoint | Flexible ducts taped then cable tied
95eaf47f-1d96-46b6-9bbb-2e7678501a99 | checkpoint | Supply cable installed correctly, protected and secured
c45e7967-0f20-41a9-a4da-24f33e0f15e0 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
e07fd02b-0e40-4d64-a442-b5294d48a22e | section | Second Fix Ext Fan
1def4d3e-3240-4394-87ff-f6967c3007a2 | checkpoint | Grilles installed square and level
cd3b8fc0-1637-4edc-8c5b-93204474b2f6 | checkpoint | Flexible ducts taped then cable tied to grilles/boots
556f2b00-a8cd-40c4-a9cb-5e2d40d11fba | checkpoint | Boots sealed to grilles
763648e0-d61f-47fa-bfda-a9652b225966 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
7972c69d-186d-40c8-b013-f8a9b9f082a0 | checkpoint | Power fitted off
6a96f32e-d7ae-4377-b8cf-08c1ea4a7831 | checkpoint | Area left clean and tidy, fingerprints removed
252d7f95-9335-4b33-b80a-2251807ebe10 | checkpoint | Plant labelled
e9f745f7-5c29-4614-82af-4c57a3e84f77 | section | Commission Ext Fan
a486e676-9399-46ef-ae8d-531fd0d7aef1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
cd94f8ef-0db5-4b7e-bc88-67fcbefc33c6 | checkpoint | Electrical testing complete
78cb19de-dc57-4126-a46a-75de8be777ef | checkpoint | COC issued
05f85889-398b-4f80-af87-296779a5b11e | checklist | SA FAN |  | SA FAN
ef1d22b1-263b-43a2-8f36-3ff0ad72711a | section | Pre-Start SA Fan
9b2e574d-5511-44f3-80e9-09a84fa78526 | checkpoint | Area clear, access good, enough space for install
f5ea197d-65a8-4439-a7e2-9a3f0c04e2b5 | checkpoint | Duct Route clear, Penetrations complete
978b8857-2d27-466d-8b2a-c236ab83995a | checkpoint | Nogs/Supports in place
c1186cc0-7850-4706-932c-b179d2edafd2 | section | First Fix SA Fan
4e0c396e-a77c-46aa-8434-f78ca99879c4 | checkpoint | Fan installed straight and level and correct orientation.
19fa0d93-d85e-41c8-b17e-aee7a43be6d7 | checkpoint | Fan or Cowl sealed to Upstand
0677e831-ac52-49e6-b271-f84f7a421ecc | checkpoint | Correct Fan installed
4468500e-a776-427b-a316-aa7bb86bd704 | checkpoint | Fan serial No. recorded
71fa1f1e-55a6-4cf7-b963-a014359de6bd | checkpoint | Fan seismically braced and vibration isolated
389cec2f-85ff-4aee-b744-f5587f806d51 | checkpoint | Heater Bank installed to Manufacturers instructions
74c0d7f6-88a0-47e4-8dea-1f9d1cf126a2 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
fec4f9ef-710c-4e14-9edf-797eff4baa75 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
67a33cd7-d3ce-4cbd-a5cb-34072f9addb7 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
583e9822-48ad-4cbd-be7a-6bab1d31d004 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
86d08e1b-90af-4b27-917c-5902a4a36e2b | checkpoint | Flexible ducts taped then cable tied
87614433-fbae-4fee-827a-49d742c0c816 | checkpoint | Supply cable installed correctly, protected and secured
5743b429-3937-44dd-b0ff-52d40b56d932 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
09b1934f-fedb-4817-8a63-cc92234bdf11 | section | Second Fix SA Fan
716a3c89-ecb5-405e-b3ab-105751c08fe0 | checkpoint | Grilles installed square and level
c485c982-1e3c-4f1c-acbd-64738ba8099f | checkpoint | Flexible ducts taped then cable tied to grilles/boots
0eb50528-2d7b-4e36-b775-8caffc4468af | checkpoint | Boots sealed to grilles
631df4f4-ebe6-4b8e-9c95-7a4912438cab | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
37544e1b-0ead-443b-9277-b932dd856ee3 | checkpoint | Controllers fitted off. Heater Bank THT set
7b069f91-3b81-4b14-baba-49abe550bbe7 | checkpoint | Power fitted off
e779e79c-4e60-4cdb-a527-0b20ee68a09d | checkpoint | Area left clean and tidy, fingerprints removed
2e858a09-7530-4b94-828f-b5967fa1019c | checkpoint | Plant and controllers labelled
3d08c2e5-8756-4a54-927d-ce035be5d942 | section | Commission SA Fan
4f09889d-fb99-47b0-8073-7f75bbdaadf4 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
05b22a43-1331-47ee-bc51-185517abb023 | checkpoint | Electrical testing complete
4020c9f0-7c70-4220-ba88-f27cb55be3c1 | checkpoint | COC issued
a92bc2a1-2eb2-48ca-8447-4e19a7341686 | checklist | SPLIT HIGH WALL |  | SPLIT HIGH WALL
789f4de3-3a76-42fd-a1d4-0c7e33d76e50 | section | Pre-Start SHW
b4bc0f27-02fd-4698-837a-a68790de7bfa | checkpoint | Area clear, access good, enough space for install
6858c00c-9e6c-4576-b12b-f9b19c04475b | checkpoint | Area/base ready for outdoor unit
343dd2b9-d3f9-4a16-82c2-aa345d6e7073 | checkpoint | Any required drains for outdoor unit in place
070c324f-5833-4a3b-99d8-83765e43e7cd | checkpoint | Pipework route all clear, penetrations complete
e8bc791b-405f-40ff-a216-d160b6961764 | checkpoint | Nogs in place
e5b041aa-1d27-4519-a731-5b8797833142 | checkpoint | Drain 1m from Indoor unit location by plumber
70ee6988-911c-413f-bac0-bf6bd95af512 | section | First Fix SHW
b07cfe3f-8603-4eb9-be15-b80964227a4d | checkpoint | Pipework Insulated complete length
e171b2c3-faf6-4d77-a4a7-5368a303379c | checkpoint | Drain installed
f62283c4-afa7-44b4-b3cf-b94d0f174f52 | checkpoint | Supply cable installed correctly, protected and secured
f422977f-475b-4918-8b59-476143a21ff0 | checkpoint | Interconnecting cables correctly installed and protected
c44a6eb0-9780-46a1-8e4a-e3c32653a50f | section | Second Fix SHW
fc5913c5-d8e0-47b0-8fb6-59d79f56c29e | checkpoint | System pressure checked and still holding 1st fix pressure
76ac2099-52df-438c-a00c-5247b3d7b32a | checkpoint | Indoor unit secure, level and tight to wall
1776644c-7637-49d4-bb18-d57e44f9bd5d | checkpoint | Correct Indoor unit installed
05fdcc30-9a0c-4120-95f4-17578f2a8488 | checkpoint | Outdoor unit secure and level
65eaefb6-8f36-4543-b723-36c4c1a0d224 | checkpoint | Correct Outdoor unit installed
a532ff55-3a9f-498f-b90e-870473845ab6 | checkpoint | Indoor unit serial no. recorded
4037dfdb-2bda-4a1a-9510-839359e5c271 | checkpoint | Outdoor Unit serial no. recorded
255b0c1b-2191-4b5e-a0a7-2e2f1073cd29 | checkpoint | Area left clean and tidy, fingerprints removed
09e5c530-ad92-48ec-be77-de07117a7daf | checklist | VRV CASSETTE |  | VRV CASSETTE
43ca3406-9706-446f-8a2e-0f4e443094f1 | section | Pre-Start VRV Cass
a8631225-9b92-4474-b3d8-5bdc585fa744 | checkpoint | Area clear, access good, enough space for install
9215e9d4-f9a1-421d-a347-1ad2748d07af | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
542d4ac2-34e6-4ec7-a914-f83216d3f608 | section | First Fix VRV Cass
71933f3f-132d-4a89-922f-25137733f1ed | checkpoint | Pipework connected to BS Box and Indoor unit
1a52fc0e-56d5-4d17-b6b1-882b13fe3790 | checkpoint | Pipework Insulated complete length
b6956042-fe87-4370-834f-50b6885de703 | checkpoint | Pipework supported incl any seismic restraints
cc95e0f4-3d61-4ad1-b6b8-fcc6ca2003a9 | checkpoint | Indoor unit level, secure, vibration isolated and seismically restrained
23499976-843d-4a57-996d-63ecf3e87b95 | checkpoint | Correct Indoor unit installed
a1daa1d9-49d7-4500-82b1-1467c161b541 | checkpoint | Indoor unit serial no. recorded
8a8dfd53-5b98-40f8-b9d8-38df4cbbe432 | checkpoint | Drain 1m from Indoor unit location by plumber
dd028826-10e6-4b07-a181-ccd0584cfbac | checkpoint | Drain installed and insulated
0a8b52f1-3bfc-4648-acf7-4df826c26757 | checkpoint | Supply cable installed correctly, protected and secured
2b60914d-8fbb-4613-8753-0fe7a58f1bbd | checkpoint | Interconnecting cables correctly installed and protected
a3a378f8-5bc9-4c96-bd9e-0101724403d9 | checkpoint | Remote controller cable installed
575e5cea-b5a5-493e-a7c9-a69231132593 | checkpoint | Access Panel requirements are marked and given to builders
bda7e629-1410-41e2-a91a-55fbc1f24c0a | checkpoint | Plans marked up for As Builts
65306b3e-95fd-4a62-b657-5616e8b58ec6 | section | Second Fix VRV Cass
ba37633a-d331-4edb-b909-1267d48fb2a5 | checkpoint | Face plate installed flush and square
350bcd86-d66d-40e5-a00e-1864f47b6caf | checkpoint | Controller installed
ffa77276-9787-4587-a506-fa3c693fba01 | checkpoint | Area left clean and tidy, fingerprints removed
8693a94c-6fee-4215-897d-8e3235706740 | checkpoint | Plant and controller labelled
973724b9-3503-465b-8d40-97dff9416a98 | checklist | VRV HIGH WALL |  | VRV HIGH WALL
727ffa6a-26f2-4dee-9397-fc0503a2a5a4 | section | Pre-Start HW
eb73ac16-48ba-4abe-8755-d1a7f968d7a8 | checkpoint | Area clear, access good, enough space for install
9bd8b474-61cf-491c-a682-57fb22171e25 | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
01e85cbf-83ba-4d45-9a28-66e7fa393b05 | section | First Fix HW
6456d40f-d3c4-460b-803c-cf23ed515b71 | checkpoint | Pipework connected to BS Box and Indoor unit
419f445c-5343-4631-ab1f-9a2f552cf276 | checkpoint | Pipework Insulated complete length
ca51c5ca-b186-4dbc-9b88-840b7f0da6ea | checkpoint | Insulation Joins Glued and taped
22625a39-c2c5-4334-8ef3-3e083577331c | checkpoint | Pipework supported incl any seismic restraints
3333a95d-bf75-4fdf-8169-cb9aea35a51a | checkpoint | Drain 1m from Indoor unit location by plumber
ab2769cb-d6b5-408d-b69a-64f054d359e3 | checkpoint | Drain installed and insulated
b18ab79f-c0a0-4dc6-a891-5997ca187f5b | checkpoint | Supply cable installed correctly, protected and secured
2423b53a-5a66-46ba-9941-7cc259187868 | checkpoint | Interconnecting cables correctly installed and protected
355c07ce-de86-41a4-a4e9-7ae069635569 | checkpoint | Remote controller cable installed
2a4893fc-ec0e-4d49-ba5a-6acc23c55ee1 | section | Second Fix HW
82ef401d-9d53-4c43-8768-9e065a8d577a | checkpoint | Indoor unit secure, level and tight to wall
c5cc8a88-52f1-44cb-b18e-4569eb3c4b58 | checkpoint | Correct Indoor unit installed
2a50bc66-bebc-416e-b3e3-9bbcb794da63 | checkpoint | Indoor unit serial no. recorded
ac1ad7e5-4b84-4b2d-937b-3a6539136406 | checkpoint | Installer confirmed drain tested
a864147c-a326-4212-9447-6fc6d047e51a | checkpoint | Controller installed
a11e6474-3451-4061-9606-ff441061ab4c | checkpoint | Area left clean and tidy, fingerprints removed
b83e56f7-8c50-4fbd-81ac-539b6d09fd51 | checkpoint | Plant and controller labelled
8c83dec3-cb11-4935-8199-3d740ec23d8f | checkpoint | Access for future maintenance all clear. Filter can be easily removed
1d1a409b-0de3-4e4d-89d5-fb8a8df6a771 | checklist | VRV OUTDOOR UNIT |  | VRV OUTDOOR UNIT
264a076b-1aa8-4eb7-8c1b-dd4a32a32780 | section | Pre-Start VRV OU
dda73fd3-c94c-4a92-9505-2033c6698321 | checkpoint | Area/base ready for outdoor unit
cb357ada-0bd3-40ae-a4c5-9c50d5ea8b93 | checkpoint | Outdoor unit area accessible
9f985001-1fee-458a-bfb9-ae292471b5da | checkpoint | Pipework route from OU to BS box all clear, penetrations complete
a97ec165-cbc3-4cc1-8942-bce433c80b9f | checkpoint | Area clear for BS Box installation
45544d76-812a-4688-8c7e-6bf8f3cfa6a3 | section | First Fix VRV OU
8f4cff0d-1253-47c1-9585-a5745e19d6d7 | checkpoint | Outdoor unit brackets/feet/strut in place
c927dbed-2423-46e1-b931-ddf7a76cb5c5 | checkpoint | Unit level, secure, bolted down, seismically restrained
f364a25e-803d-44c3-8ec2-0112757c43dc | checkpoint | Correct outdoor unit installed
f4781d73-7eb4-4ff3-9cc2-0ab54d4edfbe | checkpoint | Clearance under unit for cleaning
60bc5eaf-aeb9-42cf-abd8-dba8495bf2e9 | checkpoint | Pipework connected from OU unit to BS box
fb96698b-f3e1-4d19-8452-fa531953a2bc | checkpoint | Pipework Insulated
3b37cdda-2948-4dc1-b3c1-59a28de834a0 | checkpoint | Insulation joins glued and taped
489e8704-3df0-46a0-8605-6846f2aa1f14 | checkpoint | Pipework supported incl any seismic restraints
e800c74f-187c-4038-b3bb-f7f16e224eaf | checkpoint | BS Box level, secure and seismically restrained
0b516356-b2be-479c-8c2d-6c6d8fc104e4 | checkpoint | Correct BS Box installed
be115e63-aace-4aa4-8789-d1c30fe17323 | checkpoint | BS Box serial no. recorded
1681a323-3cb5-473e-97e5-e8c2dfb93a07 | checkpoint | Drain 1m from BS Box location by plumber
0343660e-d2fe-4941-8198-b6de5df1b294 | checkpoint | Drain installed and insulated
e923201c-e905-403a-97e7-cd0e8d80a6f0 | checkpoint | Supply cable installed correctly, protected and secured
8dd8b489-0818-4d7d-8287-33cd3ccdfe84 | checkpoint | Interconnecting cables correctly installed and protected
342c7e68-076a-446c-b736-15ffaac5b5c9 | checkpoint | Remote controller cable installed
eab65455-28b0-42ff-9964-c641a101a5dd | checkpoint | Access Panel requirements are marked and given to builders
ca594dbb-e810-48ad-bc71-ffd267b80dd8 | checkpoint | Plans marked up for As Builts
7a81d04b-d00d-4000-90ed-8b17726db1d6 | section | Commission VRV OU
5cbbda93-c6b2-4d8d-8304-2fcce0fd9e3b | checkpoint | Access to OU unit is good
805a9f7d-30e9-45e1-8d24-26f483a3ea57 | checkpoint | Access to BS Box is good
c75d7743-0c43-4639-a033-7b6b6b9f7eac | checkpoint | Access to Indoor units is good
3e6f3518-f400-45c7-a918-43a10cc1dfaf | checkpoint | Commissioned by Daikin
d27c8549-fe7a-4c9f-b01e-39fe07116dee | checkpoint | OU model and serial number(write in comments and take photo)
01042fce-8c77-4608-8344-26af388549a7 | checkpoint | All plant labelled incl OU/BS/Indoors/Controllers/Pipework