## Master List Templates
Id | Type | Name | Values | Prompting Name
4f727a59-4299-4227-9052-e8b429dd1fd6 | checklist | Fire Dampers |  | Fire Dampers
3e7f85da-877b-4efa-b47b-efce9a349cce | section | Pre-Start Fire Damper
a125b3ab-1bd0-4c4d-8c71-2051fddc6705 | checkpoint | Area clear, access good, enough space for install
6ba5c600-debb-430a-a872-ca1c59e0c7a7 | checkpoint | Duct Route clear, Penetrations complete
79b55644-e611-4038-81bf-3c09f44b52a3 | section | First Fix Fire Damper
7eb77dd2-6432-4ae1-9810-c78af312c5e5 | checkpoint | Correct Fire Damper installed. (Insert Photo)
edb13b58-7d6c-4d0f-a300-f69795250fb9 | checkpoint | Fire Damper installed straight and level with correct orientation.
02e08761-75ee-43d2-9591-b920d72f825a | checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
d697b986-ba81-4a91-8993-ce055e73dfab | checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
cb49af99-b40d-4d66-97f2-46692fef3658 | checkpoint | Access Panels in duct for fire dampers.
28cba624-b158-4d97-8a03-bfa1a24e76d4 | checkpoint | Building Access Panel requirements are marked and given to builders
6a38b280-855c-4c00-8255-23a3f8cf5289 | checkpoint | Plans marked up for As Builts with Access Panel locations
d33ba6eb-28c8-4854-8b42-2940a154e9b8 | section | Second Fix Fire Damper
1d369191-28df-40f0-9afa-3521d492b676 | checkpoint | Fire Damper Label affixed, Asset Number applied.
99fcfadd-4ea2-45ef-b749-c0a4c1d2672b | checkpoint | Fire Dampers Access Panels still accessible for maintenance
5d2eb6ef-1c00-4070-a498-8e46333efb04 | checkpoint | Area left clean and tidy, finger prints removed
ae2acbc5-9afe-4989-8c9f-a1b92fad8b30 | checkpoint | Fire Damper sealed to structure both sides.
f68972b4-6d81-41aa-aa09-4be60adafed1 | section | Commission Fire Damper
35abf88d-b375-479f-8b77-924971281f8a | checkpoint | Drop Tested as applicable
3399aa37-48d7-492c-8a16-93ef940f0411 | checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
7be34150-c368-48a3-ba66-611937573253 | checkpoint | Fire Damper Label filled out, photo uploaded.
40670fb4-21e7-4227-bdb5-faa6329dd3e3 | checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
91a77d34-03fe-4f7c-b402-578d38b427d1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
129fc4fa-7d45-4d1d-a4a7-e5653d60a988 | checklist | B01 - AHU |  | AHU
f94fa9e4-f372-4c30-b1eb-2d8435f77986 | section | Pre-Start
e07a8567-a5d6-428e-8966-c0da744895ce | checkpoint | Area clear, access good, enough space for install
ff49fc13-aeeb-4af0-8f0b-c355c64cd148 | checkpoint | Duct Route clear, Penetrations complete
87498c6f-95ab-4bf4-b446-efd36dd8f462 | checkpoint | Nogs/Supports in place
a6b27bda-b816-4a29-bc3c-db1f86945cbf | section | First Fix
6eb8b836-2454-4185-8cb5-f1d7b210ff4c | checkpoint | AHU installed straight and level and correct orientation.
c1c5db7c-c1d4-46d9-ad59-d2effd572e22 | checkpoint | Cowl sealed to Upstand
cf9bf589-9026-4e03-9fe8-345db6896ce0 | checkpoint | Correct AHU installed. (Insert Photo)
58496346-9b40-4a02-8568-b9f8cfab00d9 | checkpoint | Filter installed and easily accessible
48b52699-c084-4c9d-9b4a-4cf7e3af8781 | checkpoint | AHU seismically braced and vibration isolated
15f4da3a-a85a-4438-8525-10b3db1c869f | checkpoint | Heater Bank installed to Manufacturer's instructions
89110aeb-5df2-43f3-b4e7-c3f859bc62af | checkpoint | Fire dampers installed to Manufacturer's instructions. Drop tested where applicable
a0d2898d-f223-4d2d-8943-08b8369cd4f4 | checkpoint | Breakaway joins either side of fire dampers
d8d416d2-8ec9-4825-9d24-93b00b86f2e0 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
2853c7b0-c4c4-4ddb-aaeb-fef3432b75ee | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
6cccee04-9bb0-4ec7-a622-1b4981660df3 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
a0b78e8a-224c-4d7a-8d7e-8a7d800bc573 | checkpoint | Balancing Dampers locked open and accessible
1d30a5b6-6dab-4f8b-aabc-217e6f426ac0 | checkpoint | Flexible ducts taped then cable tied
5e7e3ff1-46d1-4505-93a2-787e8e263815 | checkpoint | Second fix grille and access panel locations recorded
98124075-0779-47db-b662-d5c0f32ca4e4 | checkpoint | All open ducts sealed off with plastic film or similar
0d37e69a-cebd-4151-a0de-dc44b8e1562a | checkpoint | Control Cables installed
9ad3b572-0f90-4aa8-9b29-4757599f1f21 | checkpoint | Power Cables installed
23b670f6-86f9-4e30-8ec0-10a6b10f359b | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
382a6ff9-c1bd-424f-8d1d-fedf87da6a85 | section | Second Fix
e8a77dc3-9739-4b8f-ae54-333e0720ce45 | checkpoint | Grilles installed square and level
ac271563-0ed5-459e-992b-3238c4cbb93c | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
363ba469-0b32-4e82-8a2a-787c76781dd5 | checkpoint | Area left clean and tidy, fingerprints removed
b589dad2-8f5c-49c4-9f2a-59e6b00ae1c0 | checkpoint | Controllers fitted off
0e92f8bf-895c-4967-a933-c7d582623be0 | checkpoint | Power fitted off
e27365ec-c54a-4c3d-b939-b1d08796ea9c | checkpoint | Plant and controllers labelled
469b1a60-d630-4d98-b1fe-13cb085ff6f1 | section | Commission
9748f0df-2223-42dd-af08-5081a593ad86 | checkpoint | Commissioned and Paperwork submitted
fd625f39-8bb8-4094-8c0f-a0e5ff40bb9b | checkpoint | COC issued
5d8f0cdd-cf03-4aee-a269-fca2fec32fcd | checklist | B01 - Ceiling Fan |  | Ceiling Fan
ee86de68-ecac-4535-a334-b585567543cc | section | Pre-Start
64fe8425-ba0e-4139-b3a5-2e64d3c2200b | checkpoint | Area clear, access good, enough space for install
0bc395bf-bda5-41a9-8d7a-bbd36df01bb7 | checkpoint | Duct Route clear, Penetrations complete
a38a654a-37bd-4c71-a95a-56fe0dfed15a | checkpoint | Nogs/Supports in place
276041b7-b220-4944-befd-fa226a7f75e4 | section | First Fix
4c059091-63df-4246-97de-02e94964fafe | checkpoint | Fan installed straight and level and correct orientation.
db7f5aec-b72e-474b-b0dd-0bab696993a3 | checkpoint | Fan or Cowl sealed to Upstand
73357582-1932-4666-bfe7-81df0212b874 | checkpoint | Correct Fan installed. (Insert Photo)
b67b54c2-8dbb-4cb3-83de-c7d4e34e1d5a | checkpoint | Fan seismically braced and vibration isolated
c958bcdf-3e31-403f-96ef-3ab6fd943910 | checkpoint | Fire dampers installed to Manufacturer's instructions. Drop tested where applicable
10452f8b-a857-4e00-847f-b4f6e4e37a83 | checkpoint | Breakaway joins either side of fire dampers
1834975e-0527-42d5-b704-102294720db6 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
12d52b66-9573-4356-b376-d56db95f6a33 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
e43d4f82-c363-4437-a2ad-40f63a1bec15 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
26c224ea-ae9b-4e06-baed-49bfaaf86d77 | checkpoint | Balancing Dampers locked open and accessible
06032bbd-b883-4164-9144-1db73fc25fd5 | checkpoint | Flexible ducts taped then cable tied
abd12903-2285-42ed-a8b2-7f7c16260693 | checkpoint | Second fix grille and access panel locations recorded
3753e0b1-2b4e-4876-b108-e1aa282ea7e3 | checkpoint | All open ducts sealed off with plastic film or similar
0f73fdba-d0cf-4f64-8e9a-e50139d8a18d | checkpoint | Control Cables installed
5cd00eee-c173-4726-b5a3-900522e7dead | checkpoint | Power Cables installed
2684414a-7c7d-4f5c-adbb-2962d91b6554 | section | Second Fix
93495668-3b6a-4c1e-a5d8-f367b2934ee0 | checkpoint | Grilles installed square and level
e20b526f-1a33-432d-8418-c46ff5c02be1 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
b2e3131f-26e8-4f4d-83d3-c1c308aaa7f8 | checkpoint | Area left clean and tidy, fingerprints removed
ba41f769-9ad1-4530-8cdc-d96a0ecf4fb2 | checkpoint | Controllers fitted off
07d48ec0-da2a-4707-9d88-483f272d51f1 | checkpoint | Power fitted off
aee78316-6e57-46e9-b8f3-ee02b38e7aaf | checkpoint | Plant and controllers labelled
93ef621f-d922-438a-9b99-a6ec1a83a0bc | section | Commission
5c9a4d46-759d-47c8-87e2-fef4593681be | checkpoint | Commissioned and Paperwork submitted
9f693135-acea-4b5c-9839-93973badf572 | checkpoint | COC issued
2f7b0918-5876-464a-b18e-daa9f64b2e29 | checkpoint | Plant and controller labelled
0e15fe58-1451-4f3d-9596-fd37bfc023ca | checklist | B01 - Coolroom |  | Coolroom
b0285f22-f40b-46e4-a39d-6c45468740a2 | section | Pre-Start
5d72f115-46b6-4a2c-a22c-3ccaa0d0d36d | checkpoint | Area clear, access good, enough space for install
fae71f5d-ee6e-4670-a98e-6a42c87364cd | checkpoint | Area/base ready for outdoor unit
ff419f1a-7f12-4a01-8af8-0ca87f725cb9 | checkpoint | Area/Base/Walls ready for Coolroom Panels. Floor requirements met.
a598f31e-2c86-47be-a6e9-9d61b8d929f2 | checkpoint | Check set down for any rough surfaces (Smooth set down required).
5166ad24-1c13-4046-9092-e1681b1db2b1 | checkpoint | Pipework route all clear, penetrations complete
9da07313-ea8b-447d-89ba-b7506a7ec059 | checkpoint | Nogs in place
220b5496-c84a-481a-9c12-08dc2c5698f9 | checkpoint | Drain in place by plumber
07593d90-1fa0-4706-ba60-a7a3008b5f1a | checkpoint | Measure set down and mark out door cut out
94280b1d-2fe9-42ce-9af2-383688582700 | checkpoint | Check if set down is dry and area is water tight
c6482681-9039-44ad-83d6-1d8ad775bd97 | section | First Fix
c3aa9c2f-0b6d-4d7a-8bd9-eaf5493ff4a6 | checkpoint | Panels installed square, level, tidy. No sharp edges
4e45597e-a918-4e29-9d92-d24e43f59e76 | checkpoint | Vapour sealed
b5851cb4-ea72-4368-9ce7-191f953308cf | checkpoint | Evaporator hung straight and level
869d36a8-31b9-4c2c-9e52-201faabd0cb4 | checkpoint | Correct Indoor unit installed. (Insert Photo)
d1c4e6f6-54ec-4f32-8769-26e6a695a98d | checkpoint | All Panel Penetrations well sealed
2b23f07f-3f3d-4f93-9ce9-28c9cba721c5 | checkpoint | Pipework Insulated complete length, glued and taped
5addc0ab-304a-4c10-9812-62d720932f35 | checkpoint | Pipework supported incl any seismic restraints
0e4fc5af-ab68-4555-822a-8653ba5a15e0 | checkpoint | Drain installed and insulated
d9d51efb-7258-4b65-9d08-71e1263380b3 | checkpoint | Pipe lengths are recorded accurately. INSERT PIPE LENGTH (IN NOTES):
44d8f0bf-7766-436b-9192-26ae0f42ac37 | checkpoint | Plans marked up for As Builts
fc79adde-8c9b-489b-affc-65d17c0e381d | section | Second Fix
f878ccb8-5c6d-4b74-86af-088ca389ea72 | checkpoint | Outdoor unit secure and level
78f6ab33-c483-476e-b604-3af3d1965682 | checkpoint | Correct Outdoor unit installed. (Insert Photo)
0243822d-3943-4078-8e9d-02a2236db43d | checkpoint | Drain tested
571153c9-13f5-4a09-a68f-c5af024efbb2 | checkpoint | Access for future maintenance all clear
a0674259-8dad-4aea-9e47-5535d1035611 | checkpoint | Area left clean and tidy, fingerprints removed
f71c2bcf-d050-4c2b-9431-497d07eb912a | checkpoint | Controllers fitted off
259067e7-fde9-4ff8-8987-86506dd9457b | checkpoint | Power fitted off
35993f2d-3222-4ba3-969d-9f8ab6b2611c | section | Commission
c0db0c0e-364a-40e3-9788-b6c9d41f26d9 | checkpoint | Commissioned and paperwork submitted
e736b9dc-f9c0-4628-ab63-c886ebf833c8 | checkpoint | COC issued
5d48b975-c127-4d8b-b6c7-ee3004ca8641 | checkpoint | Plant and controller labelled
5e2f77a2-f773-4907-9536-0c8d5c0bdd8d | checkpoint | Plant and controller labelled
a9731a7d-95f6-4be2-80cf-e276d4b2b5da | checklist | B01 - Ext Fan |  | Ext Fan
2299f4fe-f93d-4647-9522-58d5e47b6783 | section | Pre-Start
1ad12ab4-b7b6-4f0b-b64f-9fd134bcd472 | checkpoint | Area clear, access good, enough space for install
786ceab0-1517-4742-ac84-ffc8a6502b26 | checkpoint | Duct Route clear, Penetrations complete
e0145ad8-9172-46cd-8695-7e030a017412 | checkpoint | Nogs/Supports in place
c81716ed-05e3-455b-a871-fcf23ab02581 | section | First Fix
d7894121-1167-465b-9cbc-5c97c54dc477 | checkpoint | Fire dampers installed to Manufacturer's instructions. Drop tested where applicable
f6527a02-a2ad-486f-b410-c955ce990ec2 | checkpoint | Breakaway joins either side of fire dampers
5ee750bb-2d6c-4c62-b9cf-41f465644df6 | checkpoint | Access Panels in duct for fire dampers
7226b36b-d9a6-4092-814e-fdc5abacd1de | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
b110e81c-e425-4a75-9b4b-19c8361187f7 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
9eda8cf5-51ed-4a20-bce3-2fa7aecc700d | checkpoint | Flexible ducts taped then cable tied
caf35278-ae0e-48bf-bd20-bf14e1205c56 | checkpoint | Second fix fan locations recorded
04173ecc-6515-46f4-ac6c-262446a66f10 | checkpoint | All open ducts sealed off with plastic film or similar
6a7e7f3f-43c3-4758-ac83-fac9ab89ea74 | checkpoint | Power Cables installed
32e630fc-c781-4b11-916f-ca1eca031403 | section | Second Fix
0cf80475-adbd-403a-929e-8c61e7c86556 | checkpoint | Fan installed square and level
51cf34c5-dc26-4019-af72-d80da9e0ebda | checkpoint | Area left clean and tidy, fingerprints removed
4ca22e3c-bdb5-4d7d-9335-0143a9c042ed | checkpoint | Power fitted off
1e0b1727-b356-4546-a8c4-6e1ad06be23a | section | Commission
b3aa3576-7f1b-4f38-950c-cb3c18c5d59e | checkpoint | Commissioned and Paperwork submitted
d7f931ac-6e21-4024-affb-980da4b99e85 | checkpoint | COC issued
fcd3d23d-d260-4f34-894d-4017fa1e1855 | checklist | B01 - HRV |  | HRV
6ef3498f-8ecd-4ef8-afa5-09c27600e574 | section | Pre-Start
7a84841f-818f-4585-9abf-960f317442ac | checkpoint | Area clear, access good, enough space for install
2bbf8efb-0de9-4227-9527-c747ec4da22f | checkpoint | Duct Route clear, Penetrations complete
f71d0345-2886-456f-8d81-43b242ff4c3c | checkpoint | Nogs/Supports in place
ee8253d0-6268-4b0f-8917-9fe779506502 | section | First Fix
af2d742f-edcd-4bf5-ae55-216f1be1cfa1 | checkpoint | HRV installed straight and level and correct orientation.
164f3bd2-3ce5-459d-a1fc-47c6be7dcfbb | checkpoint | Cowl sealed to Upstand
4638d9fa-44d5-4afe-ba7c-834ed6becde1 | checkpoint | Correct HRV installed. (Insert Photo)
71537f8c-0670-43c4-af46-9bbf1ff15c3f | checkpoint | Filter installed and easily accessible
f6cb8f83-93b3-4999-b99a-139be4933da4 | checkpoint | HRV seismically braced and vibration isolated
14385388-e36f-4f2b-8796-764c34bc0607 | checkpoint | Heater Bank installed to Manufacturer's instructions
7fdbf90d-6f4b-401c-9eaf-f0c67a122ea5 | checkpoint | Fire dampers installed to Manufacturer's instructions. Drop tested where applicable
781f5c6c-b1e8-463e-a1c6-d883e4d103ab | checkpoint | Breakaway joins either side of fire dampers
ef6b89dc-f7e0-4399-b482-f13d4e20679f | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
c4e28623-63e2-453e-bfc9-baf506a7eb9b | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
7d4894c3-5ea4-4fd3-8240-1cf4a981f667 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
9f43cae2-2061-438e-bf4d-515b29a72e3d | checkpoint | Balancing Dampers locked open and accessible
d1f44fd5-36d4-494e-a1ca-cd6d3e898ddd | checkpoint | Flexible ducts taped then cable tied
1ac38c52-9e2d-47b9-bfce-cae8050ec975 | checkpoint | Second fix grille and access panel locations recorded
700d8e0f-5914-4fba-843b-b77a332e3b6c | checkpoint | All open ducts sealed off with plastic film or similar
ac4e5b23-975e-4608-9b64-fd2520a0ccb5 | checkpoint | Control Cables installed
8efd16d0-e336-4c0b-88fa-e5e2d973ac14 | checkpoint | Power Cables installed
64357936-9d87-441f-af52-9a722ee37969 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
3e072cae-312c-4db4-8e68-8e93ba7cb985 | section | Second Fix
e76f7c53-e4ea-41d4-943f-ead35bfed50d | checkpoint | Grilles installed square and level
444df4df-c3d7-445f-9b65-415ba266be10 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
159d501f-a4d7-4741-9476-7cad8382e94a | checkpoint | Area left clean and tidy, fingerprints removed
389bfd0f-93e1-4e85-8d4e-c98417e18f29 | checkpoint | Controllers fitted off
c397e5e0-6417-4969-8081-2af203299603 | checkpoint | Power fitted off
5047a1c3-b38d-4c62-852c-6ceee976610a | checkpoint | Plant and controllers labelled
5c88a672-5b1f-4db2-a528-3f08fc83b37b | section | Commission
ecea2f3f-81c8-439b-868d-8afce43cefa9 | checkpoint | Commissioned and Paperwork submitted
7bc2c221-5109-44ee-adef-e424044a4021 | checkpoint | COC issued
03a5895f-46d9-446e-aae7-3fc0950deab8 | checklist | B01 - Kitch Ext |  | Kitch Ext
f7d9b354-258c-4d1a-84af-131b7b76ab5b | section | Pre-Start
742a0fd6-5f0e-47b3-86dd-eacb016a23a2 | checkpoint | Area clear, access good, enough space for install
7d5fba97-348f-421d-8eab-a15d0c35a065 | checkpoint | Duct Route clear, Penetrations complete
6c6f3d30-daf7-4e3a-8af4-104ef143c5ea | checkpoint | Nogs/Supports in place
8116a56f-4649-4b62-b332-611355f3a8d9 | section | First Fix
ec4cb837-83af-4588-a0ae-91e4ae255390 | checkpoint | Fan installed straight and level and correct orientation.
45407f22-dd37-40b9-a549-18ca607f23b5 | checkpoint | Fan or Cowl sealed to Upstand
b0199b6a-48dc-43ba-bfd4-8f228fd9aa27 | checkpoint | Correct Fan installed. (Insert Photo)
8c1f6ac2-bfb8-4a8a-bbbf-74755c892260 | checkpoint | Fan seismically braced and vibration isolated
efec58b3-988a-49db-8de8-90da0013e2ac | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
9c9568f2-c000-4cfc-b812-f912eabc83b2 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
5b69f30f-eee5-4b64-9d8b-49310072b362 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
69f26612-a206-4dd0-83fc-2c7a6c5f8a18 | checkpoint | Second fix grille and access panel locations recorded
607a05cc-458f-4432-b6f1-765d0bb39057 | checkpoint | All open ducts sealed off with plastic film or similar
dae2403c-8943-4a87-bdbe-a63e3e7eb468 | checkpoint | Control Cables installed
89c12f74-b7f6-4db0-924d-e491c3833767 | checkpoint | Power Cables installed
5a67916e-ab67-47c0-aef3-a7ab52746827 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
1ed8de8c-348c-4406-8aca-14939b41cba6 | section | Second Fix
62d4ad93-ce45-4f4e-a2e3-6811beb28dfb | checkpoint | Hoods and Grilles installed square and level
a605f04d-5777-401d-bc7a-d6bfe96a528f | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
6aa73fec-234b-42c0-ba74-4d4c8408da3e | checkpoint | Area left clean and tidy, fingerprints removed
d9b08c2f-a655-4eec-a6bf-66c6e25c787c | checkpoint | Controllers fitted off
fd8deb79-6808-4b31-be10-003f4b36bc14 | checkpoint | Power fitted off
83de2038-43e6-4b83-b65b-3f8a7de0b7f9 | checkpoint | Plant and controllers labelled
358e7c97-cc37-424f-ac30-e91ecabec4dd | section | Commission
7339a94f-6797-4efc-bf10-da78dd16cdaf | checkpoint | Commissioned and Paperwork submitted
fcd480bf-8d05-48d2-8b05-917810c3edae | checkpoint | COC issued
d171ed14-0dee-4ff1-a5d3-136b64f8f89f | checkpoint | Plant and controller labelled
1f944c27-e493-4495-bea0-5eda27f81d93 | checklist | B01 - SA Fan |  | SA Fan
26b99c01-4586-4c85-b104-9ed704128c00 | section | Pre-Start
bb6960a9-5b3c-45e5-8ea6-c167d083426f | checkpoint | Area clear, access good, enough space for install
772ef44c-8b92-4fbc-9a88-aeabdd3e1587 | checkpoint | Duct Route clear, Penetrations complete
6e0aafd1-32d6-4a49-992f-c2561a5c5e0a | checkpoint | Nogs/Supports in place
a8647702-f2ed-4d8d-abd1-b4303c4f595a | section | First Fix
e1ba0c8e-9312-4fc1-9fbb-9fc2f8684675 | checkpoint | Fan installed straight and level and correct orientation.
bc50405a-3594-401e-8b50-d61ff19faa53 | checkpoint | Fan or Cowl sealed to Upstand
ff27315b-8ed1-4e7c-8d65-350e588cfff1 | checkpoint | Correct Fan installed. (Insert Photo)
17d89d59-1a8c-4796-bfe9-e35fdebe9051 | checkpoint | Correct Heater Bank Installed. (Insert Photo)
c687f5fd-7eec-4ae8-82ea-376212578860 | checkpoint | Fan seismically braced and vibration isolated
b156eaca-bc1d-42a0-924f-f0086b67c7f4 | checkpoint | Fire dampers installed to Manufacturer's instructions. Drop tested where applicable
a952ddfd-0304-47e2-85f1-7032c474f644 | checkpoint | Breakaway joins either side of fire dampers
45769f95-6760-4ea9-bc5b-179dd4059615 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
ab47f27e-3d3d-4a66-866f-38df1a9d48d8 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
19510267-9a50-406c-95bf-275f906abb89 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
9fdc713a-6d8b-4c1a-8b44-da70e621e490 | checkpoint | Balancing Dampers locked open and accessible
9277ca31-eb2e-4606-9ac4-f57061280b58 | checkpoint | Flexible ducts taped then cable tied
6021ee8c-3a1e-44a6-b29b-d07ded6f2622 | checkpoint | Second fix grille and access panel locations recorded
96f3f409-60f3-4c93-843b-be6431f7198c | checkpoint | All open ducts sealed off with plastic film or similar
3321d53c-e32c-460e-aea6-2bd0117328ff | checkpoint | Control Cables installed
4c650a41-f87a-45b1-893a-d11c3c26de6f | checkpoint | Power Cables installed
69849427-a38f-4cb8-802f-d7a1c6eecbf6 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
ba8f64ad-a063-4090-a245-8f4c072f4d3c | section | Second Fix
7e8780a7-6381-4b96-8b1d-d398d1b0da7a | checkpoint | Grilles installed square and level
5acbe13e-b827-4ed8-b09d-faea16c00512 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
fb72e984-d7cc-4548-9059-24f616b565b6 | checkpoint | Area left clean and tidy, fingerprints removed
798e9748-d082-4523-9d1e-08e3ef5693b4 | checkpoint | Controllers fitted off
dc568d33-72b8-4291-ad51-47b55126f139 | checkpoint | Power fitted off
b8c01a1c-510d-46ee-8b0a-a87eadfbbbb4 | checkpoint | Plant and controllers labelled
375b4706-0259-45fc-9121-7d16f5eead5d | section | Commission
d30a0c5f-5cca-45c6-a908-b47db7152cc0 | checkpoint | Commissioned and Paperwork submitted
188abf5f-d871-416c-9008-33ca06b4df34 | checkpoint | COC issued
800f9d12-4ab7-4495-8bc4-bb0d028d9bb9 | checkpoint | Plant and controller labelled
7e3fee14-9592-4c0b-bbd5-fd2247d94816 | checklist | B01 - Split HW |  | Split HW
60fa16f1-ec3a-4f25-a27e-1c39d4438ed0 | section | Pre-Start
38b79f6d-4038-426a-963b-853bbf87e19b | checkpoint | Area clear, access good, enough space for install
eb7c7ed2-15e3-43ca-a807-a8495602292b | checkpoint | Area/base/wall ready for outdoor unit
23e0e3d6-4608-4981-9430-8a7573d59630 | checkpoint | Pipework route all clear, penetrations complete
877a417f-7cba-4250-b85c-c5c0024eab20 | checkpoint | Nogs in place
7fe95aec-1e2e-4cf5-8e31-565a5df74ce1 | checkpoint | Drain 1m from Indoor unit location by plumber
bd70ff64-9937-4413-ada3-6f8b07a1aab8 | section | First Fix
1290f762-e2e3-41fa-880c-712fc14496d8 | checkpoint | Pipework Insulated complete length, glued and taped
820f352c-fe86-4c16-a72a-a71a5e66830b | checkpoint | Pipework supported incl any seismic restraints
d04af376-e410-4837-8ba9-719397a8fc48 | checkpoint | Drain installed and insulated
5c87f8be-ca01-4d0a-8ca1-779f1a6b472d | checkpoint | Pipe lengths are recorded accurately. INSERT PIPE LENGTH (IN NOTES):
d0ae31fd-318d-4129-b5af-403face999d5 | checkpoint | Control cables installed
7b87a22a-507a-4c36-91aa-68e7d01c159f | checkpoint | Power Cables installed
91487126-d7c5-49d2-8510-4edd71919be3 | checkpoint | Plans marked up for As Builts
2a898093-ed60-4657-b4ac-9deb5f05c84f | section | Second Fix
3f9936f4-a5c8-4a88-be62-0fe50e1fa76e | checkpoint | Correct Indoor unit installed. (Insert Photo)
0f7863ff-5e43-4fa6-9339-51b32f2bbfb9 | checkpoint | Correct Outdoor unit installed. (Insert Photo)
7b64323f-6f28-4666-9f09-f1a10d5c538a | checkpoint | Outdoor unit level and secure
978b0bd9-cd73-4b03-958d-92424b042361 | checkpoint | High Wall cover installed flush and square
7afbeabd-bb44-4829-9e39-3c0fbeda8119 | checkpoint | Area left clean and tidy, fingerprints removed
b133ac59-0125-43dc-85e5-3cf1e129a937 | checkpoint | Controllers fitted off
8fec4c61-7fac-4945-b319-2fe63828402e | checkpoint | Power fitted off
74a56e25-3595-402c-a376-6ec2eaad399e | section | Commission
f0b357a7-c1d4-426d-a907-a96a34c52604 | checkpoint | Commissioned and paperwork submitted
5c95d21b-63d1-4230-854e-63b6aaddd0b2 | checkpoint | COC issued
7578d0d9-5ca6-44a5-8719-1d47fd94b37c | checkpoint | Plant and controller labelled
afa101dc-2855-49ee-ba10-570e790a797e | checklist | B01 - VRV Cass |  | VRV Cass
db2096e7-27ea-4459-95c6-7d5b3cb77c4f | section | Pre-Start
be2141ed-6fc7-42e8-83f5-264504683651 | checkpoint | Area clear, access good, enough space for install
d9036510-61fb-4b75-ab01-f83639bb4ace | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
f8a44157-3055-45ae-ab0b-08ae1fe83562 | section | First Fix
cb6e91c9-a96b-405a-87b1-b81ad356e47c | checkpoint | Pipework connected to BS Box and Indoor unit
583474ae-d2ab-4d9f-a3ba-a37330e4dab4 | checkpoint | Pipework Insulated, glued and taped complete length
9f35efc2-71df-4688-8df2-9f8f828953fd | checkpoint | Pipework supported incl any seismic restraints
e622af83-01b7-409b-b3a9-e97c5dc6130c | checkpoint | Indoor unit level, secure, vibration isolated and seismically restrained
959bd22a-e69f-433a-ad78-d23be5ce1f86 | checkpoint | Correct unit installed. (INSERT PHOTO)
6ef4a658-6249-486a-a80b-041fa49690bc | checkpoint | Drain installed and insulated
16144376-9585-4630-869a-12de4ef8365b | checkpoint | Pipe lengths are recorded accurately. INSERT PIPE LENGTH (IN NOTES):
e4a608a3-07bb-44be-adda-a94572e3d82c | checkpoint | Control cables installed
dd8be657-2259-4a0a-9e58-3dcd40b3d5e4 | checkpoint | Power Cables installed
3ee53698-9452-4894-99cd-9266ef0129fb | checkpoint | Access Panel requirements are marked and given to builders
9895dee8-4808-4f02-a8da-e3b33d88b03a | checkpoint | Plans marked up for As Builts
b42b8d81-5a91-4d66-81af-50624b9960b8 | section | Second Fix
5cf40084-c193-4341-b7e4-5906cb2e291a | checkpoint | Face plate installed flush and square
dc304317-2344-4bcf-8cb5-f1701dc03403 | checkpoint | Access for future maintenance all clear. Filter can be easily removed
51de2caa-9514-4cce-8647-4024c95dd686 | checkpoint | Area left clean and tidy, fingerprints removed
b92be124-fcfe-4266-a665-f151ec15451b | checkpoint | Controller fitted off
48365e00-6d82-4356-9d86-0dec02f69b0f | checkpoint | Plant and controller labelled
e020decf-31a3-4f39-a2f8-df3efb459259 | checklist | B01 - VRV Ducted |  | VRV Ducted
e7bb3520-559a-49e5-bf79-51985113877d | section | Pre-Start
e5fecd57-a05d-47b0-8056-32f5e6eb97e3 | checkpoint | Area clear, access good, enough space for install
07264a33-dfc8-4566-84d3-7a455009dfe8 | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
c1812a55-1e76-42c8-88e8-cac0446abeba | section | First Fix
898cc568-51f1-44d7-b491-b5002139663d | checkpoint | Pipework connected to BS Box and Indoor unit
62817948-935e-4dd5-ba31-d1c133ef1e85 | checkpoint | Pipework Insulated, glued and taped complete length
f2fc47dc-6f1c-49cb-9cd9-12a0d2c907fa | checkpoint | Pipework supported incl any seismic restraints
15725f7c-375f-45b7-ac95-4e3583d8074a | checkpoint | Indoor unit level, secure, vibration isolated and seismically restrained
0615721a-8e5c-482b-9353-3b421405ae64 | checkpoint | Correct unit installed. (INSERT PHOTO)
eefb50f4-dbad-4db1-aa39-2670bde0feeb | checkpoint | Drain installed and insulated
c93d7d3b-81ac-4bbf-a163-5a5c6021ab74 | checkpoint | Pipe lengths are recorded accurately. INSERT PIPE LENGTH (IN NOTES):
ff083905-3781-46eb-9c07-89cd211e9354 | checkpoint | Control cables installed
28de7622-8f09-477c-b588-851c95dccc7b | checkpoint | Power Cables installed
6994dc3f-026d-4151-9d20-5bd6035c9695 | checkpoint | Fire dampers installed to Manufacturer's instructions. Drop tested where applicable
280ea866-06f5-4bfa-a46c-6dcf9680ae6d | checkpoint | Breakaway joins either side of fire dampers
0253153c-e46d-4d9e-8af1-ed637e7961b8 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
314f9e28-cfe1-4443-bb5d-5d5b0f3153a3 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
6c4913c3-ba66-4b37-851d-366f588b7cff | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
8cd7ab33-891e-41a1-8823-330980cc45aa | checkpoint | Balancing Dampers locked open and accessible
f2e6621d-f617-47ce-983e-7e2ab020cc9e | checkpoint | Flexible ducts taped then cable tied
2e648511-dc35-414b-a70e-858ba859bb7b | checkpoint | Second fix grille and access panel locations recorded
52f08cfc-6533-4356-9006-8d87164d2323 | checkpoint | All open ducts sealed off with plastic film or similar
beec74d1-436e-4a39-b8fc-e64ed24c9d45 | checkpoint | Plans marked up for As Builts
fc9b8b3b-1766-4e71-930c-7199ababea84 | section | Second Fix
11f82578-02a8-42e0-93d1-24d5b2f88863 | checkpoint | Grilles installed flush and square
595d60ec-bf64-48f5-ba56-7a37fb4a6b1d | checkpoint | Access for future maintenance all clear. Filter can be easily removed
6a84568c-6e15-4097-834a-f9e7395d87f5 | checkpoint | Area left clean and tidy, fingerprints removed
43017135-6622-41a9-b61a-02d81461d493 | checkpoint | Controller fitted off
d888334f-98a0-4578-b338-05ded2b3b2fa | checkpoint | Plant and controller labelled
ac9accc1-5ba6-4536-9045-83671e27c6fa | checklist | B01 - VRV HW |  | VRV HW
03b079ea-de5c-4484-b2d0-a7f87c32b7e2 | section | Pre-Start
ec7ee0b2-6565-473a-9577-d0aa5eaed0ee | checkpoint | Area clear, access good, enough space for install
fc0373c0-c849-4bf9-9561-84c38d55d8bb | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
8eabf5ff-8eb2-4e72-8aa5-b75039fb60ba | section | First Fix
8001ba5e-86a4-4396-8ce5-5f1e2ebe39a9 | checkpoint | Pipework connected to BS Box and run to Indoor unit location
f8afc625-6903-46c0-8d10-16d3724617b6 | checkpoint | Pipework Insulated, glued and taped complete length
5ad84c9e-696a-4d1a-9092-4e36b146c70d | checkpoint | Pipework supported incl any seismic restraints
58208532-d825-47c5-bb8f-d861667fe274 | checkpoint | Drain installed and insulated
88f2de49-223a-4aa8-9513-08b5c38fb9ff | checkpoint | Pipe lengths are recorded accurately. INSERT PIPE LENGTH (IN NOTES):
9b7cb600-de1b-4aa0-a83b-d408edc25d52 | checkpoint | Control cables installed
78fc6c0c-c65e-4b94-b167-936f3dd0041e | checkpoint | Power Cables installed
e380469a-fb8c-4fe0-84cf-2db6b2f6aebb | checkpoint | Plans marked up for As Builts
807e5bf1-e829-4547-873f-e455cc4c8f07 | section | Second Fix
0c1520f6-544b-47cc-9e34-6211fda247bf | checkpoint | Unit installed flush and square
13a6a87e-b754-4717-ba50-ce4d27b82de1 | checkpoint | Correct Unit installed (Insert Photo)
d5f6b9ca-659e-4948-87fc-dd1a8beedfb5 | checkpoint | Area left clean and tidy, fingerprints removed
e8a8d093-b44c-42bd-827d-348258f02c29 | checkpoint | Controller fitted off
2dc87f28-9312-4695-b595-24f2e29fefd8 | checkpoint | Plant and controller labelled
046b3dad-a1c6-4a32-9389-75eaf7452c98 | checklist | B01 - VRV OU |  | VRV OU
113b34f6-1c47-48af-adeb-87a65805f2f7 | section | Pre-Start
d5d83e25-74c7-4fc5-a3a6-56ddd0407ceb | checkpoint | Area/base ready for outdoor unit
7fba6e62-8ef3-418c-8aa7-290246fd7f68 | checkpoint | Any required drains in place
71739e90-a62c-4b5c-8b42-b685264c41a7 | checkpoint | Outdoor unit area accessible
bb61cfc0-4c7a-4160-8c6f-1be0f9af35f4 | checkpoint | Pipework route from OU to BS box all clear, penetrations complete
a7b93ff8-89fc-44e9-b497-b84186c61c73 | checkpoint | Area clear for BS Box installation
e3350c8b-e398-447d-98b7-6ebada1ac9e0 | section | First Fix
7514f9c6-82ea-4f1a-aecd-12b9f71976aa | checkpoint | Outdoor unit brackets/feet/strut in place
b04cc948-29c8-4b4e-9461-e5f6aa9555fc | checkpoint | Unit level, secure, bolted down, seismically restrained
276c3762-0498-44ea-a272-268b83ec7f74 | checkpoint | Correct VRV unit installed. (INSERT PHOTO)
00ecfced-9898-486c-9f24-1fe6ec7cf568 | checkpoint | Pipework connected from OU unit to BS box
d9a6dcda-cebf-49cf-8125-fd5568fe6c28 | checkpoint | Pipework Insulated, glued and taped
16ff9185-cae1-45a5-bd88-af388913f396 | checkpoint | Pipework supported incl any seismic restraints
7f68d779-496b-4e33-a4eb-c4bd120ee9eb | checkpoint | Pipework supported up off the ground
1ca98d84-7f0a-4588-9d65-4ace0c88900a | checkpoint | Refnets installed as per Manufacturer's Instructions
a7d44912-5458-4614-97a9-aa3e7b8b005c | checkpoint | BS Box level, secure and seismically restrained
db4f20f9-cd07-48cf-9c61-134347b0c452 | checkpoint | Correct BS unit installed. (INSERT PHOTO)
faca3bbe-97e7-4518-9ab9-5f44c411f2c1 | checkpoint | Drain installed and insulated
0d1ae048-d6e2-491a-9368-5a9faef2dffa | checkpoint | Pipe lengths are recorded accurately. INSERT PIPE LENGTH (IN NOTES):
4ff1d958-7418-4c13-b94f-c6460e512c17 | checkpoint | Access Panel requirements are marked and given to builders
13ed0530-2dd8-4e3c-8433-e34af137dc79 | checkpoint | Plans marked up for As Builts
89367707-32fb-4330-9b50-c7ef57c52141 | section | Commission
aaa87c20-43d3-44ae-a016-9d59dbb21093 | checkpoint | Access to OU unit is good
6140deb4-ab41-4b90-98fe-fcd1f90cc0b6 | checkpoint | Access to BS Box is good
52728437-38af-4f8e-93f2-d0f41ab3569b | checkpoint | Access to Indoor units is good
a885836f-b0c5-4b35-b12e-0d661a57cfd7 | checkpoint | Pre-commissioning paperwork completed and sent to TSL PM
8861c80c-e540-46c2-8c89-8ababd3cc3b8 | checkpoint | Power on to compressor for 24 hours (impt: only once evac completed)
a3ae509b-8284-4994-b473-5188bc3856c7 | checkpoint | Commissioned by Supplier
190489e0-7e4c-4b42-ab97-62c570a498ef | checkpoint | All plant labelled incl OU/BS/Indoors/Controllers/Pipework
f9f5de7f-ddd2-4606-930a-aecc4dfb0ac6 | checklist | B02 - Commission |  | Commission
496731b6-c3ef-4602-8f19-2c371c3745e5 | checkpoint | Mechanical Plant commissioned
649bc8c3-c7c6-4a14-892e-969affe44cf2 | checklist | B02 - Common Areas |  | Common Areas
398fc2c4-8e27-40e3-9626-1ca7e20d89e2 | section | Pre-start
0000cf8f-3760-4824-828a-8da02b820437 | checkpoint | Area clear, access good, enough space for install
07a3d91a-8b04-407e-b21d-db0696b67d04 | checkpoint | Duct route clear, Penetrations complete
8d3447df-f94f-4beb-87c9-c638fc422387 | checkpoint | Nogs/Supports in place
2f1a0af0-ff4c-410a-a856-c29bc6b09b93 | section | First Fix
1cde1dd6-958b-41eb-a0e6-c6bf3df1ee8e | checkpoint | Access Panel requirements marked up on drawings and submitted to client
35643e85-a3e2-4116-b486-c41c49df7d42 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
04846828-c091-4022-8b80-24f185858256 | checkpoint | Mechanical First Fix complete
f4506e64-117f-405c-9066-9453fba7e44b | signoff | Raise Remedial/Request Sign Off
86b0e46c-00ff-4bef-afa4-c45c28524330 | checklist | B02 - Ext Fan |  | Ext Fan
344aec4f-b40f-47d4-b6cf-b59e098175ea | section | Pre-start
7894edfb-4ab0-4074-b4f0-47919dee1a01 | checkpoint | Area clear, access good, enough space for install
6757b48d-1762-4d9a-88a5-cc822c63f513 | checkpoint | Duct route clear, Penetrations complete
63a7b2da-f912-4ce7-ae54-e7fa3e3e13a5 | checkpoint | Nogs/Supports in place
32da8d0a-5f31-4c40-8660-69b1025539b7 | section | First Fix
83c8a0e4-c1a4-49b3-93bb-925425dfa15d | checkpoint | Access Panel requirements marked up on drawings and submitted to client
c912f671-2c50-4378-bf80-2f572385a903 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
57de5a30-6cd6-47d4-a9d0-289c83a21993 | checkpoint | Mechanical First Fix complete
01430f80-3088-4cc8-abbb-a45ab24070a1 | section | Second Fix
0f0be43e-05cd-417b-a07a-72189fa52afb | checkpoint | Area clear and access good for Second Fix
c5430562-4119-4d92-ad22-ef5c910da49c | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
0c356eb5-aa7c-4d36-a3fc-cf0825bfe604 | checkpoint | Mechanical Second Fix complete
5c08359f-af8e-4ca3-bf4d-5463fc59438c | section | Commission
ece31b27-1627-4eae-886a-b1bd8ab2a087 | checkpoint | Good access to all areas of building
486e4786-00bb-41d3-a6e2-11c5340e0f36 | checkpoint | Power live to Mechanical Plant
1c07dc3f-0800-4599-ab43-172d72995af5 | checkpoint | Mechanical Plant commissioned
d3bdf909-b861-4a95-af90-890a9f230596 | checklist | B02 - First Fix |  | First Fix
319b02b4-4798-437c-92a6-0696c438da82 | section | Pre-start
77ca7bf9-527b-4357-b6d7-8283b3bc5f66 | checkpoint | Area clear, access good, enough space for instal
4bad8d7a-fda3-45a4-935f-6a1d4658a4c2 | checkpoint | Area/base/wall ready for outdoor unit
84a33643-b2c4-44ad-ab99-dd1089ed32a8 | checkpoint | Pipework route all clear, penetrations complete
44d0da83-0c13-43d8-8caf-23dd1c0b58bf | checkpoint | Nogs in place
96c6a06c-f502-447f-9e7a-75207cdfcc23 | checkpoint | Drain 1m from Indoor unit location by plumber
61791d81-31e7-40d3-8e34-7fef0347b233 | section | First Fix
bb7400b6-838c-4152-937c-56e8b4c7f863 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
d1a66871-0d8c-448b-a643-e60ac641f698 | checkpoint | Mechanical First Fix complete
5759d223-4152-4416-a86f-0353c65f14d8 | signoff | Raise Remedial/Request Sign Off
3a34c294-249a-4719-a3ad-35eaca764fe9 | checklist | B02 - SA Fan |  | SA Fan
24b4c790-d3ce-4b09-a557-78cd919a2997 | section | Pre-start
f7892374-27c2-4a64-ad9f-106549069aa1 | checkpoint | Area clear, access good, enough space for install
379d2b94-0c01-43b0-956a-afbfa0cf5231 | checkpoint | Duct route clear, Penetrations complete
89bd9637-d5ab-4cb8-8cc7-bcaa0f5e33ee | checkpoint | Nogs/Supports in place
b592d30a-950e-4d25-8f67-863f1fc935b0 | section | First Fix
a65a9112-d8ab-40cb-9916-72d8961ebe4b | checkpoint | Access Panel requirements marked up on drawings and submitted to client
45a35f6a-926f-4433-be87-bdf9e8f7bf2e | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
10546dc1-2c16-4fa2-ace8-dafb6c85115d | checkpoint | Mechanical First Fix complete
a06b81e4-2259-44af-a634-aaca7e771a35 | section | Second Fix
cfce7852-a00b-406f-b96c-d1c06a1681a2 | checkpoint | Area clear and access good for Second Fix
42b0560c-22d4-4f0c-9d4c-faf1da773a64 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
d5b742a5-44d1-43f1-94b5-61b9f5cfb33d | checkpoint | Mechanical Second Fix complete
229641b6-348f-47e6-99b1-f918e272a625 | section | Commission
de948b86-225d-44ff-93e0-520637b6a1cb | checkpoint | Good access to all areas of building
b5236940-0ff0-4636-815d-d467e72af044 | checkpoint | Power live to Mechanical Plant
97681280-67b7-4f25-96f2-8c28b7440603 | checkpoint | Mechanical Plant commissioned
c6866959-6b30-454a-b888-3e38c9830452 | checklist | B02 - Second Fix |  | Second Fix
7c8b17d9-68e4-4853-a7a1-a0051883bef7 | checkpoint | Area clear and access good for Second Fix
89e41ec4-4894-4054-89ad-60a39cc2a162 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
f5591a83-d7d5-43e1-87a7-1ff1e1b3f2ca | checkpoint | Mechanical Second Fix complete
f7592e2f-c0d0-4278-8baf-4883b13e9119 | signoff | Raise Remedial/Request Sign Off
aa8363c8-d038-4a82-b48b-42f855b304e7 | checklist | B02 - Split HW |  | Split HW
24c5b31d-7862-41ee-af9f-9ffa1c452524 | section | Pre-start
f543940d-08ab-4800-a273-4fdcd0c4f299 | checkpoint | Area clear, access good, enough space for install
71b7c95b-c382-42b8-a84a-8838ec59d533 | checkpoint | Area/base/wall ready for outdoor unit
b177f4c0-ebc4-4e58-8e5f-a395c72b3acb | checkpoint | Any required drains for outdoor unit in place
67f0ac09-e84d-411d-a38c-ed9faed3d1fe | checkpoint | Pipework route all clear, penetrations complete
d45a6006-7877-4791-9d13-1b95c002c757 | checkpoint | Nogs in place
ebfe4840-bff0-4e89-be87-3d3ae7cdc1f4 | checkpoint | Drain 1m from Indoor unit location by plumber
eb091803-3372-42e4-aa64-75ff9744879d | section | First Fix
1447aa76-c07a-4d6e-aa2e-6e912de31140 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
9254f730-4125-4e50-8f5c-9979acb8489b | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
dec796f9-8862-4650-a654-66a07e4be063 | checkpoint | Mechanical First Fix complete
6d8c04f2-5eab-4983-85c6-a55a3e0ecaca | section | Second Fix
c48c4d64-767f-4ee2-934a-e0838849c925 | checkpoint | Area clear and access good for Second Fix
590f8278-0201-4e42-93ad-7c7bf597ef8f | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
16300a0c-e44c-4450-947a-150754306ca2 | checkpoint | Mechanical Second Fix complete
b05a8eff-578a-432a-9347-e55a41ef39ef | section | Commission
f7db2ed2-8849-4b2c-854d-b9e1ed781205 | checkpoint | Good access to all areas of building
0ed4b29d-17fc-40af-afa3-0b001bf4e240 | checkpoint | Power live to Mechanical Plant
966137e9-568f-4aa4-b222-2c08600db713 | checkpoint | Mechanical Plant commissioned
ffeaeb72-9012-4965-aac9-6df77db5c8a6 | checklist | B02 - Ventilation |  | Ventilation
8aa7f9ac-8e4a-4d88-9f8b-ed916421404e | section | Preinstall checks
409c1679-7364-4f29-8f97-d8828a9ce6ef | checkpoint | Area accessible, clean and tidy
9fa00bb2-8085-4990-8151-34ffe27a158a | checkpoint | Penetrations done in floors and walls (if needed)
7f88c6cb-3a01-4a37-be24-6641bfc42652 | checkpoint | Space for ducting (no trades in the way)
c3d5eb18-b925-4d76-9af9-916eb7dbc1f0 | checkpoint | Pipe through exterior wall installed by RHC to connect to
4be3cc5e-5381-4579-9777-b85974f50ab4 | checkpoint | Drawings and work scope confirmed
4248a6a8-2a60-4a1a-934a-112328a050a1 | section | First Fix - Apartment Ventilation
9b96369b-9134-4f7d-a552-e4f32d10e3f7 | checkpoint | Ductwork run straight level and well supported
769fa9bd-29a3-4e72-9773-b67dd9d253a6 | checkpoint | All ductwork joints sealed
a994dd5c-40b7-4c72-a52d-4328af2f2cbe | checkpoint | All SAB joints sealed and taped
6ce3c30a-be31-40d0-bb82-80b83a0dd914 | checkpoint | All flexible ducts cable tied and taped to duct
d338fb89-60ec-4c78-a462-3d0fa63a2fa0 | checkpoint | All seismic restraints in place (if needed)
fff97212-2502-4db4-abee-bf4d6091f904 | checkpoint | Flexible ducts fixed in place to grille location
f40f50bf-bd65-4c7c-aba5-fe75bd33b585 | checkpoint | Grille locations/access panels marked on plans
3fec8245-c322-4fb3-8e58-029a4e56c88c | checkpoint | Mechanical First Fix complete
c7eca3ff-4366-4786-be87-08c16ef3a6d4 | section | Second Fix - Apartment Ventilation
b15ae1e5-2745-4209-b081-94415720e70e | checkpoint | Ceiling fans installed square and level
dbd1e70e-6aba-4a67-90c7-36755896859e | checkpoint | Kitchen range hood installed by RHC to connect to
f878b3fd-3762-4743-b6c6-f6f8af07c14f | checkpoint | Fingerprints removed from grilles/walls/ceilings
5b71a331-a5d3-4bb7-8053-34c5a22de2a1 | checkpoint | Fan plugged in before install to ceiling
dceaa1a3-18ac-480a-bdfe-6a8694bbc1b3 | checkpoint | External louver supplied by TSL, installed by RHC completed
ed35d386-049b-4ee8-9ca3-e5bdf0c6be01 | checkpoint | Commissioning form completed & given to TSL
b986073e-7168-4fdd-b92e-088bf4097576 | checkpoint | Mechanical Second Fix complete
ed94a8b7-b125-41b6-ac71-2f1179832433 | section | Post check & Commission
25b1107b-2878-402a-bdab-e7735be90807 | checkpoint | Correct product used as per requirements
e0036f05-00ac-4fb6-a7c4-657a9cf1d4f7 | checkpoint | Correct design followed as per drawings
7dbb778a-67c1-4c19-8971-edc7d81805b5 | checkpoint | Mechanical Plant commissioned
9d445079-f114-4573-b587-f79b262dd4df | signoff | Request sign off/remedial from RHC
669c4631-c48f-4ac1-b461-5f87cdc7cfa2 | checklist | Completion documents |  | Completion documents
94acd944-b94e-469c-b291-a5309dd68eaf | checkpoint | Warranties compiled and attached
789c2a93-d42e-4484-86bc-f33700fcec40 | checkpoint | Producer statements attached
22232f90-92fb-41e9-96fb-e7f96264eb92 | checkpoint | All handover documentation supplied
4200126f-9727-4602-8c08-8044a98391f3 | checklist | S - S - Ventilation - Apartment Ventilation |  | S - S - Ventilation - Apartment Ventilation
21743c0c-d902-469e-b4d6-9acffd9bf561 | section | Pre-start checks
4630882f-b98b-46ab-9060-face96131ebc | checkpoint | Penetrations done in floors and walls (if needed)
81b2cb35-3e77-4ab6-844c-abb4647b4962 | checkpoint | Space for ducting (no trades in the way)
38cc96c4-11be-405a-bfaa-a62961933de2 | checkpoint | Pipe through exterior wall installed by RHC to connect to
5954517f-43ff-41b9-b4da-fb1e5e320b86 | checkpoint | Drawings and work scope confirmed
f1145ec9-d8c8-4ced-9163-3732349bd6d8 | section | First Fix
0b6eef7e-529c-4e5a-bb74-aa3072c62789 | checkpoint | Ductwork run straight level and well supported
f9fe88ce-d975-4027-930d-e752ccd18ed7 | checkpoint | All ductwork joints sealed
c264d53c-83b7-40f3-9b9b-459539bb6836 | checkpoint | All SAB joints sealed and taped
27fb8a23-ea5a-406e-9989-6f32e4cea11d | checkpoint | All flexible ducts cable tied and taped to duct
58a65daa-60d5-411a-88f3-e649cfa3c67c | checkpoint | Identify locations and correct model of Fire damper to be installed
bc6655c4-f6f2-436c-8047-fc1c22290482 | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
fc9a0dcb-c3dd-4bc5-8608-f2cad9398c59 | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
7b403925-ab0f-4e62-81a5-7d2f9b6700f9 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
3da09060-551a-43a9-a4bc-35042255649c | checkpoint | Install using Materials specified in the PS1
2965c007-86b4-4547-9dc3-3492d68d714e | checkpoint | Upload Photos of Install
85355582-c017-47f7-ad6c-33956b55c979 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
0bf4ccbc-04fa-4a09-990a-f51fb2f363f6 | checkpoint | Flexible ducts fixed in place to grille location
13d313d6-fe3d-40e5-9e78-d41fdc743d6f | checkpoint | Identify Fan Upgrade Requirement
c84ba278-02f1-4e92-a5f1-d6d68a7c9b8d | checkpoint | Area Clear for Install of Ducting, Fan, and Control Box
7a05f21a-21b9-4fed-b74e-2145918df126 | checkpoint | Install Fan, ducting and control box as per spec.
ab26cb9d-63b7-4458-bd08-027a4687640b | checkpoint | Grille locations/access panels marked on plans
3323d394-a2dd-4e82-bc93-e1c3e6d0f177 | checkpoint | Mechanical First Fix complete
a226c38d-2e3e-4171-83fc-a02b56bf26f7 | section | Second Fix
a67ef991-9c20-413b-b79d-61bec3a7147d | checkpoint | Ceiling fans installed square and level
fb79af67-3bb9-47df-8541-9d2cbaaf8211 | checkpoint | Kitchen range hood installed by RHC to connect to
45854faf-4a35-41d1-b472-cbe7d451da6d | checkpoint | Fingerprints removed from grilles/walls/ceilings
77456e3d-23e3-49bd-a1c3-a23a73c638f6 | checkpoint | Fan plugged in before install to ceiling
186e7d7d-72de-4789-9e57-bbfe22ffe0ad | checkpoint | External louver supplied by TSL, installed by RHC completed
4983ec68-7286-4b09-a8f4-e44f05c32b53 | checkpoint | Commissioning form completed & given to TSL
12ae4156-1dbd-4776-b826-f6be009e2023 | checkpoint | Mechanical Second Fix complete
89b9c40b-a42b-40f6-bec3-69be3fd4581c | section | Commissioning
d4a27be1-6558-48c8-8f40-bdd0059fff5a | checkpoint | Correct product used as per requirements
13750a75-2c53-44cd-aecf-6f30389432b2 | checkpoint | Correct design followed as per drawings
55d1f6e0-5572-45f8-a70e-d48b37e9e126 | checkpoint | Mechanical Plant commissioned
c7c2b067-6d67-48c2-b7f9-ed31f7deb934 | checkpoint | Inspections completed and issued to Foreman
813c84c1-3c0b-4558-a6fb-be0cbc6ff759 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
012c6998-9318-4e96-b7db-17feec2381da | checklist | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan |  | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
f872b688-07a2-456f-8621-54535f3e0e86 | section | Pre-start check
896aab1e-4565-4ca9-979e-bf33a0116cd8 | checkpoint | Area clear, access god, enough space for install
0f149ddb-0a43-4a15-8c33-0e350ca8f776 | checkpoint | Duct Route clear, Penetrations completed
b09d71b4-c976-4645-a6fe-c5521806b928 | checkpoint | Nogs/Supports in place
9f4496f6-b315-4160-b1e0-f2cb8ed26a9d | section | First Fix
d051ecbf-5b67-4028-9d5f-d904ac1c162f | checkpoint | Access Panel requirements marked up on drawings and submitted to client
0470c885-6270-4649-b377-6eae88617580 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
4433f725-d8f5-42db-8169-bc309bfb3592 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
43643cee-7b5b-4eb9-aa5a-896c340655c0 | checkpoint | Install using Materials specified in the PS1
8991685c-96ac-4fc9-9916-9c57cafcec5a | checkpoint | Upload Photos of Install
6575b3a1-5abc-420e-a947-994607c28b37 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
506c39e8-f6f5-4de1-a4aa-3ba49c13cce8 | checkpoint | All seismic restraints in place (if needed)
f6705275-c73a-4c1c-bd61-d5316a7a151b | checkpoint | Mechanical First Fix complete
946fbb31-69ff-492b-87a4-4509461ce019 | section | Second Fix
653b99ca-7990-4e8f-9884-a9f8c01170af | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
d2bde8e6-7579-4efa-81f9-8db5ccd0db76 | checkpoint | Mechanical Second Fix complete
9162c673-b69c-4153-a81f-99a6052f8c05 | section | Commissioning
6b425771-84f7-4b0f-82c0-4eaf22285753 | checkpoint | Good access to all areas of building
ab62c109-5d01-4ece-b341-eb1db6a91be1 | checkpoint | Power live to Mechanical Plant
745a3e8e-dff2-4f81-9229-ff4424611032 | checkpoint | Mechanical Plant commissioned
0d007fe6-adff-4bc9-8dc2-4526ebed05e7 | checkpoint | Inspections completed and issued to Foreman
f251fb5d-eb88-418a-b609-be10f84422f9 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
93e20d23-70fc-4a36-9be8-f3b96e5f8887 | checklist | S - S - Ventilation - Corridors Ventilation |  | S - S - Ventilation - Corridors Ventilation
1995c848-b229-40d9-a67c-5f6776068fad | section | Pre-start checks
ad5fea1c-be50-47b5-910d-310659d4f5d0 | checkpoint | Area clear, access god, enough space for install
b274b82b-1545-4983-9de7-908e5bb25552 | checkpoint | Duct Route clear, Penetrations completed
e2f25726-6610-4286-b5c6-cbe4c1759134 | checkpoint | Nogs/Supports in place
16238fc4-0753-4056-845a-36336c4c56e4 | section | First Fix
f3a37efe-fac1-44c0-8d80-afe69f34b904 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
19170d22-c6c4-4613-b81e-3264b348e8e4 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
df4f9664-6df5-4dcf-9b59-885b25f92402 | checkpoint | All flexible ducts cable tied and taped to duct
1e8b6e7b-7718-4db2-be63-67f2a89a6310 | checkpoint | Identify locations and correct model of Fire damper to be installed
f301a3dd-cf99-44aa-a385-6adbddfb8ec9 | checkpoint | Install to Manufacturers Specifications
400357cd-3ec4-4eeb-a652-86df904a4c25 | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
5953d6b4-007d-4586-b7c9-dd5c307ff82f | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
dbf40bc1-9ac5-4135-b987-2f41776dcb76 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
6c3e1b28-4f00-4aaa-b365-e7dbb6f5fd09 | checkpoint | Install using Materials specified in the PS1
9b2640d0-7ae4-4763-928c-cb9dd8ac2793 | checkpoint | Upload Photos of Install
293e7abb-0899-4415-975d-1ba22c237f03 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
0ee58639-872e-4797-869f-2f2cd20cb161 | checkpoint | Mechanical First Fix complete
cafa6035-4684-43d9-bafc-1bdd34dcd868 | section | Second Fix
3493a352-b1a9-4dcd-81b3-1c55b1081543 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
fe13faab-532e-4feb-b7b3-40d889515f18 | checkpoint | Mechanical Second Fix complete
343954ff-66ab-4b73-857d-ea7b51ed4a88 | section | Commissioning
07c6a5aa-f269-49d6-a2be-b0cdaf529665 | checkpoint | Mechanical Plant commissioned
ea3510ae-0bc9-46cd-bd3e-cef61043971b | checkpoint | Inspections completed and issued to Foreman
e83236e1-869d-4610-a9f1-69caf410904b | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS