## Master List Templates
Id | Type | Name | Values | Prompting Name
4f727a59-4299-4227-9052-e8b429dd1fd6 | checklist | Fire Dampers |  | Fire Dampers
3e7f85da-877b-4efa-b47b-efce9a349cce | section | Pre-Start Fire Damper
a125b3ab-1bd0-4c4d-8c71-2051fddc6705 | checkpoint | Area clear, access good, enough space for install
6ba5c600-debb-430a-a872-ca1c59e0c7a7 | checkpoint | Duct Route clear, Penetrations complete
79b55644-e611-4038-81bf-3c09f44b52a3 | section | First Fix Fire Damper
7eb77dd2-6432-4ae1-9810-c78af312c5e5 | checkpoint | Correct Fire Damper installed. (Insert Photo)
edb13b58-7d6c-4d0f-a300-f69795250fb9 | checkpoint | Fire Damper installed straight and level with correct orientation.
02e08761-75ee-43d2-9591-b920d72f825a | checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
d697b986-ba81-4a91-8993-ce055e73dfab | checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
cb49af99-b40d-4d66-97f2-46692fef3658 | checkpoint | Access Panels in duct for fire dampers.
28cba624-b158-4d97-8a03-bfa1a24e76d4 | checkpoint | Building Access Panel requirements are marked and given to builders
6a38b280-855c-4c00-8255-23a3f8cf5289 | checkpoint | Plans marked up for As Builts with Access Panel locations
d33ba6eb-28c8-4854-8b42-2940a154e9b8 | section | Second Fix Fire Damper
1d369191-28df-40f0-9afa-3521d492b676 | checkpoint | Fire Damper Label affixed, Asset Number applied.
99fcfadd-4ea2-45ef-b749-c0a4c1d2672b | checkpoint | Fire Dampers Access Panels still accessible for maintenance
5d2eb6ef-1c00-4070-a498-8e46333efb04 | checkpoint | Area left clean and tidy, finger prints removed
ae2acbc5-9afe-4989-8c9f-a1b92fad8b30 | checkpoint | Fire Damper sealed to structure both sides.
f68972b4-6d81-41aa-aa09-4be60adafed1 | section | Commission Fire Damper
35abf88d-b375-479f-8b77-924971281f8a | checkpoint | Drop Tested as applicable
3399aa37-48d7-492c-8a16-93ef940f0411 | checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
7be34150-c368-48a3-ba66-611937573253 | checkpoint | Fire Damper Label filled out, photo uploaded.
40670fb4-21e7-4227-bdb5-faa6329dd3e3 | checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
91a77d34-03fe-4f7c-b402-578d38b427d1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
e707b120-381f-4217-bb27-f23a94556bd0 | checklist | CST - S - Completion Documents |  | CST - S - Completion Documents
a392a837-d14f-40b5-aaa6-cb5f87c537da | checkpoint | All relevant Compliance Documentation completed and attached above
50e32a58-b9ce-54ca-a0ce-9a08333c1c04 | button | LBP Memorandum/ Record of works filled out, signed and attached | Yes, No, N/A
f4b0ed10-2eb5-5994-9fd9-e40cf6b5bd77 | button | Any Additional Compliance Documentation - Completed and Attached | Yes, No, N/A
2de7d7a1-dd29-5ea2-b80d-27682081a447 | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
eb990081-1178-4d05-87c5-a5b561755d8e | signoff | Request Signoff
3f0ddbd1-9dea-446c-b7b8-0c2089f00c73 | checklist | QA - Air Conditioning Checklist |  | Air Conditioning Checklist
b155e2ed-a09c-45a1-9da2-a0b512ae17c8 | checkpoint | Air Conditioning First Fix completed (2-3 Photos attached)
9324f4b1-8b67-4aa3-8fb6-8e3d7dcdeaf6 | checklist | QA - Extract Fan |  | QA - Extract Fan
1a61b256-4b65-43ad-af1b-f36b6e0ef458 | section | Pre-Start Ext Fan
0695529d-b130-4728-8a97-c02158dae4b2 | checkpoint | Area clear, access good, enough space for install
98205fde-b908-469a-8c78-bfefa86dc40a | checkpoint | Duct Route clear, Penetrations complete
91ccb09d-41a9-4621-be92-f509e417c36f | checkpoint | Nogs/Supports in place
1a65dfd0-cdcd-4cfe-b39c-4565ab52595c | section | First Fix Ext Fan
cdd414e7-4b3e-4b30-969d-8bd0a04c21f2 | checkpoint | Fan installed straight and level and correct orientation.
4f554b69-2631-4c5c-beb4-5322fec8a2dd | checkpoint | Attenuators installed Level and secure
5778cbc2-2104-4590-9571-7854b85faff5 | checkpoint | Fan or Cowl sealed to Upstand
f0ef0c6d-d11f-4ba4-b6f0-5f897a25d7dd | checkpoint | Correct Fan installed
1a316c55-eba3-45c0-b21b-44e03e07acce | checkpoint | Fan serial No. recorded
bbbfe6b5-2d60-4ab3-b58e-7bc2380ffb09 | checkpoint | Access Panels in duct for fire dampers
fd58a42b-f7e2-4f64-bcfb-33effa6bbf9e | checkpoint | Access Panel for Extract Fan
2a6f887b-c4aa-44ce-b0cf-0829eaf56b19 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
8f172d9c-bf1d-4bd0-83ca-773733c272e0 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
3c947542-58da-4cba-a0b2-197186a25b7f | checkpoint | Flexible ducts taped then cable tied
a0980cfd-2cba-44ee-aec1-39974ec889b7 | checkpoint | Supply cable installed correctly, protected and secured
fe67b2df-8e03-449d-9cd8-2c4bebb804f0 | checkpoint | Interconnecting cables correctly installed and protected
20e36244-0ea5-4cf5-9be8-20b25fefd361 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
cf7cfab8-d4bd-4dda-bead-40f2f56ef1ba | section | Second Fix Ext Fan
86748939-1cca-4bfd-9a00-cb97ceddb4ad | checkpoint | Grilles installed square and level
8f8795ce-b649-4669-b074-17c67d0ef43d | checkpoint | Flexible ducts taped then cable tied to grilles/boots
3578f9df-efae-4a91-ab61-f97706ca37d0 | checkpoint | Boots sealed to grilles
5e0646f9-fd3b-4491-b760-037e814db969 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
e7005327-0c19-4138-9849-a074d9331587 | checkpoint | Controllers fitted off
21ee405e-c577-4438-acff-44c0a1e36e2b | checkpoint | Power fitted off
bab194e8-5a8c-4f3f-a563-7e67385c0e32 | checkpoint | Area left clean and tidy, finger prints removed
a8d5781c-edef-45ed-9310-b9e2d64f96f7 | checkpoint | Plant and controllers labelled
c0f77751-10ac-4911-9106-39ca89fefa2e | section | Commission Ext Fan
ce701032-59d7-447d-80d2-9bb5feacc1ed | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
40ad875d-7e80-48a3-ada3-4519d1758e2d | checkpoint | Electrical testing complete
d944d9e5-0ceb-407a-9974-626d8bec1e45 | checkpoint | COC issued
2389ab72-1995-4473-bf3d-be124877522c | checkpoint | Fire Matrix Commisioning Tests
a9c53971-7947-4c03-ad80-5c37ad423b53 | checkpoint | O&M Manuals Submissions
34ed63ba-b2ce-49ea-a59d-f4363fd4b2ee | checkpoint | Services interface.
b548176a-b2ba-4276-9ef9-865005503195 | checklist | QA - Kitchen Extract |  | QA - Kitchen Extract
07a1816a-d92f-4237-a0a4-9ea70eec1d7f | section | Pre-Start Kitchen Ext
99a4393b-71e9-4a37-84be-22c54a92263a | checkpoint | Area clear, access good, enough space for install
63470bc3-b3e1-4c3e-9b01-18ca2d48ec80 | checkpoint | Duct Route clear, Penetrations complete
19c74e02-1181-4ba9-8afc-898392676698 | checkpoint | Nogs/Supports in place
c351bc15-fb27-4ba7-82ef-1ea010b6b77a | section | First Fix Kitchen Ext
aaa5f022-9acf-4c81-ab6f-3b2d4045c342 | checkpoint | Fan installed straight and level and correct orientation.
01b67471-7708-4325-95f4-02012ac61e41 | checkpoint | Fan or Cowl sealed to Upstand
3b28cbad-958b-4ef1-9a51-3795a427d5e8 | checkpoint | Correct Fan installed
84e1fc4f-a8ff-46c0-b304-94f163c971a1 | checkpoint | Fan serial No. recorded
cb1afc90-018b-4cb0-a573-08a02781c10d | checkpoint | Access Panels in duct for cleaning
3ca3c731-e0b4-4fae-b090-7af0c97f5575 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
598e964b-2e86-4c29-98c1-d3744b0c2e3a | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
e3ed5a92-0789-45f6-af53-921feeb26efc | checkpoint | Balancing Dampers locked open and accessible
c2159583-5d91-40ac-a88e-307e7a2242aa | checkpoint | Interconnecting cables correctly installed and protected
54bdbea5-d63a-4c9b-858d-0ced8b2614f7 | checkpoint | Remote controller cable installed
abb87c4c-1ed1-43e9-8eb3-cbb8eee2c812 | checkpoint | Building Access Panel requirements are marked and given to builders
1dfbec71-7afd-436d-8bb6-020b249c1583 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
15934852-e4e4-495a-a914-c4ee6de33270 | section | Second Fix Kitchen Ext
48258778-7742-4f6c-b760-2a5b6b5165b7 | checkpoint | Hoods installed square and level and seismically braced
7581eb47-7120-42ac-a9d1-fa630092c612 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
dc7b7e65-f739-4678-9c0d-2c3be3c7e329 | checkpoint | Controllers fitted off
fb869f54-28d0-40af-84b6-d058f531826a | checkpoint | Power fitted off
a62e78a9-9ee3-462c-8a18-cf276feddb42 | checkpoint | Area left clean and tidy, finger prints removed
179d60e3-7c25-46c8-8023-305f1f2762bf | checkpoint | Plant and controllers labelled
24167f58-368b-4cbb-bd00-ae220bfc047f | section | Commission Kitchen Ext
21c73893-e348-4a7e-95d6-e43613178274 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
e1408955-e0df-4138-82ca-d119c519863c | checkpoint | Electrical testing complete
b37cfbbe-65d1-408f-bc9c-cb807eb2fdd8 | checkpoint | COC issued
c8713f41-8327-4108-96d8-0ee9ea9454de | checkpoint | O&M manuals Submissions
bbe99e88-66db-4b25-868e-a5d63fabe3ed | checklist | QA - SA Fan |  | QA - SA Fan
a4b7874a-ad05-4f50-a859-4ffd0156b059 | section | Pre-Start SA Fan
91f2742a-7e11-4a9f-bcb7-b4b4347ca206 | checkpoint | Area clear, access good, enough space for install
474af5a6-6d6c-4841-9a0f-8192edbec32f | checkpoint | Duct Route clear, Penetrations complete
e656db7b-b2b1-4ddf-bd90-cfe32f5d247b | checkpoint | Nogs/Supports in place
08c4c966-b568-43d3-a5ad-0157cd808bca | section | First Fix SA Fan
dca998d9-d23f-4858-8254-f509fa9e9331 | checkpoint | Fan installed straight and level and correct orientation.
403d73ea-e8a6-4608-b3c9-cdc327b97be7 | checkpoint | Fan or Cowl sealed to Upstand
8750b825-9e99-498d-bca8-c07aaf79d275 | checkpoint | Correct Fan installed
f36246ad-d686-4a59-b9c0-19b77ad8d877 | checkpoint | Fan serial No. recorded
f361978e-a61b-4ba3-a303-240bef79f7b7 | checkpoint | Fan seismically braced and vibration isolated
87723768-9c65-4e56-aee7-8b73fc571dd2 | checkpoint | Heater Bank installed to Manufacturers instructions
50f13077-1da3-4a65-ba19-9813d533fe33 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
331baa81-1b27-484c-9dd5-424b85e26b4a | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
dfbef78e-1a80-4bd3-b815-6c1d37f761fa | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
32f098ca-04d9-4a76-a708-2fd898d91e5a | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
fa69ad22-23f9-4bb7-a188-88976d3ef737 | checkpoint | Flexible ducts taped then cable tied
0c88fcd6-b443-4194-a728-dde7328b70da | checkpoint | Supply cable installed correctly, protected and secured
66814ff8-3d17-4260-9b52-ad84acb3964e | checkpoint | Interconnecting cables correctly installed and protected
8e122998-b553-4b3f-a346-791480ba81a8 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
1491fbf1-5f7e-446e-8f5c-e5b7f0a819e5 | section | Second Fix SA Fan
5368686b-339c-4016-b354-b1b6fc626d35 | checkpoint | Grilles installed square and level
d9b7dbda-0d70-457e-8b2b-b7713df4305d | checkpoint | Flexible ducts taped then cable tied to grilles/boots
dd8a4df0-2c2f-40b7-9956-1eb13938d21b | checkpoint | Boots sealed to grilles
bcd63437-acb4-4124-a3e0-5e77528fe9f3 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
821bda67-14fe-4c74-ae97-478729ec1b73 | checkpoint | Controllers fitted off. Heater Bank THT set
7742985b-ebb9-4ee6-b12e-717e5fbdb4bc | checkpoint | Power fitted off
467b9ac9-0b3b-43e7-a457-02f12ba62f66 | checkpoint | Area left clean and tidy, finger prints removed
deeb912e-d1d6-41a9-97b7-6dd2b8d900d3 | checkpoint | Plant and controllers labelled
c8fcf9cd-b496-45d6-80b7-412213f8a188 | section | Commission SA Fan
c8e5d67b-06e5-47aa-9b24-d49253405b88 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
40cc93dd-c3f9-47c6-bb03-f9c40d8663c0 | checkpoint | Electrical testing complete
078739de-adfd-4cb9-9ed4-0a97c219599a | checkpoint | COC issued
c27e01d8-b56a-4e62-9464-0a5956a05337 | checkpoint | Fire Matrix Commissioning Tests
e85a7b77-3474-43d0-a5bc-8ac0fe78e10b | checkpoint | O&M Manuals submissions
592291ee-1a05-4964-bd9f-eddf31c0aa59 | checkpoint | Services interface
693c3a95-b444-4b67-8b64-15f6acfd0ee7 | checklist | QA - Split HW (V1) |  | QA - Split HW (V1)
fa7ebd18-d7a4-498d-a501-06f7545abefc | section | Pre-start
7a7d2177-0ae4-4ae7-9a03-684f0671a433 | checkpoint | Area clear, access good, enough space for install
05aeef58-4433-479f-8145-e4031d05feee | checkpoint | Area/base/wall ready for outdoor unit
1c4c255c-f446-42e5-aa4e-1c1e90f8d8b6 | checkpoint | Any required drains for outdoor unit in place
f71104b2-cbc0-40d9-a90e-67d09beab51f | checkpoint | Pipework route all clear, penetrations complete (2-3 Photos attached)
9ff46f8e-0589-438d-8826-c2d412f105ce | checkpoint | Nogs in place (2-3 Photos attached)
de6c31e9-9ed8-4add-9b9b-77c4a38acf1b | checkpoint | Drain 1m from Indoor unit location by plumber
e7273c7b-21bf-4be2-8343-d0ec15d13999 | section | First Fix
22316cd2-4e89-48d2-a4f1-98e5f36d6012 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
0a16a5a2-c5e9-4337-b90e-da03479dd805 | checkpoint | All works from builders or other trades to enable Mechanical First is to be completed (e.g. drains, framing, penetration)
dcbb09a8-418f-4305-a498-1ae462ff51be | checkpoint | Mechanical First Fix completed (2-3 Photos attached)
cc7c9f5a-52c5-4429-9a00-5eed948d22be | signoff | Request sign off
154d611d-7fd8-4ace-8118-03aa8b50a109 | section | Second Fix
58a3d490-aea3-4f1e-b2d4-746e9bd3effa | checkpoint | Area clear and access good for Second Fix
4d8659b4-ed94-4704-b33a-a0e1d1d18709 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing)
ab7d4d6d-4e4a-4dac-ae6f-e05d74e835d0 | checkpoint | Mechanical Second Fix completed (2-3 Photos attached)
248ea228-8ac4-4fdd-9789-df5563a0cb20 | signoff | Request sign off
174280e4-63ff-41af-9ada-078e4b3f8001 | section | Commission
5a0c7f35-13b8-4a49-b4b7-6aa63848a250 | checkpoint | Good access to all areas of building
c9347114-1c81-40d3-b0da-202b0461a95a | checkpoint | Power live to Mechanical Plant
2036adae-9a5e-4ac8-b9cd-badd48b4ad8d | checkpoint | Mechanical Plant commissioned (2-3 Photos attached)
a0c17aa7-e39f-4b01-af2a-260408a93e5b | signoff | Request sign off
0b037d5c-61b8-4ffb-9c45-94b3635d9bcb | checklist | QA - Split HW (V2) |  | QA - Split HW (V2)
99824a59-c8de-4531-b533-3c2004180bc3 | section | Pre-start
495b2552-e3c8-4c65-a506-be047c1a485f | checkpoint | Area clear, access good, enough space for install
813527b4-be19-4f7a-8399-42f3eb473af2 | checkpoint | Area/base/wall ready for outdoor unit
631e130d-e12c-475f-b690-c8b3d0d783f7 | checkpoint | Any required drains for outdoor unit in place
10d33045-0649-4488-a0c2-4162f7cb0eab | checkpoint | Pipework route all clear, penetrations complete (2-3 Photos attached)
0eb3209b-e199-4e22-bda5-548b49fd28c6 | checkpoint | Nogs in place (2-3 Photos attached)
ba0e7cda-eb71-46c8-91cd-3052a1244924 | checkpoint | Drain 1m from Indoor unit location by plumber
ec5f5755-297f-4da9-966b-48dc61c4487a | section | First Fix
a85d0c9c-d1b6-4317-ad46-623bd75b69ca | checkpoint | Access Panel requirements marked up on drawings and submitted to client
9f492542-0268-4be8-8866-807937690f14 | checkpoint | All works from builders or other trades to enable Mechanical First is to be completed (e.g. drains, framing, penetration)
36085c08-e777-44b9-8278-504583dbd7b8 | checkpoint | Airconditioning First Fix completed (2-3 Photos attached)
7c128b86-77f6-4ae0-81ab-b163d6a347e4 | checkpoint | Mechanical First Fix completed (2-3 Photos attached)
f69bdf3f-5fd8-4a35-ac0c-689666bbc07c | signoff | Request sign off
0eca5f0d-b04f-4269-bea0-6969eb82f95e | section | Second Fix
bf37b2af-fce8-408b-97b0-c511631aeb9a | checkpoint | Area clear and access good for Second Fix
3d6e7122-dab4-4ca5-ab44-488f07a06936 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing)
22332052-996b-4ed2-a21d-f412e7e4723c | checkpoint | Mechanical Second Fix completed (2-3 Photos attached)
558653e6-5484-4186-88be-bc1be7a5641c | signoff | Request sign off
fc07c49c-5da3-497a-89d2-65046353811b | section | Commission
7cdc40d7-3192-4364-8711-beec55e91715 | checkpoint | Good access to all areas of building
6b617b4c-68a1-461a-927e-11f25d9b6f30 | checkpoint | Power live to Mechanical Plant
e7fb3e1f-701e-41e0-8f52-f7be2f6afa02 | checkpoint | Mechanical Plant commissioned (2-3 Photos attached)
6d744775-142e-45e6-bf04-62a61ca7cb57 | signoff | Request sign off
5677efe2-6832-47b5-8581-4414277a80da | checklist | QA - Split HW (V3) |  | QA - Split HW (V3)
6aaaeee9-747e-462c-9fcf-bb8b62ca5bb3 | section | PRE-START SPLIT HW
5120c25d-b9d3-45b0-bf11-ccd1ac3adaaa | checkpoint | Area clear, access good, enough space for install
1e541dec-2a31-48af-a1a5-fc1831fb788f | checkpoint | Area/base/wall ready for outdoor unit
0d57fa2c-abb1-4bf2-8745-8b35eac3c9fd | checkpoint | Pipework route all clear, penetrations complete
dd210608-f0fb-4824-beb1-418427c3c3dd | checkpoint | Nogs in place
e234eb25-3200-446c-b87d-bf10405d8f59 | checkpoint | Drain 1m from Indoor unit location by plumber
82d6ee57-da77-4c62-a648-3b4b9f441474 | section | FIRST FIX SPLIT HW
2947667b-8e35-46f6-9793-aee2a1c5dceb | checkpoint | Pipework Insulated complete length, glued and taped
8d16ff3f-d52d-4156-9249-387ff50cac78 | checkpoint | Pipework supported incl any seismic restraints
eef4fc25-22db-434e-b280-dc52ae29a918 | checkpoint | Drain installed and insulated
8d16554e-3a05-465f-aa46-5e210301f2f3 | checkpoint | Pipe lengths are recorded accuratley. INSERT PIPE LENGTH (IN NOTES):
e5ce67b9-0e60-4008-90b4-32d4fc5ef045 | checkpoint | Control cables installed
f3365d6d-b8a8-402c-b43a-54add93a2df6 | checkpoint | Power Cables installed
d65fcfb2-5a4b-4263-abfe-a616a7d15367 | checkpoint | Plans marked up for As Builts
ee4c205c-66db-4e9c-b9f3-1ca118e3b582 | section | SECOND FIX SPLIT HW
63dfb361-1769-4dee-a116-8feaf7f84fdc | checkpoint | Correct Indoor unit installed. (Insert Photo)
fcf4bf15-212c-4cc1-a8e9-b99e6ee9eaf0 | checkpoint | Correct Outdoor unit installed. (Insert Photo)
43768adc-b639-4448-84d4-ab7f13926b48 | checkpoint | Outdoor unit level and secure
fdda60f3-e9ca-4533-94bf-d949568ce5dc | checkpoint | High Wall cover installed flush and square
a27228fa-1b1b-4158-9f59-0725e71e5d75 | checkpoint | Area left clean and tidy, finger prints removed
310d1cb8-7e30-49d6-9e71-ef948cef3067 | checkpoint | Controllers fitted off
a7e650c7-9440-4a74-b3de-9ba77224a08b | checkpoint | Power fitted off
4274f85f-d538-4c33-9807-ee3a75fb1939 | section | COMMISSION SPLIT HW
e61876dc-952a-428f-b4df-8cac375a925a | checkpoint | Commissioned and paperwork submitted
eaee9b43-4257-459f-9650-ecd48b2a61bc | checkpoint | COC issued
c4a69bbe-6d9b-41af-8cb3-ea434f08aeb1 | checkpoint | Plant and controller labelled
14393fe7-3b55-426c-bda1-586c475a12ff | checklist | QA - Ventilation, ducting , fans |  | Ventilation, ducting , fans
49581465-60d1-4a87-b802-e128b0b7f840 | section | Pre-start: Extract Fans
7c3ccdf3-84c0-48b0-b127-5665a0ba7714 | checkpoint | Area clear, access good, enough space for install
3102bcd6-1af6-4e0c-89d5-0e377e3d1e15 | checkpoint | Duct route clear, Penetrations complete
770a16a0-a45c-4da6-a5cc-a7e21713091b | checkpoint | Nogs/Supports in place
e87b6710-fe93-4caf-91fc-da97b4edffcb | signoff | Request sign off
f3596e62-a63d-4493-83dd-1d7e0a1835ae | section | First Fix: Extract Fans
b34cb749-06c7-4f5d-8b23-5d9fc2d9cc32 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
95776656-2ed9-45da-b422-bdae25743bba | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
45f79f65-d968-480b-bd34-c5ac6cb10ac0 | checkpoint | Mechanical First Fix completed
1d249066-2ec7-425e-b588-085e7ffe3d78 | signoff | Request sign off
9c334901-c3be-4f9f-9e90-e7ea1fc689d0 | section | Second Fix: Extract Fans
2be5ce9f-9f77-42d5-8614-fdf44bf2022f | checkpoint | Area clear and access good for Second Fix
a24be3c6-dca7-44ab-bbdb-d077043c8607 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
a3638757-ae16-47e5-a80d-eceb9ca10136 | checkpoint | Mechanical Second Fix completed
acfb5243-2d59-475e-88a1-1a8660b0572d | signoff | Request sign off
cc05a7bc-b041-40a9-b17a-975e2e59bad9 | section | Commission: Extract Fans
e14534c0-abbb-4ae6-998a-98595adbc946 | checkpoint | Clear access to all areas of building
38088b75-715d-4bb3-8bff-efd941d9e1c0 | checkpoint | Power live to Mechanical Plant
9ac1d099-6b08-4332-9e85-d3eaf83464fb | checkpoint | Mechanical Plant commissioned
4f5df008-459b-4ce3-981c-50c13279e126 | signoff | Request sign off
c47b91c6-c798-402f-a24d-04530f9a243d | checklist | S - S - Air conditioning |  | S - S - Air conditioning
0a304385-574d-4f5e-ae71-54b7eec0281c | section | Pre-start checks
0cfbcded-3a6f-4fed-aac1-decc623dd807 | checkpoint | Area/base/wall ready for outdoor unit
cdda6f35-63c7-438c-83b5-0853a2812abe | checkpoint | Pipework route all clear, penetrations complete
f05b5139-5a8d-42f7-b25d-f08ae83ca7ec | checkpoint | Nogs/ply in place for indoor unit
a72589e1-ca65-4997-91a3-0d70faf04f2c | checkpoint | Drain 1m from indoor unit location by plumber
7e01d159-2b8a-49c9-b125-9ddeadbb084b | section | First Fix
e73dac11-10a1-4b71-aef3-92813b293cf9 | checkpoint | Complete length of pipework is insulated and acceptable
74092009-7ebc-4eea-b8b1-1023d0a65df9 | checkpoint | Drain installed and insulated
e8eead24-e859-4fd3-be91-320826388cd2 | checkpoint | Supply cable installed correctly, protected and secured
fcf82204-b391-4b83-a775-ec8d0c594eaa | checkpoint | Outdoor wall brackets in place
815de061-8561-452e-ae23-8d05669b4789 | checkpoint | Interconnecting cables correctly installed and protected
abae0e96-4305-4659-944a-71f65c0603fd | checkpoint | Mechanical First Fix complete and acceptable
cf3ca395-98ec-4d5f-89cf-e3c400810d85 | section | Second Fix
d72c43fb-7986-48bd-81ed-d9949daf3fef | checkpoint | System pressure checked and still holding pressure and acceptable
070b8f5f-906e-4a08-a136-9eb337a5fc35 | checkpoint | Correct Indoor unit installed, level and tight to wall and acceptable
a2dd4156-e97c-4f3e-bf0b-edc494ef7685 | checkpoint | Correct Outdoor unit installed and secure
e3b6c3cc-9565-4676-afb2-80f93e940c24 | checkpoint | Indoor unit serial no. recorded
4a989b79-be61-4f43-ac0b-1a235eca6a99 | checkpoint | Outdoor Unit serial no. recorded
9e7d54b2-2c63-4994-987e-b32bd84615f9 | checkpoint | Indoor unit run, fan speeds, modes etc. are acceptable
d51acc68-91e1-4dea-99e4-970e4705774b | checkpoint | Air conditioning Second Fix complete and acceptable
c01b7566-98b9-432f-8dd8-ea13ac0ffdfd | section | Commissioning
eb09c82d-c6d2-441f-8480-83d8faec6bfb | checkpoint | Installer confirmed commissioned and paperwork submitted
3d942c10-7929-4b0b-9fb6-a33de75c6a16 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
64bc67a5-6d94-4802-aa68-561056ed60e1 | checkpoint | Electrical testing complete
c565aff5-0826-4e75-8717-7767f3a22546 | checkpoint | Commissioning complete and acceptable
200d5f33-5c73-4b06-b09a-f694870e83bf | checklist | S - S - Ventilation - Apartment Ventilation |  | S - S - Ventilation - Apartment Ventilation
449eeae9-2c8c-4e6a-ba8b-f0c997399bd6 | section | Pre-start checks
89590078-6b4d-4066-9843-7009c64902dd | checkpoint | Penetrations done in floors and walls (if needed)
c2a7a976-3a2b-4a4f-b248-aa9dbacb389e | checkpoint | Space for ducting (no trades in the way)
d2973208-f9c7-4e27-a758-6d5688dfc809 | checkpoint | Pipe through exterior wall installed by RHC to connect to
7fbbe774-ed8c-4569-b163-8d8df29fbef7 | checkpoint | Drawings and work scope confirmed
cc91374d-d3e1-4a6d-abc7-ed9a108ca674 | section | First Fix
8182f04c-cc66-4284-9f68-0615671bdafb | checkpoint | Ductwork run straight level and well supported
bd2baefe-4b8c-4fe2-a8a1-0ead1e98bd7e | checkpoint | All ductwork joints sealed
35ad4f46-5f22-46ac-a6c2-bdb718897d03 | checkpoint | All SAB joints sealed and taped
0a2387b5-ff6f-4740-985b-3dea28341c0e | checkpoint | All flexible ducts cable tied and taped to duct
d466bc6c-138e-4792-a992-795ba55cf5fd | checkpoint | Identify locations and correct model of Fire damper to be installed
cb23fed0-b4f8-4dd1-8272-6258cfab739a | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
15f838f2-2bff-4081-9bf3-cbad32de9c53 | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
7256c185-40e7-404a-abd8-9d8a94f8d035 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
9681bc7f-11af-4b57-8603-4544e22a2575 | checkpoint | Install using Materials specified in the PS1
1ee7a74e-09a5-4d00-96cb-87ec565ebca6 | checkpoint | Upload Photos of Install
a6b565a7-b3bf-460c-bf7c-37608b839859 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
250a0e69-310b-478e-a2c5-efcc706d47bc | checkpoint | Flexible ducts fixed in place to grille location
94c77441-8d94-4e32-baa0-ede433896488 | checkpoint | Identify Fan Upgrade Requirement
f5633063-988d-412d-b961-24bd68565058 | checkpoint | Area Clear for Install of Ducting, Fan, and Control Box
15c8fdc0-1043-422b-a628-039b301bb399 | checkpoint | Install Fan, ducting and control box as per spec.
e37b76ef-f0bc-4753-a54e-342429d6fb86 | checkpoint | Grille locations/access panels marked on plans
a8dd91d9-3e70-4a99-9af0-f067a737c7cf | checkpoint | Mechanical First Fix complete
f20fc340-570e-4c9b-8ab1-2573e9114c2f | section | Second Fix
9434d235-9e0c-42f5-be01-46d305122f91 | checkpoint | Ceiling fans installed square and level
bde42de2-cf67-487a-b8a2-9f0fa24f9796 | checkpoint | Kitchen range hood installed by RHC to connect to
ee000d49-90c4-4071-94de-17ef1f2ae0b8 | checkpoint | Fingerprints removed from grilles/walls/ceilings
5e5b8fe7-cd3c-42c5-b4a2-e03cae754ca0 | checkpoint | Fan plugged in before install to ceiling
c9a07d84-ad05-4edb-8863-f59888fd1006 | checkpoint | External louver supplied by TSL, installed by RHC completed
e8811f39-6b09-49b4-b03f-21d99d4a21fa | checkpoint | Commissioning form completed & given to TSL
1f3a82da-afc3-45de-ba51-d6e222824bb6 | checkpoint | Mechanical Second Fix complete
331048a7-43a6-4f1f-bacb-43bdfe071fc9 | section | Commissioning
d042e8a6-b6d4-4402-8285-fb79f17d1384 | checkpoint | Correct product used as per requirements
7fb39825-74ab-491a-b4a3-fce5dafe821f | checkpoint | Correct design followed as per drawings
180c6ad8-5c2b-4a27-99b4-33f2ecdb938b | checkpoint | Mechanical Plant commissioned
8169ecec-f64b-428f-89af-cff0e100dd3d | checkpoint | Inspections completed and issued to Foreman
b07654a0-483f-4a5f-b7c1-23cff2eec695 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
0dbc774b-4dbf-485b-8982-6ba0fb3411c6 | checklist | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan |  | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
3cebf8fc-35c4-44bb-9609-f9d2392f5815 | section | Pre-start check
9fb7b50a-daa5-4fbd-83b3-34886cec1817 | checkpoint | Area clear, access god, enough space for install
b2eb1990-5a98-4a90-8592-079c521275fc | checkpoint | Duct Route clear, Penetrations completed
a8d10b85-10fe-4ee3-849e-8e8b687bd313 | checkpoint | Nogs/Supports in place
c6035643-160e-4bfa-9fa3-7963ec45177c | section | First Fix
c7dd5826-fe99-4507-a8e7-a85fc8c17c6b | checkpoint | Access Panel requirements marked up on drawings and submitted to client
fe2af5ba-75f8-48bc-9b64-e3c4163ee975 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
f97c124e-1cfa-424e-9bcd-7f7679e9c3f2 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
e3f864ac-c031-49e7-aabd-10d185fd3c2c | checkpoint | Install using Materials specified in the PS1
ef7dac80-b621-4311-8f68-e524050a1e7d | checkpoint | Upload Photos of Install
88fd2b5e-aef2-43a6-a8d3-4b7f02b3d20e | checkpoint | Refer back to Seismic Engineer for PS4 Production.
3e0fccf4-9cc2-48ad-b6ff-a67c33e96117 | checkpoint | All seismic restraints in place (if needed)
b701edbd-58c8-4bbf-bec4-42918255152a | checkpoint | Mechanical First Fix complete
535d4a47-c061-41b0-b30b-b469681f2445 | section | Second Fix
ec120dc3-4fae-4ad2-bdd1-740ff0b5ba25 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
59fde572-744c-4d27-a8e3-90062060f853 | checkpoint | Mechanical Second Fix complete
c4743d6a-a824-43a4-8daa-ad61a67e213a | section | Commissioning
90d153e1-9d4a-4440-b2b1-1ded3a8c4e4e | checkpoint | Good access to all areas of building
917ea3d8-1967-4173-a72d-b25eebbdd782 | checkpoint | Power live to Mechanical Plant
39f2d799-d646-4099-92e5-3c1cbde09de3 | checkpoint | Mechanical Plant commissioned
944453a2-efe9-4a0b-91ec-746435996ea0 | checkpoint | Inspections completed and issued to Foreman
693e3520-1a89-409e-901d-91eda2a0e36a | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
59f77910-e276-4102-8342-9ea16f07b479 | checklist | S - S - Ventilation - Corridors Ventilation |  | S - S - Ventilation - Corridors Ventilation
9f2d48af-84fa-4e5b-a85e-413f8a9856d9 | section | Pre-start checks
c07102ce-3904-4509-ae75-0a67f8acbadb | checkpoint | Area clear, access god, enough space for install
ae20b4d7-9da4-4677-9869-0fe834d93fd0 | checkpoint | Duct Route clear, Penetrations completed
50dd26c7-1dc9-43f1-b748-f3840a5fe41b | checkpoint | Nogs/Supports in place
cafa4da0-49f2-4699-87d5-1cd2d4d9264a | section | First Fix
9ebe2645-1b26-4e27-8f87-c793a4be0dfb | checkpoint | Access Panel requirements marked up on drawings and submitted to client
91937316-218b-4cb7-92fa-4d548bc15661 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
c43f4ac1-2d3f-4a10-bbde-ae7bcbcd023d | checkpoint | All flexible ducts cable tied and taped to duct
054ea7ab-1231-4879-9ae7-7f0fcebfdf16 | checkpoint | Identify locations and correct model of Fire damper to be installed
c552db51-d042-45b5-b613-07f5dd000191 | checkpoint | Install to Manufacturers Specifications
e857d5b0-8470-449d-b1a9-dff03b174eeb | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
afe9dbb2-7832-4d0b-8e0b-c402603b921b | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
d97666f4-daed-4bdb-a095-7dbdcad75592 | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
3828a5ee-d84c-4e51-b7d7-2098c9555e8f | checkpoint | Install using Materials specified in the PS1
8b5e629b-84c4-43da-a983-b4853298c7ab | checkpoint | Upload Photos of Install
4715d0c6-1a52-4f8a-82cc-3c3143f15b35 | checkpoint | Refer back to Seismic Engineer for PS4 Production.
e79b48ef-bc1d-442a-bf2d-9cdd03ad88b4 | checkpoint | Mechanical First Fix complete
d1ccc31c-de77-4900-99be-6d271347bdcf | section | Second Fix
3877c6ab-93de-42a3-b47f-260abb314afa | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
645ba248-fe75-489b-b2ec-060ccb15dbf1 | checkpoint | Mechanical Second Fix complete
2c46b82d-c3e4-4918-886d-8dae2f2a76c1 | section | Commissioning
9653832c-6f43-482a-87f5-629775c8e90d | checkpoint | Mechanical Plant commissioned
ac8e4282-c88e-49e6-b4d7-316e5326d070 | checkpoint | Inspections completed and issued to Foreman
fcc6f931-75dd-4a1b-9dda-ee9cb9e231d8 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
eb9bf8ff-570f-4d98-b27c-e2e8a485f7fa | checklist | SYS - Compliance / Completion Documentation |  | Compliance / Completion Documentation (V1)
010ff53c-56d5-4e61-b903-e931caca3770 | checkpoint | All relevant Compliance Documentation completed and attached below
6e1e6861-efb7-4e21-9ed9-21b1e64fb0ee | button | LBP Memorandum/ Record of works filled out, signed and attached | YES, N/A
d2abf4f6-231c-4b09-a37d-05029b5a10d7 | button | As-built plans attached | YES, N/A
79dd3fde-71ef-44b2-a653-49a1eaa01054 | button | Any Additional Compliance Documentation - completed and attached | YES, N/A
f66ac706-679e-4649-a4e2-929866544d51 | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
3a3336ad-4559-4c5a-a747-bfa7750e07f3 | signoff | Request Sign Off
3530c8df-caa1-4355-abc3-e753dc3cab6c | checklist | SYS - Job Details Checklist |  | Add Job Details Checklist (V1)
299be909-0be2-4497-b92a-6062319e6dcd | checkpoint | Site Information Recorded
38095843-54de-426d-88a9-a609ac1095ec | note | Site Address - Riccarton Park - 25 Steadman Rd, Riccarton
cd0c467f-ebab-456c-af09-f6157d89caad | note | Main Contractor Details - Ryman Healthcare
07026073-f4e0-487e-9ad1-cfb199a6acce | note | Project Managers Details - Andrew Inch - andrew.inch@rymanhealthcare.com
db8c6331-4d47-4c28-af20-24d4051884bc | note | Site Manager Details - Martin Collins - martin.collins@rymanhealthcare.com
517370a0-d7e0-4e6c-b9b2-06eb52c7fda4 | note | QA Admin Details - Leshani Gunawardana - Leshani.Gunawardana@rymanhealthcare.com
64007800-7c15-4cb4-9fce-85117fbad80f | checkpoint | Scope of Works Attached
e5b0c9a6-50a2-41ed-9057-7a261b6b7ee8 | checkpoint | Additional Pre Start Docs
9014f0b9-04f4-49a3-b0c3-5d1103f26551 | checkpoint | All relevant job details entered above
12ef59fe-d6e9-4211-ae64-3c9056cf7fa1 | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or "N/A"
3adf960f-a6b7-4866-a3d7-0b3824c36de4 | checklist | SYS - Pre-Commencement Checklist |  | Add Pre-Commencement Checklist (V3)
382f7cfb-8d7e-45df-b1e4-c1442fcbceea | section | Health & Safety Pre-Commencement Checks
82939fad-5e13-4949-b27f-7b433797294b | checkpoint | Trade Contractor H&S Policy - Completed & Attached
3ed67973-444d-41b1-8b49-e7ee08f415f4 | checkpoint | Trade Contractor Site Specific Safety Plan (SSSP) - Completed & Attached
4929e61e-f0a6-44c5-89da-1d39983d57c3 | checkpoint | Any Additional Prestart H&S Documentation uploaded
5b1ffe56-18af-451c-aac3-391166ee4fe9 | note | Pass once uploaded or select "N/A" if there are no additional requirements to those listed above
af723d7f-a446-401a-9da8-938f0463bc97 | checkpoint | All Health & Safety Pre-Commencement Checks Completed
0dfd3f77-7f5e-49c9-afe9-d93e93f92f93 | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or you have selected "N/A"
01256633-23be-4327-ba14-df8994eb5825 | tickbox | Report with all Health & Safety Pre-Commencement checks sent to Main Contractor
58845825-dbd8-4305-8933-fe49f4f227e1 | note | Click the three dots in the top right of the Conqa app to send this completed documentation to the respective Main Contractor
0bd021cb-5af4-4325-98df-a40f86e4e078 | signoff | Request Review
1fb67372-bc93-4401-8d06-5b98f729f6ed | section | Quality Pre-Commencement Checks
606cf102-58a1-4100-af50-dd72e87e5862 | checkpoint | Trade Contractor Quality Management Plan Completed, Agreed & Attached
43379460-c4dc-473e-ad58-5e2515d2d617 | checkpoint | Trade Contractor Inspection & Test Plan Completed, Agreed & Attached
5b63ef07-1873-46ee-967c-09f6fdd49cfb | checkpoint | Trade Contractor Licenses/Tickets attached and current
627e62b6-b69f-41f0-b9cf-1f5b3463374f | note | If required (plumbing, waterproofing, electrical etc), if not select NA
94e85b6d-996c-43e2-9ac4-144142a38e26 | checkpoint | Trade Insurances attached and current
e2e5cc92-255b-443a-90a7-256e060e5dae | note | If required, if not select NA
8ebb8a53-647f-4e2f-bf70-8485c076ff2d | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
d53674c7-35d6-4967-b4d6-8bcd89ae5756 | tickbox | Conqa EXCEL breakdown & checklists attached
2325e777-8b87-42d2-95e0-9340dcbed703 | button | Does your breakdown & checklists meet the Main Contractor requirements & have they been reviewed | YES, NO, N/A
0b74da60-1f57-4f72-8a26-7fc0b8b2d9af | checkpoint | Conqa Setup & Trade Contractor Project Team Trained & Given Access
b8383101-4c87-4819-b31c-010759c590e3 | note | Conqa Support Contact Details - support@conqa.nz, 09 886 4647 or use the live chat in app
36ff6175-cccd-42d6-a653-d740d40cc891 | checkpoint | Review Access Granted to Main Contractor & Any Relevant Third Parties
264b9330-39c8-464d-9001-38a085c2b62d | note | Contact the Conqa Support team to assist in providing access to relevant parties
dc6dbbca-54f3-4322-84e2-312f9cbdaaec | checkpoint | Matrix/Insights Setup (if required)
16e25eea-7da7-46e9-91c9-1e61308ea08e | note | login to account.con.qa & click on "insights" to see a summary of your work - if incomplete please contact the Conqa support team to assist
ae7ec44f-fb7b-4077-bb99-1086455cd12e | checkpoint | Any Additional Prestart Quality Documentation uploaded
3be9f457-2504-48a3-85d0-f2e45797befd | note | Pass once uploaded or select "N/A" if there are no additional requirements to those listed above
9c708991-6e04-4217-82b4-ab70112bef4d | checkpoint | All Quality Pre-Commencement Checks Completed
956800fc-7058-4376-b9ab-d16489e98ea5 | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or you have selected "N/A"
9b40b812-d194-46f1-8118-cffe69e5b0d1 | tickbox | Report with all Quality Pre-Commencement checks sent to Main Contractor
9b02123e-8137-4d78-80c4-3d69d675ce14 | note | Click the three dots in the top right of the Conqa app to send this completed documentation to the respective Main Contractor
1aaf6507-b468-46d9-86a4-6936f4d1b128 | signoff | Request Review
f50421db-2c91-4b9c-8f9d-1384d17ff0bb | checklist | SYS - S - S - Ventilation - Apartment Ventilation |  | S - S - Ventilation - Apartment Ventilation
8cfee6d5-e390-4733-8343-1edd9d9731ee | section | Pre-start checks
797b7078-ecf0-425b-ad0d-44a32cd52ffe | checkpoint | Penetrations done in floors and walls (if needed)
2edd45dd-3ce0-45ef-b3e6-a822dad9a3a3 | checkpoint | Space for ducting (no trades in the way)
32e7f0fa-6622-49e9-bce9-aba2a5f667fa | checkpoint | Pipe through exterior wall installed by RHC to connect to
a83c643c-f2e6-4c12-9244-56fb822e2d6c | checkpoint | Drawings and work scope confirmed
d6bc6cfb-15fe-4bbb-b933-ea4fb752db25 | section | First Fix
be58dd60-b450-4499-aabd-23052f412489 | checkpoint | Ductwork run straight level and well supported
53d3ef88-dab2-415b-9654-6f120954f04b | checkpoint | All ductwork joints sealed
3f527872-1f71-405f-89d4-8b6dcc2313dd | checkpoint | All SAB joints sealed and taped
a2b592a4-c244-48ce-913a-05d09f8dd3cf | checkpoint | All flexible ducts cable tied and taped to duct
9748bea6-13da-4e66-a7c6-fb93743c364f | checkpoint | All seismic restraints in place (if needed)
e4148735-26fb-44c4-aeaa-ade2b7fb1c4e | checkpoint | Flexible ducts fixed in place to grille location
6568a635-c1aa-42ad-953a-b69064e86fd9 | checkpoint | Grille locations/access panels marked on plans
22ad76d7-3cd9-40a7-b73f-6f3be7fac407 | checkpoint | Mechanical First Fix complete
d24b523c-1391-40c4-adb7-61928e50fc45 | section | Second Fix
4d3d0398-626f-4662-9297-25b9d005849f | checkpoint | Ceiling fans installed square and level
dee852b6-fa9a-49a6-8d5d-10d80df7d0b7 | checkpoint | Kitchen range hood installed by RHC to connect to
3e4a0a04-dd99-467f-95d3-80d43351c598 | checkpoint | Fingerprints removed from grilles/walls/ceilings
b4eb81f6-03e7-4152-a1dc-5930ccf49141 | checkpoint | Fan plugged in before install to ceiling
c6166870-dec9-4a63-b6ea-96fd81de586f | checkpoint | External louver supplied by TSL, installed by RHC completed
8822cc35-2057-4dc0-aecc-6cce9d794def | checkpoint | Commissioning form completed & given to TSL
873ccd7d-846c-47fe-8356-a98aa5a5d3c7 | checkpoint | Mechanical Second Fix complete
0d91b8f9-3d3b-4f6b-ade5-333024889a3c | section | Commissioning
ba349f07-fb99-4d76-a8b2-a0c3a15ae4eb | checkpoint | Correct product used as per requirements
29b30470-f974-4449-82ca-7d429876e922 | checkpoint | Correct design followed as per drawings
1aeec4f8-caa5-412a-86c4-11cfb9bf4e38 | checkpoint | Mechanical Plant commissioned
00fd95ca-e656-4e75-aaac-39eae80e7f51 | checklist | SYS - S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan |  | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
aaeefa1e-8138-4587-9c98-25d0651609f6 | section | Pre-start checks
f7224e78-d8af-4893-88ec-730596785494 | checkpoint | Area clear, access good, enough space for install
975e8ff0-8012-4c01-a198-9889759dbfa6 | checkpoint | Duct Route clear, Penetrations completed
fe45eb9e-83b1-4f20-9172-018b189d75ca | checkpoint | Nogs/Supports in place
30b5da27-94dc-4106-b029-40d12067de5e | section | First Fix
d2fabbeb-6bd0-40f6-a10b-43a8bc7c0c32 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
c04f68ae-c674-4bb0-b322-2cf8a953978e | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations&)
8009ea7e-5d74-4201-9044-5ebd571a30c4 | checkpoint | Mechanical First Fix complete
70b8284f-0473-4b1d-80a2-36016b4abbd1 | section | Second Fix
b6aea4c3-7cab-4a4a-8f53-e49bd8424a5c | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
eeddf177-27a8-49e5-ae83-2da65a625410 | checkpoint | Mechanical Second Fix complete
1377d9ad-834c-4991-9632-f54cdac6e70f | section | Commissioning
cc0e2714-772f-4344-9622-9cad94e6e5a1 | checkpoint | Good access to all areas of building
fb0dc81d-b486-45b8-bf5c-2b74334f6c0e | checkpoint | Power live to Mechanical Plant
4228a260-677b-4d9b-b4bc-c31cbc9ea49a | checkpoint | Mechanical Plant commissioned
e74c49b6-730f-45ae-ab0a-7c3b2fe99fb0 | checklist | SYS - S - S - Ventilation - Corridors Ventilation |  | S - S - Ventilation - Corridors Ventilation
a86261b7-c436-4fd3-b596-c7221bae140c | section | Pre-start checks
f72bacb8-404d-43e5-b0ad-614f63971635 | checkpoint | Area clear, access good, enough space for install
58221383-abc8-4030-8108-0d13202eeb93 | checkpoint | Duct route clear, Penetrations complete
1a46163c-a97e-49f8-bf1a-fc4a29ae10e1 | checkpoint | Nogs/Supports in place
00be6932-15cb-4a0c-b00d-a7c507b07836 | section | First Fix
b6db0f18-30b4-478a-84e9-427780449ece | checkpoint | Access Panel requirements marked up on drawings and submitted to client
055a94b5-0768-4709-9a3f-ca1423ab99b9 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations&)
9c4cd6ae-11bf-4d4f-aad6-62372a64537f | checkpoint | Mechanical First Fix complete
7486669b-8316-4525-bd35-cf20e2478562 | section | Second Fix
30cfeb4d-965c-4ecc-8d1b-1b542ce63789 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
329cdf18-d37c-47d0-98ca-2ee211eddb0f | checkpoint | Mechanical Second Fix complete
3a002ffb-cfc4-40a4-a6d9-7fcd0e009720 | section | Commissioning
677a9c03-f954-4d70-a57b-54a3b84ae046 | checkpoint | Mechanical Plant commissioned