## Master List Templates
Id | Type | Name | Values | Prompting Name
4f727a59-4299-4227-9052-e8b429dd1fd6 | checklist | Fire Dampers |  | Fire Dampers
3e7f85da-877b-4efa-b47b-efce9a349cce | section | Pre-Start Fire Damper
a125b3ab-1bd0-4c4d-8c71-2051fddc6705 | checkpoint | Area clear, access good, enough space for install
6ba5c600-debb-430a-a872-ca1c59e0c7a7 | checkpoint | Duct Route clear, Penetrations complete
79b55644-e611-4038-81bf-3c09f44b52a3 | section | First Fix Fire Damper
7eb77dd2-6432-4ae1-9810-c78af312c5e5 | checkpoint | Correct Fire Damper installed. (Insert Photo)
edb13b58-7d6c-4d0f-a300-f69795250fb9 | checkpoint | Fire Damper installed straight and level with correct orientation.
02e08761-75ee-43d2-9591-b920d72f825a | checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
d697b986-ba81-4a91-8993-ce055e73dfab | checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
cb49af99-b40d-4d66-97f2-46692fef3658 | checkpoint | Access Panels in duct for fire dampers.
28cba624-b158-4d97-8a03-bfa1a24e76d4 | checkpoint | Building Access Panel requirements are marked and given to builders
6a38b280-855c-4c00-8255-23a3f8cf5289 | checkpoint | Plans marked up for As Builts with Access Panel locations
d33ba6eb-28c8-4854-8b42-2940a154e9b8 | section | Second Fix Fire Damper
1d369191-28df-40f0-9afa-3521d492b676 | checkpoint | Fire Damper Label affixed, Asset Number applied.
99fcfadd-4ea2-45ef-b749-c0a4c1d2672b | checkpoint | Fire Dampers Access Panels still accessible for maintenance
5d2eb6ef-1c00-4070-a498-8e46333efb04 | checkpoint | Area left clean and tidy, finger prints removed
ae2acbc5-9afe-4989-8c9f-a1b92fad8b30 | checkpoint | Fire Damper sealed to structure both sides.
f68972b4-6d81-41aa-aa09-4be60adafed1 | section | Commission Fire Damper
35abf88d-b375-479f-8b77-924971281f8a | checkpoint | Drop Tested as applicable
3399aa37-48d7-492c-8a16-93ef940f0411 | checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
7be34150-c368-48a3-ba66-611937573253 | checkpoint | Fire Damper Label filled out, photo uploaded.
40670fb4-21e7-4227-bdb5-faa6329dd3e3 | checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
91a77d34-03fe-4f7c-b402-578d38b427d1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
b30be1d7-7f7b-4661-a006-4026300d76cf | checklist | AHU |  | AHU
e6812964-c3bd-42b6-bbdf-1ce0affa94f4 | section | Pre-Start AHU
743670fe-637f-411c-9f80-7eb438da6250 | checkpoint | Area clear, access good, enough space for install
ec802fdd-f89b-41f4-915a-8cac6447eb82 | checkpoint | Duct Route clear, Penetrations complete
b281cf55-9df0-450c-a598-88d32f55b76a | checkpoint | Nogs/Supports in place
73d7978d-b9f6-4834-86dc-d965b53270e8 | section | First Fix AHU
d8d529be-38a3-45bd-a9e1-9cd803029d90 | checkpoint | Unit installed straight and level and correct orientation.
6fab90f9-954c-4ad0-b66e-d98bfc6c4fc4 | checkpoint | Unit bolted in place, seismically restrained and vibration isolated
aad7996e-ae36-44f6-89e2-a2fe0cc32560 | checkpoint | Correct Unit installed
0faa755d-c97f-42e1-b09b-bdf7764faee6 | checkpoint | Unit serial No. recorded
5861f874-eb09-4bce-8602-f5826dceb1dc | checkpoint | Good access to Service access panel
5e328477-55ed-4b30-9838-74454aacd4ff | checkpoint | Fire dampers installed to manufacturers instructions. Drop tested where applicable
cfe12226-8e31-481b-83ab-ddbccee30f9c | checkpoint | Breakaway joins either side of fire dampers
0d6b5450-ef49-4d1a-8d72-832934093238 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
e3f6f8b2-3e96-4408-9625-9ec3ae5d979f | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
d76c09ba-ea6c-418c-9c3d-3feb6d2fc0dd | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
09ebb5b8-ba5b-4efa-aacf-7916f7d273f3 | checkpoint | Balancing Dampers locked open and accessible
ddc1f16b-71bf-484c-9a7f-09b52019bdd8 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
622f2f55-07f4-4a1f-b5a7-afedd6fa9738 | checkpoint | Flexible ducts taped then cable tied
4c74ba78-6bb4-4b5b-b911-98a05136c512 | checkpoint | Supply cable installed correctly, protected and secured
96618144-931a-4154-9752-63b8107d17f7 | checkpoint | Supply cable type, size and manufacturer
3680b1dd-e315-4cc7-bc07-3493a70cc03a | checkpoint | Circuit protection type and rating
1c9847d7-6974-48f2-8e74-4de9e359f3ef | checkpoint | Correctly rated isolator installed to standards
5c0c8847-a89d-4049-83b7-f0d3a9f75d50 | checkpoint | Interconnecting cables correctly installed and protected
b36f7dd7-75d8-401f-ae4f-7c23caa2804f | checkpoint | Control cables correct rating and type
d4acca25-9016-43d8-8c9f-1cf076ba8732 | checkpoint | Screened cables drain to earth as per specifications
189d47df-0e91-46e2-a446-8c7fa20f98ee | checkpoint | Control cables maintain minimum distance from power cables
453134e5-454f-4d6a-9e70-4d79e9e88fc5 | checkpoint | Daisy chain loops complete and correct
f717a685-8b75-4eb6-b18b-2df0f7fabeae | checkpoint | Remote controller cable installed
13af5c6c-51cc-4f60-8f83-1648e6f772c2 | checkpoint | Building Access Panel requirements are marked and given to builders
9f12eaa1-ef74-47f9-8036-0960e7b5d98f | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
4bd8fb1c-bcd8-484a-98c3-d6cf5ffb7574 | section | GREENSTAR
e8be52a4-5050-4203-952d-a9b0dd43d907 | checkpoint | Construction Drawings amended for As Built Production
79aa5b0b-f47c-423f-8467-6c4ffb2462dd | checkpoint | Materials Used - Greenstar rating verified (DETAILS RECORDED IN MATERIAL SCHEDULE)
188da2b7-f1f8-4f64-8b22-f81fdc361f49 | checkpoint | All open ducts sealed off with plastic film or similar during Construction (PHOTOS REQUIRED)
2b7196f3-4bab-4c6e-bc02-cf72207110c3 | checkpoint | All open ducts cleaned and use of covers during Construction (PHOTOS REQUIRED)
cc32baa0-9a97-4296-9e45-606a4b4914aa | checkpoint | The system has been cleaned prior to occupation and use in accordance with credit requirements.
dd49cf39-c2bf-479f-8628-a7e78886534f | checkpoint | Noise Level (LEVEL RECORDED IN EQUIPMENT SCHEDULE)
3a365480-535b-486f-b8ac-0dff8f6b7fc9 | checkpoint | Commissioning Completed with Independent Commissioning Agent
dd82801f-4543-4fbf-aced-4e56ba65e33e | checkpoint | Commissioning Data
8e6729d7-5c20-458b-9488-268b702ba253 | checkpoint | Continuous System Test Run for 1 calendar week
dbf27f77-91cc-44f1-9f1a-d1f45bbe5a0c | section | Second Fix AHU
41700ded-4f86-4745-90ad-e64c5d1eb7ad | checkpoint | Grilles installed square and level
4486912f-6c47-42c9-9535-9f371ff15bea | checkpoint | Flexible ducts taped then cable tied to grilles/boots
727521eb-4e93-40e0-b4e8-8fe8c50da00e | checkpoint | Boots sealed to grilles
ffc06691-3e5f-47b0-9ce4-06af6c8fed39 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
4fb08ec7-f682-453b-ab9e-dba00c46154a | checkpoint | Controllers fitted off. Heater Bank THT set
0082bda7-52a4-4d02-82f6-61731674078b | checkpoint | Power fitted off
de598876-c51c-473c-ad17-9438a2bb5dc2 | checkpoint | Area left clean and tidy, finger prints removed
39088e84-284f-46b7-9139-e8652b79dc4d | checkpoint | Plant and controllers labelled
8d2a05b7-d8e6-4513-8947-547f74e89e2b | section | Commission AHU
c2396f8f-e765-450c-8a05-2c265406ce93 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
d0955e4b-13f7-4ded-92b1-0fc75adba90d | checkpoint | Electrical testing complete
1dcd0afd-f1ae-45de-ba70-022df458489c | checkpoint | COC issued
1d9ff6fb-1f3a-4ed7-893c-0fcfe800ba53 | checklist | Coolroom |  | Coolroom
dffcce20-0f64-4a89-b630-9b99dc4866a7 | section | Pre-Start Coolroom
d78723fd-853f-4879-9059-29a2f77e9f11 | checkpoint | Area clear, access good, enough space for install
58dd112a-1b25-48c9-bcb1-6aab5630c524 | checkpoint | Area/base ready for outdoor unit
b898db3e-be42-4dba-af24-793d82a801c1 | checkpoint | Area/Base/Walls ready for Coolroom Panels. Floor requirements met.
06a0d313-a865-4cfe-bed3-d45d3f257a48 | checkpoint | Pipework route all clear, penetrations complete
44244000-45a8-451f-b999-36be0d8f1012 | checkpoint | Nogs in place
5b0b0d97-b1e3-41c5-8e9e-a19130d50126 | checkpoint | Drain in place by plumber
53c062d7-bf46-4dcf-bde1-ec077020ac70 | section | First Fix Coolroom
3b9d2356-f8ff-4bca-967a-70d5f4d95ef0 | checkpoint | Check set down for any rough surfaces. Smooth set down required
fd00d14d-ff82-439d-b76f-c4af55badde5 | checkpoint | Measure set down and mark out door cut out
8a32f017-8aa6-4f7f-bc2f-95f1592cda1d | checkpoint | Check if set down is dry and area is water tight
bc2ce6b2-2c6e-44e9-82a9-dc70717a7fbf | checkpoint | Panels installed square, level, tidy. No sharp edges
6b47635b-ed08-4d1d-9bfe-b9a21cf4e38f | checkpoint | Vapour sealed
7fb20de4-57ba-4695-825b-8a6f136db2e6 | checkpoint | Evaporator hung straight and level
a2e1240b-0274-451d-835d-0b5914164030 | checkpoint | Correct Evaporator installed
c7931120-85f5-41ef-945e-f6f84b8a06b7 | checkpoint | All Panel Penetrations well sealed
3d543f09-9b25-4643-9a03-20245470048c | checkpoint | Pipework Insulated complete length
0cd51475-bf9e-4872-b65e-bbb4a623f9fc | checkpoint | Insulation Joins Glued and taped
139621b6-b3f3-4a43-b4ff-e7573d377852 | checkpoint | Pipework supported incl any seismic restraints
951ab06b-58aa-498a-8d68-b39908fac6e2 | checkpoint | Flare connections/nuts insulated
91ad3e13-4b39-43f8-8166-9268d5c84beb | checkpoint | Drain installed and insulated
7b30451c-65fe-4bb0-8050-627702043d19 | checkpoint | Installer confirmed pipework under pressure (date/pressure recorded)
d096dfa4-fc29-43e9-b518-ce1d64cc3db8 | checkpoint | Installer confirmed Nitrogen purged during all welding
5f56e705-d059-4702-8f68-a949aaba2a3c | checkpoint | Supply cable installed correctly, protected and secured
8e9d45a0-ae28-4ebb-a1fe-d508ae3ab3df | checkpoint | Supply cable type, size and manufacturer
16d874be-8117-4138-8703-64d214a36274 | checkpoint | Circuit protection type and rating
d13439b3-63d2-4ce7-9198-06a7bb150353 | checkpoint | Correctly rated isolator installed to standards
73b17b47-0cec-4e66-9b45-083725deb55a | checkpoint | Interconnecting cables correctly installed and protected
83900490-6622-44db-943a-0932ea539d94 | checkpoint | Control cables correct rating and type
dd27bd8a-299c-4452-ab6d-4d83e8f68ec4 | checkpoint | Screened cables drain to earth as per specifications
ba0d70a0-c1c4-4555-b1ad-350b1a1f20b2 | checkpoint | Control cables maintain minimum distance from power cables
1029daf5-867f-47ff-af4e-446bd6f03a63 | checkpoint | Daisy chain loops complete and correct
263a9694-8107-4650-aeef-a8a8431fc27a | checkpoint | Remote controller cable installed
9c8b6f3f-bd5e-446d-bf7d-66a166b42afc | checkpoint | Pipe lengths are recorded accuratley
60e7f099-24b6-4253-a00d-b8204ff1232f | checkpoint | Plans marked up for As Builts
a0b3d5c4-d4f6-40c5-869d-d36a09122e14 | section | GREENSTAR
dd415ccf-7378-4f75-8975-1fa8713ca283 | checkpoint | Construction Drawings amended for As Built Production
6bc73b5f-fe05-4c3b-bb13-10d9fd7444d5 | checkpoint | Materials Used - Greenstar rating verified (DETAILS RECORDED IN MATERIAL SCHEDULE)
28b60234-daf5-41ca-99b0-479120f5ec63 | checkpoint | Refrigerants - Volume and type recorded (RECORDED IN EQUIPMENT SCHEDULE)
3eb5e332-d6a6-4884-8efa-190f810ee325 | checkpoint | All open pipework sealed off with plastic film or similar(PHOTOS REQUIRED)
6482a753-3600-48c2-aa57-9af5af24e998 | checkpoint | The system has been cleaned prior to occupation and use in accordance with credit requirements.
7a2c6f49-0be4-429f-bb02-bdc08dd1e593 | checkpoint | Noise Level (LEVEL RECORDED IN EQUIPMENT SCHEDULE)
78597c6e-33ec-4d51-bf7b-b0f934ebc2a5 | checkpoint | CO2 Emissions (RECORDED IN EQUIPMENT SCHEDULE)
4849787e-1dda-4aa5-ae82-7b17e0cd44df | checkpoint | Commissioning Completed with Independent Commissioning Agent
a39fb96d-334f-4103-a2e9-a5ed826535ab | checkpoint | Commissioning Data
6c5ad9e4-65ca-49a4-b172-03774698656a | checkpoint | Continuous System Test Run for 1 calendar week
eb810d94-927b-49ad-ac8a-98e06b63a074 | section | Second Fix Coolroom
4098084e-1dc1-429e-bfcf-e486a881bcc8 | checkpoint | System pressure checked and still holding 1st fix pressure
db634cfb-aecf-48c2-9855-969af2f3c755 | checkpoint | Outdoor unit secure and level
2d29ca9d-dab4-4973-a124-f8f2374e103e | checkpoint | Correct Outdoor unit installed
922b0e63-67ff-437e-bb06-d6408e97403d | checkpoint | Flare connections/nuts insulated
f52ac60c-aefa-4f05-86c4-f7238dd95a45 | checkpoint | Indoor unit serial no. recorded
375757c5-c8bb-4d35-88c1-c309c4df3d7e | checkpoint | Outdoor Unit serial no. recorded
c4fa36cc-74e0-40bf-800c-928c54d7d6fe | checkpoint | Installer confirmed drain tested
ac33d01f-6aaf-43e7-a39c-d178b2b717e9 | checkpoint | Controller installed
792771e0-0363-4e48-9f4d-0dfd37f78821 | checkpoint | Area left clean and tidy, finger prints removed
59ff614e-675c-4f07-98ee-9f6f91ba99fa | checkpoint | Plant and controller labelled
161bcede-0654-4783-9996-2bbfe3356810 | checkpoint | Access for future maintenance all clear
351642bd-4177-479c-8c7f-390cb0f946d5 | section | Commission
2b185298-61be-4b9c-b00f-9ca87a314a5d | checkpoint | Installer confirmed evacuated to Manufacturers instructions
53bef973-caae-4e30-87d9-9955fd11838b | checkpoint | Installer confirmed commissioned and paperwork submitted
e8a60da8-19e6-4cd7-a12d-52e668ff2e52 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
216247af-7f95-4409-af91-8be1b8b35feb | checkpoint | Electrical testing complete
8923c582-f7db-46ff-b3c6-63933d8361c8 | checkpoint | COC issued
d9fc9d6e-9b61-4a25-bc60-116d5cd29039 | checklist | Ext Fan |  | Ext Fan
d679b59a-6b01-428f-9641-3a945e89ba6a | section | Pre-Start Ext Fan
7f2f2857-a6bd-46a3-896d-743c07dde96c | checkpoint | Area clear, access good, enough space for install
0f57a65c-e49f-4be0-ab7c-9c54ab87b180 | checkpoint | Duct Route clear, Penetrations complete
835cfe88-e126-4fd4-b2f6-393162391fde | checkpoint | Nogs/Supports in place
9b522537-8508-4098-88c0-4096e19d3bed | section | First Fix Ext Fan
50ac5c41-7bfd-41a1-a2a9-dcfb39ed73d8 | checkpoint | Fan installed straight and level and correct orientation.
02df205c-91e7-4fb9-9301-0a8db37175f2 | checkpoint | Fan or Cowl sealed to Upstand
0b01e425-f0e1-49d8-b518-8936b4743cbe | checkpoint | Correct Fan installed
da37744a-c80d-43aa-922b-f162e3431c6d | checkpoint | Fan serial No. recorded
28460eb1-c459-45af-8257-1f03a7ba6cae | checkpoint | Fan seismically braced and vibration isolated
967c1516-aa84-40ba-8994-d88e73f49b69 | checkpoint | Fire dampers installed to manufacturers instructions. Drop tested where applicable
11d4ef5b-42c6-40a4-9575-de30459dbfa1 | checkpoint | Breakaway joins either side of fire dampers
10248970-20b8-4ef6-a35b-5c1debec7aa9 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
b73db78a-764a-46e3-94c8-4bd13b6e522c | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
3852257a-3638-412b-a987-17db484ed176 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
f5dcb943-3a83-4e1f-96d2-aa8262518168 | checkpoint | Balancing Dampers locked open and accessible
f4947b68-65c3-4df2-b93e-fd9f954a5283 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
48f197c4-1df8-4d1d-8891-6b799d15109d | checkpoint | Flexible ducts taped then cable tied
12f29307-5d5e-4dc4-a2e8-1e07e6862da2 | checkpoint | Supply cable installed correctly, protected and secured
8846315a-e7cf-4727-917a-75fae9c680dc | checkpoint | Supply cable type, size and manufacturer
c321bb95-1d53-4f3d-92f7-b4f2c1f0db6b | checkpoint | Circuit protection type and rating
8425d196-22f9-44cf-8a9a-9a05a896cac4 | checkpoint | Correctly rated isolator installed to standards
81590a31-060a-4a00-a0b5-26feb85cf11f | checkpoint | Interconnecting cables correctly installed and protected
2302f250-db21-4bae-9d9b-ea6aa81c1ba1 | checkpoint | Control cables correct rating and type
5e621768-1da6-4fe8-95b3-dd077a0b84f4 | checkpoint | Screened cables drain to earth as per specifications
4c24b7a7-0bbc-405d-aed5-bef3d037dc09 | checkpoint | Control cables maintain minimum distance from power cables
0a5a684d-0f3b-4f9a-9871-6204a4beec3e | checkpoint | Daisy chain loops complete and correct
ec758172-b6ba-46cb-a521-440d11738059 | checkpoint | Remote controller cable installed
5eb294ae-eff4-414e-b23d-99f6fe008ca0 | checkpoint | Building Access Panel requirements are marked and given to builders
2f62319d-51a9-4794-80b8-fc54e10a9b97 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
cbcd6616-1f68-4cd6-8f1c-dd4e8786dcca | section | GREENSTAR
bd160c0e-4bd5-408f-b2f3-d5e480266b99 | checkpoint | Construction Drawings amended for As Built Production
be5d8ec4-f261-4679-8289-4afe95be2b71 | checkpoint | Materials Used - Greenstar rating verified (DETAILS RECORDED IN MATERIAL SCHEDULE)
3de60ae4-d74c-43d1-8175-c3a86cb6e3bd | checkpoint | All open ducts sealed off with plastic film or similar during Construction (PHOTOS REQUIRED)
b6720c80-f2db-4ed5-aacd-2d2e3acfa520 | checkpoint | All open ducts cleaned and use of covers during Construction (PHOTOS REQUIRED)
f412effe-8718-481d-ae52-04d300b304b6 | checkpoint | The system has been cleaned prior to occupation and use in accordance with credit requirements.
6e9d36c4-2a5b-4ed3-bc62-09838aaa239d | checkpoint | Noise Level (LEVEL RECORDED IN EQUIPMENT SCHEDULE)
e300d867-b596-4f0d-acbc-96cbeb30570e | checkpoint | Sources of pollutants, such as printing or photocopy equipment, kitchen stoves or vehicles are compliant with minimum emissions standards or are not present within the nominated area in the project.
3f7a4a4c-3080-48ad-b1b1-9257e4eb0f01 | checkpoint | Sources of pollutants are exhausted directly to the outside of the project in accordance with a recognised standard; and/or physically separated from building occupants.
6a597a30-8a66-4a97-b915-e1e6f2b9e6b9 | checkpoint | Commissioning Completed with Independent Commissioning Agent
4fda92e6-2af5-4dab-b330-b63e6af1f278 | checkpoint | Commissioning Data
eb9b4490-01cf-4893-bfc7-57749a034760 | checkpoint | Continuous System Test Run for 1 calendar week
38b9e6b5-5a05-49fc-b325-60351e0b7f15 | section | Second Fix Ext Fan
3a4bab0a-6802-4594-a071-76882d775fe0 | checkpoint | Grilles installed square and level
476af3ac-9834-4116-9755-aee3214005ef | checkpoint | Flexible ducts taped then cable tied to grilles/boots
677c4709-fde8-4b2a-a2a9-3d210b76d7cd | checkpoint | Boots sealed to grilles
16f21058-930f-4279-bdc9-25a106f69833 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
4e73edbe-29a6-4773-bf8e-f3161c306176 | checkpoint | Controllers fitted off
b8069e05-ee16-4b5e-a1c9-299e187aa525 | checkpoint | Power fitted off
d478769c-c964-4c5e-80ec-6f9ed3677886 | checkpoint | Area left clean and tidy, finger prints removed
88be6fbf-5c23-445b-bac7-9b0932af036d | checkpoint | Plant and controllers labelled
bf301004-2e42-4ae7-95f1-a09c569fcd6c | section | Commission Ext Fan
ea9d2404-c5fb-4021-b004-5448e421ab71 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
07e8654a-1f0a-4f37-b79e-73c6e05b6557 | checkpoint | Electrical testing complete
f3d0a69d-c973-43b1-9415-b7a865b31710 | checkpoint | COC issued
8098e6c5-0810-4cbf-ae46-f3685aafee52 | checklist | HRV |  | HRV
32142400-a237-4440-b1cc-72a846be6727 | section | Pre-Start HRV
f7debe70-d619-4c12-9034-d705bce0ee37 | checkpoint | Area clear, access good, enough space for install
5ac540cf-8c6c-4d7f-a418-59d1efcc7cc9 | checkpoint | Duct Route clear, Penetrations complete
df104fe0-9e7b-45d1-94a5-321d1359da2b | checkpoint | Nogs/Supports in place
66edd211-353b-4d18-8e2c-b330fb864606 | section | First Fix HRV
ad221a4f-28bd-4561-9465-c33504b76534 | checkpoint | Unit installed straight and level and correct orientation.
ab254985-e543-42be-874e-869f5c0cdb7f | checkpoint | Unit bolted in place, seismically restrained and vibration isolated
8cfe99d8-587d-4cbc-bb15-c86ac7585530 | checkpoint | Correct Unit installed
63cf54f3-5905-4386-8d32-c2645f1543ac | checkpoint | Unit serial No. recorded
8ab4dd5e-4b52-4ff9-88c1-35be1be7ceae | checkpoint | Good access to Service access panel
e30d6377-805e-48cc-9dbc-f7062aedbd63 | checkpoint | Fire dampers installed to manufacturers instructions. Drop tested where applicable
6a535aba-2f7c-4c06-9af2-75cae49e6c49 | checkpoint | Breakaway joins either side of fire dampers
075cd727-8eb8-4179-addc-e71a0310496f | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
b2cbd56a-eb46-4102-9c75-4e220b7e0ba2 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
99096729-1b69-4774-a455-6cd46ef28c97 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
5bc1ece7-4480-4fb2-a61a-3903d9379546 | checkpoint | Balancing Dampers locked open and accessible
1a4c0e25-6316-4171-b3bd-e070d800f62e | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
71298ff5-fb96-4ea3-87ea-afcde5f0f555 | checkpoint | Flexible ducts taped then cable tied
0f425e59-9780-4551-b1b4-21d3b732fbc6 | checkpoint | Condensate drainage connected to drainage trap utilising transparent flexible pipe.
ac60b752-b2a6-4d5a-a012-923320de11ae | checkpoint | Condensate drainage connection secured with clamps to AHU pipe and drainpipe.
cc91324a-8a7c-4731-a1cd-5ac3475c8afb | checkpoint | Supply cable installed correctly, protected and secured
5c1c21f4-e66e-4452-86a6-701479096b52 | checkpoint | Supply cable type, size and manufacturer
777b19ef-fe74-41ee-a5bd-50d8bfc71e2f | checkpoint | Circuit protection type and rating
b1a26795-11fe-40d2-8140-b7e83a6082df | checkpoint | Correctly rated isolator installed to standards
5fff7ac6-5fa6-45dc-9769-e4e58369f932 | checkpoint | Interconnecting cables correctly installed and protected
71d75b83-e34d-4225-9c4d-ee67785056fe | checkpoint | Control cables correct rating and type
34a494b7-b674-45a3-9284-6ecb87be7d3b | checkpoint | Screened cables drain to earth as per specifications
a427239c-f24d-48b8-8a44-1ae71d771901 | checkpoint | Control cables maintain minimum distance from power cables
e84e81b5-0e25-4ea3-93fa-3a16317635d5 | checkpoint | Daisy chain loops complete and correct
269d39b3-bd33-4440-be41-8ac636ae62ad | checkpoint | Remote controller cable installed
8be2003f-8d4a-4a54-82e3-335ed1c48bf4 | checkpoint | Building Access Panel requirements are marked and given to builders
31409c2d-2865-4baf-8932-b2aec8eca230 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
afe55be4-ed9f-4ea2-a771-99642eacf55b | section | GREENSTAR
fa21048f-f07d-48ed-8487-f7f5faa8a33f | checkpoint | Construction Drawings amended for As Built Production
9a28786e-ae6d-47b6-b212-9f9eac1e8e1a | checkpoint | Materials Used - Greenstar rating verified (DETAILS RECORDED IN MATERIAL SCHEDULE)
9eb0db32-1578-4598-bad7-4a4a0477e31a | checkpoint | All open ducts sealed off with plastic film or similar during Construction (PHOTOS REQUIRED)
63bf4777-96cd-4fe9-ad29-8b89bee96406 | checkpoint | All open ducts cleaned and use of covers during Construction (PHOTOS REQUIRED)
7534ad8c-7087-42b2-8b8c-292e6f9a1a92 | checkpoint | The system has been cleaned prior to occupation and use in accordance with credit requirements.
d6d9e3ac-0704-4c25-a171-16dd897b71b3 | checkpoint | Noise Level (LEVEL RECORDED IN EQUIPMENT SCHEDULE)
f6cabe21-6213-4199-b362-6596ebe2e75e | checkpoint | Commissioning Completed with Independent Commissioning Agent
38bc252f-c641-4905-8bdd-1db43084859b | checkpoint | Commissioning Data
6fbda0f3-b383-4e90-9378-3300f8e95f5e | checkpoint | Continuous System Test Run for 1 calendar week
5112738e-0e9a-4ad8-b26c-d460940614e9 | section | Second Fix HRV
10ecf1f8-d4ee-41e5-8550-df8afb4258e3 | checkpoint | Grilles installed square and level
9cf7cecd-71a2-430c-aa27-c4f517ddc453 | checkpoint | Flexible ducts taped then cable tied to grilles/boots
b08bddbf-39ba-4880-9956-a31c6ee12525 | checkpoint | Boots sealed to grilles
53019a20-bf4f-48af-97e5-853ba6f35a7e | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
c6400581-d62c-4d8b-9c40-cf2142ad5433 | checkpoint | Controllers fitted off. Heater Bank THT set
83456047-9e2f-4bdb-b744-f95bb548c40e | checkpoint | Power fitted off
48c3daf1-cdb6-45eb-adb6-713a4239b206 | checkpoint | Area left clean and tidy, fingerprints removed
f4b53507-48da-4e42-8c7d-c36cbf2a6007 | checkpoint | Condensate drain - Test and ensure no leaks
97581607-bba1-429a-87a0-3981c5a01528 | checkpoint | Plant and controllers labelled
1b23e641-36b6-4ef1-ad54-1421f22e97ad | section | Commission HRV
8106e327-3080-4e98-ad5e-4a5e6cae3404 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
21e58db5-cd23-4ef0-b2ce-41139f2f7d21 | checkpoint | Electrical testing complete
cd686b15-b8d7-4957-8396-53547140cfc1 | checkpoint | COC issued
f5794c79-f4c0-4455-bca2-509a7eebb7c0 | checklist | Kitchen Ext Fan |  | Kitch Ext
50fce0ac-75e1-4a39-a2a7-268ec9c84c61 | section | Pre-Start Kitchen Ext
7d86381f-cddf-41ce-9332-1f84af57a53c | checkpoint | Area clear, access good, enough space for install
4573bfc3-48f7-4ca2-b0e4-b779ba428206 | checkpoint | Duct Route clear, Penetrations complete
edcc518d-12a1-477e-9fd2-868a48ababc3 | checkpoint | Nogs/Supports in place
ea18ef9e-b4d8-485a-83af-0fc3588eac3e | section | First Fix Kitchen Ext
4bf0765e-265d-4b8c-a331-ce734edef301 | checkpoint | Fan installed straight and level and correct orientation.
93fafcbc-1f37-4d51-a4ab-b5edbdf46fac | checkpoint | Fan or Cowl sealed to Upstand
dca62bfb-06e2-4c68-bdd4-9ba8ab353d75 | checkpoint | Correct Fan installed
0ef4fbc7-be39-4b7a-9290-834b3afadf77 | checkpoint | Fan serial No. recorded
74d278b8-ad00-4522-92d1-629c77de4fc4 | checkpoint | Fan seismically braced and vibration isolated
9e57852a-b4cb-4fb5-9914-c7760d53ad78 | checkpoint | Fire wrap installed to manufacturers instructions
0c7d12f8-ede0-466d-a292-2e3873d88975 | checkpoint | Access Panels in duct for cleaning
8a728aaf-c105-437e-93eb-da8c71362c3c | checkpoint | Heavy Guage ductwork used
754e69c5-00ef-4199-ab1d-37c3d24fba86 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
a5a2eedb-8b2b-41a9-b6df-78112f785347 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
c8aed2b7-8a22-47ce-ac0b-6ccfa4f434bd | checkpoint | Balancing Dampers locked open and accessible
53df26d9-51c9-4ab7-a313-3b66f7b192ef | checkpoint | Supply cable installed correctly, protected and secured
c467fbf8-eb07-49d6-bdbd-d930026caae1 | checkpoint | Supply cable type, size and manufacturer
e75e3b3a-41b5-4f06-abff-24ba084e6fe9 | checkpoint | Circuit protection type and rating
df0f18c2-6b05-45da-aa0a-d69029251748 | checkpoint | Correctly rated isolator installed to standards
0895c340-b88d-4333-8f18-15cee6e0c963 | checkpoint | Interconnecting cables correctly installed and protected
b3277100-99ab-4bac-b663-be064ec31833 | checkpoint | Control cables correct rating and type
a035e378-51c0-419b-9ab0-9611958fd616 | checkpoint | Screened cables drain to earth as per specifications
a76287b4-17cc-4cf4-b742-b1f066f44f8d | checkpoint | Control cables maintain minimum distance from power cables
24d3423e-f30d-458e-8895-5856ecb83b40 | checkpoint | Daisy chain loops complete and correct
437c432f-9203-46f4-8417-2212d2568293 | checkpoint | Remote controller cable installed
2a37497f-05db-43f6-b480-48e8d3712d5b | checkpoint | Building Access Panel requirements are marked and given to builders
b2d5b411-6a17-4909-a3fe-78d50c62a26a | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
8fcb18d9-f038-4305-8b50-b8b7defaea7e | section | GREENSTAR
33279835-cfb9-4f30-99f3-9612485d2abc | checkpoint | Construction Drawings amended for As Built Production
97b590e7-ad1a-4dcb-a31f-8005091165b5 | checkpoint | Materials Used - Greenstar rating verified (DETAILS RECORDED IN MATERIAL SCHEDULE)
443c5622-0680-41e4-93e3-bc4c9cde5609 | checkpoint | All open ducts sealed off with plastic film or similar during Construction (PHOTOS REQUIRED)
8a2f6db3-405d-44c9-9f5f-79f5639aea4e | checkpoint | All open ducts cleaned and use of covers during Construction (PHOTOS REQUIRED)
628f27d0-d8b5-4b91-b761-f2e8f6080d19 | checkpoint | The system has been cleaned prior to occupation and use in accordance with credit requirements.
342bd415-f08f-49d5-9076-9582e123f7d1 | checkpoint | Noise Level (LEVEL RECORDED IN EQUIPMENT SCHEDULE)
d0cc6fa9-2eeb-49ee-b765-3bac0ef52f07 | checkpoint | Sources of pollutants, such as printing or photocopy equipment, kitchen stoves or vehicles are compliant with minimum emissions standards or are not present within the nominated area in the project.
1ac14313-e372-45b8-a886-1f11ff201052 | checkpoint | Sources of pollutants are exhausted directly to the outside of the project in accordance with a recognised standard; and/or physically separated from building occupants.
6324aa84-5000-4846-86bd-42661f2caf51 | checkpoint | Commissioning Completed with Independent Commissioning Agent
18780fdc-d055-4db7-a7e7-e8e40d46cafb | checkpoint | Commissioning Data
f758c8cf-efbc-4125-9723-57977375beb4 | checkpoint | Continuous System Test Run for 1 calendar week
a6dcd687-b01e-4ce5-b85e-f5aa32543b16 | section | Second Fix Kitchen Ext
e5e941fd-7a6f-4ff9-b411-fb8bab9448c0 | checkpoint | Hoods installed square and level and seismically braced
e534dd40-618c-48e1-b161-71c3e35d4511 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
d199307f-ba69-41b3-98d7-3110372177e3 | checkpoint | Controllers fitted off
02976223-370f-4694-bbfa-a99bdfded473 | checkpoint | Power fitted off
a9163c00-be4a-438a-b56c-cbb5552b76e7 | checkpoint | Area left clean and tidy, finger prints removed
781874f3-9329-442c-8eca-49a735f89a64 | checkpoint | Plant and controllers labelled
2b631f9e-7a87-435f-bcca-1ae8ab18e6bf | section | Commission Kitchen Ext
6e58b5f5-3dc6-44e7-adfc-43d83d9f34df | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
7a2d4f9b-9583-4455-af82-e8329e28cbc8 | checkpoint | Electrical testing complete
c7431663-014f-4203-b859-9ad4a53010d6 | checkpoint | COC issued
5ffffc27-00a4-4082-8a02-2dfd50999a04 | checklist | Radiant Heater |  | Radiant Heater
12f20e5b-12a5-44a0-850f-c08bd8f8f911 | section | PRE-START RH
f4ef9ac2-3dfe-4c64-a671-21a8636c0b1d | checkpoint | Area clear, access good, enough space for install
1e2a6105-a67e-4001-82fd-ec28f6f12d41 | checkpoint | Nogs in place
fef5860c-556d-43dd-87dc-0535147a0828 | section | FIRST FIX RH
e4d6febe-33dd-4d72-8de6-1f98be2828bf | checkpoint | Power Cables installed
3656ef52-0031-4440-8b97-98c91d7a2fc3 | checkpoint | Control Cables installed
2976559a-74ef-4514-8aaf-da7ae9f71eae | section | SECOND FIX SPLIT HW
6be79082-98da-44a4-b8f1-7db62cde9401 | checkpoint | Correct unit installed. (Insert Photo)
be77c713-9ffd-4be5-9c11-67267b2b032f | checkpoint | Heater serial no. recorded
183a82eb-bd3e-44f9-9365-3ab23964f18f | checkpoint | Unit installed flush and square
01f96c27-1290-48a5-a894-efb6c83fba67 | checkpoint | Area left clean and tidy, finger prints removed
3c387aa3-e0de-44e6-8ff1-aa09d242336b | checkpoint | Controllers fitted off
077d8ce1-4f58-4509-9443-53910c6d7598 | checkpoint | Power fitted off
478870cf-c982-43aa-a64d-f1a88254e8c0 | checkpoint | Supply cable installed correctly, protected and secured
bdfa7268-609e-4c64-953a-c27d696f3766 | checkpoint | Supply cable type, size and manufacturer
40e20a45-bd84-471f-a434-f525c0ece8cd | checkpoint | Circuit protection type and rating
c2edda05-8789-4ba0-9b42-19b4baef9fa5 | checkpoint | Correctly rated isolator installed to standards
46a60e78-92df-4440-9f1b-a5df622fc2ab | checkpoint | Interconnecting cables correctly installed and protected
a9486265-487c-4f8a-9b0d-7b17a11672d3 | checkpoint | Control cables correct rating and type
2dddace1-b5d2-4ef1-9d02-10ce961a820c | checkpoint | Screened cables drain to earth as per specifications
cd7dd8f1-ff82-4bae-80fe-688452d5da3e | checkpoint | Control cables maintain minimum distance from power cables
cfbcc707-08b3-4df7-b651-8da0b096c41f | checkpoint | Daisy chain loops complete and correct
1d8ca41c-0a16-413f-86ab-45ee07c0ff73 | checkpoint | Remote controller cable installed
acd114ed-dd76-4fbd-be2a-4e55f2487ec3 | checkpoint | Plant and controller labelled
61e5c643-68bb-4d72-b864-9aba03ba2031 | section | GREENSTAR
e88168b8-26c7-4f2e-be70-1cb64b9a050c | checkpoint | Construction Drawings amended for As Built Production
83b4c98b-f7d1-474f-b68a-5eb64337f8c0 | checkpoint | Materials Used - Greenstar rating verified (DETAILS RECORDED IN MATERIAL SCHEDULE)
531a9c95-0ecf-4e35-876c-108955c4da4c | checkpoint | Commissioning Completed with Independent Commissioning Agent
70146cef-a3ad-477e-8dd6-bb6b47ba5913 | checkpoint | Commissioning Data
aec15978-9003-4109-994d-2d449dc5136e | checkpoint | Continuous System Test Run for 1 calendar week
e73f62ea-dcbf-4cc5-805e-70f0ec35d46e | section | COMMISSION RH
6fc954af-3e70-4890-83d9-7b100a0d8abb | checkpoint | Commissioned and Paperwork submitted
edd024c5-81a1-4fb2-a2c6-62b634fa0ee5 | checkpoint | Electrical testing complete
eb53abec-d0a8-4e5f-89a8-7374d2ff8b98 | checkpoint | COC issued
b211340b-e0af-452f-9a40-6c0a5f08ae1d | checkpoint | Plant and controller labelled
e9d47cf5-c8e2-425b-aa59-55b9b987ec84 | checklist | SA Fan |  | SA Fan
904f4ce6-15a9-4fab-b67d-84e2bb40e952 | section | Pre-Start SA Fan
5b5190f3-342b-43b0-936d-57c94285eab8 | checkpoint | Area clear, access good, enough space for install
94bd023a-fde5-46fb-ae6a-dd92b386fdad | checkpoint | Duct Route clear, Penetrations complete
8113e3e2-bb6f-4aca-b048-783582155b31 | checkpoint | Nogs/Supports in place
1a9284cb-85a7-4b89-9a7b-b7915e26ee01 | section | First Fix SA Fan
11024a2c-ad71-4fa9-ae44-a8f2a8227fd5 | checkpoint | Fan installed straight and level and correct orientation.
a7b963c8-2f0d-4d30-8189-da422c0557ba | checkpoint | Fan or Cowl sealed to Upstand
7e0fe7a9-0f33-4f7e-aef5-4aed2355043a | checkpoint | Correct Fan installed
f6b2dabb-2709-4cba-bf81-d7cf9cb88672 | checkpoint | Fan serial No. recorded
bd4fc685-9f2c-4984-a373-47dbe101b196 | checkpoint | Fan seismically braced and vibration isolated
f7e8fb70-dc1f-487b-a56c-341d11557400 | checkpoint | Heater Bank installed to Manufacturers instructions
a6c9e132-9410-4509-8a1e-bbfdd795dbfc | checkpoint | Fire dampers installed to manufacturers instructions. Drop tested where applicable
4dc5a20a-8f5f-4124-88f6-38d7e14b967e | checkpoint | Breakaway joins either side of fire dampers
602d2997-781c-43b0-991e-a9da5e3830cc | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
7040da28-2d87-4a88-afae-0f922d0b76d9 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
dafbc2d3-c310-47bf-ac48-b756236a0833 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
95053c11-35ce-43f0-8054-377b917e2f0d | checkpoint | Balancing Dampers locked open and accessible
1d605295-7436-4eba-aae1-75ec9f5d23a8 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
5a5775d3-4ff0-46e7-88ec-99c9c1f732d6 | checkpoint | Flexible ducts taped then cable tied
983373f3-f41c-4263-9792-6929ab1940ce | checkpoint | Supply cable installed correctly, protected and secured
71157f41-742c-4863-bf82-244a981373c2 | checkpoint | Supply cable type, size and manufacturer
cc497c5b-d7fb-450a-a2e8-ea9db412881c | checkpoint | Circuit protection type and rating
da623484-bc9c-40d1-b569-4f4f69c3ccd5 | checkpoint | Correctly rated isolator installed to standards
29f494ef-d533-4bba-82bd-57a83d759215 | checkpoint | Interconnecting cables correctly installed and protected
752291f0-80d4-4c95-854b-51b61419e302 | checkpoint | Control cables correct rating and type
98ac15a3-ed0b-442f-98ef-5d1d558eb980 | checkpoint | Screened cables drain to earth as per specifications
501254b9-3720-4abf-a1a2-161e88e6aa2f | checkpoint | Control cables maintain minimum distance from power cables
07171bf0-f1e6-4353-b3cd-1a3161c538f6 | checkpoint | Daisy chain loops complete and correct
bf496687-2715-43c3-b4d7-ae4441bc0d08 | checkpoint | Remote controller cable installed
55268940-582d-440e-b1c4-04519ca069ad | checkpoint | Building Access Panel requirements are marked and given to builders
9c836b79-1a60-469c-a3fc-cbefe2d0e83c | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
93236a24-c8cf-4a09-86a9-6a87955bf59f | section | GREENSTAR
e7942850-97e0-4e71-b439-a2557353d5cd | checkpoint | Construction Drawings amended for As Built Production
a240f0eb-6ca2-4fcb-b3e8-6576016b92ef | checkpoint | Materials Used - Greenstar rating verified (DETAILS RECORDED IN MATERIAL SCHEDULE)
9820b3dd-fd46-47a5-b868-c87b7c522a3c | checkpoint | All open ducts sealed off with plastic film or similar during Construction (PHOTOS REQUIRED)
85e70363-1ed2-4c98-92e9-6cd31e93e516 | checkpoint | All open ducts cleaned and use of covers during Construction (PHOTOS REQUIRED)
74d42978-2e08-4a74-9db1-9e909d8db4fb | checkpoint | The system has been cleaned prior to occupation and use in accordance with credit requirements.
fcc6be1c-8917-4fbd-8468-ea3e62728c42 | checkpoint | Noise Level (LEVEL RECORDED IN EQUIPMENT SCHEDULE)
6cff466d-775b-48ba-85e1-e7fc202a4502 | checkpoint | Outdoor air is provided to the nominated area at a rate 50% greater than the minimum required.
5b8f3f1c-c895-48bd-b154-04f6b60be8b6 | checkpoint | Outdoor air is provided to the nominated area at a rate 100% greater than the minimum required.
e3eab900-0b75-41c0-aff1-eb690cb39fa1 | checkpoint | Outdoor air is provided to the nominated area at a rate so that CO2 concentrations are maintained below 800ppm controlled by the CO2 Sensors
180f3174-3446-4706-acd8-ea53b31b4367 | checkpoint | Outdoor air is provided to the nominated area at a rate so that CO2 concentrations are maintained below 700ppm controlled by the CO2 Sensors
493b8e82-ac60-4b02-816c-c5a2c836acc7 | checkpoint | The project is naturally ventilated, and the nominated area meets the requirements of the recognised standards.
482c255e-b0f9-4d70-baf1-099224db555a | checkpoint | Commissioning Completed with Independent Commissioning Agent
56654b7e-b99f-41d8-8e79-17fd7e8b3041 | checkpoint | Commissioning Data
07b6762a-e018-4d7c-9c10-33bee529dcc6 | checkpoint | Continuous System Test Run for 1 calendar week
d3aa2372-8b61-4415-bc16-401467089766 | section | Second Fix SA Fan
dab2c465-5112-4fbb-a80e-3fdec48fe442 | checkpoint | Grilles installed square and level
1ccae033-9cf9-4c03-84ec-07226993361d | checkpoint | Flexible ducts taped then cable tied to grilles/boots
8236b564-5575-4dea-abaa-e183c1a22f59 | checkpoint | Boots sealed to grilles
381c6cc5-de97-40b6-932b-85fa2362bdf0 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
ce1a06bb-d35e-498e-b689-b891e318e0f5 | checkpoint | Controllers fitted off. Heater Bank THT set
852d324e-9d06-4f3b-bd0e-c7e2ad751bb5 | checkpoint | Power fitted off
04ee2c0c-35ea-46e0-b163-31559a457559 | checkpoint | Area left clean and tidy, finger prints removed
c4950fa3-2d4b-48a5-9da8-1c57b161db75 | checkpoint | Plant and controllers labelled
9a4e45a9-f177-4f55-a49c-ce5054c81421 | section | Commission SA Fan
f0c55638-c411-44a1-a32b-26d1e35aeebd | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
e021d824-b35d-41c8-aadd-55f2e2309066 | checkpoint | Electrical testing complete
7fb78bd8-674e-47e6-9c10-92f476d80bca | checkpoint | COC issued
7bf62183-b301-497c-9b20-f1507448e96e | checklist | Split HW |  | Split HW
b184d96e-fc95-4f76-9229-0bb6191942ca | section | Pre-Start HW
a26a768b-899b-435e-b4bc-4a5351bb6614 | checkpoint | Area clear, access good, enough space for install
006d433d-1528-4249-8106-9d37e5d1e98b | checkpoint | Area/base ready for outdoor unit
bd66d69c-7f85-4877-a79e-a86c385351d4 | checkpoint | Any required drains for outdoor unit in place
90995520-c512-423a-8e02-fbafe77e4fea | checkpoint | Pipework route all clear, penetrations complete
f3500ad0-1f87-4a50-90da-ca6e1dd40881 | checkpoint | Nogs in place
8cc1fb3a-5dcc-4791-9896-ce0433c69a67 | checkpoint | Drain 1m from Indoor unit location by plumber
bf0ff8be-e1b1-4d93-be3b-673ab2e778ae | section | First Fix HW
dd592c6a-f9d3-4627-9513-48e8f7640134 | checkpoint | Pipework Insulated complete length
3d43163f-1f04-48a9-8882-baf6406a7bcf | checkpoint | Insulation Joins Glued and taped
b0640bf4-9fa5-48fb-adaa-df45b9fea484 | checkpoint | Pipework supported incl any seismic restraints
c5e67cc4-e004-4764-a2f8-56c56c5d7dc9 | checkpoint | Flare connections/nuts insulated
d27f6f07-511a-4d41-8502-a91e64dc8e19 | checkpoint | Drain installed and insulated
5ade8590-6e2f-4ddb-9655-fa935155fe3a | checkpoint | Installer confirmed pipework under pressure (date/pressure recorded)
dd35e1a3-547c-45ec-b417-3cbc00c0f817 | checkpoint | Installer confirmed Nitrogen purged during all welding
8c5ffed7-e59b-4b16-874b-de17b697c2ab | checkpoint | Pipe lengths are recorded accuratley
0c7a1fff-6502-411f-86f5-ef8137ec86b2 | checkpoint | Supply cable installed correctly, protected and secured
ae94fc8e-696c-43ef-83be-0870d0e61f11 | checkpoint | Supply cable type, size and manufacturer
dfcc9729-3070-4b86-9c1e-b2690b20b090 | checkpoint | Circuit protection type and rating
843a6722-5ed9-40d7-834b-e6bdcb8c7fb5 | checkpoint | Correctly rated isolator installed to standards
a6bd710e-8a57-41d5-afe8-9ccd4adb3160 | checkpoint | Interconnecting cables correctly installed and protected
c1db690d-f86b-4780-8a3d-793a6c8b102c | checkpoint | Control cables correct rating and type
386d863c-6436-43eb-ac87-1df9bf883d59 | checkpoint | Screened cables drain to earth as per specifications
6422b4aa-4ea3-4e17-a7ed-4012277a036d | checkpoint | Control cables maintain minimum distance from power cables
dd0117dc-2ac4-4a12-9567-d41c180ef315 | checkpoint | Daisy chain loops complete and correct
cc61faee-e76a-46e6-8602-5d87d01ddf6e | checkpoint | Remote controller cable installed
a5cace0c-e084-4161-ac0c-a6545cc6df1f | checkpoint | Plans marked up for As Builts
3e294a38-b910-46c1-abc2-7f0575503d7d | section | GREENSTAR
b16658aa-6280-4b41-bb09-1d795ad13e44 | checkpoint | Construction Drawings amended for As Built Production
134c61f3-9ab7-4a74-b2d7-f3d7dba6ce62 | checkpoint | Materials Used - Greenstar rating verified (DETAILS RECORDED IN MATERIAL SCHEDULE)
9035b94d-83f5-4a35-9282-2e1574f058e8 | checkpoint | Refrigerants - Volume and type recorded (RECORDED IN EQUIPMENT SCHEDULE)
8b51bec7-c7cd-48b7-8e1f-58edc0bb9957 | checkpoint | Refrigerant Pressure - Results sent to Consultant (RECORDED IN EQUIPMENT SCHEDULE)
d0e03e61-04f2-4126-974d-3aa6b90883e5 | checkpoint | All open pipework sealed off with plastic film or similar(PHOTOS REQUIRED)
f441e0f5-26da-49e1-9b37-0b6902472dd6 | checkpoint | The system has been cleaned prior to occupation and use in accordance with credit requirements.
e3abd7cc-14e8-4ffe-bc24-e561ab3d7b1f | checkpoint | Noise Level (LEVEL RECORDED IN EQUIPMENT SCHEDULE)
bebcca62-6c7a-4639-bb6a-4a458762cca5 | checkpoint | CO2 Emissions (RECORDED IN EQUIPMENT SCHEDULE)
ef706bc4-6128-49ec-a510-4d363cb9b93e | checkpoint | Commissioning Completed with Independent Commissioning Agent
ea1946fd-bd33-46a7-87e4-94c15ad18470 | checkpoint | Commissioning Data
a158b1ca-3b7a-4acc-b877-6b491158993c | checkpoint | Continuous System Test Run for 1 calendar week
9de91cb9-1c52-44f7-8ac7-11cf742eaecd | section | Second Fix HW
cf43bbf7-c3a5-4ad5-a8b7-14fbdbc49430 | checkpoint | System pressure checked and still holding 1st fix pressure
e53c8d6f-c88e-4ad2-8970-968ae71f380a | checkpoint | Indoor unit secure, level and tight to wall
76996a04-e085-441a-8e5a-22b90577d213 | checkpoint | Correct Indoor unit installed
f59f5d77-1d1c-469c-889c-9244a3e868b5 | checkpoint | Outdoor unit secure and level
30ecf5fc-ce8f-4df5-8680-979ad76972b9 | checkpoint | Correct Outdoor unit installed
64c3f1a7-6579-4c5f-8b0c-e17b3ebc0847 | checkpoint | Flare connections/nuts insulated
4b997c13-04fe-422b-a94d-8bd5e070363e | checkpoint | Indoor unit serial no. recorded
c37f230a-474e-4cbd-925d-8f351381922c | checkpoint | Outdoor Unit serial no. recorded
7cbf33f4-ed1a-4f6f-9be6-17eed256ba88 | checkpoint | Installer confirmed drain tested
270fb7f9-0915-4750-a161-ef738e2251df | checkpoint | Controller installed
d121e50f-f00a-43c4-b854-e5b2984b2aae | checkpoint | Area left clean and tidy, finger prints removed
874534cc-1b6b-497b-973e-b9bd040e5657 | checkpoint | Plant and controller labelled
d7c7261f-4917-4b3a-b8cd-9a9f18b9136f | checkpoint | Access for future maintenance all clear. Filter can be easily removed
203c2488-43f1-4c39-bd46-f2d11637e5d5 | section | Commission
600c7341-c51b-4f74-898f-176157f841ca | checkpoint | Installer confirmed evacuated to Manufacturers instructions
943522e3-75db-4bde-a63c-4e23d45f793a | checkpoint | Installer confirmed commissioned and paperwork submitted
0bf37c5e-4d34-4599-b575-2c3b5d7ec223 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
aec149a3-c0f2-4a24-b06b-fb689c5cdfa9 | checkpoint | Electrical testing complete
dda7253c-41ab-4111-bf87-d7fa4e891f95 | checkpoint | COC issued
a1bad560-ebb0-4219-8414-5c0f0e580d12 | checklist | VRV Bulkhead |  | VRV Blkhd
e6ac4cf1-d5b6-4faf-833c-37a3301914f1 | section | Pre-Start VRV Blkhd
350b6566-4db7-45a6-a1aa-00de38e3d084 | checkpoint | Area clear, access good, enough space for install
d00bf561-4929-49fa-a0c8-f73a1ac633ed | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
9545f124-3cae-458e-a696-a7f2e9219189 | checkpoint | Ply fixed to ceiling
db0bf28f-6a0f-4397-b5d0-1ec663a60e88 | checkpoint | Bulkhead frame built
582a1992-0ac2-41a9-9064-e2c2fabb8f02 | checkpoint | Grille openings framed out
1214f735-22f9-4359-9c5d-887cc24691d3 | checkpoint | Drain 1m from Indoor unit location by plumber
75d030a7-24c6-4ee5-90bc-20131f8a8016 | section | First Fix VRV Blkhd
8385361f-3cc6-4f8e-8357-64e2586f9163 | checkpoint | Pipework connected to BS Box and Indoor unit
70b3532a-5773-44f1-84cc-f34ea50986ac | checkpoint | Pipework Insulated complete length
e56cbe38-04c9-49f5-97c1-d9683ccc9aac | checkpoint | Insulation Joins Glued and taped
8c9d8631-bd5e-47a8-ad70-11a942438b91 | checkpoint | Pipework supported incl any seismic restraints
ce2669d3-adcb-48f8-931b-c4976c93d290 | checkpoint | Indoor unit level, secure, vibration isolated and seismically retsrained
34c40e5d-0512-4a29-baa7-88556389b337 | checkpoint | Correct Indoor unit installed
ef122db3-253e-4b9d-8fd4-43ad4b854564 | checkpoint | Flare connections/nuts insulated
0059e06f-8b72-4679-8291-fb3723d667a6 | checkpoint | Indoor unit serial no. recorded
59728367-8347-4414-90a3-4279bdfc020d | checkpoint | Flexible duct installed correctly
fd2ec906-cc09-45f0-b8e0-43636a27bbd5 | checkpoint | Drain installed and insulated
6df2ad59-12c6-413e-8e6e-c6aaacaf7dfb | checkpoint | Installer confirmed pipework under pressure (date/pressure recorded)
a646f68e-9b0b-43cd-8032-d95b0a1fb686 | checkpoint | Installer confirmed Nitrogen purged during all welding
27195824-7b9f-42d6-b182-2aa17b6cf8bd | checkpoint | Installer confirmed drain tested
a60819ee-09ad-4947-a8d4-62396b70b421 | checkpoint | Pipe lengths are recorded accuratley
65f7ae28-ea28-4ca1-afa7-3f2201824cbd | checkpoint | Supply cable installed correctly, protected and secured
55b019fa-b50f-42e6-b36f-d30ca0724300 | checkpoint | Supply cable type, size and manufacturer
fb32a4d9-b0b2-45ac-b6c7-e1ca85e78f1d | checkpoint | Circuit protection type and rating
62a319eb-41c7-40cd-84ed-502a3603e670 | checkpoint | Correctly rated isolator installed to standards
38c49ce7-b22b-4fa9-9c4b-d04dad0fa7ad | checkpoint | Interconnecting cables correctly installed and protected
ed725ed4-cad0-478d-84bb-d36222abb09c | checkpoint | Control cables correct rating and type
a6b0898d-6549-4c8b-a52b-fdfe95f32c06 | checkpoint | Screened cables drain to earth as per specifications
99f0a160-7ff1-4066-bbff-c4ebd8aaa015 | checkpoint | Control cables maintain minimum distance from power cables
4976d436-d66c-40fb-8ef6-9f936cfb3b89 | checkpoint | Daisy chain loops complete and correct
0f03fcdb-ded6-47bc-ad4e-88eed6fb343e | checkpoint | Remote controller cable installed
48db910c-18fa-4354-b473-8ee2a57d2ad4 | checkpoint | Access Panel requirements are marked and given to builders
68d982fb-e289-4fc7-a868-757a41d00b72 | checkpoint | Plans marked up for As Builts
e4adb00b-cf9a-4d64-a901-dd22b9e2630d | section | GREENSTAR
3d4825ac-383d-49aa-a251-76b597229c27 | checkpoint | Construction Drawings amended for As Built Production
dd253b9f-9ace-4394-804f-56f25a9070a1 | checkpoint | Materials Used - Greenstar rating verified (DETAILS RECORDED IN MATERIAL SCHEDULE)
5e000207-0ec2-465d-ba08-fc8750cb1c45 | checkpoint | Refrigerants - Volume and type recorded (RECORDED IN EQUIPMENT SCHEDULE)
7745bd6d-a36a-4a49-8483-5399182b62c0 | checkpoint | All open pipework sealed off with plastic film or similar(PHOTOS REQUIRED)
2f3d9d60-2456-4dcd-81b9-f82223890f80 | checkpoint | The system has been cleaned prior to occupation and use in accordance with credit requirements.
c2ddc690-a1ad-4deb-9b65-f4e5856c151e | checkpoint | Noise Level (LEVEL RECORDED IN EQUIPMENT SCHEDULE)
22c29734-d6f6-4d60-ada3-38958a831479 | checkpoint | CO2 Emissions (RECORDED IN EQUIPMENT SCHEDULE)
485492a4-5ed4-43de-ab1a-c9ac706a5695 | checkpoint | Commissioning Completed with Independent Commissioning Agent
4f111d26-b868-4217-8ad9-ed774dfd1b3c | checkpoint | Commissioning Data
365c9d17-afa0-43e8-b470-ca54839a7e31 | checkpoint | Continuous System Test Run for 1 calendar week
08028b11-312a-4c1d-8089-a8e9e84761ab | section | Second Fix VRV Blkhd
676096aa-ce3d-4af0-835d-e10249b056ab | checkpoint | System pressure checked and still holding 1st fix pressure
ef8add73-5b3f-4ead-8cb3-abf444827641 | checkpoint | Grilles installed flush and square
0c57355b-9f67-4dc7-9d5f-64fbcb562104 | checkpoint | Controller installed
556a8899-8ca4-4c30-9233-8676613538ec | checkpoint | Area left clean and tidy, finger prints removed
50ae8fd5-aec6-441b-82a1-e3ef78455255 | checkpoint | Plant and controller labelled
3aa546cb-8d3d-490b-9d53-8364eda43aa4 | checkpoint | Access for future maintenance all clear. Filter can be easily removed
3c0a3b54-b62c-481e-b695-fd9e5495ed0f | checklist | VRV Cass |  | VRV Cass
cdcd2ad8-a14e-4f17-8749-52da51611385 | section | Pre-Start VRV Cass
df133005-10f6-4ba1-b1fe-3d99c6619e96 | checkpoint | Area clear, access good, enough space for install
2738eab0-bd2a-43ab-9947-4305209eb715 | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
e86bbc4b-54f7-41f0-ba34-071ccb857804 | section | First Fix VRV Cass
803c5456-76d7-4a88-88db-8d13653c7783 | checkpoint | Pipework connected to BS Box and Indoor unit
c1c46721-974d-4460-b092-fee9a1500e55 | checkpoint | Pipework Insulated complete length
d1c7369e-1ec0-4d5d-bebf-f6edaa9140f7 | checkpoint | Insulation Joins Glued and taped
b580771c-fe52-416e-8b0e-961bd76472c7 | checkpoint | Pipework supported incl any seismic restraints
c8959828-f5da-445a-a0be-0c74f3ce35b3 | checkpoint | Indoor unit level, secure, vibration isolated and seismically retsrained
cd1bc2da-c186-45da-8fd2-e9f0db9ab940 | checkpoint | Correct Indoor unit installed
8acce931-8f40-493f-ae1f-5f4764a73f09 | checkpoint | Flare connections/nuts insulated
e3f9e021-1aed-4791-ac4a-6c63ec54a716 | checkpoint | Indoor unit serial no. recorded
31220bf7-4277-4faf-8cfc-01a64e481597 | checkpoint | Drain 1m from Indoor unit location by plumber
2b3cbd04-f81d-47bf-8174-15351615d6ac | checkpoint | Drain installed and insulated
9b368114-4da5-471f-bc40-c3ba4169cbc5 | checkpoint | Installer confirmed pipework under pressure (date/pressure recorded)
9a26cbb3-bb62-40f5-8f91-4f2cfb10867d | checkpoint | Installer confirmed Nitrogen purged during all welding
73c64caf-eb08-44bb-a419-ee8fdafad866 | checkpoint | Installer confirmed drain tested
0f207566-5f92-46f1-8d55-806add861a9a | checkpoint | Pipe lengths are recorded accuratley
b2fa653d-6587-44da-a62f-043a7def426a | checkpoint | Supply cable installed correctly, protected and secured
ae5f6887-51d6-4193-a9c9-75a3d5cab1a9 | checkpoint | Supply cable type, size and manufacturer
65ad3f64-02a9-4339-af26-cfc771b25ba1 | checkpoint | Circuit protection type and rating
ea4bd18a-d3f9-434e-a68f-9108ca7e90e0 | checkpoint | Correctly rated isolator installed to standards
8147c530-e38d-4df5-a7e8-22599e123f6d | checkpoint | Interconnecting cables correctly installed and protected
a35108e1-ea1e-474c-bff1-9c2536aae479 | checkpoint | Control cables correct rating and type
7d3d0f0e-22c1-4671-96ca-924a9e728eea | checkpoint | Screened cables drain to earth as per specifications
d227f5f6-4a96-40d5-94c1-ecdc9154e824 | checkpoint | Control cables maintain minimum distance from power cables
42807514-d586-442c-811f-0659c5ec4527 | checkpoint | Daisy chain loops complete and correct
622b1721-ece6-400a-9e60-83903679e07e | checkpoint | Remote controller cable installed
fe873309-6c2c-4031-8309-38e661d4f2a2 | checkpoint | Access Panel requirements are marked and given to builders
121e9e9e-07f6-452e-a245-72088bffe1fc | checkpoint | Plans marked up for As Builts
c3c6f174-7d9e-4f3e-ba10-fc2d57cb07f6 | section | GREENSTAR
9554c4c8-eb09-4d17-a19f-2d42277100a8 | checkpoint | Construction Drawings amended for As Built Production
48271c52-ce23-4516-b91e-5fb17f3da845 | checkpoint | Materials Used - Greenstar rating verified (DETAILS RECORDED IN MATERIAL SCHEDULE)
350d66aa-336c-43fe-9db5-50e7b208cd33 | checkpoint | Refrigerants - Volume and type recorded (RECORDED IN EQUIPMENT SCHEDULE)
ba783976-ccfc-4932-9471-910cb73980b1 | checkpoint | All open pipework sealed off with plastic film or similar(PHOTOS REQUIRED)
848c7c8b-f569-43ec-950c-7dd165bba2a5 | checkpoint | The system has been cleaned prior to occupation and use in accordance with credit requirements.
9bc3d626-85bf-4cd9-bcc5-661c0f08a62a | checkpoint | Noise Level (LEVEL RECORDED IN EQUIPMENT SCHEDULE)
2dcb8d31-ab7a-4092-b283-7a981195e0eb | checkpoint | CO2 Emissions (RECORDED IN EQUIPMENT SCHEDULE)
114ee17b-8d3b-4fb8-a003-b773d0a656c5 | checkpoint | Commissioning Completed with Independent Commissioning Agent
a0b3d5d9-a533-455b-baf6-08b120523d65 | checkpoint | Commissioning Data
76008388-e9d8-4410-9540-b9eee09c5b0f | checkpoint | Continuous System Test Run for 1 calendar week
177228e0-7166-48a4-b79d-d89694182a7c | section | Second Fix VRV Cass
e42b3356-d1a8-4b9b-aa80-a7e9937e91ec | checkpoint | System pressure checked and still holding 1st fix pressure
65216f7a-8904-4673-a22b-1ea469542d7b | checkpoint | Face plate installed flush and square
4c8b7185-aa93-4b04-a224-0c455ed1931f | checkpoint | Controller installed
b93aae20-5e09-47e0-8b4b-19ad94766d2a | checkpoint | Area left clean and tidy, finger prints removed
ad61830c-7c10-44a4-90b1-6a19a16e2eae | checkpoint | Plant and controller labelled
387718eb-7919-4951-b5ab-60aea65d5f6f | checkpoint | Access for future maintenance all clear. Filter can be easily removed
aaab1aed-0535-41da-a4b0-a44e557f9ca4 | checklist | VRV Ducted |  | VRV Ducted
fe5af706-0be4-49a7-88b0-0156aa84c00d | section | PRE-START VRV DUCTED
241dd6ed-a678-454b-9db8-5c1c0fd513f4 | checkpoint | Area clear, access good, enough space for install
26af2d7d-33fb-471a-8120-de5fb97b7031 | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
ccb65579-0501-4159-a002-5bd2b93ac0f9 | section | FIRST FIX VRV DUCTED
54f66743-3f42-45be-965b-ad5347d5da66 | checkpoint | Pipework connected to BS Box and Indoor unit
d3c7da66-2f83-49f5-822b-38e5b11a2dd3 | checkpoint | Pipework Insulated, glued and taped complete length
32c2a33d-380b-4ecb-a0e9-3733f9969cf4 | checkpoint | Pipework supported incl any seismic restraints
3ed8fa55-9503-4ded-9afb-2315ef9218e8 | checkpoint | Indoor unit level, secure, vibration isolated and seismically retsrained
de392a17-efbb-4a78-9305-2c3af81817cc | checkpoint | Correct unit installed. (INSERT PHOTO)
9e541ce8-616d-4377-be47-3e672ba12c02 | checkpoint | Drain installed and insulated
9a16b2e1-6e71-434b-bb0f-28c4c983c016 | checkpoint | Pipe lengths are recorded accuratley. INSERT PIPE LENGTH (IN NOTES):
e4e26d0b-9693-4838-b6ab-ce089f815c83 | checkpoint | Pipe sizes from BS box to indoor unit match manufacturers schematic
6c76eb1f-d5a2-43e7-83d6-a7e19a2cc740 | checkpoint | Supply cable installed correctly, protected and secured
cb12be19-9e03-4a7f-a670-a98ae2636296 | checkpoint | Supply cable type, size and manufacturer
4cc9b0a0-0850-4b1a-98a4-78518a502c6e | checkpoint | Circuit protection type and rating
ade989c6-4f40-4b94-a3eb-9389bc64e14a | checkpoint | Correctly rated isolator installed to standards
f7635a6f-7c1f-473f-837f-939b572aedf5 | checkpoint | Interconnecting cables correctly installed and protected
5d50599c-815b-467b-bb01-b8973f80041c | checkpoint | Control cables correct rating and type
ae94f054-cd97-4ce2-8e3b-644666642caa | checkpoint | Screened cables drain to earth as per specifications
0cdb4d66-f651-4cc0-85eb-b85652e5e746 | checkpoint | Control cables maintain minimum distance from power cables
37bb77dd-7e5e-418b-ba72-cb2890ff1b45 | checkpoint | Daisy chain loops complete and correct
4ba28600-22e9-430e-900e-996b319ebc68 | checkpoint | Remote controller cable installed
4159cf03-4c93-4297-b550-be22ba33fbd8 | checkpoint | Fire dampers installed to manufacturers instructions. Drop tested where applicable
0ad200f4-7846-4398-9280-5dd20d23a8b7 | checkpoint | Breakaway joins either side of fire dampers
2df112c4-fb31-44c7-94d1-5d48110449f9 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
cbfcfd9e-b5c3-49ff-bd9e-461f1d8c0995 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
2bfa7659-deaa-43c9-84dd-acf00bae0d79 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
46bbf133-9890-4d23-8ba2-3a54f3c50989 | checkpoint | Balancing Dampers locked open and accessible
3b2b9f77-c92e-4384-ba74-f5077f4b9d9a | checkpoint | Flexible ducts taped then cable tied
24fa5d07-4f77-46dd-986e-7698c7cad21c | checkpoint | Second fix grille and access panel locations recorded
7d564818-de9b-4c53-b746-9fe3e79f2427 | checkpoint | All open ducts sealed off with plastic film or similar
008e7558-13cc-4891-bcae-2284e8271b29 | checkpoint | Plans marked up for As Builts
61a3c62a-906e-416a-8ff4-268b7962aad7 | section | GREENSTAR
ed71881f-3a0d-42a2-b341-d88c330d2e19 | checkpoint | Construction Drawings amended for As Built Production
3c28963d-8716-408a-a6e0-46b684ed9713 | checkpoint | Materials Used - Greenstar rating verified (DETAILS RECORDED IN MATERIAL SCHEDULE)
e89a1c21-8613-4804-a55a-bb60c56012e1 | checkpoint | Refrigerants - Volume and type recorded (RECORDED IN EQUIPMENT SCHEDULE)
9a764492-5623-4724-a214-8b3bd690723b | checkpoint | All open ducts sealed off with plastic film or similar during Construction (PHOTOS REQUIRED)
3e759d4d-ab4a-4f86-9862-fc46090f9439 | checkpoint | All open ducts cleaned and use of covers during Construction (PHOTOS REQUIRED)
eca97b1a-611a-4699-9259-0b5099ca4972 | checkpoint | The system has been cleaned prior to occupation and use in accordance with credit requirements.
290eb863-6a81-49e8-8d38-634fb6b122d4 | checkpoint | Noise Level (LEVEL RECORDED IN EQUIPMENT SCHEDULE)
ba2c9cba-53cd-4ed5-9a7e-81ca289efa5b | checkpoint | CO2 Emissions (RECORDED IN EQUIPMENT SCHEDULE)
e6e59054-bbed-4927-8a8f-ccaeb8164748 | checkpoint | Commissioning Completed with Independent Commissioning Agent
5d263d8a-edc3-4649-b28d-4c753e4532d7 | checkpoint | Commissioning Data
641a4528-4fd3-4306-b866-d5cba7dd9675 | checkpoint | Continuous System Test Run for 1 calendar week
2292ce9c-9d9a-47cd-8192-30a5b88f4de4 | section | SECOND FIX VRV DUCTED
de180d24-7fa3-4c71-a6a4-ba166e5b3464 | checkpoint | Grilles installed flush and square
32707e5f-e310-4745-8a44-a4e218a3a7c7 | checkpoint | Access for future maintenance all clear. Filter can be easily removed
9bcd4ed6-f9ee-48b6-8758-00ea93a12e1a | checkpoint | Area left clean and tidy, finger prints removed
fb0ca706-e79a-4149-a40d-190c3c7822ed | checkpoint | Controller fitted off
fa0fc11d-3996-47e9-b68a-b351b002d7fb | checkpoint | Plant and controller labelled
c5836029-38c3-4efb-b75a-c5f1c996495b | checklist | VRV HW |  | VRV HW
494ca08d-d49a-42a5-9237-6d48cfb2797d | section | Pre-Start HW
34d8f181-5138-419b-99a4-c03b108e6660 | checkpoint | Area clear, access good, enough space for install
cb5ef34f-5561-4548-ac0c-c3c6debc02ea | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
f2631826-781b-4807-9744-cc12222c2dc0 | section | First Fix HW
9bf044a3-c77c-47ee-8347-9aba2e896583 | checkpoint | Pipework connected to BS Box and Indoor unit
6f32e15e-5095-4480-9227-bad57a251ae5 | checkpoint | Pipework Insulated complete length
c6f2fc9a-696f-43af-9f48-b750987f0a9c | checkpoint | Insulation Joins Glued and taped
cf45a5a6-c72e-4901-ac3e-100419c81072 | checkpoint | Pipework supported incl any seismic restraints
8d42adf4-088b-4fd3-95fb-7e759db5ee1f | checkpoint | Flare connections/nuts insulated
38255178-9a4b-4520-853c-742d6764baf5 | checkpoint | Drain 1m from Indoor unit location by plumber
a89ce497-6a11-4070-abc9-298a29e3886d | checkpoint | Drain installed and insulated
a53fee8a-fb13-4bf5-8e3a-d6dcd4691b9a | checkpoint | Installer confirmed pipework under pressure (date/pressure recorded)
1fc19f60-58c8-44ec-8f9e-378666a08994 | checkpoint | Installer confirmed Nitrogen purged during all welding
f733ce80-5d43-448c-addb-130c4943a01d | checkpoint | Pipe lengths are recorded accuratley
257fbc35-130f-4b7b-99d1-f76e87e990b0 | checkpoint | Supply cable installed correctly, protected and secured
4c317870-ea01-4d38-ae91-23047c23571e | checkpoint | Supply cable type, size and manufacturer
f93d942f-0fc5-4d86-837d-f6f1ebdcab88 | checkpoint | Circuit protection type and rating
f85202c3-7cbf-4528-a34a-2c59426c27e1 | checkpoint | Correctly rated isolator installed to standards
17966713-881c-4752-b8ec-0343a44a9f33 | checkpoint | Interconnecting cables correctly installed and protected
2403c8cf-38e9-4399-b410-fa140df79e33 | checkpoint | Control cables correct rating and type
cc0d6c6a-d498-4bdf-810e-ef24af33f8bb | checkpoint | Screened cables drain to earth as per specifications
2bad9941-a464-49e1-ab5c-f17df2c5ebd3 | checkpoint | Control cables maintain minimum distance from power cables
ebcd714d-a28e-442f-9eed-64629cdba6cb | checkpoint | Daisy chain loops complete and correct
0d4a13c3-51f0-49de-bbd3-0de457e42602 | checkpoint | Remote controller cable installed
1d603537-8274-43aa-827f-3b13544bc4c2 | checkpoint | Plans marked up for As Builts
e1569615-5db8-4d03-8177-9b822f746777 | section | GREENSTAR
0558dc25-ae9a-40fa-9da6-60131d6ae2ef | checkpoint | Construction Drawings amended for As Built Production
5dd5f841-845d-45dc-85ed-bc5a1aa07dea | checkpoint | Materials Used - Greenstar rating verified (DETAILS RECORDED IN MATERIAL SCHEDULE)
c09c63cf-d86f-45b5-a5e4-9bd5721d0547 | checkpoint | Refrigerants - Volume and type recorded (RECORDED IN EQUIPMENT SCHEDULE)
a927bc0d-ece4-46cb-ab7c-3b2f362eadec | checkpoint | Refrigerant Pressure - Results sent to Consultant (RECORDED IN EQUIPMENT SCHEDULE)
8a08f4eb-29e0-455f-ba9e-0cdbda731bde | checkpoint | All open pipework sealed off with plastic film or similar(PHOTOS REQUIRED)
d94ee616-a5ad-4fd8-850a-ad5f1ff587b0 | checkpoint | The system has been cleaned prior to occupation and use in accordance with credit requirements.
270ab9e2-b27a-4b4a-8bb5-f276c4d8d8f2 | checkpoint | Noise Level (LEVEL RECORDED IN EQUIPMENT SCHEDULE)
0401a75e-9706-4ffc-99f2-ee8d93c902ad | checkpoint | CO2 Emissions (RECORDED IN EQUIPMENT SCHEDULE)
cec978dd-3a80-4a90-bb45-ff41a594e583 | checkpoint | Commissioning Completed with Independent Commissioning Agent
7fa595bc-50b1-4a5a-85a7-17545cacd101 | checkpoint | Commissioning Data
e9ad008e-2e4f-4bba-8506-e4de2ff9a719 | checkpoint | Continuous System Test Run for 1 calendar week
44d87155-c9a3-40b1-9ed4-173612707e70 | section | Second Fix HW
de154cf9-5be7-457d-8516-265e7c97217b | checkpoint | System pressure checked and still holding 1st fix pressure
d942b4e7-045b-40c3-b323-a8ab9911fff7 | checkpoint | Indoor unit secure, level and tight to wall
b5d99abc-5ef8-430e-ba72-e58a7bac49e4 | checkpoint | Correct Indoor unit installed
048fb45c-cf86-467d-b9c9-9b4d844c152d | checkpoint | Flare connections/nuts insulated
012dfff2-1eb2-459e-8c88-878f6f374d04 | checkpoint | Indoor unit serial no. recorded
aaa164ea-8696-4345-b680-324d46dae9af | checkpoint | Installer confirmed drain tested
68a18f83-da78-44ac-9c35-5549b4888fc1 | checkpoint | Controller installed
732236e7-8159-4278-b798-0a78417562e9 | checkpoint | Area left clean and tidy, finger prints removed
734220b7-f571-476d-b51d-cb72c1613c70 | checkpoint | Plant and controller labelled
905dbab7-f33a-42ef-8ec2-120c98c0a630 | checkpoint | Access for future maintenance all clear. Filter can be easily removed
5be64681-aa73-43f6-9cf3-0bf4cfc1a8c0 | checklist | VRV OU |  | VRV OU
2b8562e7-cff1-47e5-93db-e8147b3e4c55 | section | Pre-Start VRV-OU
87d391c3-fa0b-48fe-871a-c9d8399d4cf1 | checkpoint | Area clear, access good, enough space for install
bafd21c0-1a24-43e7-908d-ef92a57c9afd | checkpoint | Duct Route clear, Penetrations complete
2bad7b93-d555-4a01-8780-6ccb64a0f928 | checkpoint | Nogs/Supports in place
7ef8533a-b167-469f-a256-de72aef4a9f5 | section | First Fix VRV-OU
c5ef84c0-424f-4efd-a196-979ac91714aa | checkpoint | Outdoor unit brackets/feet/strut in place
c1f78fe3-c10b-4f0c-a989-55acd5bc9716 | checkpoint | Unit level, secure, bolted down, seismically restrained
37b5d0fe-44cc-4319-ba15-17ccf341075b | checkpoint | Correct outdoor unit installed
1ccca903-0413-4058-9356-2ef76a89b348 | checkpoint | Clearance under unit for cleaning
c9b4b6ab-dbaa-41bd-a8b6-ddbe00a98c5f | checkpoint | Pipework connected from OU unit to BS box
ef264d4e-b411-4e1c-9c48-801b0d1bab16 | checkpoint | Pipework Insulated
3f427992-0c08-4f4f-baee-142db4397f57 | checkpoint | Insulation joins glued and taped
fe072e34-3a7f-4b45-b203-ed17ffc00398 | checkpoint | Pipework supported incl any seismic restraints
a351b60f-8df4-4bc4-939c-51b61d05eaa5 | checkpoint | Pipework supported up off the ground
acc96ca6-f948-4e1e-8eb5-77ba0b5779f7 | checkpoint | Refnets installed as per Manufacturers Instructions
16ef8b32-b5f3-423d-88ec-7864c187fbd1 | checkpoint | BS Box level, secure and seismically retsrained
ae9cfcd8-0605-4311-91ad-c50fa59bc23e | checkpoint | Correct BS Box installed
1f8e4ae8-0f4f-4123-ac46-703107f79988 | checkpoint | BS Box serial no. recorded
a6f88d10-ee78-4494-bc54-cce0f7674cc0 | checkpoint | Drain 1m from BS Box location by plumber
b85c76b6-8541-4b24-b7c3-7d9ff8e079c5 | checkpoint | Drain installed and insulated
0cd5ae10-e3ef-41fa-8c87-4b8a6c82e276 | checkpoint | Installer confirmed pipework under pressure (date/pressure recorded)
cc33af11-a481-4c7d-b4a6-509a3f42c46e | checkpoint | Installer confirmed Nitrogen purged during all welding
c5be29fa-9ede-446d-9f10-e50287d4e0d6 | checkpoint | Pipe lengths are recorded accuratley
fb2b484b-d09a-4b9e-8049-ddac2a0bc799 | checkpoint | Supply cable installed correctly, protected and secured
08562b96-2be1-477c-af63-d3aa7327b5bc | checkpoint | Supply cable type, size and manufacturer
fa09af90-1517-4f9a-ba4d-d976118ed475 | checkpoint | Circuit protection type and rating
a942cf28-672a-4da0-9f46-ccd02e222390 | checkpoint | Correctly rated isolator installed to standards
0cc9d0f5-5622-4a1f-bcaa-b88b0b9de50b | checkpoint | Interconnecting cables correctly installed and protected
65416b43-4ab6-48dd-82e1-055391ce109d | checkpoint | Control cables correct rating and type
48ec155b-b3f0-4515-95f1-1a0cbde24291 | checkpoint | Screened cables drain to earth as per specifications
f7e808d7-69e8-43b6-823d-27897a577b88 | checkpoint | Control cables maintain minimum distance from power cables
81b2e28b-cf0d-4747-b98f-8d02d0eea145 | checkpoint | Daisy chain loops complete and correct
4266191a-cd5e-41cb-aa49-44b3d1e45373 | checkpoint | Remote controller cable installed
e5d30108-bd28-4cde-869b-3190e9e7d6f5 | checkpoint | Access Panel requirements are marked and given to builders
909d5764-994e-4adb-be72-71771118a59d | checkpoint | Plans marked up for As Builts
5f9882bc-175d-4fbb-a811-3a2780174762 | section | Second Fix VRV-OU
d289e770-06ae-4e17-b24f-8f13b60b66ef | checkpoint | Grilles installed square and level
1b17260a-423a-4ae9-8336-a56b0f578ed8 | checkpoint | Flexible ducts taped then cable tied to grilles/boots
ea26d209-f62b-4d9b-90e3-0000ada6b4f1 | checkpoint | Boots sealed to grilles
01b2ecb1-6e4e-4abc-8e96-688b4277c90c | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
bc29d674-0f85-4125-8183-46285ff6b7dc | checkpoint | Controllers fitted off. Heater Bank THT set
284a1279-1bfe-4a1a-9ddb-d088469e726c | checkpoint | Power fitted off
8d410f81-65b5-4311-9880-027b5f794072 | checkpoint | Area left clean and tidy, finger prints removed
19ad9111-aeb7-4264-b8c8-31e9437d0904 | checkpoint | Plant and controllers labelled
526efb35-1764-43e0-9773-8c6aed1a6b41 | section | GREENSTAR
58002366-5622-4bbf-a273-91e8baae1742 | checkpoint | Construction Drawings amended for As Built Production
a2808023-c11d-45e8-a5a4-c049a2d62f4d | checkpoint | Materials - Greenstar rating verified (DETAILS RECORDED IN SSSP)
0286af2f-0b7b-4bbf-a73d-29cfc7e30e81 | checkpoint | Refrigerants - Volume and type recorded (RECORDED IN EQUIPMENT SCHEDULE)
c8b1c4b7-9bb7-4c82-b42e-61ec85dee845 | checkpoint | All open pipework sealed off with plastic film or similar
a6076ead-aba5-43b8-b660-e68243b6c532 | checkpoint | The system has been cleaned prior to occupation and use in accordance with credit requirements.
0e1650b1-d77c-40e8-99f7-70a8f6e84c63 | checkpoint | Noise Level (LEVEL RECORDED IN EQUIPMENT SCHEDULE)
21384291-78ec-4899-ad07-91736b473377 | checkpoint | CO2 Emissions (RECORDED IN EQUIPMENT SCHEDULE)
a405d8de-8f34-4583-b65d-25075ba03a4f | checkpoint | Commissioning Completed with Independent Commissioning Agent
f875ea37-3bdb-4d4b-a8d3-866d95bc2820 | checkpoint | Commissioning Data
8b37ef51-70b7-4c5f-9d79-22af11ebfb78 | checkpoint | Continuous System Test Run for 1 calendar week
40bd35cc-7f55-4d62-a7a0-2812eae3a227 | section | Commission VRV-OU
3a1296c4-ce99-4c1f-a9f3-3ae50ae8dcd3 | checkpoint | Access to OU unit is good
f5e5f23c-adb3-4ae9-9ea1-48a6a39a7173 | checkpoint | Access to BS Box is good
48ad9323-7d7e-457e-8654-f41cc980a668 | checkpoint | Access to Indoor units is good
1db97202-0847-4636-bc82-fd03ee2b2a6d | checkpoint | Pipework still under same pressure as left at first fix
f233c6a1-a9e4-464e-961f-ddc60623ccde | checkpoint | Triple Vac completed to Manufacturers instructions
b73f9398-236d-4abe-9020-a4a60190c840 | checkpoint | Pre-commissioning paperwork completed and sent to Manufacturer
8a36071b-0877-4e4c-9189-341ca0f2c008 | checkpoint | Additional charge inserted and recorded inside unit
1ad1db39-5594-4f01-a4c4-b432cbd79f7f | checkpoint | Power on to compressor for 24 hours (impt: only once evac completed)
76ca0420-f94d-4d1d-8f26-142ef8d8c1f2 | checkpoint | Commissioned by Daikin
e8f2c05a-182e-42df-9c98-861859d29fef | checkpoint | OU model and serial number(write in comments and take photo)
847f9bea-ad96-4fae-b855-3b99c037ee82 | checkpoint | All plant labelled incl OU/BS/Indoors/Controllers/Pipework
46bdda24-de78-4e0e-9a6e-4fbde63d7652 | checkpoint | Any issues noted? E.g. noise/vibration etc. Detail in comments
7263f19c-0ef5-45f6-bd2d-df485b16d492 | checkpoint | Electrical testing complete
ece45756-4102-4a4f-8f23-6ebe0237cc25 | checkpoint | COC issued