## Master List Templates
Id | Type | Name | Values | Prompting Name
4f727a59-4299-4227-9052-e8b429dd1fd6 | checklist | Fire Dampers |  | Fire Dampers
3e7f85da-877b-4efa-b47b-efce9a349cce | section | Pre-Start Fire Damper
a125b3ab-1bd0-4c4d-8c71-2051fddc6705 | checkpoint | Area clear, access good, enough space for install
6ba5c600-debb-430a-a872-ca1c59e0c7a7 | checkpoint | Duct Route clear, Penetrations complete
79b55644-e611-4038-81bf-3c09f44b52a3 | section | First Fix Fire Damper
7eb77dd2-6432-4ae1-9810-c78af312c5e5 | checkpoint | Correct Fire Damper installed. (Insert Photo)
edb13b58-7d6c-4d0f-a300-f69795250fb9 | checkpoint | Fire Damper installed straight and level with correct orientation.
02e08761-75ee-43d2-9591-b920d72f825a | checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
d697b986-ba81-4a91-8993-ce055e73dfab | checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
cb49af99-b40d-4d66-97f2-46692fef3658 | checkpoint | Access Panels in duct for fire dampers.
28cba624-b158-4d97-8a03-bfa1a24e76d4 | checkpoint | Building Access Panel requirements are marked and given to builders
6a38b280-855c-4c00-8255-23a3f8cf5289 | checkpoint | Plans marked up for As Builts with Access Panel locations
d33ba6eb-28c8-4854-8b42-2940a154e9b8 | section | Second Fix Fire Damper
1d369191-28df-40f0-9afa-3521d492b676 | checkpoint | Fire Damper Label affixed, Asset Number applied.
99fcfadd-4ea2-45ef-b749-c0a4c1d2672b | checkpoint | Fire Dampers Access Panels still accessible for maintenance
5d2eb6ef-1c00-4070-a498-8e46333efb04 | checkpoint | Area left clean and tidy, finger prints removed
ae2acbc5-9afe-4989-8c9f-a1b92fad8b30 | checkpoint | Fire Damper sealed to structure both sides.
f68972b4-6d81-41aa-aa09-4be60adafed1 | section | Commission Fire Damper
35abf88d-b375-479f-8b77-924971281f8a | checkpoint | Drop Tested as applicable
3399aa37-48d7-492c-8a16-93ef940f0411 | checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
7be34150-c368-48a3-ba66-611937573253 | checkpoint | Fire Damper Label filled out, photo uploaded.
40670fb4-21e7-4227-bdb5-faa6329dd3e3 | checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
91a77d34-03fe-4f7c-b402-578d38b427d1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
c911ef9e-772f-4529-b4b6-2b8de1537ef5 | checklist | CST - S - Completion Documents |  | CST - S - Completion Documents
06f77a39-bc22-40be-8410-8fd9de93e39b | checkpoint | All relevant Compliance Documentation completed and attached above
80cc5cb4-750f-512f-bda5-10adceaab6c5 | tickbox | LBP Memorandum/ Record of works filled out, signed and attached
014cb820-556a-5d43-84fd-dcccbe70ac1a | tickbox | Any Additional Compliance Documentation - Completed and Attached
88668685-e79c-5bdb-b69d-bbeb7e3732ec | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
2819a379-e6ef-4635-adc0-6e39704b0bd1 | signoff | Request Signoff
811f7ca9-914f-4e42-bb04-81ef18d7b4c5 | checklist | Ext Fan |  | Ext Fan
843b9f40-19e4-4f27-8a14-26751d466196 | section | Pre-Start Ext Fan
b0724d76-b3ed-4d18-8d91-3feb5a5ee50b | checkpoint | Area clear, access good, enough space for install
3bfc60f8-7635-4c69-9868-3895c58de608 | checkpoint | Duct Route clear, Penetrations complete
7a31342d-6af2-4876-a0d2-d211f4f1f5ca | checkpoint | Nogs/Supports in place
489676ef-908d-41b9-8e94-889e97b976e3 | section | First Fix Ext Fan
afb7cda6-e4b6-4dd3-bbbf-229f154cb4a9 | checkpoint | Fan installed straight and level and correct orientation.
96e4988b-d107-4920-a5f6-3521c827ef83 | checkpoint | Attenuators installed Level and secure
203d6d28-a979-4e7c-b2e2-deb7e982e6f4 | checkpoint | Fan or Cowl sealed to Upstand
0b703f43-f772-44a9-9ef7-d4d7ce52a280 | checkpoint | Correct Fan installed
7771aa7b-f5bd-43e2-9831-5c5fbaca0212 | checkpoint | Fan serial No. recorded
35a118db-ef4a-4d47-b128-f2d6b8af711c | checkpoint | Access Panels in duct for fire dampers
30bc9800-0c2a-47b6-85ac-b20c4b0526a0 | checkpoint | Access Panel for Extract Fan
48586fcb-7280-4240-ace5-04e74126b24b | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
bd11be8e-62ee-4d92-bd4a-dfa77b03c049 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
de53596a-1dde-4244-ac95-c8f82f643db3 | checkpoint | Flexible ducts taped then cable tied
f35cdf16-5fc7-4bd6-93bf-ff48343bdf25 | checkpoint | Supply cable installed correctly, protected and secured
1c375cef-4567-462a-953b-c1218a04929b | checkpoint | Interconnecting cables correctly installed and protected
1c7887a2-f017-494d-a6ab-0bff3bc3e6c6 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
27a20f25-f994-4c17-bd2a-8a0b5003449a | section | Second Fix Ext Fan
c443a924-f41f-44ab-bc1e-8d445ae391d5 | checkpoint | Grilles installed square and level
77735f8f-a515-48b9-bafe-a15896b0c047 | checkpoint | Flexible ducts taped then cable tied to grilles/boots
78c7eb0c-7fb3-4a10-8d87-7344f5e3d227 | checkpoint | Boots sealed to grilles
4e3c3339-79bc-4c6c-8fad-07e1956658cf | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
a9273cfc-7934-4b55-b318-71cb174e1f8d | checkpoint | Controllers fitted off
99604bac-faca-431f-b107-30aac10195ba | checkpoint | Power fitted off
56328d5f-ea61-4be8-97b8-38d77586716d | checkpoint | Area left clean and tidy, fingerprints removed
0c5fddc1-4cec-4244-bac0-f66c782adea1 | checkpoint | Plant and controllers labelled
f12bfdc8-8733-480d-8ec7-e0d7ceb21cba | section | Commission Ext Fan
cb792ca2-2b6f-43b6-afb7-ce8ad43a4258 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
0dac759b-37a2-43ee-8210-967556be483b | checkpoint | Electrical testing complete
aac24173-6f92-4735-9a8b-622847d2ef4d | checkpoint | COC issued
d4a73859-270a-4c9a-bb0d-5169497e1eae | checkpoint | Fire Matrix Commissioning Tests
ed2ca257-a1a9-4bea-8415-a2db0e1c53a7 | checkpoint | O&M Manuals Submissions
c9363529-099f-4ead-b412-527723996bd4 | checkpoint | Services interface.
bf700b96-f393-46f1-8222-25747d1ffe99 | checklist | HRV Checklist |  | HRV Checklist
c7a2a8df-a8b0-41f8-bcc2-5c4537477d44 | section | PRE-START HRV
7c70ee2a-5e10-4fc9-95b4-b8c592f41842 | checkpoint | Area clear, access good, enough space for install
5550899a-d5ea-4c2c-83c2-d0046ee4a1b3 | checkpoint | Duct Route clear, Penetrations complete
98ca2d2f-d98f-4b6e-a02f-cb35c6c61d31 | checkpoint | Nogs/Supports in place
a15da3ff-d03f-47fc-bdfe-95e8c5200945 | section | FIRST FIX HRV
c5f2b241-e925-4cb6-97d1-b4ac9328f732 | checkpoint | HRV installed straight and level and correct orientation.
fe14b70f-5937-4188-8862-0aebfa60de4e | checkpoint | Cowl sealed to Upstand
f552dadc-8cec-4875-af10-fd2198d4ac1e | checkpoint | Correct HRV installed. (Insert Photo)
6e038dfb-25d0-4e01-9fcb-cd2178c5208d | checkpoint | Filter installed and easily accessable
970c760e-071f-4ce2-b5a3-ec83ebf2b36f | checkpoint | HRV seismically braced and vibration isolated
154c92cd-7c2f-4724-8467-14a1d71e5fa3 | checkpoint | Heater Bank installed to Manufacturers instructions
05088eb3-6a50-4a58-8ce4-8e5e397d0102 | checkpoint | Fire dampers installed to manufacturers instructions. Drop tested where applicable
25a49aa8-d744-4177-a805-9ed5fe4a6292 | checkpoint | Breakaway joins either side of fire dampers
5792bf5b-af1f-4dbf-8185-14b0faf59f66 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
1c9f3a95-257d-4488-ba41-93a28a37e094 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
db813c7f-6836-42c7-9fb6-2bdd4aa62bab | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
d76a65d2-a015-42b3-a293-35dc4dc9dfff | checkpoint | Balancing Dampers locked open and accessible
6ba957d3-41f9-4450-9ac5-3159e3728b85 | checkpoint | Flexible ducts taped then cable tied
48a39dd6-c051-4524-b03a-43799b3099c1 | checkpoint | Second fix grille and access panel locations recorded
b6708e2d-f081-4328-8264-93598c455e8f | checkpoint | All open ducts sealed off with plastic film or similar
506f1f5e-6ef6-49f3-a9a8-812a1b56213e | checkpoint | Control Cables installed
d49d5078-b072-45a9-a416-5e580c8c2bda | checkpoint | Power Cables installed
1b2dd895-1b56-413b-99bf-798a5712ab6f | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
0ee81768-f52e-4e74-ae7c-47f8d13870c4 | section | SECOND FIX HRV
3bc6d07f-3dfd-4596-8e89-0a90eaba3a36 | checkpoint | Grilles installed square and level
c294f9cc-7949-4830-bdc5-a197dd97c650 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
80e873ab-e390-4d66-9315-73907bcf132b | checkpoint | Area left clean and tidy, finger prints removed
45a08f55-c811-4583-b68a-006175751997 | checkpoint | Controllers fitted off
2cc3ddca-333e-4e8b-8230-481e89c45840 | checkpoint | Power fitted off
f0cfecad-7118-4e89-977e-cd590d2280eb | checkpoint | Plant and controllers labelled
cc7ec78f-5339-4039-9397-481d31d0d8b2 | section | COMMISSION HRV
3ba7c757-25b6-480c-9650-e79febcd5269 | checkpoint | Commissioned and Paperwork submitted
ea0f2537-a569-4a73-baf3-209d73393fbc | checkpoint | COC issued
55264063-9f0e-4b4a-b168-50447f707898 | checklist | Kitchen Ext |  | Kitchen Ext
2ef8ef69-c0ec-49bb-a6c5-074c2f128241 | section | Pre-Start Kitchen Ext
89f15022-7b0f-4fc7-969a-d887bd474c01 | checkpoint | Area clear, access good, enough space for install
34bd0df8-55dc-4660-8ea0-285bd95b9975 | checkpoint | Duct Route clear, Penetrations complete
3c4f7292-447b-467a-8113-2868d8bdeec4 | checkpoint | Nogs/Supports in place
a8b683a0-cb95-40d8-8e4c-58d57ede4748 | section | First Fix Kitchen Ext
96430da1-78c7-45d4-b869-48b8efd5644a | checkpoint | Fan installed straight and level and correct orientation.
dbcc6fcc-52f6-4c27-89c0-0c37c409a9f5 | checkpoint | Fan or Cowl sealed to Upstand
92de32d9-f9ec-4dcc-8fba-2dfb06251089 | checkpoint | Correct Fan installed
84f9c616-99e8-4200-9539-e8170e434cf5 | checkpoint | Fan serial No. recorded
b20c294a-aa5a-44f9-9505-262d62b0603e | checkpoint | Access Panels in duct for cleaning
67acfd29-66be-402f-aa8d-e208f79a6901 | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
7c1f2d24-b1c0-419b-8247-c0a88a47f26c | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
75597730-a83d-426b-8f1d-db708831784c | checkpoint | Balancing Dampers locked open and accessible
2fb16002-7070-4e8f-9f99-6f9bb6c01b07 | checkpoint | Interconnecting cables correctly installed and protected
e5429a3a-e8d7-4b05-beb0-882b08034c81 | checkpoint | Remote controller cable installed
2f884823-6411-41d1-80e5-123156c700ae | checkpoint | Building Access Panel requirements are marked and given to builders
b453c29c-d1bf-432c-aef2-001ef3d97b37 | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
5c1782fb-0bef-445d-a010-872e8ef9223d | section | Second Fix Kitchen Ext
ad17f777-247c-4c3c-a537-239e039dbb6e | checkpoint | Hoods installed square and level and seismically braced
771476d4-e321-483e-8be5-565bcb307fe1 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
8de7b266-cf48-42d6-83b9-9b4bfb306afd | checkpoint | Controllers fitted off
89f029f9-5551-41fa-9182-aa089728d805 | checkpoint | Power fitted off
abaf752d-b51c-4ee3-9eeb-6a0caef3d1b8 | checkpoint | Area left clean and tidy, fingerprints removed
ab79d3de-039b-4174-8f50-0cf793850683 | checkpoint | Plant and controllers labelled
56986407-e2f2-482b-a680-d9a6845f29a9 | section | Commission Kitchen Ext
2bf7c9ac-27c8-4b80-bee2-a47eeea3e137 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
8018b046-e614-48f7-b796-469d78377571 | checkpoint | Electrical testing complete
3346e6d6-276f-4dd3-995a-f60a9220d92d | checkpoint | COC issued
cf8aa6f1-94dc-41cc-bb8e-727d7fe5e7cb | checkpoint | O&M manuals Submissions
3454dce9-a1b3-489a-973b-69871b59ecc6 | checklist | SA |  | SA
2cbf257a-1ea3-4e73-b476-de4a258ae6f2 | section | Pre-Start SA Fan
c2685cba-c13d-4bad-b36f-eebf419992a5 | checkpoint | Area clear, access good, enough space for install
856dad1c-fcc2-4064-9f91-faa9f0eaa6ff | checkpoint | Duct Route clear, Penetrations complete
748b0490-723d-40bb-9825-93a1fe5115f8 | checkpoint | Nogs/Supports in place
3a4627cc-d023-45b2-bd9e-4e6823681081 | section | First Fix SA Fan
fe6c1da8-072d-45a1-8d28-572ce48eb06d | checkpoint | Fan installed straight and level and correct orientation.
ffc2b222-efb1-456a-a305-5b264c06f917 | checkpoint | Fan or Cowl sealed to Upstand
39a2749c-4d5c-4590-a178-a1403f6f372b | checkpoint | Correct Fan installed
e5b27a17-a891-4830-b582-c94689f75354 | checkpoint | Fan serial No. recorded
250f79d3-cbbf-4720-aed7-e1a61410ea96 | checkpoint | Fan seismically braced and vibration isolated
a19fdcb5-1634-45e2-b631-7d937a59a3ee | checkpoint | Heater Bank installed to Manufacturers instructions
1aefefe9-f092-4975-9a72-262b5820e9f2 | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
cd131616-40b4-4e36-b3ac-aa0a2b6dc8be | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
4458ccd1-bc72-4a52-be87-be8e76cb26a9 | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
9c183d7e-c4c1-44e8-bc4f-da8b69d62709 | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
c3faa5c0-8e17-47f9-a7bf-52cabfcd4160 | checkpoint | Flexible ducts taped then cable tied
8f3154ec-efc1-4671-bb10-fdab6882bc04 | checkpoint | Supply cable installed correctly, protected and secured
13a35a3f-d051-4495-8ac3-0510163f22d7 | checkpoint | Interconnecting cables correctly installed and protected
28d9ccdb-d198-4c7c-8dc6-c3fd656c7faa | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
ed84d611-fd63-48c0-b954-749cf431bf7d | section | Second Fix SA Fan
e9250da5-1ef3-41c2-af7d-789a8a084a9e | checkpoint | Grilles installed square and level
54a9cce8-2018-442e-ac6f-544a00ed1772 | checkpoint | Flexible ducts taped then cable tied to grilles/boots
db1cc813-f77a-45a7-9438-a86342b3f164 | checkpoint | Boots sealed to grilles
a23913f2-da7b-490f-981e-367cf04e516a | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
3e1f69ca-0cc5-4dac-a19c-7304fef6b1df | checkpoint | Controllers fitted off. Heater Bank THT set
ddb16b59-43e9-42f8-8b10-98f320bebe88 | checkpoint | Power fitted off
69206208-fa17-43f8-a069-0ed9acb720b8 | checkpoint | Area left clean and tidy, fingerprints removed
a57fd351-983b-4d7c-bb81-96579d7637d6 | checkpoint | Plant and controllers labelled
77fd242e-d161-4534-8311-49ab58ea0c7b | section | Commission SA Fan
1b133de9-c38c-45eb-8b5e-1705f4dc00c6 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
afa16463-7d9c-4cd4-8e29-dfe2fb1056b3 | checkpoint | Electrical testing complete
ebbb4cd7-43a1-4c44-9476-cece14932593 | checkpoint | COC issued
2a0ad024-b218-4782-a0ec-c78f7ab94d05 | checkpoint | Fire Matrix Commissioning Tests
e38af5d4-acfc-4328-a39b-4e1839d6a6ae | checkpoint | O&M Manuals submissions
3dfaae20-26e0-4b7b-9633-a57208327e90 | checkpoint | Services interface
400925ae-804a-45ef-bf36-c51fd2920615 | checklist | Split HW |  | Split HW
f4c1cafb-0e90-44a7-8eaa-cc91daf6c733 | section | PRE-START SPLIT HW
689a9b3d-7ec9-4d3f-9dc6-2c41d2e2d92b | checkpoint | Area clear, access good, enough space for install
8d933e35-2ee3-473d-974c-b9ba6faf441c | checkpoint | Area/base/wall ready for outdoor unit
ff5e1304-7a16-45a6-96a8-aee9a6f6bcb8 | checkpoint | Pipework route all clear, penetrations complete
34ca4ec7-f3f3-413c-8022-8e87f88dd56a | checkpoint | Nogs in place
63d134e9-8890-479d-b5dd-5546df6f0eae | checkpoint | Drain 1m from Indoor unit location by plumber
c8663955-100f-4c4b-9614-6c007a188655 | section | FIRST FIX SPLIT HW
f3c9659f-bcde-4085-8cf8-888f9bf2fe40 | checkpoint | Pipework Insulated complete length, glued and taped
f02b465f-952c-41a9-9fd1-4c021816bd26 | checkpoint | Pipework supported incl any seismic restraints
469d87b1-9d26-43ea-9e68-3b0e9098ddc1 | checkpoint | Drain installed and insulated
fc0ee141-def1-4be1-b127-51defdac1713 | checkpoint | Pipe lengths are recorded accurately. INSERT PIPE LENGTH (IN NOTES):
6e3a3387-9ad5-43fa-a26f-b4af0cd5fc2a | checkpoint | Control cables installed
01443423-5511-43e3-8c2a-1d511bf9fc6a | checkpoint | Power Cables installed
1bc74e10-df14-43a5-85b2-75cf25c01c48 | checkpoint | Plans marked up for As Builts
850d17e6-f96f-4ab8-b957-5df49da7f37a | section | SECOND FIX SPLIT HW
bd0a02f6-9bae-4c9e-9947-946a0c7a3fa4 | checkpoint | Correct Indoor unit installed. (Insert Photo)
0755c450-f15a-4ab7-b441-3e80249ed3bd | checkpoint | Correct Outdoor unit installed. (Insert Photo)
f17a5fe4-7eee-408d-a7bf-9ca977b120c0 | checkpoint | Outdoor unit level and secure
799e0bbd-36ed-4463-91e6-59adfaa5be6e | checkpoint | High Wall cover installed flush and square
7394ae30-fb82-4515-aad7-da220fbd07e7 | checkpoint | Area left clean and tidy, fingerprints removed
5e1e0251-894e-40e8-9172-431bd84f766b | checkpoint | Controllers fitted off
fca141c6-2bbc-4bfe-9bb7-d46463a7fb6f | checkpoint | Power fitted off
f1f5a157-dce4-4f01-ae62-6db0325ceeb0 | section | COMMISSION SPLIT HW
01ebbb60-1193-452d-b6d3-952a01e22a01 | checkpoint | Commissioned and paperwork submitted
2d75434d-5260-45eb-a859-d66591a648a4 | checkpoint | COC issued
c18e8467-3e24-429e-a1c4-fbc57ead4ba0 | checkpoint | Plant and controller labelled