## Master List Templates
Id | Type | Name | Values | Prompting Name
4f727a59-4299-4227-9052-e8b429dd1fd6 | checklist | Fire Dampers |  | Fire Dampers
3e7f85da-877b-4efa-b47b-efce9a349cce | section | Pre-Start Fire Damper
a125b3ab-1bd0-4c4d-8c71-2051fddc6705 | checkpoint | Area clear, access good, enough space for install
6ba5c600-debb-430a-a872-ca1c59e0c7a7 | checkpoint | Duct Route clear, Penetrations complete
79b55644-e611-4038-81bf-3c09f44b52a3 | section | First Fix Fire Damper
7eb77dd2-6432-4ae1-9810-c78af312c5e5 | checkpoint | Correct Fire Damper installed. (Insert Photo)
edb13b58-7d6c-4d0f-a300-f69795250fb9 | checkpoint | Fire Damper installed straight and level with correct orientation.
02e08761-75ee-43d2-9591-b920d72f825a | checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
d697b986-ba81-4a91-8993-ce055e73dfab | checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
cb49af99-b40d-4d66-97f2-46692fef3658 | checkpoint | Access Panels in duct for fire dampers.
28cba624-b158-4d97-8a03-bfa1a24e76d4 | checkpoint | Building Access Panel requirements are marked and given to builders
6a38b280-855c-4c00-8255-23a3f8cf5289 | checkpoint | Plans marked up for As Builts with Access Panel locations
d33ba6eb-28c8-4854-8b42-2940a154e9b8 | section | Second Fix Fire Damper
1d369191-28df-40f0-9afa-3521d492b676 | checkpoint | Fire Damper Label affixed, Asset Number applied.
99fcfadd-4ea2-45ef-b749-c0a4c1d2672b | checkpoint | Fire Dampers Access Panels still accessible for maintenance
5d2eb6ef-1c00-4070-a498-8e46333efb04 | checkpoint | Area left clean and tidy, finger prints removed
ae2acbc5-9afe-4989-8c9f-a1b92fad8b30 | checkpoint | Fire Damper sealed to structure both sides.
f68972b4-6d81-41aa-aa09-4be60adafed1 | section | Commission Fire Damper
35abf88d-b375-479f-8b77-924971281f8a | checkpoint | Drop Tested as applicable
3399aa37-48d7-492c-8a16-93ef940f0411 | checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
7be34150-c368-48a3-ba66-611937573253 | checkpoint | Fire Damper Label filled out, photo uploaded.
40670fb4-21e7-4227-bdb5-faa6329dd3e3 | checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
91a77d34-03fe-4f7c-b402-578d38b427d1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
9458cd4c-aa4c-4ac8-a11e-79a4ede6851c | checklist | EXTRACT FANS CHECKLIST |  | EXTRACT FANS
f1bdf957-a819-4695-b365-0df96ec6f25c | section | Prestart
4352902d-1393-4ddc-b1fe-c1cd105b6014 | checkpoint | Area clear, Access good, enough space for install
aa667d25-d562-458c-b1d6-0335b3cf012f | checkpoint | Duct route clear, Penetrations complete
646d78bc-7e0b-4d03-8fe0-3b394f729074 | checkpoint | Nogs and supports in place
49f5fee9-9054-479d-807f-f6e455768ff8 | section | 1st Fix
e8b80f38-a6e1-4a22-af0b-daeffdc28778 | checkpoint | Correct Fan installed
674decfd-8544-4ccb-9db0-fbaa7e130d74 | checkpoint | Ductwork straight/level, well supported including seismic restraints
1865f482-49e9-4115-8307-7e2b385a3a5b | checkpoint | Duct fittings/joints sealed and mechanically fixed to duct. SAB joints sealed
6122498f-2328-40ac-8c12-b40f032d42a6 | checkpoint | Flexible ducts taped then cable tied
65df9ea9-f2ce-4f6d-9570-ee8756212cd1 | checkpoint | Second fix grille and access panel locations recorded
8d000409-2aa1-4322-8950-e3e0637114e3 | checkpoint | All open ducts sealed off with plastic film or similar
ab79d5ef-6b04-4c9f-8852-f0bee55ff66f | checkpoint | Control cables installed
ff5c63d3-8b97-4791-ab80-19b140acf134 | section | 2nd Fix
227d9613-213f-4b15-aec8-282d60b1d6c0 | checkpoint | Grilles installed square and level
e35ae0e6-7c62-49e5-8243-6c740f964b69 | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accesible for maintenance
ec69dbd2-e60d-4bc0-bdec-f7c3df1d8890 | checkpoint | Area left clean and tidy, finger prints removed
4bb200ec-7824-402e-a4b7-9596602b1ae1 | checkpoint | Controllers fitted off
fe914554-81fb-41f9-9d43-54e5c34669fd | checkpoint | Power fitted off
9375a240-3e10-4a7c-9b93-fbf599230fc1 | section | Commissioning
cb01d312-47fe-470f-9110-381263a6410e | checkpoint | Commissioned and paperwork submitted
6a77ba83-9594-4b9b-9fcb-be28069129e8 | checkpoint | COC Issued
ad175799-fb36-46b8-9c90-40b6d89544c2 | checkpoint | Plant and Controller labelled
8945b439-9dcc-4ea0-ab72-75babb382264 | checkpoint | Photos attached
2dda2660-3414-4bb8-a895-a80d6f4e88fb | checklist | HI WALL CHECKLIST |  | HI WALL
7b19acda-9e98-404d-99f8-7cccf71215e4 | section | Prestart
c76f8a9b-7871-4aa2-9c5c-b5cb5799206d | checkpoint | Area Clear, access good, enough space for install
d70d6254-e6d5-42ea-baab-0c5347ffbe29 | checkpoint | Area/Base/Wall ready for Outdoor Unit
c32f17a0-e4e1-479c-8319-b42c36c9cce9 | checkpoint | Pipework route clear, penetrations complete
a3ef6dd3-08bc-4a6e-b4b2-5f834318fbb8 | checkpoint | Nogs in place
acc9daeb-ba41-4178-b3ce-8a79cb65051f | checkpoint | Drain 1m from indoor unit by plumber
a31e9f54-2b40-474c-bd5f-20483e93437b | section | 1st Fix
4434264d-7871-4a05-aee8-e1b9a5bba281 | checkpoint | Pipework Insulated complete length, glued and taped
fb7fd7cc-308d-4688-b4b8-d4fc0d265bd8 | checkpoint | Pipework supported including any seismic restraints
fd33a090-d34b-4538-ac43-67f99afb6267 | checkpoint | Drain installed and insulated
1b540386-c8ad-4ffb-9d6f-1da7d64835f1 | checkpoint | Pipe lengths recorded accurately as in Commissioning below
8e049596-5125-4195-85f2-1f2bf3a05b87 | checkpoint | Control Cables Installed
77448354-960e-4318-83be-48c2cdcf389b | checkpoint | Power Cables Installed
41c55b7e-aa7c-41b6-acfd-ab781a19b940 | checkpoint | Plans Marked up for As Builts
44bf494b-ceec-4fe5-a5b8-0d78f1738175 | section | 2nd Fix
61a1087e-accd-40a9-9505-cae467d7139a | checkpoint | Correct Indoor Unit installed
509fe335-0f39-4c70-a127-ac2c65916c73 | checkpoint | Correct Outdoor Unit installed
d5ab3891-e0e7-4d80-969c-c76c61c82560 | checkpoint | Outdoor Unit level and secure
c95f5368-f4f6-4efc-ba27-8ad09bf37927 | checkpoint | High Wall cover installed flush and square
847a763e-fae6-429b-9ec8-fed1b13d2611 | checkpoint | Area left clean and tidy, finger prints removed
9e5dfd5a-785c-49cd-b5fc-e3d080b7c5b4 | checkpoint | Controllers fitted off
67fbc069-b719-4b1f-b6c3-6612325c6539 | checkpoint | Power fitted off
721a68d7-729b-4b8e-b80a-8f702a4181c1 | section | Commissioning
34625e8c-f59e-4777-9569-de9b27c07840 | checkpoint | Commissioned and paperwork submitted
8fc90bd2-d1d1-4044-ae4c-272fbcc6368b | checkpoint | COC Issued
6dedd431-5d7f-40d9-a83a-1a3faaf9b81c | checkpoint | Plant and Controller labelled
694e23bf-4d52-4b4c-a96e-a90964b2cbba | checkpoint | Photos attached
fab5fbee-5072-4e7b-ad26-0ed6ebcb9ce7 | checkpoint | Pipe Length