## Master List Templates
Id | Type | Name | Values | Prompting Name
4f727a59-4299-4227-9052-e8b429dd1fd6 | checklist | Fire Dampers |  | Fire Dampers
3e7f85da-877b-4efa-b47b-efce9a349cce | section | Pre-Start Fire Damper
a125b3ab-1bd0-4c4d-8c71-2051fddc6705 | checkpoint | Area clear, access good, enough space for install
6ba5c600-debb-430a-a872-ca1c59e0c7a7 | checkpoint | Duct Route clear, Penetrations complete
79b55644-e611-4038-81bf-3c09f44b52a3 | section | First Fix Fire Damper
7eb77dd2-6432-4ae1-9810-c78af312c5e5 | checkpoint | Correct Fire Damper installed. (Insert Photo)
edb13b58-7d6c-4d0f-a300-f69795250fb9 | checkpoint | Fire Damper installed straight and level with correct orientation.
02e08761-75ee-43d2-9591-b920d72f825a | checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
d697b986-ba81-4a91-8993-ce055e73dfab | checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
cb49af99-b40d-4d66-97f2-46692fef3658 | checkpoint | Access Panels in duct for fire dampers.
28cba624-b158-4d97-8a03-bfa1a24e76d4 | checkpoint | Building Access Panel requirements are marked and given to builders
6a38b280-855c-4c00-8255-23a3f8cf5289 | checkpoint | Plans marked up for As Builts with Access Panel locations
d33ba6eb-28c8-4854-8b42-2940a154e9b8 | section | Second Fix Fire Damper
1d369191-28df-40f0-9afa-3521d492b676 | checkpoint | Fire Damper Label affixed, Asset Number applied.
99fcfadd-4ea2-45ef-b749-c0a4c1d2672b | checkpoint | Fire Dampers Access Panels still accessible for maintenance
5d2eb6ef-1c00-4070-a498-8e46333efb04 | checkpoint | Area left clean and tidy, finger prints removed
ae2acbc5-9afe-4989-8c9f-a1b92fad8b30 | checkpoint | Fire Damper sealed to structure both sides.
f68972b4-6d81-41aa-aa09-4be60adafed1 | section | Commission Fire Damper
35abf88d-b375-479f-8b77-924971281f8a | checkpoint | Drop Tested as applicable
3399aa37-48d7-492c-8a16-93ef940f0411 | checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
7be34150-c368-48a3-ba66-611937573253 | checkpoint | Fire Damper Label filled out, photo uploaded.
40670fb4-21e7-4227-bdb5-faa6329dd3e3 | checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
91a77d34-03fe-4f7c-b402-578d38b427d1 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
03803796-47c6-41e8-bce8-11f22d707b9b | checklist | Ext Fan |  | Ext Fan
d4ecadff-89a9-4f7c-b0f5-53d0b218bbdb | section | Pre-start
b9d89e46-28ea-4ad5-a7fd-bd0dda9c11a7 | checkpoint | Area clear, access good, enough space for install
98161fbf-e535-4742-b32a-36bd802abd45 | checkpoint | Duct route clear, Penetrations complete
b464048b-213b-4866-8e7e-017b8b4a9c0c | checkpoint | Nogs/Supports in place
a0a86a31-bf76-4540-beff-be82ff1ae851 | section | First Fix
8695c426-404d-4a4b-9348-546cdaa82f1b | checkpoint | Access Panel requirements marked up on drawings and submitted to client
3f283274-3f68-429b-8200-16e462afce47 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
e931375f-ae9f-497d-95ff-f19364027f68 | checkpoint | Mechanical First Fix complete
d3ac773f-7274-4b21-bcf1-8ad61447d2a9 | section | Second Fix
5062d3f9-7dbb-468f-ac9e-3b60ea20421f | checkpoint | Area clear and access good for Second Fix
7052457d-fbd4-4790-9bca-3523c83f629a | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
855d5cd7-349a-4028-9dca-fa1686cdec55 | checkpoint | Mechanical Second Fix complete
76f9ad47-18b4-47af-ba76-e80ed601b092 | section | Commission
fc492215-044f-4e6e-8641-1c8c79c9247c | checkpoint | Good access to all areas of building
971438b6-7323-4c74-bc2d-12cf1ecf06b7 | checkpoint | Power live to Mechanical Plant
f784a0d5-0e59-45ec-96bc-726de16c7c4f | checkpoint | Mechanical Plant commissioned
98c15982-4f0c-4fbf-b67d-344f802814db | checklist | HRV |  | HRV
91ffbf65-34e2-4d89-89e7-b63545e558be | section | Pre-start
e6202336-88f6-4973-a71d-9b79a9e433e2 | checkpoint | Area clear, access good, enough space for install
965d18e3-b142-4c15-9827-6220430aa8a7 | checkpoint | Duct route clear, Penetrations complete
03e34541-984c-4f7e-b2a2-426067174895 | checkpoint | Nogs/Supports in place
2b2ea8cc-e23d-4eeb-aca8-02060296083b | section | First Fix
be337883-d99f-4ea3-98ac-5ecc04436f44 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
2954e4af-f034-4750-975d-779f2d73189e | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
fae18e47-b0d8-49b8-bb3e-0de12d00cf41 | checkpoint | Mechanical First Fix complete
941fe5c9-32ab-46f4-af8b-bed472038938 | section | Second Fix
711778dd-7ee0-4851-a027-161ff93248dc | checkpoint | Area clear and access good for Second Fix
da1dce99-9a8d-46f7-a1f1-77dddca9b06e | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
f0f5b68d-87f5-4d78-b1ab-d1fbfc87eb73 | checkpoint | Mechanical Second Fix complete
c84a528c-80b1-4eea-a124-ccc3e5b3021e | section | Commission
7202dff2-490a-4312-aaa7-a4753fdc99bc | checkpoint | Good access to all areas of building
e557887d-b768-4767-9372-b6e61edfd53b | checkpoint | Power live to Mechanical Plant
39dac64e-32bf-4341-89b5-9d03ed4dd1be | checkpoint | Mechanical Plant commissioned
b7d55a2c-ed74-45d1-a134-722654e562ac | checklist | SA Fan |  | SA Fan
79749da3-bf64-4795-a24d-0fc1f957948b | section | Pre-start
eba4da4c-a134-471b-a2a4-1dbee87a2878 | checkpoint | Area clear, access good, enough space for install
d8c5176d-615b-4d9d-b73a-51aaefcc899c | checkpoint | Duct route clear, Penetrations complete
d9d5d1ba-fc3b-4cae-b6cb-0f3b498de907 | checkpoint | Nogs/Supports in place
50bd0d88-6575-440c-b292-621e77d58ad9 | section | First Fix
f9865165-8194-4acc-b582-dbb476686a42 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
0ba18e5e-bef6-4a8a-9399-b569e23f2d14 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
500777c5-9a3a-42b1-ac83-18994dccb349 | checkpoint | Mechanical First Fix complete
f46a52d8-557d-4988-a1fa-2ad0760c1830 | section | Second Fix
a1e25f60-0b3c-41b4-be93-ad4a0732aff5 | checkpoint | Area clear and access good for Second Fix
a931e203-a54b-4f39-9498-f4439220562d | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
d3c3c0fd-0678-4a49-91ef-b5093cc91f64 | checkpoint | Mechanical Second Fix complete
9b8999b4-3c66-488d-91f4-8059259ceb0b | section | Commission
4914ca3e-5dae-43f1-9985-622fe97a7ad8 | checkpoint | Good access to all areas of building
70f8546e-1c21-41da-9c89-e8fc891d4f37 | checkpoint | Power live to Mechanical Plant
0e22b00b-fa91-44f9-ac2e-e9283ffbf6ea | checkpoint | Mechanical Plant commissioned
00576504-4c88-4b13-b347-a715684db305 | checklist | Split HW |  | Split HW
8a50b317-8214-41d5-9a52-8ceb349cec0e | section | Pre-start
97cb7340-a584-4685-8c49-549d2c9ba8a3 | checkpoint | Area clear, access good, enough space for install
f7d9cab7-56dd-433b-83d5-8131165a5e27 | checkpoint | Area/base/wall ready for outdoor unit
b7735fcb-dda6-4490-b4a2-450222013c17 | checkpoint | Any required drains for outdoor unit in place
968af54e-c72e-4a0f-9414-30921330c57f | checkpoint | Pipework route all clear, penetrations complete
dc7315b1-a630-4286-93a4-8f1e7c8c69c8 | checkpoint | Nogs in place
27bbf04f-6977-4958-a6b5-5fbbd81bc80e | checkpoint | Drain 1m from Indoor unit location by plumber
86a1da62-5cf4-43e9-9f4a-d7ee3b904608 | section | First Fix
dfe2f016-e288-4ac2-9aea-31b26f04c9c8 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
14be689e-15f8-4b11-8f4f-0ebd049a93ba | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
44300008-bf60-4533-a18d-88b4a8e7ff8d | checkpoint | Mechanical First Fix complete
84efd995-cbd4-4358-964b-6ac934ec4742 | section | Second Fix
0483d0ff-6cfe-46db-8db0-89c68b1be379 | checkpoint | Area clear and access good for Second Fix
ec09c971-f36d-4597-9871-edfb14990f50 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
a07355a3-17b4-46bc-9d1a-5a302cfb51a8 | checkpoint | Mechanical Second Fix complete
3d769c88-d2d3-4900-b4b5-6826e8c038b6 | section | Commission
0d234b45-ceee-4ee1-b805-efae2b9a65ea | checkpoint | Good access to all areas of building
25ce35f6-c27f-436d-a72d-64577f578fc3 | checkpoint | Power live to Mechanical Plant
72c76911-9217-4ee8-9a41-31f9a7075686 | checkpoint | Mechanical Plant commissioned
98521c3b-b67b-48b9-957b-2e2017b1b2b8 | checklist | VRV Ducted System OU1 |  | VRV Ducted System OU1
e410c658-e597-4454-8d35-b524069f0b6a | section | Pre-start
4e879090-f103-40a3-87ca-c9fa324f6bf5 | checkpoint | Area clear, access good, enough space for install
7bf25c60-e906-44e0-87e9-4cc7c9e02ceb | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
1e7700ee-37cb-43d3-9fbe-cd8769370dc1 | checkpoint | Grille openings framed out
41c1d2d1-8677-482e-834b-694d35da79e5 | checkpoint | Drain 1m from Indoor unit location by plumber
bacdbbd7-e518-42ef-be77-465266753478 | section | First Fix
dc38c5b4-71b8-4c99-ae98-c562c5285a0e | checkpoint | Access Panel requirements marked up on drawings and submitted to client
82d2c8bd-813b-4423-bd99-ab1e9371a45c | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
5d65046e-4568-4afa-9dc8-9687f286fdeb | checkpoint | Mechanical First Fix complete
b3d706fa-9140-46f8-a4e5-b2ee46b7e255 | section | Second Fix
7e904aac-c5c8-4980-857a-0f2a5f20d725 | checkpoint | Area clear and access good for Second Fix
d27c3fff-84d0-4c1d-b7db-b818192ecf0a | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
4ac5e9b7-2943-41d7-9c90-f795da94f311 | checkpoint | Mechanical Second Fix complete
ac3ff22f-1a51-40a9-ac81-5788f5b64feb | checklist | VRV Ducted System OU2 |  | VRV Ducted System OU2
a96e7a91-a96f-4f80-900d-e522fc1ea11e | section | Pre-start
73b855b1-a73a-439e-9d3c-371c930ffb23 | checkpoint | Area clear, access good, enough space for install
d5a7bf99-712b-49ac-9143-91da275c47c8 | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
9bf06fe5-5ddc-486d-9e7f-fd184fe95275 | checkpoint | Grille openings framed out
b5bddcf1-f65a-453e-8f77-a5b382c15a01 | checkpoint | Drain 1m from Indoor unit location by plumber
2512ba4a-60c2-450d-9bb5-5b8f7bc62bb6 | section | First Fix
0db70bcf-f639-4e84-b560-ffae2aa1f21a | checkpoint | Access Panel requirements marked up on drawings and submitted to client
7bef7470-049b-4779-a2b9-8936a3641de5 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
82f670e8-a87c-41b9-95b0-4339a56c9bf3 | checkpoint | Mechanical First Fix complete
6837688f-a084-4794-b2e0-b484a67d08cf | section | Second Fix
b4c50374-7e4d-4af4-9de7-4b9eee5a3001 | checkpoint | Area clear and access good for Second Fix
469ef6fd-9a5c-490b-b11d-cf8abe43e82e | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
9722dfa2-49dd-47e5-8d91-6acc6e669aee | checkpoint | Mechanical Second Fix complete
fd6ae792-b20a-43c7-8375-81edade39b45 | checklist | VRV Ducted System OU3 |  | VRV Ducted System OU3
779d3c99-413d-44e2-afed-bbcefc28ee01 | section | Pre-start
b31b008c-44b2-4f95-8960-63b2dfba6ccd | checkpoint | Area clear, access good, enough space for install
71ed18f6-017b-44c7-9b8c-4d1fa25ebcb9 | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
0a9fac1c-2930-4052-a1ff-14b1a43eb407 | checkpoint | Grille openings framed out
8b384aa0-0712-468f-a472-2cb74ae329b4 | checkpoint | Drain 1m from Indoor unit location by plumber
526f4a19-5ab0-4beb-bd81-330449157bb4 | section | First Fix
2d5c0b64-cd26-409a-b584-3fc25383d29c | checkpoint | Access Panel requirements marked up on drawings and submitted to client
7075e0a2-af8f-4795-8c18-df426a4571c2 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
dca956ac-27d2-4f3d-b0eb-1be1c15ca135 | checkpoint | Mechanical First Fix complete
3f544a6c-e9a0-49b5-bb62-f9f789e55355 | section | Second Fix
b6245f83-ad9c-42bb-9c04-f9309de83442 | checkpoint | Area clear and access good for Second Fix
2e2e3ac0-07e9-4eb3-b66c-3cafc56defcf | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
2f96264e-79ba-400c-b63c-5a39ab674d9a | checkpoint | Mechanical Second Fix complete
01c52c07-756a-4b17-ba77-dc3153e2caa5 | checklist | VRV OU |  | VRV OU
c5f22e1d-b71f-493a-95d6-a050e57ac64d | section | Pre-start
cb026fd1-1e80-4421-8e97-28d685bfca62 | checkpoint | Area/base ready for outdoor unit
36a17e5d-139f-42c5-8173-4b1a6f88259e | checkpoint | Any required drains in place
acc170d5-9e8e-4f97-ae68-19f2693f92c5 | checkpoint | Outdoor unit area accessible
19a5f68e-02ce-4d5e-b2b3-c44683f3be7d | checkpoint | Pipework route from OU to BS box all clear, penetrations complete
dcf87783-322f-43e2-8c44-5d65e1fbf976 | checkpoint | Area clear for BS Box installation
43c488e6-b61f-4064-ac31-7ee802747215 | section | First Fix
536ff748-7235-4629-8afb-268c3633c41b | checkpoint | Access Panel requirements marked up on drawings and submitted to client
ea3a35c6-d1a9-4c7c-99c7-8d4fa8bf0858 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
fbdb1053-e234-47ec-a578-2633c5207680 | checkpoint | Mechanical First Fix complete
e4c45cdb-a66a-41b4-8e7e-306cb742ac6a | section | Commission
3cc3f2f7-8b8a-400e-be20-e7c727ffd21c | checkpoint | Good access to all areas of building
62ac5c75-c722-4098-a568-742f5c2169f6 | checkpoint | Power live to Mechanical Plant
b532633f-8bf0-4581-a6eb-d83200fe0359 | checkpoint | Mechanical Plant commissioned