## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
7ad3dace-77f3-5b83-857e-ce49e66672af | checklist | Jet Pulse Fan |  | Jet Pulse Fan
d53c9c00-f161-5e99-a902-c5ca41fd3083 | section | Pre-Start Jet Pulse Fan
da2534a7-c54d-58b8-bdb4-03fca3bcb625 | checkpoint | Area clear, access good, enough space for install.
523f8f81-a708-5af5-8b8f-47a44f2f3d96 | checkpoint | Nogs/Supports in place.
c83195a6-4ac6-55b4-84b2-ec9b7cd5a913 | section | First Fix Jet Pulse Fan
301f26a6-09ca-55ed-b9c0-d193f8e95f1d | checkpoint | Fan installed straight and level and correct height and orientation.
e0ee8f71-7a1f-593b-96aa-7834627113e4 | checkpoint | Correct Fan installed.
b2cd2979-64d3-54ef-9594-2751b8c492fd | checkpoint | Fan serial No. recorded.
78a81fa0-6c8c-5844-98b4-27716dfcc55f | checkpoint | Fan seismically braced and vibration isolated.
bae452f7-7e96-53f4-8611-95128a9ed3ab | checkpoint | Plans Marked up showing Jet Fan and CO Sensor Location.
cb9731c7-20ea-5b5a-9b30-3c42b8cd370c | checkpoint | CO sensor installed.
decd263d-3a63-5f96-9bf0-fa5e17d72e97 | checkpoint | Control Cables Installed.
34707a92-7a33-56a4-986b-671475ef52ec | checkpoint | Power Cables Installed
| section | Second Fix Jet Pulse Fan
8733697c-8467-5a6b-9ed6-15fa5a9b1b23 | checkpoint | Fans accessible for maintenance.
bac628c8-4ee9-57fa-b53d-b277b2b3f5b6 | checkpoint | Controllers fitted off.
2d839e9b-7ab2-5662-b4c2-6fe6009a0c8e | checkpoint | Power fitted off
00e2c824-bc70-5dff-b460-feb60427395f | checkpoint | Area left clean and tidy, finger prints removed.
ebaa347d-ce9c-5f56-8788-d18bae4c017e | checkpoint | Plant and controllers labelled.
| section | Commission Jet Pulse Fan
6ddcbc6d-41ba-54d8-abd5-5388053b4420 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager.
b929e51e-bf6d-5092-b7ee-24252d6267e2 | checkpoint | Aviator Max Controller Commissioned
| checkpoint | Fire Isolate Function Commissioned.
| checkpoint | Electrical testing complete.
| checkpoint | COC issued.
| checkpoint | Electrical As Built updated with DB Board and Breaker Information.