## Master List Templates
Id | Type | Name | Values | Prompting Name
4b90694d-c1b1-501d-b8f8-671072cf68d5 | checklist | Air Con QA |  | AirCon QA
2e6301c3-1dee-5ce9-a500-9153938730b4 | section | Preinstall checks
c0e9bd74-e7d8-5ee9-bae7-2272d9eaa5db | checkpoint | Area Accessible
77b6c9b4-38dd-5dd2-bd44-2f76686fdaba | checkpoint | Holes/penetration in place
aff7b82e-6170-5eeb-ad26-88fac7a7ec5f | checkpoint | Nogs/ ply in place for Indoor unit
263db9dc-c42d-58ad-a9f5-b6dda9a5d9b6 | checkpoint | Drain 1 meter from final location
442d9760-bb1f-52a8-b863-f16df563558b | checkpoint | Substrate acceptable and ok to begin work
84845e85-e4df-5236-958b-8ce4a71e1a87 | signoff | Request Review/Raise remedial
fd3ac60e-3a52-53d8-a6b3-fe800bca9443 | section | AirCon 1st Fix
becb9700-60e0-5639-887e-d60160c3ca1e | checkpoint | Pipework Insulated complete length
48c53969-c500-5b36-abae-e5d1b20272b2 | checkpoint | Insulation Joins Glued and taped
8a247279-0153-522b-af4a-580a5258e718 | checkpoint | Pipe ends supported to prevent bending (indoor)
0557f9e4-033f-58c7-9c05-ca4237e247f0 | checkpoint | Pipe strapped to the ciling in sofite (outdoor)
a95c8139-1bf7-52dc-b6e2-214f55c93f2d | checkpoint | Pipe length supported
f0a519d0-44f6-54a8-8ea5-37108bafb505 | checkpoint | Building envelope sealed
41293506-38d7-5ab8-a2f2-859331a92eda | checkpoint | Outdoor wall brackets in place (done by RHC)
23084c7e-1349-507d-b61f-df7efa0476d4 | checkpoint | Interconnect run and taped to pipes
31e524a9-a6a6-5f46-bf54-15700390e52b | checkpoint | System under pressure
903b4b15-57db-4197-90ec-a162b1f5437d | textbox | Date
024d2e8e-db17-4d2e-b390-ab8db2cf0815 | textbox | Pressure
c9c7c69b-9c07-5439-81b0-3d08ef1e8cff | signoff | Request Review/Raise remedial
5fb32e69-9491-587d-a24d-004aa160e8d7 | section | AirCon 2nd Fix
b48298c9-3f47-57d0-94bc-03590c580c99 | checkpoint | System Pressure checked and still holding pressure
777f4b04-ba2d-50d0-96b7-6434f288c795 | checkpoint | Indoor fitted, level and tight to wall
dc7cfbab-62ec-5cb6-b355-2d387d11ff10 | checkpoint | All finger prints removed from unit and wall
51fd5cf3-c396-5713-83c2-92b2ad45aa98 | checkpoint | Drain tested
63069d72-a87f-537c-837b-ded58112188c | checkpoint | Remote into box to hand to Client
9f4504a9-c800-5e51-a31c-1bf962450a3c | checkpoint | Interconnect terminated each end
ba51270d-4633-56dc-ab7b-2dfb920e6bd2 | checkpoint | Outdoor fitted, level and secure
6b891aaa-fb22-5d06-8b9f-0eaa6db227f6 | checkpoint | Flare nuts tightened to correct tourqe
3d00fa86-0d60-5db6-92c9-c551ac119537 | checkpoint | System Vacced out to Daikin requirements
bf73e896-cc00-551e-8995-3d10ce44ae64 | checkpoint | Gas released into system
62aef16b-a501-5a5a-a9ac-0995efadb72c | checkpoint | Power feed wired to Condenser and live
d8ac9f9f-453a-553e-ab58-7c18b41f754b | checkpoint | Indoor Unit run, fan speeds, modes etc
695373f1-733f-5214-9bbe-7efc8e042ec6 | checkpoint | Commissioning form completed & given to TSL
7ff22ae7-5c2a-5825-834e-b7c3580f4166 | section | Handover checks
e272e1a1-3b89-5f1a-8a97-c6614ff00009 | checkpoint | All works completed 100% as per spec
1e2a3dac-543d-5eec-9ba8-b776b2e05299 | checkpoint | Area left tidy
12ace0ba-1a15-4972-8071-fdedac3e8c3c | checkpoint | All works completed 100% as per spec
55a7ad37-ac1b-5564-9f30-4c9351b5290c | signoff | Request Review/Raise remedial
74e54999-546a-5dd6-9dc2-50addba76db5 | checklist | Ducting QA |  | Ducting QA
2e6301c3-1dee-5ce9-a500-9153938730b4 | section | Preinstall checks
c0e9bd74-e7d8-5ee9-bae7-2272d9eaa5db | checkpoint | Area Accessible
9fbbfadc-ce9e-519d-b0d4-ed277d2481df | checkpoint | Penetratios done in floors and walls by RHC (if needed)
85b27dbb-e924-5812-aa29-27cc4b0e0714 | checkpoint | Area clear and no obstructions
cea0d2df-c1cd-5c8e-99cf-237b873012b2 | checkpoint | Space for ducting, no other trades in our way
442d9760-bb1f-52a8-b863-f16df563558b | checkpoint | Substrate acceptable and ok to begin work
84845e85-e4df-5236-958b-8ce4a71e1a87 | signoff | Request Review/Raise remedial
f5ac3e19-1f50-5de3-8b84-04d91bb5a4fa | section | Ducting 1st Fix checks
27c207e9-dd9f-5ff9-977a-f1d59f12aadc | checkpoint | Fan/AHU installed straight and level
4e507924-686c-5948-9505-b46f90352f61 | checkpoint | Flexible connections on fan
3187ea52-abc8-516c-b21a-c7ddeeb0e18d | checkpoint | Vibration Isolators on fan
a58f42f4-99b2-55a2-9619-08e2314ae9e6 | checkpoint | Fan sealed to upstand/Ductwork
7347526a-7274-5cbf-9c65-5703e31f0177 | checkpoint | Heater installed to correct orientation
bdec3869-1cee-5d57-a633-a12fb3358a6a | checkpoint | Ductwork run straight level and well supported
de689ce9-7f3c-56eb-bae8-25f47b2aac35 | checkpoint | All ductwork joins sealed
a8bed24d-b6d8-5d2c-97ce-db17d8a4d15f | checkpoint | All SAB joins sealed and taped
0703ffc0-6997-5402-bfa6-9b07d6f72d49 | checkpoint | Ductwork Insulated where required
708e4e17-519d-594c-a82b-e430423d88a6 | checkpoint | All flexible ducts cable tied and taped to duct
f544b74e-d2f0-5f81-819f-8b8e49169f45 | checkpoint | All seismic restraints in place
0cf2d316-5f6c-53c1-9b33-ae9d5604d9fb | checkpoint | Flexible ducts fixed in place to grille location
7d8f40ed-696b-572d-863c-3acce6550de2 | checkpoint | Grille locations/Access Panels marked on plans
8658e89d-4945-54e0-b6ca-31e67d96b352 | checkpoint | Wiring in place, power and control
810b05cf-7902-515a-84a2-31e80f79327a | checkpoint | Filter in place and accessible
f2118d22-b9ae-563b-8e10-4653999066e5 | checkpoint | Fire Dampers installed to manufacturers instructions
eeaa774c-fef4-523c-bf09-6b6e60f028c2 | checkpoint | Balancing dampers locked open and accessible
58a17b2b-582e-5646-b7d8-3e423767a274 | checkpoint | Fan Serial Number
664355a3-7f97-52ca-904e-9ad47c122fdc | checkpoint | Heater Bank Serial Number
225c84fb-f0b8-5bde-9f0f-ab7b75168086 | checkpoint | Duct cleaning access panels in place
62f11f63-d185-5789-a50d-50e251d9091e | signoff | Request Review/Raise remedial
7662dacd-338e-59e8-98ac-864b95d19b60 | section | Ducting 2nd Fix checks
fa735cc5-ca14-5191-9baa-8d0ba72f4ec4 | checkpoint | Grilles installed square and level
6cf4ffda-8d30-56d6-b3b5-146fdd9930e7 | checkpoint | Fingerprints removed grilles/walls/ceilings
a4eec9d9-a5f7-5d9e-bb49-295a77c5a557 | checkpoint | Flexible duct cable tied and taped to grilles
ccbc579d-27eb-5a02-b4d4-4da30b5906d9 | checkpoint | Fans/Filters/Dampers accessible
534eee55-7884-578b-af75-0bc3ba146c92 | checkpoint | Filter can be removed
b4089446-0854-5f9a-a832-9c56533c184d | checkpoint | Controllers fittted off
695373f1-733f-5214-9bbe-7efc8e042ec6 | checkpoint | Commissioning form completed & given to TSL
1ff39581-d8eb-5b41-bd8b-44f76fac4d73 | signoff | Request Review/Raise remedial
7ff22ae7-5c2a-5825-834e-b7c3580f4166 | section | Handover checks
e272e1a1-3b89-5f1a-8a97-c6614ff00009 | checkpoint | All works completed 100% as per spec
1e2a3dac-543d-5eec-9ba8-b776b2e05299 | checkpoint | Area left tidy
db652377-a401-4be6-b3ea-8ed1317d1a7d | checkpoint | All works completed 100% as per spec
1624cb52-f3af-50f5-bb69-a5f4423fe327 | signoff | Request Review/Raise remedial
7ad3dace-77f3-5b83-857e-ce49e66672af | checklist | Jet Pulse Fan |  | Jet Pulse Fan
d53c9c00-f161-5e99-a902-c5ca41fd3083 | section | Pre-Start SA Fan
da2534a7-c54d-58b8-bdb4-03fca3bcb625 | checkpoint | Area clear, access good, enough space for install
523f8f81-a708-5af5-8b8f-47a44f2f3d96 | checkpoint | Duct Route clear, Penetrations complete
301f26a6-09ca-55ed-b9c0-d193f8e95f1d | checkpoint | Nogs/Supports in place
c83195a6-4ac6-55b4-84b2-ec9b7cd5a913 | section | First Fix SA Fan
e0ee8f71-7a1f-593b-96aa-7834627113e4 | checkpoint | Fan installed straight and level and correct orientation.
b2cd2979-64d3-54ef-9594-2751b8c492fd | checkpoint | Correct Fan installed
78a81fa0-6c8c-5844-98b4-27716dfcc55f | checkpoint | Fan serial No. recorded
bae452f7-7e96-53f4-8611-95128a9ed3ab | checkpoint | Fan seismically braced and vibration isolated
cb9731c7-20ea-5b5a-9b30-3c42b8cd370c | checkpoint | Supply cable installed correctly, protected and secured
decd263d-3a63-5f96-9bf0-fa5e17d72e97 | checkpoint | Supply cable type, size and manufacturer
34707a92-7a33-56a4-986b-671475ef52ec | checkpoint | Circuit protection type and rating
8733697c-8467-5a6b-9ed6-15fa5a9b1b23 | checkpoint | Correctly rated isolator installed to standards
bac628c8-4ee9-57fa-b53d-b277b2b3f5b6 | checkpoint | Interconnecting cables correctly installed and protected
2d839e9b-7ab2-5662-b4c2-6fe6009a0c8e | checkpoint | Control cables correct rating and type
00e2c824-bc70-5dff-b460-feb60427395f | checkpoint | Screened cables drain to earth as per specifications
ebaa347d-ce9c-5f56-8788-d18bae4c017e | checkpoint | Control cables maintain minimum distance from power cables
6ddcbc6d-41ba-54d8-abd5-5388053b4420 | checkpoint | Daisy chain loops complete and correct
b929e51e-bf6d-5092-b7ee-24252d6267e2 | checkpoint | Remote controller cable installed