## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Fire Dampers
section | Pre-Start Fire Damper
checkpoint | Area clear, access good, enough space for install
checkpoint | Duct Route clear, Penetrations complete
section | First Fix Fire Damper
checkpoint | Correct Fire Damper installed. (Insert Photo)
checkpoint | Fire Damper installed straight and level with correct orientation.
checkpoint | Breakaway joints either side of fire dampers, taped then cable tied.
checkpoint | Fire Dampers installed to manufacturers specifications. Drop tested where applicable
checkpoint | Access Panels in duct for fire dampers.
checkpoint | Building Access Panel requirements are marked and given to builders
checkpoint | Plans marked up for As Builts with Access Panel locations
section | Second Fix Fire Damper
checkpoint | Fire Damper Label affixed, Asset Number applied.
checkpoint | Fire Dampers Access Panels still accessible for maintenance
checkpoint | Area left clean and tidy, finger prints removed
checkpoint | Fire Damper sealed to structure both sides.
section | Commission Fire Damper
checkpoint | Drop Tested as applicable
checkpoint | Drop Test Motorised Fire Dampers with Fire Engineer.
checkpoint | Fire Damper Label filled out, photo uploaded.
checkpoint | Form TSL05.8A, Fire/Smoke Damper Test Sheet, updated for Project Completion
checkpoint | Commissioning paperwork reviewed and accepted by Project Manager