## Master List Templates
Id | Type | Name | Values | Prompting Name
474e22cd-c1c6-5690-9265-46640d3c020c | checklist | ITP - Pavement Detail 'H' RAB | itp | ITP - Pavement Detail 'H' RAB
af47e411-ce3d-57a0-a879-13c797d51078 | checkpoint | 1 - Existing Pavement
4110ad7a-77f4-41ee-addd-23a8f894a06b | note | Activity Task: Construction
2c5bda63-7cad-46f5-b581-0bf7e48eeadb | note | Acceptance Criteria: Visual inspection during shoulder check out works of entire project, including measurement of low areas or at least 25m intervals with a minimum of 3 per exposed area.
977e2c34-ec20-49aa-9ff3-5963b524aef0 | note | Certifying Documents and Frequency: 25m intervals. Engineer notification prior to commencement of pavement construction
40c004ec-59e4-41ae-962d-7918d7539674 | note | Engineer’s Representative: H
68510cd8-8102-581a-a1c7-1c28355d8541 | signoff | HOLD POINT AUTHORITY
048bd58a-e6a3-5bd9-83b8-a28e8b66df11 | checkpoint | 2 - Subgrade
9d307d61-1daa-4935-9a6c-2f69be83d13e | note | Activity Task: Construction
0ba80f38-5f38-45d6-afe6-ecceba91175a | note | Acceptance Criteria: Check insitu lower subbase is minimum of 150mm over a subgrade of Min CBR 5. If not undercut to 580mm and construct lower subbase 200mm with Gap65
16b350b2-4820-4d28-8a66-c9a6c2462b08 | note | Certifying Documents and Frequency: 1 Scala CBR Equivalent test per 10 m2 (minimum) and Engineer’s visual inspection at each dig out location. Scala Test sheetse
a9efc592-ba54-434a-acac-0fcf0ae816a9 | note | Supervisor, Foreman or Subcontractor: W
ed38c259-b13d-5bb2-b4e6-022383ddcfb9 | checkpoint | 3 - Subgrade/Dig outs
cc6f4a90-5735-4116-b190-58685a0c8b27 | note | Activity Task: Construction/Test
72fb6962-f70b-4d16-afaa-2bb5e7eeb81f | note | Acceptance Criteria: Weak areas of subgrade to be cut out and backfilled where determined necessary: Check insitu lower subbase is minimum of 150mm over a subgrade of Min CBR 5. If not undercut to 580mm and construct lower subbase 200mm with Gap65, Inspection Check sheet
4460a5cd-5d23-4787-828d-4f71f18e9b4c | note | Certifying Documents and Frequency: 1 Scala CBR Equivalent test per 10 m2 (minimum) and Engineer’s visual inspection at each dig out location. Yes – prior to dig out, results required prior to payment.
2835080b-df7b-412b-a068-40f17d10b83e | note | Engineer’s Representative: H
df8ff0ad-f20a-5897-84ab-519e26dea928 | signoff | HOLD POINT AUTHORITY
5c086610-bd1e-55a8-91f2-969be902104e | checkpoint | 4 - Proof Roll
2cdf64fd-d110-4c96-abe0-e40c836cc36b | note | Activity Task: Construction
eb4a4640-2917-4f32-8391-c0d6403e4b9d | note | Acceptance Criteria: Roll with 10T steel wheel roller in presence of Engineer
ad5698e6-362b-48d4-9de9-d683b0ea2bbf | note | Certifying Documents and Frequency: Any unsatisfactory areas which become evident during such testing shall be undercut 200mm and backfilled with GAP 65
9bbf8a97-52a9-58b8-8b4f-df48e4c485b0 | checkpoint | 4.1 - Subsoils
e2399b80-ceb2-46a7-bbf3-f703d2fffdad | note | Activity Task: Material Supply
dfe6f441-2bdc-4962-b804-b7cdce4dd84e | note | Acceptance Criteria: Subsoil drain materials shall comply with TNZ F/2:2000– Specification for pipe subsoil drains. Pipes for subsoil drains shall be slotted 110mm diameter corrugated HDPE.
2b18eb4d-2a1c-44ee-ac1c-12ee43612eef | note | Certifying Documents and Frequency: Compliance certification from supplier
1a56c66a-bbe4-5d44-ae48-450613de1458 | checkpoint | 4.2 - Subsoils
ef3bb461-3ae1-4cf8-92a5-dccf7edf60c6 | note | Activity Task: Construction
5cf03f74-2598-49ae-a106-abf117df7729 | note | Acceptance Criteria: Subsoil pipes for pavement drainage shall be in accordance with TNZ F/5:2000 except that the subsoil pipe may be placed immediately underneath the overlying granular pavement layer, with 50mm of drainage metal each side and below the pipe. Subsoil drains to be laid on hard pan below subgrade or otherwise governed by the height of stormwater outlets from CPs into existing Stormwater line. 20/7 drainage metal to be used
64171071-ed0d-4cd9-a3b2-0d1d1f0420c2 | note | Certifying Documents and Frequency: Photos and checklist
c905620f-0551-5c59-a793-01dc3904d9d6 | checkpoint | 5 - Sub-base
0012d7ad-7169-44f5-b6b9-c43814b04bd6 | note | Activity Task: Material Supply
72afa857-d1f5-441f-8dd7-8a303f984d08 | note | Acceptance Criteria: Gap 65
f64d94ee-8f8e-5229-81e4-f7ce2a483351 | checkpoint | 6 - Sub-base
96415c76-6bb4-4950-8ab8-f49390f8d273 | note | Activity Task: Test/ Material Supply
bd0677e1-3585-4f48-bc75-41b781d45049 | note | Acceptance Criteria: Proportion of broken faces. Test to TNZ M/4 broken faces content, NZS 4407: 2015 Test 3.14 no less than 70%
96e4f4d0-511c-4b10-a849-8b0eda991460 | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
3cdee05e-6e0d-47a2-bd0b-b55e8715e776 | note | Project Manager or Delegated Person: R
60803864-0d51-550d-b6f8-b48442638f1e | checkpoint | 7 - Sub-base
ddc6d472-0c7d-467f-8af1-d06004e8662b | note | Activity Task: Test/ Material Supply
5dfd18b1-e744-4893-bb5d-e7426bcb2518 | note | Acceptance Criteria: Sand equivalent to NZS 4407:1991 Test 3.6. Sand equivalent to meet specification
3f89314b-4883-4fbc-8d2d-2b94001c9161 | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
8999844c-2a62-4043-a20a-5683f26de4c4 | note | Project Manager or Delegated Person: R
8f086650-2934-5dce-8198-22dab48b4fb3 | checkpoint | 8 - Sub-base
967bbd3b-79fb-4140-af75-85c6f537f100 | note | Activity Task: Test/ Material Supply
7047924b-4f14-4e32-bdc6-067a73e265a5 | note | Acceptance Criteria: Crushing resistance to NZS 4407:1991 Test 3.10.
1d152566-3743-42fc-9d55-75773a46778b | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
6cc43409-eece-49ff-a161-767c5fb246e2 | note | Project Manager or Delegated Person: R
5ee52333-6255-51e1-878a-06e678461be0 | checkpoint | 9 - Sub-base
0470060d-4533-49ba-aa43-4225b2d86acd | note | Activity Task: Test/ Material Supply
11063b13-3d7b-4a69-8b96-616abacd4f5c | note | Acceptance Criteria: Weathering quality to NZS 4407:1991 Test 3.1.1 Compliance certificate < 6 months old or test result on sample from site, per source (stockpile).
5e83f876-f240-459a-be3f-adbb6a2d7d97 | note | Certifying Documents and Frequency: Prior to placement of subbase and base course
0bfccc44-f78b-4f66-b67c-ab2055801904 | note | Project Manager or Delegated Person: R
b0433263-2107-5bb8-a9ab-f88cc155d70c | checkpoint | 10 - Sub-base
9e6a9491-983f-4e25-a928-1360c1ed107c | note | Activity Task: Construction/Test
1af2714c-71a2-4519-8fec-63802fba4cb7 | note | Acceptance Criteria: Maximum Laboratory Dry Density (MDD) of aggregate at Optimum Moisture Content (OMC) to NZS 4402:1986, Test 4.1.3 Per source (stockpile) – to be undertaken on representative stockpiled aggregate.
efe2eda9-c8c9-4927-a02b-301c3c073689 | note | Certifying Documents and Frequency: A minimum of 5 samples is required for stabilisation lengths less than or equal to 400m
2a931fa4-3e1c-4717-b8b4-3ace503fe63d | note | Engineer’s Representative: H
b1268d83-f5cb-5efe-9809-b0b6b30d3d8e | signoff | HOLD POINT AUTHORITY
8c95b94b-4d6f-5903-9aac-be1d7c42888e | checkpoint | 11 - Lower Subbase
872a3bd8-c64c-428f-9158-445803f764aa | note | Activity Task: Construction
02ae493d-30f3-4969-840e-c2f037b74c14 | note | Acceptance Criteria: Check insitu lower subbase is minimum of 150mm over a subgrade of Min CBR 5. If not undercut to 580mm and construct lower subbase 200mm with Gap65. Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
ed6d34e2-55dc-4af3-ba82-7d7e35439e5e | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 95% of MDD, no individual test less than 92% of MDD.
107f7b53-f51c-4cd0-bd2d-55136ee5b8a4 | note | Project Manager or Delegated Person: P
f8c00493-c5c7-5efa-b018-2a4a65691c2e | checkpoint | 11.1 - Upper Subbase
0268ce79-d03c-4bed-bdcd-3fc3de506db2 | note | Activity Task: Cement Supply
7b1b52a5-f4f9-4423-ae5e-54ff782fee2f | note | Acceptance Criteria: Application rate to be 2% as specified
98ab10fb-a0d3-42b2-8956-6e98a1c82f82 | note | Certifying Documents and Frequency: Application rate to be checked per 400 m2 of stabilisation.
da816172-7499-5256-a481-ea253ad50e17 | checkpoint | 12 - Upper Subbase
e4eb3601-a79a-46b8-9580-1bee564d0004 | note | Activity Task: Construction
2a747d5d-d00f-4640-975e-eabee78f5957 | note | Acceptance Criteria: 150mm Cement modified AP65 upper subbase
af2b1eb5-e599-449a-b60a-110836fc296c | note | Project Manager or Delegated Person: P
b01ef088-9e4d-5d57-9a50-98f1530f2cb1 | checkpoint | 13 - Completed sub-base prior to placement of AC20
7145f854-50ee-49c8-afe5-bef6e3af0c2a | note | Activity Task: Test
5fd0cf98-a185-4c75-ac6a-d0c681bd0e3a | note | Acceptance Criteria: Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
6671c9d6-2227-4008-990f-4784a2ebd890 | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 98% of MDD, no individual test less than 95% of MDD.
983fe555-1e69-49de-8ab1-38517248704c | note | Engineer’s Representative: H
9b4f1ca5-0ef7-5a5e-b5cd-219d8aa4796b | signoff | HOLD POINT AUTHORITY
27c891b7-6241-5e90-9b8e-9a5514839d83 | checkpoint | 14 - Completed sub-base prior to placement of AC20
462d7b35-fb93-40a4-b249-8a2cd5abfc11 | note | Activity Task: Construction
10ed2c82-ba33-4272-94c6-bfe3bfaa2436 | note | Acceptance Criteria: Straight edge checks on surface shape at randomly staggered transverse positions at 20m intervals throughout.
53615b9d-d0c4-47ad-8caf-3f39ca2178b0 | note | Certifying Documents and Frequency: No point on the surface shall vary more than 10mm from a 3m straight edge. No area of the completed surface shall pond water
3ca552ce-55c0-4c7e-9d46-4820b205ec8b | note | Supervisor, Foreman or Subcontractor: W
05d0df6e-24e0-503a-aab8-b94149b4d2c9 | checkpoint | 15 - Completed sub-base prior to placement of AC20
752d4a67-ab34-4eda-bcf4-7adfd5f82af1 | note | Activity Task: Construction
59f272d5-73ea-4769-82d7-15cda5bf749c | note | Acceptance Criteria: Provide a sound finished surface to line and level as specification. Surface shape matches design and minimum pavement depth provided.
996bf5de-12cd-48a6-b2a5-4c5920a34abd | note | Certifying Documents and Frequency: Visual inspection by Engineer. Surface to be as specified. Engineer to be informed when surface is ready for inspection.
01611e15-cce6-4ceb-aacf-0591cf72adfd | note | Engineer’s Representative: H
1969c378-cc3b-58fa-abc5-e6ece89fef64 | signoff | HOLD POINT AUTHORITY
0de2bef6-0554-59c4-9cec-66898b16f2cf | checkpoint | 16 - Tack Coat
7598989f-db9e-4a4a-a198-1eced07925e0 | note | Activity Task: Construction
ea20250f-c5ba-468c-98f2-411c7a29e7f7 | note | Acceptance Criteria: Shall comply with TNZ M1 and TNZ M3. Apply Tack Coats between asphalt layers
45b37ac6-d1a6-495b-8ccf-72dbd9756180 | note | Certifying Documents and Frequency: Two samples per distributor load on Request. Refer to Subcontractors QA in separate ITP
e7f4028b-2b9d-5f9d-8faa-e3cb7f108414 | checkpoint | 17 - Asphaltic Concrete
bad0e199-a41f-4403-9959-0fee881c5aaf | note | Activity Task: Material supply
fb2f973a-7656-4eec-a9b3-722269591923 | note | Acceptance Criteria: As detailed in NZTA M/10:2014 specification
225bc549-172f-4b33-9de9-663ab620052d | note | Certifying Documents and Frequency: As detailed in NZTA M/10:2014 specification. Refer to Subcontractors QA in separate ITP
0f30817b-e0ff-53a5-817a-847bb0a0df0e | checkpoint | 18 - AC20
30863a0c-9401-41c6-9494-984b5e18e996 | note | Activity Task: Construction
216115ad-87ca-43b2-8c29-255c173d0429 | note | Acceptance Criteria: 180mm AC20 to be laid in two layers
d513a6fb-9a8f-4da8-b2f6-66eceac82d87 | note | Certifying Documents and Frequency: Testing to be done. Refer to Subcontractors QA in Separate ITP
78113b45-01f7-59cd-adb1-94430538ee25 | checkpoint | 19 - A14
54f50d76-9181-4011-b2f4-8fdbb1a5a209 | note | Activity Task: Construction
0e61d885-2a38-415e-b269-7f429f50a172 | note | Acceptance Criteria: 50mm A14
a6f23a6b-7d06-4237-8f54-d47395d4e026 | note | Certifying Documents and Frequency: Testing to be done. Refer to Subcontractors QA in separate ITP
4769e9ff-1359-5493-9a58-e9ec8a9894a9 | checkpoint | 20 - As -Builts
23d89377-4fa3-45d5-aba6-089802a97036 | note | Activity Task: As -Builts
fdf71285-16c0-4f7e-ac5f-c6cc878bb27d | note | Acceptance Criteria: A complete set of as-builts as per Contract 792 Specification Document shall be provided on the completion of the project. This will include but not limited to
c8cfc826-0da5-4939-bf9d-d0e727f62e4b | note | 1. The subgrade under new pavement areas;
b3879031-f42e-492b-ac65-1a2d965d5b15 | note | 2. Road construction – including subgrade, thicknesses and nature of materials used, surfacing; j. Extent of formation;
350c37ac-7edf-43ca-a2a5-a17de0e07e24 | note | Certifying Documents and Frequency: Prior to placement of Structural Asphalt Refer to Subcontractors QA in Separate ITP
65334946-7ad1-40ae-94fa-2e6946071ac2 | checklist | Upload Attachments |  | Upload Attachments
6da6f498-e18e-4121-84fe-5cd5ddfb8d03 | section | Details
abd1894c-f4ca-4bd7-adb7-c536eb29dab6 | checkpoint-no-value | Upload Attachments

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
442aad93-adf0-466b-9b61-28d2479dd0bb | checklist | ITP - SP1 Construction Works | itp | ITP - SP1 Construction Works
2c7af539-bc98-4b87-b9fe-c0204162b203 | section | Details
e21ad945-49df-4d29-8490-22885212e691 | checkpoint | 1 - Earthworks (Confluence upstream of Pump Station)
bcc937b5-8345-5eda-a7f3-c9c6e8621bf4 | note | ACTIVITY TASK - Stripped Surface
08d19a0d-cec2-52c3-8a92-61fe396c8576 | note | ACCEPTANCE CRITERIA - Visual Inspection
84fd8607-fd31-54b9-a7d2-12573cfae06e | note | FREQUENCY - At the completion of surface stripping prior to further construction
676e78d4-84ad-5889-9a61-63abd10d9e69 | note | Hold Point - W
38953851-063a-5fdb-b9e2-fcf3bc24971d | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A
a369fd65-114d-5b03-b6d9-ef6d8c589166 | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
6a003786-e28d-4117-bc52-73f3e071dae4 | checkpoint | 2 - Earthworks (Confluence upstream of Pump Station)
9b80deb8-3409-51dd-b798-e90b3ac93f44 | note | ACTIVITY TASK - Install Bunds
d91667b7-c004-53cf-8722-9521b5a3afef | note | ACCEPTANCE CRITERIA - Visual Inspection
388996f8-ea03-532e-82a3-414840fddef3 | note | FREQUENCY - At the completion of bund construction
2d062714-e87a-5074-9fc8-5c2db5dc57dd | note | Hold Point - W
d40d63b7-d817-5657-82c2-5cc460c0bd9a | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP
efae3c4c-dfd6-519c-b2bd-9ab1e304ab1a | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
6665f360-7cb9-4c98-9986-5f99101c89c6 | checkpoint | 3 - Earthworks (Confluence upstream of Pump Station)
faec83ec-0762-56c3-84db-fe6745b34161 | note | ACTIVITY TASK - Install Silt Control
85c09c47-d103-508b-8cc3-938074a0f6ba | note | ACCEPTANCE CRITERIA - Visual Inspection
27be0d24-149b-50c6-85be-070a3e8070df | note | FREQUENCY - At the completion of silt control install
b8b73e9c-f10f-5364-aa06-92d8ed17d5b6 | note | Hold Point - W
9d857ec5-6e9d-50ca-b27a-bd1c1ad317e3 | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP
b0acf5af-3433-5de0-b179-eea147629b33 | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
c616e160-9ca8-4324-a0f3-f0f7d7b29110 | checkpoint | 4 - Downstream Stilling Station
7609524f-0a87-57d5-83a8-ff529ea273a5 | note | ACTIVITY TASK - Stripped Surface
81b449d3-7a68-551e-ada7-f340f9eb5d98 | note | ACCEPTANCE CRITERIA - Visual Inspection
9d95864b-e268-52c6-8ecf-7fe7896aae31 | note | FREQUENCY - At the completion of surface stripping prior to further construction
f83d531f-a3f7-5e7e-9b21-a8ba56d642e7 | note | Hold Point - W
8c11615b-f059-5d0d-bd4c-8ed16ce742b2 | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A
40dfbf9a-0ced-5ccd-a6f9-28823aa434b3 | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
b5d76452-9082-49f2-9c75-c3c02d0980f4 | checkpoint | 5 - Downstream Stilling Station
d92b62c2-7b11-59b1-9422-60d1df2d6da8 | note | ACTIVITY TASK - Supply and place Geotextile and Reno Mattress
8c797cda-855d-5abe-ac2b-e22327b33d5f | note | ACCEPTANCE CRITERIA - Visual Inspection
fdac41d3-d241-570e-b197-5278ae93549b | note | FREQUENCY - At the completion of placement of Geotextile and Reno Mattress
a64ad89b-b6fa-56ae-9c20-d1ed661703ee | note | Hold Point - W
c681ab15-c395-5e52-a3fe-2b43caf12443 | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP
f3233b71-3bdc-533d-bd43-83a11f16831f | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
9cbeb004-a3ca-4b7d-a134-68585c36e8fc | checkpoint | 6 - Pump Station
43b93c2f-dfe6-569c-ac29-4daa847da626 | note | ACTIVITY TASK - Stripped Surface
abed088d-ac0f-581d-ba8e-11c3ec8a6bd2 | note | ACCEPTANCE CRITERIA - Visual Inspection
ad3fbec4-639b-5277-bce4-7c0f7e2cec96 | note | FREQUENCY - At the completion of surface stripping prior to further construction
981ef285-00db-5651-b827-2b84d644fea8 | note | Hold Point - W
5865c3e1-6dfe-54f9-84c8-7859c360bc30 | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A
abfb1b34-ef10-5e46-bc14-c445a4ac312b | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
3c9e5547-7560-48fe-a572-2bd5a83fe391 | checkpoint | 7 - Pump Station
e4b6d9cd-17fe-599b-bb8a-50eb30e50951 | note | ACTIVITY TASK - Hardfill against Walls
fd8f792d-7706-5f7a-b835-968d71270479 | note | ACCEPTANCE CRITERIA - 95% compaction required
a7895790-c272-5190-983c-00771d9643ef | note | FREQUENCY - Each layer, Max layer thickness 200mm
a984ba2a-9ab6-5cb0-b5f3-952741c86d66 | note | Hold Point - H
36703dff-fd44-5fd6-8ae0-e2e38c471232 | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test Certificates required
a8fbb1cc-4bba-5d1a-89a9-13d52127f924 | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
84c99834-9941-460c-9739-a00cdce892d8 | signoff | HOLD POINT
de4aec12-323d-4206-8fd9-ee15eaac0a8c | checkpoint | 8 - Pump Station
e9575ef3-83bf-59f7-98bc-8201416a039e | note | ACTIVITY TASK - Outlet and Discharge
6e3ec5dd-b83f-5263-b88d-21b0ab538083 | note | ACCEPTANCE CRITERIA - As per IFC drawings or Engineers instruction
dcd95400-f92d-5a6a-bc86-87eb6f824925 | note | FREQUENCY - Prior to construction
c231cee8-0073-5e84-9fe5-1b979afd0203 | note | Hold Point - H
ee9eb1ba-66a3-54de-9057-d07f15edb4c7 | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Check against IFC drawings specification
39e50bfa-ab67-56f1-b909-34f78c13c380 | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
91ad4e11-5da6-4acb-8f1d-b40369cb1442 | signoff | HOLD POINT
db7a99c2-bc76-4c5c-bacc-d9b24a65b90b | checkpoint | 9 - Pile driving
356f3e9a-6921-545f-a304-cdbf5d6d8858 | note | ACTIVITY TASK - Delivery inspection of piles
51341a57-33d7-5948-a0ac-94636c41ee68 | note | ACCEPTANCE CRITERIA - 10M 300 SED H5
155720f1-c141-5366-99c8-e8a3554d214d | note | FREQUENCY - Prior to pile driving
f4626f29-732f-588f-8aad-0e1727c946ff | note | Hold Point - H
91141e1c-0d01-5af6-994c-cea7583d4d43 | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Check pile tags
45cecd29-80ae-58e0-a924-edcc9f0f345c | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
9ac8976a-132a-46af-9f2d-42b88e5a05a8 | signoff | HOLD POINT
8283678e-a1ef-4ad0-bfd3-13785927207a | checkpoint | 10 - Pile driving
f1ab5b56-d105-527c-8974-e172d268bd19 | note | ACTIVITY TASK - Driving of timber piles
864d3784-3b7d-56f0-800f-af50ad78a22e | note | ACCEPTANCE CRITERIA - As per IFC drawings
43ee08cd-fd78-5694-8b38-52f319ec372d | note | FREQUENCY - Prior to backfill
34b76b2a-ead2-5182-8788-e228b8b58e55 | note | Hold Point - H
8c4c38aa-0a52-5b68-834c-4a693ba33b34 | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Piles driven to 10M depth top of pile RL-2800
d4ce7188-6020-5ea4-8f8d-246d42fc014f | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
7d796945-7b01-49bc-a7d4-5d3b78635f37 | signoff | HOLD POINT
52d3417e-c173-4876-a0ee-fde9827fd01b | checkpoint | 11 - Pile driving
76b9eb8e-3ae5-59aa-a877-f330564c9203 | note | ACTIVITY TASK - Piling card
fee7aeec-dc13-5d55-88c6-15f938550060 | note | ACCEPTANCE CRITERIA - As per IFC drawings
1eaccef8-8f35-51a6-bb12-27e521c81f79 | note | FREQUENCY - Prior to Backfill
8a627147-0fd7-59d1-8057-90a375e34315 | note | Hold Point - H
cd0f45ea-c7d0-56fb-9462-f5502d5578de | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Subcontractor QA
49fe34d5-4ca6-5916-8fa3-68aedc002686 | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
5e680913-5ed0-44c8-888d-fa19c77ae588 | signoff | HOLD POINT
595781d9-d4e2-4a3e-afc3-8a22b327fb0c | checkpoint | 12 - Excavation
e5a24f04-072c-5f80-9058-9f967a5148bc | note | ACTIVITY TASK - Excavate to RL - 1.2
e5b77532-c51b-5a20-befd-320e515658f5 | note | ACCEPTANCE CRITERIA - Surveyed as built
186b2856-3793-577f-9a3b-70d42760dae5 | note | FREQUENCY - Upon completion of Excavation
37a6a773-1a1b-5d6f-be49-56f96bfe6cc9 | note | Hold Point - H
a42f3944-3b8e-5982-b94f-66660036951a | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey data
d7e4cf18-fb79-569c-8133-2a7c0f4f8a4d | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
87f03f2b-0606-4f84-9d7f-d131a7839032 | signoff | HOLD POINT
7be1bc19-0325-40c8-8be6-2cd335368e82 | checkpoint | 13 - Installation of retaining wall plates
35e6a6a5-6031-567f-969e-6034e3653a93 | note | ACTIVITY TASK - Install plates
64e3f72a-8ff0-5ad4-a430-bf725ba6edfc | note | ACCEPTANCE CRITERIA - 22mm Steel plates
eba450c6-5638-55ac-bd36-6543d4d723a8 | note | FREQUENCY - During construction
1131696b-7066-5105-89af-822342085406 | note | Hold Point - H
b9fb1b39-18d6-5574-8ff1-ada5ce0fe9ca | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
70693c6c-7090-528f-9a0e-49adfdd46005 | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
32d8fa8b-82e4-45c8-aaf4-e79b47eee57d | signoff | HOLD POINT
8bac8f33-ce63-455c-88f1-438102c08e6b | checkpoint | 14 - Excavation
0a7ba927-92a1-5436-ae67-f3ea9b8b878a | note | ACTIVITY TASK - Excavate to RL - 2.8
fe54ea3c-c70b-5590-829d-8ffac7719e8b | note | ACCEPTANCE CRITERIA - Surveyed as built
80193549-2613-54c3-ae35-109f2b5346f8 | note | FREQUENCY - Upon completion of Excavation
09e9f3f4-1051-55f6-8f13-9edc22a68c33 | note | Hold Point - H
1636b95c-785d-5fb9-b9fc-ef113f634a96 | note | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey data
4d03bb9f-c309-5bc9-a282-9240ce246c10 | note | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
debfd15c-8e8d-4b45-898d-77f371a92867 | signoff | HOLD POINT