## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - SP1 Construction Works | itp |  |  |  |  | ITP - SP1 Construction Works
section | Details
checkpoint | 1 - Earthworks (Confluence upstream of Pump Station)
label | ACTIVITY TASK - Stripped Surface
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - At the completion of surface stripping prior to further construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 2 - Earthworks (Confluence upstream of Pump Station)
label | ACTIVITY TASK - Install Bunds
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - At the completion of bund construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 3 - Earthworks (Confluence upstream of Pump Station)
label | ACTIVITY TASK - Install Silt Control
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - At the completion of silt control install
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 4 - Downstream Stilling Station
label | ACTIVITY TASK - Stripped Surface
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - At the completion of surface stripping prior to further construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 5 - Downstream Stilling Station
label | ACTIVITY TASK - Supply and place Geotextile and Reno Mattress
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - At the completion of placement of Geotextile and Reno Mattress
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 6 - Pump Station
label | ACTIVITY TASK - Stripped Surface
label | ACCEPTANCE CRITERIA - Visual Inspection
label | FREQUENCY - At the completion of surface stripping prior to further construction
label | Hold Point - W
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
checkpoint | 7 - Pump Station
label | ACTIVITY TASK - Hardfill against Walls
label | ACCEPTANCE CRITERIA - 95% compaction required
label | FREQUENCY - Each layer, Max layer thickness 200mm
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test Certificates required
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
holdpoint | HOLD POINT
checkpoint | 8 - Pump Station
label | ACTIVITY TASK - Outlet and Discharge
label | ACCEPTANCE CRITERIA - As per IFC drawings or Engineers instruction
label | FREQUENCY - Prior to construction
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Check against IFC drawings specification
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
holdpoint | HOLD POINT
checkpoint | 9 - Pile driving
label | ACTIVITY TASK - Delivery inspection of piles
label | ACCEPTANCE CRITERIA - 10M 300 SED H5
label | FREQUENCY - Prior to pile driving
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Check pile tags
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
holdpoint | HOLD POINT
checkpoint | 10 - Pile driving
label | ACTIVITY TASK - Driving of timber piles
label | ACCEPTANCE CRITERIA - As per IFC drawings
label | FREQUENCY - Prior to backfill
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Piles driven to 10M depth top of pile RL-2800
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
holdpoint | HOLD POINT
checkpoint | 11 - Pile driving
label | ACTIVITY TASK - Piling card
label | ACCEPTANCE CRITERIA - As per IFC drawings
label | FREQUENCY - Prior to Backfill
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Subcontractor QA
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
holdpoint | HOLD POINT
checkpoint | 12 - Excavation
label | ACTIVITY TASK - Excavate to RL - 1.2
label | ACCEPTANCE CRITERIA - Surveyed as built
label | FREQUENCY - Upon completion of Excavation
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey data
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
holdpoint | HOLD POINT
checkpoint | 13 - Installation of retaining wall plates
label | ACTIVITY TASK - Install plates
label | ACCEPTANCE CRITERIA - 22mm Steel plates
label | FREQUENCY - During construction
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
holdpoint | HOLD POINT
checkpoint | 14 - Excavation
label | ACTIVITY TASK - Excavate to RL - 2.8
label | ACCEPTANCE CRITERIA - Surveyed as built
label | FREQUENCY - Upon completion of Excavation
label | Hold Point - H
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey data
label | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
holdpoint | HOLD POINT