## Sheet1
1.1 | Check for correct documentation | Prior to commencing any activity | Current revision drawing is being used including the Subcontractor’s copy. Current revision to be obtained via Aconex. | Drawings and drawing registers on Aconex | Visual inspection | This ITP signed by contractors Quality Represent ative. | HP* | Project Engineer | 1.1 - Check for correct documentation | Frequency - Prior to commencing any activity | Acceptance Criteria - Current revision drawing is being used including the Subcontractor’s copy. Current revision to be obtained via Aconex. | Reference Documents - Drawings and drawing registers on Aconex | Inspection/Test Method - Visual inspection | Record of conformity - This ITP signed by contractors Quality Represent ative. | HP* | Responsibility - Project Engineer | Date Completed: | 1.1 - Check for correct documentation
1.2 | Implementation of all measures and controls | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS CHAR(AMP) WP | PSP, EMP, TMP, SWMS, WP | Visual Inspection | This ITP signed by contractors Quality Represent ative. | HP* | Project Engineer | 1.2 - Implementation of all measures and controls | Frequency - Prior to commencing any activity | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS CHAR(AMP) WP | Reference Documents - PSP, EMP, TMP, SWMS, WP | Inspection/Test Method - Visual Inspection | Record of conformity - This ITP signed by contractors Quality Represent ative. | HP* | Responsibility - Project Engineer | Date Completed: | Frequency - Prior to commencing any activity
1.3 | Definition of the work area | Prior to commencing any activity | Work area has been cleared and limits of works defined on site. | Drawings | Visual Inspection | This ITP signed by contractors Quality Represent ative. | HP* | Project Engineer | 1.3 - Definition of the work area | Frequency - Prior to commencing any activity | Acceptance Criteria - Work area has been cleared and limits of works defined on site. | Reference Documents - Drawings | Inspection/Test Method - Visual Inspection | Record of conformity - This ITP signed by contractors Quality Represent ative. | HP* | Responsibility - Project Engineer | Date Completed: | Acceptance Criteria - Current revision drawing is being used including the Subcontractor’s copy. Current revision to be obtained via Aconex.
2.1 | Plant, Equipment and Tools | Prior to commencement. | List of all plant, equipment and tools to Contract Administrator prior to commencement of Works. | Cl 5605-1 WP5605-1 | Visual Inspection. | List of all plant equipment and tools to be submitted to Contract administrator. | WP | Site Engineer | 2.1 - Plant, Equipment and Tools | Frequency - Prior to commencement. | Acceptance Criteria - List of all plant, equipment and tools to Contract Administrator prior to commencement of Works. | Reference Documents - Cl 5605-1 WP5605-1 | Inspection/Test Method - Visual Inspection. | Record of conformity - List of all plant equipment and tools to be submitted to Contract administrator. | WP | Responsibility - Site Engineer | Date Completed: | Reference Documents - Drawings and drawing registers on Aconex
2.2 | Stabilised Calibration and demonstration of spraying equipment | 7 days Prior to commencement. | The Contractor must demonstrate to the Contract Administrator prior to the commencement of work that the spraying equipment complies with the Specifications. | Cl 5605-1 HP5605-1 | Verify | Aconex Submissio n/This ITP signed by Contract administrator. | HP | Site Engineer | 2.2 - Stabilised Calibration and demonstration of spraying equipment | Frequency - 7 days Prior to commencement. | Acceptance Criteria - The Contractor must demonstrate to the Contract Administrator prior to the commencement of work that the spraying equipment complies with the Specifications. | Reference Documents - Cl 5605-1 HP5605-1 | Inspection/Test Method - Verify | Record of conformity - Aconex Submissio n/This ITP signed by Contract administrator. | HP | Responsibility - Site Engineer | Date Completed: | Inspection/Test Method - Visual inspection
3.1 | Intention to proceed with works | 24 hours prior to commencement of works | Written intention to proceed with the Works and on what basis this decision has been made, at least 24 hours prior to commencement of works. Application of the rejuvenation material must only proceed when the pavement temperature is above 15 °C and rising. | Cl 5606-1 WP5606-1 | Notificatio n | This ITP signed by contractors Quality Represent ative. | WP | Site Engineer | 3.1 - Intention to proceed with works | Frequency - 24 hours prior to commencement of works | Acceptance Criteria - Written intention to proceed with the Works and on what basis this decision has been made, at least 24 hours prior to commencement of works. Application of the rejuvenation material must only proceed when the pavement temperature is above 15 °C and rising. | Reference Documents - Cl 5606-1 WP5606-1 | Inspection/Test Method - Notificatio n | Record of conformity - This ITP signed by contractors Quality Represent ative. | WP | Responsibility - Site Engineer | Date Completed: | Record of conformity - This ITP signed by contractors Quality Represent ative.
4.1 | Inspection of Surface | 24hours notice prior to commencement of works | 24 hours’ notice to the Contract Administrator for inspection of the surface to be rejuvenated. Prior to applying the Rejuvenating Material, the Contractor must prepare the pavements surface. This preparation may include but not be limited to: – Sweeping those areas of the surface contaminated with accumulations of soil, silt or other foreign and/or loose material. – Protecting all airfield light fittings and other structures and abutting concrete by suitable means. – Protecting all pavement markings by suitable means unless stated otherwise on the drawings. | Cl 5607-1 WP5607-1 | Verify | This ITP signed by all parties present including contractors administrator | WP | Site Engineer | 4.1 - Inspection of Surface | Frequency - 24hours notice prior to commencement of works | Acceptance Criteria - 24 hours’ notice to the Contract Administrator for inspection of the surface to be rejuvenated. Prior to applying the Rejuvenating Material, the Contractor must prepare the pavements surface. This preparation may include but not be limited to: – Sweeping those areas of the surface contaminated with accumulations of soil, silt or other foreign and/or loose material. – Protecting all airfield light fittings and other structures and abutting concrete by suitable means. – Protecting all pavement markings by suitable means unless stated otherwise on the drawings. | Reference Documents - Cl 5607-1 WP5607-1 | Inspection/Test Method - Verify | Record of conformity - This ITP signed by all parties present including contractors administrator | WP | Responsibility - Site Engineer | Date Completed: | HP*
5.1 | Transport and Storage of Rejuvenating material to site | 7 days prior to transporting rejuvenating material to site | During construction, the contractor must submit records on the transport and storage of the material on request by the Contract Administrator. | Cl 5608-1 HP5608-1 | Check | This ITP signed by contractors administrator | HP | Site Engineer | 5.1 - Transport and Storage of Rejuvenating material to site | Frequency - 7 days prior to transporting rejuvenating material to site | Acceptance Criteria - During construction, the contractor must submit records on the transport and storage of the material on request by the Contract Administrator. | Reference Documents - Cl 5608-1 HP5608-1 | Inspection/Test Method - Check | Record of conformity - This ITP signed by contractors administrator | HP | Responsibility - Site Engineer | Date Completed: | Responsibility - Project Engineer
5.2 | Application of Rejuvenating Material | 24hours notice prior to commencement of works | The Rejuvenating Material must be applied only in the presence of the Contract Administrator. Rejuvenating Material must only be applied using a suitably calibrated sprayer/applicator. Before each run is applied, the Contractor must mark out the pavement with removable markings to guide the sprayer when applying the Rejuvenating Material to ensure correct application. | Cl 5608-1 | Verify | This ITP signed by all parties present including contractors administrator | WP | Site Engineer | 5.2 - Application of Rejuvenating Material | Frequency - 24hours notice prior to commencement of works | Acceptance Criteria - The Rejuvenating Material must be applied only in the presence of the Contract Administrator. Rejuvenating Material must only be applied using a suitably calibrated sprayer/applicator. Before each run is applied, the Contractor must mark out the pavement with removable markings to guide the sprayer when applying the Rejuvenating Material to ensure correct application. | Reference Documents - Cl 5608-1 | Inspection/Test Method - Verify | Record of conformity - This ITP signed by all parties present including contractors administrator | WP | Responsibility - Site Engineer | Date Completed: | Date Completed:
5.3 | Application rate | During | The Rejuvenating Material must be applied at the application rates indicated as per the specification. Application rates will be included in daily record sheets. | Cl 5608-1 | Verify | This ITP signed by Contract administrator / Daily Spray Record Sheets | WP | Site Engineer | 5.3 - Application rate | Frequency - During | Acceptance Criteria - The Rejuvenating Material must be applied at the application rates indicated as per the specification. Application rates will be included in daily record sheets. | Reference Documents - Cl 5608-1 | Inspection/Test Method - Verify | Record of conformity - This ITP signed by Contract administrator / Daily Spray Record Sheets | WP | Responsibility - Site Engineer | Date Completed: | 1.2 - Implementation of all measures and controls
6.1 | Application of fuel resistant surface treatment | Prior to commencement of works | Proposed production and process control testing programme. | Cl 5612-1 HP5612-1 | Verify | Aconex Submissio n of PQP / This ITP signed by Contract administrator | HP | Quality Engineer/ Site Engineer | 6.1 - Application of fuel resistant surface treatment | Frequency - Prior to commencement of works | Acceptance Criteria - Proposed production and process control testing programme. | Reference Documents - Cl 5612-1 HP5612-1 | Inspection/Test Method - Verify | Record of conformity - Aconex Submissio n of PQP / This ITP signed by Contract administrator | HP | Responsibility - Quality Engineer/ Site Engineer | Date Completed: | Frequency - Prior to commencing any activity
6.2 | Test Certificates | During surface treatment works | Reference samples, test certificates, MSDS and technical data as specified for component materials and previous usage of the Rejuvenating Material and sand | Cl 5612-2 HP5612-2 | Verify | Test Certificate s / Reference Samples / This ITP signed by Contract administrator | HP | Site Engineer | 6.2 - Test Certificates | Frequency - During surface treatment works | Acceptance Criteria - Reference samples, test certificates, MSDS and technical data as specified for component materials and previous usage of the Rejuvenating Material and sand | Reference Documents - Cl 5612-2 HP5612-2 | Inspection/Test Method - Verify | Record of conformity - Test Certificate s / Reference Samples / This ITP signed by Contract administrator | HP | Responsibility - Site Engineer | Date Completed: | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS CHAR(AMP) WP
6.3 | Work Method Statement | Prior to commencement of works | The Contractor’s work method statement for the processes to be used for the application of the Rejuvenating Material, including surface cleaning/preparation, priming (as required), number of coats to be applied and curing time must be submitted with the reference samples. | Cl 5612-3 HP5612-3 | Verify | Aconex Submissio n / Reference samples / This ITP signed by Contract administrator | HP | Site Engineer | 6.3 - Work Method Statement | Frequency - Prior to commencement of works | Acceptance Criteria - The Contractor’s work method statement for the processes to be used for the application of the Rejuvenating Material, including surface cleaning/preparation, priming (as required), number of coats to be applied and curing time must be submitted with the reference samples. | Reference Documents - Cl 5612-3 HP5612-3 | Inspection/Test Method - Verify | Record of conformity - Aconex Submissio n / Reference samples / This ITP signed by Contract administrator | HP | Responsibility - Site Engineer | Date Completed: | Reference Documents - PSP, EMP, TMP, SWMS, WP
6.4 | Lot Submission for Surface Rejuvenation | Per shift | Submit detailed information for each shift. Details include application rate, location, test certificates and daily spray records etc. | Method Statement | Review of Lot Submissio n details | Lot Submissio n document s submitted to Contract administrator | WP | Site Engineer | 6.4 - Lot Submission for Surface Rejuvenation | Frequency - Per shift | Acceptance Criteria - Submit detailed information for each shift. Details include application rate, location, test certificates and daily spray records etc. | Reference Documents - Method Statement | Inspection/Test Method - Review of Lot Submissio n details | Record of conformity - Lot Submissio n document s submitted to Contract administrator | WP | Responsibility - Site Engineer | Date Completed: | Inspection/Test Method - Visual Inspection
6.5 | Rejected materials and work | As required | Non-conforming materials or areas must be repaired or rectified by the contractor to comply fully with the specification. | Cl 5613 | Review and verification | This ITP signed by Contract administrator | HP | Site Engineer | 6.5 - Rejected materials and work | Frequency - As required | Acceptance Criteria - Non-conforming materials or areas must be repaired or rectified by the contractor to comply fully with the specification. | Reference Documents - Cl 5613 | Inspection/Test Method - Review and verification | Record of conformity - This ITP signed by Contract administrator | HP | Responsibility - Site Engineer | Date Completed: | Record of conformity - This ITP signed by contractors Quality Represent ative.
HP*
Responsibility - Project Engineer
Date Completed:
1.3 - Definition of the work area
Frequency - Prior to commencing any activity
Acceptance Criteria - Work area has been cleared and limits of works defined on site.
Reference Documents - Drawings
Inspection/Test Method - Visual Inspection
Record of conformity - This ITP signed by contractors Quality Represent ative.
HP*
Responsibility - Project Engineer
Date Completed:
2.1 - Plant, Equipment and Tools
Frequency - Prior to commencement.
Acceptance Criteria - List of all plant, equipment and tools to Contract Administrator prior to commencement of Works.
Reference Documents - Cl 5605-1 WP5605-1
Inspection/Test Method - Visual Inspection.
Record of conformity - List of all plant equipment and tools to be submitted to Contract administrator.
WP
Responsibility - Site Engineer
Date Completed:
2.2 - Stabilised Calibration and demonstration of spraying equipment
Frequency - 7 days Prior to commencement.
Acceptance Criteria - The Contractor must demonstrate to the Contract Administrator prior to the commencement of work that the spraying equipment complies with the Specifications.
Reference Documents - Cl 5605-1 HP5605-1
Inspection/Test Method - Verify
Record of conformity - Aconex Submissio n/This ITP signed by Contract administrator.
HP
Responsibility - Site Engineer
Date Completed:
3.1 - Intention to proceed with works
Frequency - 24 hours prior to commencement of works
Acceptance Criteria - Written intention to proceed with the Works and on what basis this decision has been made, at least 24 hours prior to commencement of works. Application of the rejuvenation material must only proceed when the pavement temperature is above 15 °C and rising.
Reference Documents - Cl 5606-1 WP5606-1
Inspection/Test Method - Notificatio n
Record of conformity - This ITP signed by contractors Quality Represent ative.
WP
Responsibility - Site Engineer
Date Completed:
4.1 - Inspection of Surface
Frequency - 24hours notice prior to commencement of works
Acceptance Criteria - 24 hours’ notice to the Contract Administrator for inspection of the surface to be rejuvenated. Prior to applying the Rejuvenating Material, the Contractor must prepare the pavements surface. This preparation may include but not be limited to: – Sweeping those areas of the surface contaminated with accumulations of soil, silt or other foreign and/or loose material. – Protecting all airfield light fittings and other structures and abutting concrete by suitable means. – Protecting all pavement markings by suitable means unless stated otherwise on the drawings.
Reference Documents - Cl 5607-1 WP5607-1
Inspection/Test Method - Verify
Record of conformity - This ITP signed by all parties present including contractors administrator
WP
Responsibility - Site Engineer
Date Completed:
5.1 - Transport and Storage of Rejuvenating material to site
Frequency - 7 days prior to transporting rejuvenating material to site
Acceptance Criteria - During construction, the contractor must submit records on the transport and storage of the material on request by the Contract Administrator.
Reference Documents - Cl 5608-1 HP5608-1
Inspection/Test Method - Check
Record of conformity - This ITP signed by contractors administrator
HP
Responsibility - Site Engineer
Date Completed:
5.2 - Application of Rejuvenating Material
Frequency - 24hours notice prior to commencement of works
Acceptance Criteria - The Rejuvenating Material must be applied only in the presence of the Contract Administrator. Rejuvenating Material must only be applied using a suitably calibrated sprayer/applicator. Before each run is applied, the Contractor must mark out the pavement with removable markings to guide the sprayer when applying the Rejuvenating Material to ensure correct application.
Reference Documents - Cl 5608-1
Inspection/Test Method - Verify
Record of conformity - This ITP signed by all parties present including contractors administrator
WP
Responsibility - Site Engineer
Date Completed:
5.3 - Application rate
Frequency - During
Acceptance Criteria - The Rejuvenating Material must be applied at the application rates indicated as per the specification. Application rates will be included in daily record sheets.
Reference Documents - Cl 5608-1
Inspection/Test Method - Verify
Record of conformity - This ITP signed by Contract administrator / Daily Spray Record Sheets
WP
Responsibility - Site Engineer
Date Completed:
6.1 - Application of fuel resistant surface treatment
Frequency - Prior to commencement of works
Acceptance Criteria - Proposed production and process control testing programme.
Reference Documents - Cl 5612-1 HP5612-1
Inspection/Test Method - Verify
Record of conformity - Aconex Submissio n of PQP / This ITP signed by Contract administrator
HP
Responsibility - Quality Engineer/ Site Engineer
Date Completed:
6.2 - Test Certificates
Frequency - During surface treatment works
Acceptance Criteria - Reference samples, test certificates, MSDS and technical data as specified for component materials and previous usage of the Rejuvenating Material and sand
Reference Documents - Cl 5612-2 HP5612-2
Inspection/Test Method - Verify
Record of conformity - Test Certificate s / Reference Samples / This ITP signed by Contract administrator
HP
Responsibility - Site Engineer
Date Completed:
6.3 - Work Method Statement
Frequency - Prior to commencement of works
Acceptance Criteria - The Contractor’s work method statement for the processes to be used for the application of the Rejuvenating Material, including surface cleaning/preparation, priming (as required), number of coats to be applied and curing time must be submitted with the reference samples.
Reference Documents - Cl 5612-3 HP5612-3
Inspection/Test Method - Verify
Record of conformity - Aconex Submissio n / Reference samples / This ITP signed by Contract administrator
HP
Responsibility - Site Engineer
Date Completed:
6.4 - Lot Submission for Surface Rejuvenation
Frequency - Per shift
Acceptance Criteria - Submit detailed information for each shift. Details include application rate, location, test certificates and daily spray records etc.
Reference Documents - Method Statement
Inspection/Test Method - Review of Lot Submissio n details
Record of conformity - Lot Submissio n document s submitted to Contract administrator
WP
Responsibility - Site Engineer
Date Completed:
6.5 - Rejected materials and work
Frequency - As required
Acceptance Criteria - Non-conforming materials or areas must be repaired or rectified by the contractor to comply fully with the specification.
Reference Documents - Cl 5613
Inspection/Test Method - Review and verification
Record of conformity - This ITP signed by Contract administrator
HP
Responsibility - Site Engineer
Date Completed: