## Sheet1
1 | Earthworks (Confluence upstream of Pump Station) | Stripped Surface | Visual Inspection | At the completion of surface stripping prior to further construction | W | N/A | Not Required | 1 - Earthworks (Confluence upstream of Pump Station) | ACTIVITY TASK - Stripped Surface | ACCEPTANCE CRITERIA - Visual Inspection | FREQUENCY - At the completion of surface stripping prior to further construction | Hold Point - W | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | 1 - Earthworks (Confluence upstream of Pump Station)
2 | Earthworks (Confluence upstream of Pump Station) | Install Bunds | Visual Inspection | At the completion of bund construction | W | As per approved EMP | Not Required | 2 - Earthworks (Confluence upstream of Pump Station) | ACTIVITY TASK - Install Bunds | ACCEPTANCE CRITERIA - Visual Inspection | FREQUENCY - At the completion of bund construction | Hold Point - W | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | ACTIVITY TASK - Stripped Surface
3 | Earthworks (Confluence upstream of Pump Station) | Install Silt Control | Visual Inspection | At the completion of silt control install | W | As per approved EMP | Not Required | 3 - Earthworks (Confluence upstream of Pump Station) | ACTIVITY TASK - Install Silt Control | ACCEPTANCE CRITERIA - Visual Inspection | FREQUENCY - At the completion of silt control install | Hold Point - W | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | ACCEPTANCE CRITERIA - Visual Inspection
4 | Downstream Stilling Station | Stripped Surface | Visual Inspection | At the completion of surface stripping prior to further construction | W | N/A | Not Required | 4 - Downstream Stilling Station | ACTIVITY TASK - Stripped Surface | ACCEPTANCE CRITERIA - Visual Inspection | FREQUENCY - At the completion of surface stripping prior to further construction | Hold Point - W | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | FREQUENCY - At the completion of surface stripping prior to further construction
5 | Downstream Stilling Station | Supply and place Geotextile and Reno Mattress | Visual Inspection | At the completion of placement of Geotextile and Reno Mattress | W | As per approved EMP | Not Required | 5 - Downstream Stilling Station | ACTIVITY TASK - Supply and place Geotextile and Reno Mattress | ACCEPTANCE CRITERIA - Visual Inspection | FREQUENCY - At the completion of placement of Geotextile and Reno Mattress | Hold Point - W | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | Hold Point - W
6 | Pump Station | Stripped Surface | Visual Inspection | At the completion of surface stripping prior to further construction | W | N/A | Not Required | 6 - Pump Station | ACTIVITY TASK - Stripped Surface | ACCEPTANCE CRITERIA - Visual Inspection | FREQUENCY - At the completion of surface stripping prior to further construction | Hold Point - W | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A
7 | Pump Station | Hardfill against Walls | 95% compaction required | Each layer, Max layer thickness 200mm | H | Test Certificates required | Not Required | 7 - Pump Station | ACTIVITY TASK - Hardfill against Walls | ACCEPTANCE CRITERIA - 95% compaction required | FREQUENCY - Each layer, Max layer thickness 200mm | Hold Point - H | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test Certificates required | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
8 | Pump Station | Outlet and Discharge | As per IFC drawings or Engineers instruction | Prior to construction | H | Check against IFC drawings specification | Not Required | 8 - Pump Station | ACTIVITY TASK - Outlet and Discharge | ACCEPTANCE CRITERIA - As per IFC drawings or Engineers instruction | FREQUENCY - Prior to construction | Hold Point - H | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Check against IFC drawings specification | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | 2 - Earthworks (Confluence upstream of Pump Station)
9 | Pile driving | Delivery inspection of piles | 10M 300 SED H5 | Prior to pile driving | H | Check pile tags | Not Required | 9 - Pile driving | ACTIVITY TASK - Delivery inspection of piles | ACCEPTANCE CRITERIA - 10M 300 SED H5 | FREQUENCY - Prior to pile driving | Hold Point - H | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Check pile tags | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | ACTIVITY TASK - Install Bunds
10 | Pile driving | Driving of timber piles | As per IFC drawings | Prior to backfill | H | Piles driven to 10M depth top of pile RL -2800 | Not Required | 10 - Pile driving | ACTIVITY TASK - Driving of timber piles | ACCEPTANCE CRITERIA - As per IFC drawings | FREQUENCY - Prior to backfill | Hold Point - H | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Piles driven to 10M depth top of pile RL -2800 | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | ACCEPTANCE CRITERIA - Visual Inspection
11 | Pile driving | Piling card | As per IFC drawings | Prior to Backfill | H | Subcontractor QA | Not Required | 11 - Pile driving | ACTIVITY TASK - Piling card | ACCEPTANCE CRITERIA - As per IFC drawings | FREQUENCY - Prior to Backfill | Hold Point - H | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Subcontractor QA | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | FREQUENCY - At the completion of bund construction
12 | Excavation | Excavate to RL - 1.2 | Surveyed as built | Upon completion of Excavation | H | Survey data | Not Required | 12 - Excavation | ACTIVITY TASK - Excavate to RL - 1.2 | ACCEPTANCE CRITERIA - Surveyed as built | FREQUENCY - Upon completion of Excavation | Hold Point - H | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey data | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | Hold Point - W
13 | Installation of retaining wall plates | Install plates | 22mm Steel plates | During construction | H | Visual Inspection | Not Required | 13 - Installation of retaining wall plates | ACTIVITY TASK - Install plates | ACCEPTANCE CRITERIA - 22mm Steel plates | FREQUENCY - During construction | Hold Point - H | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP
14 | Excavation | Excavate to RL - 2.8 | Surveyed as built | Upon completion of Excavation | H | Survey data | Not Required | 14 - Excavation | ACTIVITY TASK - Excavate to RL - 2.8 | ACCEPTANCE CRITERIA - Surveyed as built | FREQUENCY - Upon completion of Excavation | Hold Point - H | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey data | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required | VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
3 - Earthworks (Confluence upstream of Pump Station)
ACTIVITY TASK - Install Silt Control
ACCEPTANCE CRITERIA - Visual Inspection
FREQUENCY - At the completion of silt control install
Hold Point - W
CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP
VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
4 - Downstream Stilling Station
ACTIVITY TASK - Stripped Surface
ACCEPTANCE CRITERIA - Visual Inspection
FREQUENCY - At the completion of surface stripping prior to further construction
Hold Point - W
CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A
VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
5 - Downstream Stilling Station
ACTIVITY TASK - Supply and place Geotextile and Reno Mattress
ACCEPTANCE CRITERIA - Visual Inspection
FREQUENCY - At the completion of placement of Geotextile and Reno Mattress
Hold Point - W
CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - As per approved EMP
VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
6 - Pump Station
ACTIVITY TASK - Stripped Surface
ACCEPTANCE CRITERIA - Visual Inspection
FREQUENCY - At the completion of surface stripping prior to further construction
Hold Point - W
CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - N/A
VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
7 - Pump Station
ACTIVITY TASK - Hardfill against Walls
ACCEPTANCE CRITERIA - 95% compaction required
FREQUENCY - Each layer, Max layer thickness 200mm
Hold Point - H
CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Test Certificates required
VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
8 - Pump Station
ACTIVITY TASK - Outlet and Discharge
ACCEPTANCE CRITERIA - As per IFC drawings or Engineers instruction
FREQUENCY - Prior to construction
Hold Point - H
CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Check against IFC drawings specification
VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
9 - Pile driving
ACTIVITY TASK - Delivery inspection of piles
ACCEPTANCE CRITERIA - 10M 300 SED H5
FREQUENCY - Prior to pile driving
Hold Point - H
CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Check pile tags
VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
10 - Pile driving
ACTIVITY TASK - Driving of timber piles
ACCEPTANCE CRITERIA - As per IFC drawings
FREQUENCY - Prior to backfill
Hold Point - H
CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Piles driven to 10M depth top of pile RL -2800
VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
11 - Pile driving
ACTIVITY TASK - Piling card
ACCEPTANCE CRITERIA - As per IFC drawings
FREQUENCY - Prior to Backfill
Hold Point - H
CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Subcontractor QA
VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
12 - Excavation
ACTIVITY TASK - Excavate to RL - 1.2
ACCEPTANCE CRITERIA - Surveyed as built
FREQUENCY - Upon completion of Excavation
Hold Point - H
CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey data
VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
13 - Installation of retaining wall plates
ACTIVITY TASK - Install plates
ACCEPTANCE CRITERIA - 22mm Steel plates
FREQUENCY - During construction
Hold Point - H
CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Visual Inspection
VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required
14 - Excavation
ACTIVITY TASK - Excavate to RL - 2.8
ACCEPTANCE CRITERIA - Surveyed as built
FREQUENCY - Upon completion of Excavation
Hold Point - H
CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET - Survey data
VERIFICATION SIGN OFFS: CRITICAL HOLD POINT AUTHORITY - Not Required