## General
SECTION 1 – GENERAL DETAILS
Project Name: | SH1 O2NL Northern (South Foxton Section) | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | 558021 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | 345084-NZ Transport Agency | [5 empty] | B | Report by Breach | CM | Construction Manager | Chris Colman | CC
Contract Number: | NZTA 9500 | [5 empty] | C | Check | ER | Engineers Representative | Luke Cameron | LC
Area/ Sub-System: | Sh1 Foxton to Levin |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | O2L ITP 10 |  |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager
ITP Description: | Covers all inspection points pre, during and post construction of all Rip Rap project wide. | [5 empty] | I | Inspection | PM | Project Manager | Meyer Du Plessis | MDP
Discipline: | Rip Rap | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Richard Wild | RW
Specification: | Consultants Standard Technical Specifications TS1 & all relative specifications noted within. | [5 empty] | O | Operation | QE | Quality Engineer
[7 empty] | R | Review | QM | QA Manager | Cody Graham | CG
Drawings: | For construction drawings : | [5 empty] | S | Subcontractor | SP | Supervisor | Richard Wild | RW
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: | Meyer Du Plessis |  |  | Date: | 2024-01-11 |  | W | Witness Point | SV | Surveyor | Stefan Kilian | SK
Quality Specified: | Project Technical Specifications cross referencing relevant to Transit New Zealand (TNZ) & NZTA Z8:2022 | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Chris Colman |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Items
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection
[7 empty] | Key | By | Checked (PM Initial) | Date
10.0 | Rip Rap | Final Sign Off | All below requirements are met and approved by ER | Referenced Item numbers as below | Once post construction | Hold Point | H | ER
10.1 | Source Properties
10.1.1 | Density | Material Compliace Check | Density > 2.6t/m3 when tested in accordance with NZS 4407 1991 Test 3.7.2 | IANZ Lab Report | Once per supplier | Hold Point | H | ER
10.1.2 | Crushing Resistance | Material Compliace Check | CR > 150kN when tested in accordance with NZS 4407 1991 Test 3.10 | IANZ Lab Report | Once per supplier | Hold Point | H | ER
10.1.3 | Weathering Classification | Material Compliace Check | AA, BA, AB or BB when tested in accordance with NZS 4407 1991 Test 3.11 | IANZ Lab Report | Once per supplier | Hold Point | H | ER
10.1.4 | Abrasion Resistance | Material Compliace Check | AR ≤ 26% when tested in accordance with NZS 4407 1991 Test 3.12 | IANZ Lab Report | Once per supplier | Hold Point | H | ER
10.1.5 | Visual Check | Material Compliace Check | Rock shall be free from calcite intrusions and shall not be broken concrete or asphalt. | IANZ Lab Report | Once per supplier | Hold Point | H | ER
10.2 | Production Properties
10.2.1 | Grading | Material Compliace Check | Rock shall be nominal D50 size shown on the drawings and shall be well graded as follows. | IANZ Lab Report | Once per supplier | Hold Point | H | ER
Please Add Bidim and AP150 Material Approval
10.3 | Placement
10.3.1 | Filter Cloth | Pre placement inspection | Filter cloth to be placed and securly pegged prior to placement, material to comply as per NZTA F7. | Site Checklist Form | Once per Rip Rap bed | Inspection / Review | I / R | PM/ER
10.3.2 | Rock Placement | Post construction inspection | Rip Rap to be placed by machine or hand and not dumped. Placing to begin from the lowest point of bed in an unwatered state. No deformation of underlying surface during placement. Rocks should be placed so as not to deviate the bed/channel grade from the design drawings. Rocks to be evenly distributed in size to lock togeather and minimise voids. | Site Checklist Form | Once per Rip Rap bed | Inspection / Review | I / R | PM/ER
COMMENTS
[6 empty] | ☐ Yes | ☐ No | Date:
when tested in accordance with NZS 4407 1991 Test 3.11