## General
SECTION 1 – GENERAL DETAILS
Project Name: | Ōtaki to Levin Saftey Improvements | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | 558010 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | 345084-NZ Transport Agency | [5 empty] | B | Report by Breach | CM | Construction Manager | Chris Colman | CC
Contract Number: | NZTA 6581 | [5 empty] | C | Check | ER | Engineers Representative | Luke Cameron | LC
Area/ Sub-System: | Ōtaki to Levin State Highway 1 |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | O2L ITP 7 |  |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager | Glen Flint | GF
ITP Description: | Covers all inspection points pre, during and post construction of the sealing works project wide. | [5 empty] | I | Inspection | PM | Project Manager | Sam Christensen | SC
Discipline: | Sealing | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Richard Wild | RW
Specification: | Consultants Standard Technical Specifications TS1 & all relative sealing specifications noted within. | [5 empty] | O | Operation | QE | Quality Engineer
[7 empty] | R | Review | QM | QA Manager
Drawings: | For construction drawings : | [5 empty] | S | Subcontractor | SP | Supervisor | Richard Wild | RW
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: | Sam Christensen |  |  | Date: | 2023-05-10 |  | W | Witness Point | SV | Surveyor | Andre Wilkes | AW
Quality Specified: | Project Technical Specifications cross referencing relevant to Transit New Zealand (TNZ) & NZTA Z8:2022 | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Matt Tipping |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Item
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection
[7 empty] | Key | By | Checked (PM Initial) | Date
7.0 | Sealing | Final Sign Off | All below requirements are met and approved by ER | Referenced Item numbers as below | Once post construction | Hold Point | H | ER
7.1 | Bitumen Approval
7.1.1 | NZTA M1: 2022: Bitumen Material Approval | Test Report Review | Bitumen/binder compliant with NZTA M/1 - Table 5.1 | Manufacturers Certificate | Minimum 5 working days prior to construction | Hold Point | H | PM/ER
7.2 | Source Properties
7.2.1 | NZTA M6: 2022: 4.2 Crushing Resistance | Test Report Review | Maximum of 10% fines shall be produced under a load of 230kN. | IANZ Lab Report | Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser | Hold Point | H | PM/ER
7.2.2 | NZTA M6: 2022: 4.3 Weathering Resistance | Test Report Review | The aggregate shall have a quality index of AA or BA | IANZ Lab Report | Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser | Hold Point | H | PM/ER
7.2.3 | NZTA M6: 2022: 4.4 Weak Particles Test | Test Report Review | Note - only required if source properties are disputed. The aggregate shall have a maximum of 1% of unsound materials | IANZ Lab Report | Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser | Hold Point | H | PM/ER
7.2.4 | NZTA M6: 2022: 4.6 Polished Stone Value | Test Report Review | Polished Stone Value (PSV) - compliant with NZTA M6: 2022: 4.6 & project requirements | IANZ Lab Report | Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser | Hold Point | H | PM/ER
7.3 | Production Properties |  | Grade 2, 3 & 4 Chip
7.3.1 | NZTA M6: 2022: 5.1 Cleanness | Test Report Review | Cleaness of aggregate samples compliant with NZTA M6: 2022 5.2 Cleanness | IANZ Lab Report | Three initially per grade of chip from stockpile, then repeat as follows: 1 test per < 100m3; 2 tests per 100-500m3; or 3 tests per > 500m3 | Hold Point | H | PM/ER
7.3.2 | NZTA M6: 2022: 5.2 Size and Shape | Test Report Review | Size and Shape of Aggregate Particles compliant with NZTA M6: 2022: 5.2 Size and Shape | IANZ Lab Report | Three initially per grade of chip from stockpile, then repeat as follows: 1 test per < 100m3; 2 tests per 100-500m3; or 3 tests per > 500m3 | Hold Point | H | PM/ER
7.4 | Production Properties |  | Grade 5 & 6 Chip
7.4.1 | NZTA M6: 2022 5.3 PSD | Test Report Review | Particle Size Distribution compliant with NZTA M6: 2022 5.1 Table 4 | IANZ Lab Report | Three initially per grade of chip from stockpile, then repeat as follows: 1 test per < 100m3; 2 tests per 100-500m3; or 3 tests per > 500m3 | Hold Point | H | PM/ER
7.5 | Pre-Construction
Add - Require formal sign off record of previous layer prior to placment of next layer. DNZ to develop sign off sheet or approval system of work.
Add - Bitumen distributors shall possess a current Certificate of Compliance with the BCA E/2 Specification for Performance of Bitumen Distributors administered by the New Zealand Bitumen Contractors' Association Inc.
7.5.1 | Chipseal Design Submission | Design Review | Designer to approve sealing design, prior to sealing. | NTC confirming acceptance | Once per seal design | Hold Point | H | PM/ER
7.5.2 | Pre-seal Inspection | Visual Site Inspection | Basecourse/Subbase (Membrane seal) - To be prepped to a tight, uniform surface, swept to remove any dust and other foreign objects. Prime or previous seal - Full surface swept with a power broom to remove excess chip and any other foreign material The Contractor shall give the Engineer 24 hours’ notice of its intention to seal | Site Inspection Form | Prior to construction of sealing coat | Hold Point | H | PM/ER
7.5.3 | Pre-seal testing | Degree of Saturation test TNZB/02 Clause 12 | Compliant as per TNZ B/02 Clause 12 DOS at each of minimim 5 points < 70% | Testing results | Minimum 5 tests per 1000m2 | Hold Point | H | PM/ER
7.6 | Construction
7.6.1 | Working Temperature Prior to Spraying | Onsite check & Document | The road shall be reasonably dry before the binder is applied, and no spraying shall be carried out when the pavement surface temperature is below 10 degrees C. | Sealing Checklist | Prior to Spraying | Review | R | PM/ER
7.6.2 | Application rate for Bituminous Seal | Onsite check & Document | Sprayed Rate measured compliant with the Approved Seal Design | Sealing Checklist | Per spray run | Review | R | PM/ER
7.6.3 | Chip Spread Rate | Onsite check & Document | Sealing Records showing compliant spread rate of the chips based on C0213.5;TNZ P/3: 1995-21 Cl. 28 | Sealing Checklist | 1 test per chip grade per 2,000m2 seal constructed | Review | R | PM/ER
7.6.4 | Rolling Requirements | Onsite check & Document | Sealing Records showing compliant rolling requirements based on C0213.5;TNZ P/3: 1995-22 ROLLING | Sealing Checklist | Per Shift | Review | R | PM/ER
7.6.5 | On Site Checks - Post PTR and Brooming | Onsite check & Document | Surface Compliant and Surplus chip removed | Sealing Checklist | Prior to construction of next layer/ Prior removal of the temporary speed restriction signs | Review | R | PM/ER
COMMENTS
Item 7.5.3: DOS changed from 80% to 70%, Item 7.6.1: Temperature changed from air temperature to surface temperature. | [5 empty] | ☐ Yes | ☐ No | Date: