## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | F2LSIP - ITP 10 - Rip Rap | itp |  |  |  |  | F2LSIP - ITP 10 - Rip Rap
section | 10.0 - Rip Rap
checkpoint | Rip Rap
label | Inspection Point: Quality Control Activity - Final Sign Off
label | Acceptance Criteria - All below requirements are met and approved by ER
label | Verifying Document - Referenced Item numbers as below
label | Frequency - Once post construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 10.1 - Source Properties
checkpoint | 10.1.1 - Density
label | Inspection Point: Quality Control Activity - Material Compliace Check
label | Acceptance Criteria - Density > 2.6t/m3 when tested in accordance with NZS 4407 1991 Test 3.7.2
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per supplier
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.1.2 - Crushing Resistance
label | Inspection Point: Quality Control Activity - Material Compliace Check
label | Acceptance Criteria - CR > 150kN when tested in accordance with NZS 4407 1991 Test 3.10
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per supplier
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.1.3 - Weathering Classification
label | Inspection Point: Quality Control Activity - Material Compliace Check
label | Acceptance Criteria - AA, BA, AB or BB when tested in accordance with NZS 4407 1991 Test 3.11
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per supplier
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.1.4 - Abrasion Resistance
label | Inspection Point: Quality Control Activity - Material Compliace Check
label | Acceptance Criteria - AR ≤ 26% when tested in accordance with NZS 4407 1991 Test 3.12
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per supplier
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.1.5 - Visual Check
label | Inspection Point: Quality Control Activity - Material Compliace Check
label | Acceptance Criteria - Rock shall be free from calcite intrusions and shall not be broken concrete or asphalt.
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per supplier
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 10.2 - Production Properties
checkpoint | 10.2.1 - Grading
label | Inspection Point: Quality Control Activity - Material Compliance Check
label | Acceptance Criteria - Rock shall be nominal D50 size shown on the drawings and shall be well graded as follows.
label | – – – – – – – – – – – – – – – – – – – – –
label | Stone Size Range (m) ¦¦ Stone Weight Range (kilograms) ¦¦ % of Gradation smaller than
label | – – – – – – – – – – – – – – – – – – – – –
label | 1.5 D50 to 1.7 D50 ¦¦ 3.0 W50 to 5.0 W50 ¦¦ 100
label | 1.2 D50 to 1.4 D50 ¦¦ 2.0 W50 to 2.75 W50 ¦¦ 85
label | 1.0 D50 to 1.4 D50 ¦¦ 1.0 W50 to 1.5 W50 ¦¦ 50
label | 0.4 D50 to 0.6 D50 ¦¦ 0.1 W50 to 0.2 W50 ¦¦ 15
label | – – – – – – – – – – – – – – – – – – – – –
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per supplier
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 10.3 - Placement
checkpoint | 10.3.1 - Filter Cloth
label | Inspection Point: Quality Control Activity - Pre placement inspection
label | Acceptance Criteria - Filter cloth to be placed and securly pegged prior to placement, material to comply as per NZTA F7.
label | Verifying Document - Site Checklist Form
label | Frequency - Once per Rip Rap bed
label | Inspection Type - Inspection / Review
label | Inspection: Key - I / R
label | Inspection: By - PM/ER
checkpoint | 10.3.2 - Rock Placement
label | Inspection Point: Quality Control Activity - Post construction inspection
label | Acceptance Criteria - Rip Rap to be placed by machine or hand and not dumped.
label | ○ Placing to begin from the lowest point of bed in an unwatered state.
label | ○ No deformation of underlying surface during placement.
label | ○ Rocks should be placed so as not to deviate the bed/channel grade from the design drawings.
label | ○ Rocks to be evenly distributed in size to lock togeather and minimise voids.
label | Verifying Document - Site Checklist Form
label | Frequency - Once per Rip Rap bed
label | Inspection Type - Inspection / Review
label | Inspection: Key - I / R
label | Inspection: By - PM/ER